## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-08-01 | 70.1077 | AIC - Overhead 2025 |  | 0 | -9184.38 | 2025-12-01
2025-08-01 | 71.1077 | AIC - NorCal Overhead 2025 |  | 0 | -2286148.81 | 2025-12-01
2025-08-01 | 72.1179 | ECAWP - Padre Dam - Sales Pursuits |  | 749 | 0
2025-08-01 | 72.118 | Mojave Groundwater Storage LLC - Cadiz Water - Sales Pursuits |  | 214 | 0
2025-08-01 | 72.1181 | City of Banning - Sales Pursuits |  | 133.75 | 0
2025-08-01 | 72.1183 | Caltrans - Caldecott Tunnel - Sales Pursuits |  | 749 | 0
2025-08-01 | 73.1003 | WML- Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment |  | 3193.75 | 0 | 2025-12-01
2025-08-01 | 73.1004 | WML- San Joaquin Electric - Liberty Ranch Sewer Pump Station |  | 881.89 | 0 | 2025-12-01
2025-08-01 | 73.1005 | WML- SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold |  | 33630.03 | 0 | 2025-12-01
2025-08-01 | 73.1007 | WML- Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield |  | 2253.75 | 0 | 2025-12-01
2025-08-01 | 73.1015 | WML- Calistoga, City of - Riverside Ponds & Headworks Mitigation |  | 6172.14 | 0 | 2025-09-01
2025-08-01 | 73.1017 | WML- SFO - SDDS Gate Valves Replacement |  | 133.75 | 0 | 2025-12-01
2025-08-01 | 73.1018 | WML- CM Controls - Salinas AG Industrial Phase 1 – City of Salinas |  | 337.5 | 0 | 2026-03-01
2025-08-01 | 73.1019 | WML- Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. |  | 31132.09 | 0 | 2025-12-01
2025-08-01 | 73.1023 | WML- Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade |  | 9006.81 | 0 | 2025-09-01
2025-08-01 | 73.1032 | WML- Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods |  | 3290.63 | 0 | 2026-03-01
2025-08-01 | 73.1036 | WML- Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 |  | 6826.56 | 0 | 2026-03-01
2025-08-01 | 73.1038 | WML- Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 |  | 3600.94 | 0 | 2026-03-01
2025-08-01 | 73.1039 | WML- Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station |  | 51029.66 | 0 | 2025-12-01
2025-08-01 | 73.1043 | WML- SD Electric, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh |  | 25602.5 | 0 | 2026-03-01
2025-08-01 | 73.1047 | WML- SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 |  | 707548.82 | 0 | 2026-12-01
2025-08-01 | 73.1048 | WML- Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement |  | 43274.27 | 0 | 2025-12-01
2025-08-01 | 73.105 | WML- Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat |  | 672231.81 | 0 | 2026-12-01
2025-08-01 | 73.1055 | WML- Tranquility Irrigation District - Tranquility Well 8 Project |  | 23565.75 | 0 | 2026-03-01
2025-08-01 | 73.1059 | WML- Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou |  | 62988.93 | 0 | 2026-03-01
2025-08-01 | 73.106 | WML- Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar |  | 11475.32 | 0 | 2026-09-01
2025-08-01 | 73.1063 | WML- Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project |  | 7139.07 | 0 | 2026-03-01
2025-08-01 | 73.1065 | WML- TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact |  | 15623.38 | 0 | 2025-09-01
2025-08-01 | 73.1066 | WML- CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather |  | 120489.5 | 0 | 2025-12-01
2025-08-01 | 73.1067 | WML- Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto |  | 11321.69 | 0 | 2026-09-01
2025-08-01 | 73.1072 | WML- Bullert Industrial Electric, Inc - Washwater Equializer Tank Replacement Project |  | 4457.49 | 0 | 2025-12-01
2025-08-01 | 73.1085 | WML- Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service |  | 48.75 | 0 | 2026-06-01
2025-08-01 | 73.1086 | WML- Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service |  | 2567.19 | 0 | 2026-06-01
2025-08-01 | 73.1101 | Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject |  | 795000 | 95861 | 2026-03-01
2025-08-01 | 73.1102 | San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal |  | 394657 | 0 | 2026-03-01
2025-08-01 | 73.1103 | Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District |  | 128000 | 21775.3635 | 2025-12-01
2025-08-01 | 73.1105 | Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun |  | 180000 | 24106.4754 | 2026-03-01
2025-08-01 | 73.1106 | Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - |  | 464000 | 72796.2001 | 2025-12-01
2025-08-01 | 73.1107 | San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W |  | 485000 | 0 | 2026-06-01
2025-08-01 | 73.1109 | Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U |  | 123000 | 2257.474 | 2026-06-01
2025-08-01 | 73.1111 | California American Water - Luzern Well Treatment Design |  | 180000 | 8902.4829 | 2026-03-01
2025-08-01 | 73.1113 | Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr |  | 1800000 | 0 | 2026-12-01
2025-08-01 | 73.1119 | SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit |  | 59545 | 5740.3069 | 2025-12-01
2025-08-01 | 73.112 | Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio |  | 50000 | 0 | 2026-03-01
2025-08-01 | 73.1121 | San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro |  | 1325000 | 0 | 2026-06-01
2025-08-01 | 73.1124 | Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of |  | 2822000 | 0 | 2026-12-01
2025-08-01 | 73.1125 | Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation |  | 198000 | 0 | 2025-12-01
2025-08-01 | 73.1126 | Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat |  | 225000 | 0 | 2026-06-01
2025-08-01 | 73.1127 | Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co |  | 734780 | 0 | 2026-12-01
2025-08-01 | 73.1128 | Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase |  | 194000 | 0 | 2026-03-01
2025-08-01 | 73.1131 | North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame |  | 105895 | 9373.7125 | 2026-03-01
2025-08-01 | 73.1135 | San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa |  | 163000 | 0 | 2026-03-01
2025-08-01 | 73.1141 | Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos |  | 32150 | 0 | 2026-03-01
2025-08-01 | 73.1142 | Fusion Electric, Inc - Lake Supply Well Pump Station - Lennar |  | 127000 | 0 | 2026-06-01
2025-08-01 | 73.1145 | Strategic Mechanical - Replace Water Storage Tank 731 (#6) – Lemoore Naval Air Stat |  | 73120 | 6718.7135 | 2026-03-01
2025-08-01 | 73.1146 | Darrel Varni Electric, Inc.- Recycled Water Conveyance – City of Soledad |  | 39500 | 0 | 2026-03-01
2025-08-01 | 73.1147 | Strategic Mechanical - West Creek Village Mixed Use Development Improvement Plans |  | 275000 | 0 | 2026-09-01
2025-08-01 | 73.1148 | Big Valley Electric - Harvest Water On-Farm Connection Assemblies Project - Sac Ar |  | 2750000 | 0 | 2026-12-01
2025-08-01 | 73.115 | Conco-West - Machado Ranch Phase 2 Lumina Park - City of Manteca |  | 53600 | 0 | 2026-09-01
2025-08-01 | 73.1153 | Sac Valley Electric Inc - Lammers Road Zone B Pump Station, Tracy Recycled Water Syste |  | 1295000 | 0 | 2027-06-01
2025-08-01 | 73.1154 | PB Electric, Inc.- Bickford Ranch – Phase 1B Caperton Canal – Placer County Wat |  | 129000 | 0 | 2026-06-01
2025-08-01 | 73.1156 | Darrel Varni Electric, Inc. - Salinas Stormwater Grant Programs TP1 and IWTF Facilities Im |  | 872500 | 0 | 2027-03-01
2025-08-01 | 73.1157 | Fox Electrical, Inc. - SMD3 Sewer Lift Station Improvement Porject - County of Plac |  | 81500 | 0 | 2027-03-01
2025-08-01 | 73.1159 | Core Electrical Services Inc - Nitrogen Removal Phase 1 Improvements – Fairfield Suisun Sew |  | 1500000 | 0 | 2027-09-01
2025-08-01 | 73.116 | San Joaquin Electric - Reservoir 4 and 7A and 7B Tanks Rehabilitation - El Dorado I |  | 15750 | 0 | 2026-03-01
2025-08-01 | 73.1163 | Strategic Mechanical, Inc.- Water Storage Tank, Ancillary Facility, Pipelines, and Equip |  | 277000 | 0 | 2026-06-01
2025-08-01 | 73.1167 | Fusion electric, Inc.- Copper Cove - C Tank BPS Modifications - Calaveras County Wa |  | 760000 | 0 | 2027-03-01
2025-08-01 | 73.1168 | Con J. Franke Electric Inc.- Influent Pump Nos 2 and 5 Install Project - Sac Area Sewer D |  | 529000 | 0 | 2026-06-01
2025-08-01 | 73.117 | Central Sierra Electric Co., Inc. - Industrial Water Treatment Plant Expansion and Test Well Con |  | 198200 | 0 | 2026-09-01
2025-08-01 | 73.1174 | Strategic Mechanical, Inc.- Construction of Storm Drainage Facilities in Drainage Area |  | 138000 | 0 | 2026-12-01
2025-08-01 | 73.1176 | SD Electric Inc - Consolidated Treatment Facility Phase 4A Expansion CIP WW 22 |  | 256260 | 0 | 2026-12-01
2025-08-01 | 73.1177 | Cupertino Electric Inc. - Cupertino Electric Headworks - SFPUC |  | 26235 | 0 | 2025-12-01
2025-08-01 | 74.101 | WML - Placer County Water Agency -PCWA Time & Material Contract |  | 3076.88 | 0 | TBD
2025-08-01 | 74.1037 | WML - East Orange County Water District - EOCWD - On-Call SCADA Integration Services |  | 5297.81 | 0 | TBD
2025-08-01 | 74.1046 | WML - California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods |  | 29588.56 | 0 | 2025-12-01
2025-08-01 | 74.1051 | WML - Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives |  | 1148.75 | 0 | 2025-12-01
2025-08-01 | 74.1073 | WML - California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W |  | 14772.6 | 0 | 2026-03-01
2025-08-01 | 74.1075 | WML - California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF |  | 5344.38 | 0 | 2026-06-01
2025-08-01 | 74.1078 | WML - City of Napa - On-Call Control Systems Integrator Services |  | 2216.95 | 0 | TBD
2025-08-01 | 74.1079 | San Jose Water Co - Montevina PLC Upgrade |  | 405000 | 0 | 2026-03-01
2025-08-01 | 74.108 | San Jose Water Co - PLC System Assessment |  | 253225.17 | 222050.31 | 2025-09-01
2025-08-01 | 74.1081 | WML - Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA |  | 79080.04 | 0 | 2025-12-01
2025-08-01 | 74.1088 | WML - California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo |  | 5180.94 | 0 | 2026-03-01
2025-08-01 | 74.1089 | San Jose Water - ASE Bell Modem Assistance |  | 14350 | 1583.9934 | 2025-12-01
2025-08-01 | 74.1108 | City of Davis - Programming and Panel Modifications at Turnout Sit |  | 45200 | 9834.8085 | 2025-09-01
2025-08-01 | 74.1117 | UC Davis - Wastewater Integration Service Contract |  | 3497.75 | 1879.9 | TBD
2025-08-01 | 74.1122 | West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit |  | 30300 | 3799.6649 | 2025-12-01
2025-08-01 | 74.1129 | RMCSD - VEEAM SFTWR |  | 9820 | 1726.9211 | 2025-12-01
2025-08-01 | 74.1132 | UC Davis - CABA Well Pump Station Rehabilitation – UC Davis |  | 49530 | 1272.8093 | 2025-12-01
2025-08-01 | 74.1133 | UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis |  | 34935 | 4637.7802 | 2025-12-01
2025-08-01 | 74.1138 | City of Brentwood - SCADA System Upgrade |  | 1785125 | 348719.9816 | 2026-03-01
2025-08-01 | 74.1139 | City of Brentwood - Brentwood, City of - On-Call Agreement |  | 13161.13 | 0 | TBD
2025-08-01 | 74.1143 | East Contra Costa Irrigation District - On-Call Contract |  | 6896 | 3576.03 | TBD
2025-08-01 | 74.1144 | East Contra Costa Irrigation District - Fiber Optic Network Infrastructure - East Contra Costa Irrig |  | 1830.29 | 0 | TBD
2025-08-01 | 74.1151 | UC Davis - SCADA Assessment and Recommendations - UC Davis |  | 12500 | 0 | 2026-06-01
2025-08-01 | 74.1155 | FOWD Winding Way PRV Comm TRBLSHTING |  | 3663.5 | 2637.88 | TBD
2025-08-01 | 74.1158 | Rancho Murieta Community Services District - Laptop Additions |  | 7820 | 0 | 2025-12-01
2025-08-01 | 74.1169 | West Bay Sanitary District - Henderson Pump Station Main Service Disconnect Retrofit |  | 15315 | 0
2025-08-01 | 75.1077 | AIC - SoCal Overhead 2025 |  | 0 | -317175.74 | 2025-12-01
2025-08-01 | 75.113 | AIC - Estimating 2025 |  | 0 | -8626.62 | 2025-12-01
2025-08-01 | 76.1054 | WML - W.M. Lyles - Riverside Public Works - Digester 5 Rehab |  | 81258.14 | 0 | 2026-03-01
2025-08-01 | 78.1042 | WML - Trabuco Canyon Water Dist. - SCADA Integration Services |  | 14592.81 | 0 | 2026-03-01
2025-08-01 | 78.1049 | WML - East Orange County Water District - SCADA Field Site RTU Prog Ph.1 |  | 13465.79 | 0 | 2026-03-01
2025-08-01 | 78.1083 | WML - West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM |  | 65846.74 | 0 | 2026-06-01
2025-08-01 | 78.1087 | WML - San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters |  | 5937.7 | 0 | 2025-12-01
2025-08-01 | 78.1136 | Irvine Rranch District - MWRP Fueling Facility CP-100 Programming |  | 53457 | 12430.203 | 2025-12-01
2025-08-01 | 78.1137 | Irvine Ranch Water District - Michelson Water Recycling Plan |  | 326800 | 61482 | 2026-09-01
2025-08-01 | 78.1161 | City of Redlands - On-Call Support |  | 31666.64 | 0 | 2027-03-01
2025-08-01 | 78.1162 | Trabuco Canyon Water District - SCADA Systems Integrator On-Call Services |  | 2883.72 | 0 | 2027-03-01
2025-08-01 | 78.1164 | South Orange County Wasterwater Authority - Solids Open P.O |  | 5000 | 0 | 2027-03-01
2025-08-01 | 78.1165 | South Orange County Wasterwater Authority - SCADA Support Solids Open P.O |  | 225 | 0 | 2027-03-01
2025-08-01 | 78.1171 | San Gabriel Valley Water Company - Temp Radio System to Support Plant 13 Renovations |  | 37530 | 1694.6986 | 2026-03-01
2025-08-01 | 73.1134 | Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc |  | 4871 | 3905.49 | 2025-09-01
2025-08-01 | 73.1149 | Aveva Select California - AVEVA Historian Implementation - Kaiser Los Angeles |  | 13160 | 6791.86 | 2025-09-01
2025-08-01 | 73.1152 | Fusion Electric, In. - Sonoma Truck Level Transmitter Replacement - City of Modesto |  | 2995 | 767.03 | 2025-09-01
2025-08-01 | 74.1082 | WML - City of Clovis - Pump Station E New Pump 5 VFD Startup |  | 5141.49 | 0 | 2025-09-01
2025-08-01 | 74.1104 | Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric |  | 48860 | 31806.56 | 2025-09-01
2025-08-01 | 74.111 | WML - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M |  | 9960 | 5363.58 | 2025-09-01
2025-08-01 | 74.1112 | Westside Water Authority - Pump Station A On-Site Support - Westside Water Au |  | 42902.3 | 15623.13 | 2025-06-01
2025-08-01 | 74.1115 | UC Davis - WWTP Annual Instrument Calibrations |  | 12725 | 5625.48 | 2025-06-01
2025-08-01 | 74.1123 | UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis |  | 12450 | 6086.18 | 2025-09-01
2025-08-01 | 74.1166 | Chlorine Analyzer Installation Assistance – Valley Springs Public Utility District |  | 4250 | 2150 | 2025-09-01
2025-08-01 | 78.1016 | WML - Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District |  | 13214.1 | 0 | 2025-09-01
2025-08-01 | 78.1084 | WML - South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut |  | 1243.13 | 0 | 2025-09-01

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-08-01 | 70.1077 | AIC - Overhead 2025 |  | 9184.38
2025-08-01 | 71.1077 | AIC - NorCal Overhead 2025 |  | 2286148.81
2025-08-01 | 72.1179 | ECAWP - Padre Dam - Sales Pursuits |  | 749
2025-08-01 | 72.118 | Mojave Groundwater Storage LLC - Cadiz Water - Sales Pursuits |  | 214
2025-08-01 | 72.1181 | City of Banning - Sales Pursuits |  | 133.75
2025-08-01 | 72.1183 | Caltrans - Caldecott Tunnel - Sales Pursuits |  | 749
2025-08-01 | 73.1003 | WML- Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment |  | 3193.75
2025-08-01 | 73.1004 | WML- San Joaquin Electric - Liberty Ranch Sewer Pump Station |  | 881.89
2025-08-01 | 73.1005 | WML- SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold |  | 33630.03
2025-08-01 | 73.1007 | WML- Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield |  | 2253.75
2025-08-01 | 73.1015 | WML- Calistoga, City of - Riverside Ponds & Headworks Mitigation |  | 6172.14
2025-08-01 | 73.1017 | WML- SFO - SDDS Gate Valves Replacement |  | 133.75
2025-08-01 | 73.1018 | WML- CM Controls - Salinas AG Industrial Phase 1 – City of Salinas |  | 337.5
2025-08-01 | 73.1019 | WML- Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. |  | 31132.09
2025-08-01 | 73.1023 | WML- Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade |  | 9006.81
2025-08-01 | 73.1032 | WML- Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods |  | 3290.63
2025-08-01 | 73.1036 | WML- Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 |  | 6826.56
2025-08-01 | 73.1038 | WML- Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 |  | 3600.94
2025-08-01 | 73.1039 | WML- Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station |  | 51029.66
2025-08-01 | 73.1043 | WML- SD Electric, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh |  | 25602.5
2025-08-01 | 73.1047 | WML- SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 |  | 707548.82
2025-08-01 | 73.1048 | WML- Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement |  | 43274.27
2025-08-01 | 73.105 | WML- Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat |  | 672231.81
2025-08-01 | 73.1055 | WML- Tranquility Irrigation District - Tranquility Well 8 Project |  | 23565.75
2025-08-01 | 73.1059 | WML- Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou |  | 62988.93
2025-08-01 | 73.106 | WML- Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar |  | 11475.32
2025-08-01 | 73.1063 | WML- Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project |  | 7139.07
2025-08-01 | 73.1065 | WML- TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact |  | 15623.38
2025-08-01 | 73.1066 | WML- CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather |  | 120489.5
2025-08-01 | 73.1067 | WML- Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto |  | 11321.69
2025-08-01 | 73.1072 | WML- Bullert Industrial Electric, Inc - Washwater Equializer Tank Replacement Project |  | 4457.49
2025-08-01 | 73.1085 | WML- Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service |  | 48.75
2025-08-01 | 73.1086 | WML- Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service |  | 2567.19
2025-08-01 | 73.1101 | Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject |  | 686904
2025-08-01 | 73.1102 | San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal |  | 351625
2025-08-01 | 73.1103 | Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District |  | 103701
2025-08-01 | 73.1105 | Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun |  | 130981
2025-08-01 | 73.1106 | Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - |  | 312631
2025-08-01 | 73.1107 | San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W |  | 418395
2025-08-01 | 73.1109 | Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U |  | 112265
2025-08-01 | 73.1111 | California American Water - Luzern Well Treatment Design |  | 144956
2025-08-01 | 73.1113 | Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr |  | 1629439
2025-08-01 | 73.1119 | SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit |  | 47941
2025-08-01 | 73.112 | Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio |  | 40662
2025-08-01 | 73.1121 | San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro |  | 1174927
2025-08-01 | 73.1124 | Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of |  | 2306698
2025-08-01 | 73.1125 | Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation |  | 165468
2025-08-01 | 73.1126 | Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat |  | 188110
2025-08-01 | 73.1127 | Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co |  | 648296
2025-08-01 | 73.1128 | Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase |  | 138018
2025-08-01 | 73.1131 | North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame |  | 72836
2025-08-01 | 73.1135 | San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa |  | 110078
2025-08-01 | 73.1141 | Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos |  | 29392
2025-08-01 | 73.1142 | Fusion Electric, Inc - Lake Supply Well Pump Station - Lennar |  | 111593
2025-08-01 | 73.1145 | Strategic Mechanical - Replace Water Storage Tank 731 (#6) – Lemoore Naval Air Stat |  | 54700
2025-08-01 | 73.1146 | Darrel Varni Electric, Inc.- Recycled Water Conveyance – City of Soledad |  | 25924
2025-08-01 | 73.1147 | Strategic Mechanical - West Creek Village Mixed Use Development Improvement Plans |  | 190392
2025-08-01 | 73.1148 | Big Valley Electric - Harvest Water On-Farm Connection Assemblies Project - Sac Ar |  | 2314444
2025-08-01 | 73.115 | Conco-West - Machado Ranch Phase 2 Lumina Park - City of Manteca |  | 34827
2025-08-01 | 73.1153 | Sac Valley Electric Inc - Lammers Road Zone B Pump Station, Tracy Recycled Water Syste |  | 1128409
2025-08-01 | 73.1154 | PB Electric, Inc.- Bickford Ranch – Phase 1B Caperton Canal – Placer County Wat |  | 99167
2025-08-01 | 73.1156 | Darrel Varni Electric, Inc. - Salinas Stormwater Grant Programs TP1 and IWTF Facilities Im |  | 679971
2025-08-01 | 73.1157 | Fox Electrical, Inc. - SMD3 Sewer Lift Station Improvement Porject - County of Plac |  | 65980
2025-08-01 | 73.1159 | Core Electrical Services Inc - Nitrogen Removal Phase 1 Improvements – Fairfield Suisun Sew |  | 1339918
2025-08-01 | 73.116 | San Joaquin Electric - Reservoir 4 and 7A and 7B Tanks Rehabilitation - El Dorado I |  | 11878
2025-08-01 | 73.1163 | Strategic Mechanical, Inc.- Water Storage Tank, Ancillary Facility, Pipelines, and Equip |  | 83221
2025-08-01 | 73.1167 | Fusion electric, Inc.- Copper Cove - C Tank BPS Modifications - Calaveras County Wa |  | 514653
2025-08-01 | 73.1168 | Con J. Franke Electric Inc.- Influent Pump Nos 2 and 5 Install Project - Sac Area Sewer D |  | 458570
2025-08-01 | 73.117 | Central Sierra Electric Co., Inc. - Industrial Water Treatment Plant Expansion and Test Well Con |  | 168084
2025-08-01 | 73.1174 | Strategic Mechanical, Inc.- Construction of Storm Drainage Facilities in Drainage Area |  | 83199
2025-08-01 | 73.1176 | SD Electric Inc - Consolidated Treatment Facility Phase 4A Expansion CIP WW 22 |  | 185160
2025-08-01 | 73.1177 | Cupertino Electric Inc. - Cupertino Electric Headworks - SFPUC |  | 17947
2025-08-01 | 74.101 | WML - Placer County Water Agency -PCWA Time & Material Contract |  | 3076.88
2025-08-01 | 74.1037 | WML - East Orange County Water District - EOCWD - On-Call SCADA Integration Services |  | 5297.81
2025-08-01 | 74.1046 | WML - California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods |  | 29588.56
2025-08-01 | 74.1051 | WML - Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives |  | 1148.75
2025-08-01 | 74.1073 | WML - California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W |  | 14772.6
2025-08-01 | 74.1075 | WML - California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF |  | 5344.38
2025-08-01 | 74.1078 | WML - City of Napa - On-Call Control Systems Integrator Services |  | 2216.95
2025-08-01 | 74.1079 | San Jose Water Co - Montevina PLC Upgrade |  | 287431.836
2025-08-01 | 74.108 | San Jose Water Co - PLC System Assessment |  | 31174.86
2025-08-01 | 74.1081 | WML - Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA |  | 79080.04
2025-08-01 | 74.1088 | WML - California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo |  | 5180.94
2025-08-01 | 74.1089 | San Jose Water - ASE Bell Modem Assistance |  | 9428
2025-08-01 | 74.1108 | City of Davis - Programming and Panel Modifications at Turnout Sit |  | 35298
2025-08-01 | 74.1117 | UC Davis - Wastewater Integration Service Contract |  | 1617.85
2025-08-01 | 74.1122 | West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit |  | 25315
2025-08-01 | 74.1129 | RMCSD - VEEAM SFTWR |  | 6899
2025-08-01 | 74.1132 | UC Davis - CABA Well Pump Station Rehabilitation – UC Davis |  | 44530
2025-08-01 | 74.1133 | UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis |  | 27435
2025-08-01 | 74.1138 | City of Brentwood - SCADA System Upgrade |  | 1139524
2025-08-01 | 74.1139 | City of Brentwood - Brentwood, City of - On-Call Agreement |  | 13161.13
2025-08-01 | 74.1143 | East Contra Costa Irrigation District - On-Call Contract |  | 3319.97
2025-08-01 | 74.1144 | East Contra Costa Irrigation District - Fiber Optic Network Infrastructure - East Contra Costa Irrig |  | 1830.29
2025-08-01 | 74.1151 | UC Davis - SCADA Assessment and Recommendations - UC Davis |  | 8087
2025-08-01 | 74.1155 | FOWD Winding Way PRV Comm TRBLSHTING |  | 1025.62
2025-08-01 | 74.1158 | Rancho Murieta Community Services District - Laptop Additions |  | 5980
2025-08-01 | 74.1169 | West Bay Sanitary District - Henderson Pump Station Main Service Disconnect Retrofit |  | 9228
2025-08-01 | 75.1077 | AIC - SoCal Overhead 2025 |  | 317175.74
2025-08-01 | 75.113 | AIC - Estimating 2025 |  | 8626.62
2025-08-01 | 76.1054 | WML - W.M. Lyles - Riverside Public Works - Digester 5 Rehab |  | 81258.14
2025-08-01 | 78.1042 | WML - Trabuco Canyon Water Dist. - SCADA Integration Services |  | 14592.81
2025-08-01 | 78.1049 | WML - East Orange County Water District - SCADA Field Site RTU Prog Ph.1 |  | 13465.79
2025-08-01 | 78.1083 | WML - West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM |  | 65846.74
2025-08-01 | 78.1087 | WML - San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters |  | 5937.7
2025-08-01 | 78.1136 | Irvine Rranch District - MWRP Fueling Facility CP-100 Programming |  | 33310
2025-08-01 | 78.1137 | Irvine Ranch Water District - Michelson Water Recycling Plan |  | 201037
2025-08-01 | 78.1161 | City of Redlands - On-Call Support |  | 31666.64
2025-08-01 | 78.1162 | Trabuco Canyon Water District - SCADA Systems Integrator On-Call Services |  | 2883.72
2025-08-01 | 78.1164 | South Orange County Wasterwater Authority - Solids Open P.O |  | 5000
2025-08-01 | 78.1165 | South Orange County Wasterwater Authority - SCADA Support Solids Open P.O |  | 225
2025-08-01 | 78.1171 | San Gabriel Valley Water Company - Temp Radio System to Support Plant 13 Renovations |  | 31444
2025-08-01 | 73.1134 | Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc |  | 965.51
2025-08-01 | 73.1149 | Aveva Select California - AVEVA Historian Implementation - Kaiser Los Angeles |  | 6368.14
2025-08-01 | 73.1152 | Fusion Electric, In. - Sonoma Truck Level Transmitter Replacement - City of Modesto |  | 2227.97
2025-08-01 | 74.1082 | WML - City of Clovis - Pump Station E New Pump 5 VFD Startup |  | 5141.49
2025-08-01 | 74.1104 | Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric |  | 17053.44
2025-08-01 | 74.111 | WML - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M |  | 4596.42
2025-08-01 | 74.1112 | Westside Water Authority - Pump Station A On-Site Support - Westside Water Au |  | 27279.17
2025-08-01 | 74.1115 | UC Davis - WWTP Annual Instrument Calibrations |  | 7099.52
2025-08-01 | 74.1123 | UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis |  | 6363.82
2025-08-01 | 74.1166 | Chlorine Analyzer Installation Assistance – Valley Springs Public Utility District |  | 2100
2025-08-01 | 78.1016 | WML - Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District |  | 13214.1
2025-08-01 | 78.1084 | WML - South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut |  | 1243.13