## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-06-01 | 70.1077 | AIC - Overhead 2025 | 0 | 0 | -2856.37 | 2025-12-01
2025-06-01 | 71.1077 | AIC - NorCal Overhead 2025 | 0 | 0 | -688153.09 | 2025-12-01
2025-06-01 | 73.1003 | WML- Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 133.75 | 133.75 | 0 | 2025-12-01
2025-06-01 | 73.1004 | WML- San Joaquin Electric - Liberty Ranch Sewer Pump Station | 784.39 | 784.39 | 0 | 2025-09-01
2025-06-01 | 73.1005 | WML- SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 228.75 | 228.75 | 0 | 2025-09-01
2025-06-01 | 73.1007 | WML- Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 133.75 | 133.75 | 0 | 2025-09-01
2025-06-01 | 73.1018 | WML- CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 195 | 195 | 0 | 2026-03-01
2025-06-01 | 73.1019 | WML- Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 14941.83 | 14941.83 | 0 | 2025-12-01
2025-06-01 | 73.1023 | WML- Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 2707.5 | 2707.5 | 0 | 2025-09-01
2025-06-01 | 73.1032 | WML- Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 97.5 | 97.5 | 0 | 2026-03-01
2025-06-01 | 73.1036 | WML- Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 4057.94 | 4057.94 | 0 | 2026-03-01
2025-06-01 | 73.1038 | WML- Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 944.07 | 944.07 | 0 | 2026-03-01
2025-06-01 | 73.1039 | WML- Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 8096.22 | 8096.22 | 0 | 2025-12-01
2025-06-01 | 73.1043 | WML- SD Electric, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 14097.5 | 14097.5 | 0 | 2026-03-01
2025-06-01 | 73.1047 | WML- SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 9600.43 | 9600.43 | 0 | 2026-12-01
2025-06-01 | 73.1048 | WML- Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 1608.75 | 1608.75 | 0 | 2025-09-01
2025-06-01 | 73.105 | WML- Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 6594.88 | 6594.88 | 0 | 2026-12-01
2025-06-01 | 73.1059 | WML- Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 16982.94 | 16982.94 | 0 | 2026-03-01
2025-06-01 | 73.106 | WML- Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 2618.76 | 2618.76 | 0 | 2026-09-01
2025-06-01 | 73.1063 | WML- Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 500.63 | 500.63 | 0 | 2026-03-01
2025-06-01 | 73.1065 | WML- TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 3213.69 | 3213.69 | 0 | 2025-09-01
2025-06-01 | 73.1066 | WML- CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 27560.95 | 27560.95 | 0 | 2025-12-01
2025-06-01 | 73.1067 | WML- Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 3456.88 | 3456.88 | 0 | 2026-06-01
2025-06-01 | 73.1072 | WML- Bullert Industrial Electric, Inc - Washwater Equializer Tank Replacement Project | 15.06 | 15.06 | 0 | 2025-12-01
2025-06-01 | 73.1086 | WML- Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 678.13 | 678.13 | 0 | 2026-06-01
2025-06-01 | 73.1101 | Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 795000 | 795000 | 95861 | 2025-12-01
2025-06-01 | 73.1102 | San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 181657 | 181657 | 0 | 2025-12-01
2025-06-01 | 73.1103 | Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 128000 | 128000 | 11485.9961 | 2025-12-01
2025-06-01 | 73.1105 | Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 180000 | 180000 | 0 | 2026-03-01
2025-06-01 | 73.1106 | Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 464000 | 464000 | 0 | 2025-12-01
2025-06-01 | 73.1107 | San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 485000 | 485000 | 0 | 2026-06-01
2025-06-01 | 73.1109 | Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 123000 | 123000 | 0 | 2026-03-01
2025-06-01 | 73.1111 | California American Water - Luzern Well Treatment Design | 180000 | 180000 | 0 | 2026-03-01
2025-06-01 | 73.1113 | Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 1800000 | 1800000 | 0 | 2026-12-01
2025-06-01 | 73.1119 | SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 59545 | 59545 | 0 | 2026-09-01
2025-06-01 | 73.112 | Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 50000 | 50000 | 0 | 2026-03-01
2025-06-01 | 73.1121 | San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 1325000 | 1325000 | 0 | 2026-06-01
2025-06-01 | 73.1124 | Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 2822000 | 2822000 | 0 | 2026-12-01
2025-06-01 | 73.1125 | Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 198000 | 198000 | 0 | 2025-12-01
2025-06-01 | 73.1126 | Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 225000 | 225000 | 0 | 2026-06-01
2025-06-01 | 73.1127 | Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 734780 | 734780 | 0 | 2026-12-01
2025-06-01 | 73.1128 | Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 214000 | 214000 | 0 | 2025-12-01
2025-06-01 | 73.1131 | North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 105895 | 105895 | 0 | 2026-03-01
2025-06-01 | 73.1134 | Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 4871 | 4871 | 3761.01
2025-06-01 | 73.1135 | San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 163000 | 163000 | 0 | 2026-03-01
2025-06-01 | 73.1141 | Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 32150 | 32150 | 0 | 2026-03-01
2025-06-01 | 73.1142 | Fusion Electric, Inc - Lake Supply Well Pump Station - Lennar | 127000 | 127000 | 0 | 2026-06-01
2025-06-01 | 73.1145 | Strategic Mechanical - Replace Water Storage Tank 731 (#6) – Lemoore Naval Air Stat | 73120 | 73120 | 0 | 2026-03-01
2025-06-01 | 73.1147 | Strategic Mechanical - West Creek Village Mixed Use Development Improvement Plans | 275000 | 275000 | 0 | 2026-09-01
2025-06-01 | 73.1148 | Big Valley Electric - Harvest Water On-Farm Connection Assemblies Project - Sac Ar | 2750000 | 2750000 | 0 | 2026-12-01
2025-06-01 | 73.1149 | Aveva Select California - AVEVA Historian Implementation - Kaiser Los Angeles | 13160 | 13160 | 0 | 2025-12-01
2025-06-01 | 73.115 | Conco-West - Machado Ranch Phase 2 Lumina Park - City of Manteca | 53600 | 53600 | 0 | 2026-09-01
2025-06-01 | 73.1152 | Fusion Electric, In. - Sonoma Truck Level Transmitter Replacement - City of Modesto | 2995 | 2995 | 0
2025-06-01 | 73.1153 | Sac Valley Electric Inc - Lammers Road Zone B Pump Station, Tracy Recycled Water Syste | 1295000 | 1295000 | 0 | 2027-06-01
2025-06-01 | 74.101 | WML - Placer County Water Agency -PCWA Time & Material Contract | 971.56 | 971.56 | 0 | TBD
2025-06-01 | 74.1037 | WML - East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 666.56 | 666.56 | 0 | TBD
2025-06-01 | 74.1046 | WML - California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 5598 | 5598 | 0 | 2025-09-01
2025-06-01 | 74.1051 | WML - Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 55 | 55 | 0 | 2025-09-01
2025-06-01 | 74.1073 | WML - California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 655.63 | 655.63 | 0 | 2026-03-01
2025-06-01 | 74.1075 | WML - California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 527.5 | 527.5 | 0 | 2025-12-01
2025-06-01 | 74.1078 | WML - City of Napa - On-Call Control Systems Integrator Services | 110.63 | 110.63 | 0 | TBD
2025-06-01 | 74.1079 | WML - San Jose Water Co - Montevina PLC Upgrade | 8582.66 | 8582.66 | 0 | 2025-12-01
2025-06-01 | 74.108 | WML - San Jose Water Co - PLC System Assessment | 9297.19 | 9297.19 | 0 | 2025-09-01
2025-06-01 | 74.1081 | WML - Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 10806.88 | 10806.88 | 0 | 2025-09-01
2025-06-01 | 74.1082 | WML - City of Clovis - Pump Station E New Pump 5 VFD Startup | 100.31 | 100.31 | 0 | 2025-09-01
2025-06-01 | 74.1088 | WML - California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 485.31 | 485.31 | 0 | 2026-03-01
2025-06-01 | 74.1089 | WML - San Jose Water - ASE Bell Modem Assistance | 533.44 | 533.44 | 0 | 2025-12-01
2025-06-01 | 74.1104 | Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 48860 | 48860 | 6714.0657 | 2025-09-01
2025-06-01 | 74.1108 | City of Davis - Programming and Panel Modifications at Turnout Sit | 45200 | 45200 | 7336.2472 | 2025-09-01
2025-06-01 | 74.111 | WML - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 9960 | 9960 | 5363.58
2025-06-01 | 74.1112 | Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 42902.3 | 42902.3 | 2297.6181 | TBD
2025-06-01 | 74.1115 | UC Davis - WWTP Annual Instrument Calibrations | 12725 | 12725 | 6829.23 | 2025-06-01
2025-06-01 | 74.1117 | UC Davis - Wastewater Integration Service Contract | 995.63 | 995.63 | 0 | TBD
2025-06-01 | 74.1122 | West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 30300 | 30300 | 1036.6555 | 2025-09-01
2025-06-01 | 74.1123 | UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 12450 | 12450 | 2757.3634 | 2025-09-01
2025-06-01 | 74.1129 | RMCSD - VEEAM SFTWR | 9820 | 9820 | 0 | 2025-09-01
2025-06-01 | 74.1132 | UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 49530 | 49530 | 0 | 2025-09-01
2025-06-01 | 74.1133 | UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 34935 | 34935 | 0 | 2025-09-01
2025-06-01 | 74.1138 | City of Brentwood - SCADA System Upgrade | 1785125 | 1785125 | 229245.0387 | 2025-12-01
2025-06-01 | 74.1139 | City of Brentwood - Brentwood, City of - On-Call Agreement | 5900 | 5900 | -1296.46 | TBD
2025-06-01 | 74.1143 | East Contra Costa Irrigation District - On-Call Contract | 4304 | 4304 | 2307.12 | TBD
2025-06-01 | 74.1144 | East Contra Costa Irrigation District - Fiber Optic Network Infrastructure - East Contra Costa Irrig | 1423.25 | 1423.25 | 0 | TBD
2025-06-01 | 74.1151 | UC Davis - SCADA Assessment and Recommendations - UC Davis | 12500 | 12500 | 0 | 2026-06-01
2025-06-01 | 75.1077 | AIC - SoCal Overhead 2025 | 0 |  | -94464 | 2025-12-01
2025-06-01 | 75.113 | AIC - Estimating 2025 | 0 |  | -8626.62 | 2025-12-01
2025-06-01 | 76.1054 | WML - W.M. Lyles - Riverside Public Works - Digester 5 Rehab | 4354.53 | 4354.53 | 0 | 2026-03-01
2025-06-01 | 78.1016 | WML - Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 6761.45 | 6761.45 | 0 | TBD
2025-06-01 | 78.1042 | WML - Trabuco Canyon Water Dist. - SCADA Integration Services | 12178.75 | 12178.75 | 0 | 2025-09-01
2025-06-01 | 78.1049 | WML - East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 5670.47 | 5670.47 | 0 | 2025-12-01
2025-06-01 | 78.1083 | WML - West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 5419.1 | 5419.1 | 0 | 2026-06-01
2025-06-01 | 78.1084 | WML - South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 901.88 | 901.88 | 0 | TBD
2025-06-01 | 78.1087 | WML - San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 401.25 | 401.25 | 0 | 2025-12-01
2025-06-01 | 78.1136 | Irvine Rranch District - MWRP Fueling Facility CP-100 Programming | 49013 | 49013 | 13970.6945 | 2025-09-01
2025-06-01 | 78.1137 | Irvine Ranch Water District - Michelson Water Recycling Plan | 326800 | 326800 | 61481.5525 | 2026-09-01

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-06-01 | 70.1077 | AIC - Overhead 2025 | 2856.37 | 2856.37
2025-06-01 | 71.1077 | AIC - NorCal Overhead 2025 | 688153.09 | 688153.09
2025-06-01 | 73.1003 | WML- Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 133.75 | 133.75
2025-06-01 | 73.1004 | WML- San Joaquin Electric - Liberty Ranch Sewer Pump Station | 784.39 | 784.39
2025-06-01 | 73.1005 | WML- SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 228.75 | 228.75
2025-06-01 | 73.1007 | WML- Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 133.75 | 133.75
2025-06-01 | 73.1018 | WML- CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 195 | 195
2025-06-01 | 73.1019 | WML- Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 14941.83 | 14941.83
2025-06-01 | 73.1023 | WML- Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 2707.5 | 2707.5
2025-06-01 | 73.1032 | WML- Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 97.5 | 97.5
2025-06-01 | 73.1036 | WML- Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 4057.94 | 4057.94
2025-06-01 | 73.1038 | WML- Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 944.07 | 944.07
2025-06-01 | 73.1039 | WML- Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 8096.22 | 8096.22
2025-06-01 | 73.1043 | WML- SD Electric, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 14097.5 | 14097.5
2025-06-01 | 73.1047 | WML- SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 9600.43 | 9600.43
2025-06-01 | 73.1048 | WML- Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 1608.75 | 1608.75
2025-06-01 | 73.105 | WML- Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 6594.88 | 6594.88
2025-06-01 | 73.1059 | WML- Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 16982.94 | 16982.94
2025-06-01 | 73.106 | WML- Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 2618.76 | 2618.76
2025-06-01 | 73.1063 | WML- Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 500.63 | 500.63
2025-06-01 | 73.1065 | WML- TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 3213.69 | 3213.69
2025-06-01 | 73.1066 | WML- CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 27560.95 | 27560.95
2025-06-01 | 73.1067 | WML- Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 3456.88 | 3456.88
2025-06-01 | 73.1072 | WML- Bullert Industrial Electric, Inc - Washwater Equializer Tank Replacement Project | 15.06 | 15.06
2025-06-01 | 73.1086 | WML- Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 678.13 | 678.13
2025-06-01 | 73.1101 | Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 686904 | 686904
2025-06-01 | 73.1102 | San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 138625 | 138625
2025-06-01 | 73.1103 | Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 103701 | 103701
2025-06-01 | 73.1105 | Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 130981 | 130981
2025-06-01 | 73.1106 | Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 312631 | 312631
2025-06-01 | 73.1107 | San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 418395 | 418395
2025-06-01 | 73.1109 | Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 112265 | 112265
2025-06-01 | 73.1111 | California American Water - Luzern Well Treatment Design | 144956 | 144956
2025-06-01 | 73.1113 | Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 1629439 | 1629439
2025-06-01 | 73.1119 | SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 47941 | 47941
2025-06-01 | 73.112 | Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 40662 | 40662
2025-06-01 | 73.1121 | San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 1174927 | 1174927
2025-06-01 | 73.1124 | Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 2306698 | 2306698
2025-06-01 | 73.1125 | Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 165468 | 165468
2025-06-01 | 73.1126 | Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 188110 | 188110
2025-06-01 | 73.1127 | Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 648296 | 648296
2025-06-01 | 73.1128 | Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 158018 | 158018
2025-06-01 | 73.1131 | North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 72836 | 72836
2025-06-01 | 73.1134 | Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 1109.99 | 1109.99
2025-06-01 | 73.1135 | San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 110078 | 110078
2025-06-01 | 73.1141 | Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 26782.9038 | 26782.9038
2025-06-01 | 73.1142 | Fusion Electric, Inc - Lake Supply Well Pump Station - Lennar | 110347.76 | 110347.76
2025-06-01 | 73.1145 | Strategic Mechanical - Replace Water Storage Tank 731 (#6) – Lemoore Naval Air Stat | 53467.5 | 53467.5
2025-06-01 | 73.1147 | Strategic Mechanical - West Creek Village Mixed Use Development Improvement Plans | 189796.67 | 189796.67
2025-06-01 | 73.1148 | Big Valley Electric - Harvest Water On-Farm Connection Assemblies Project - Sac Ar | 2310428.26 | 2310428.26
2025-06-01 | 73.1149 | Aveva Select California - AVEVA Historian Implementation - Kaiser Los Angeles | 9716 | 9716
2025-06-01 | 73.115 | Conco-West - Machado Ranch Phase 2 Lumina Park - City of Manteca | 34826.65 | 34826.65
2025-06-01 | 73.1152 | Fusion Electric, In. - Sonoma Truck Level Transmitter Replacement - City of Modesto | 2995 | 2995
2025-06-01 | 73.1153 | Sac Valley Electric Inc - Lammers Road Zone B Pump Station, Tracy Recycled Water Syste | 1126309.2075 | 1126309.2075
2025-06-01 | 74.101 | WML - Placer County Water Agency -PCWA Time & Material Contract | 971.56 | 971.56
2025-06-01 | 74.1037 | WML - East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 666.56 | 666.56
2025-06-01 | 74.1046 | WML - California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 5598 | 5598
2025-06-01 | 74.1051 | WML - Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 55 | 55
2025-06-01 | 74.1073 | WML - California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 655.63 | 655.63
2025-06-01 | 74.1075 | WML - California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 527.5 | 527.5
2025-06-01 | 74.1078 | WML - City of Napa - On-Call Control Systems Integrator Services | 110.63 | 110.63
2025-06-01 | 74.1079 | WML - San Jose Water Co - Montevina PLC Upgrade | 8582.66 | 8582.66
2025-06-01 | 74.108 | WML - San Jose Water Co - PLC System Assessment | 9297.19 | 9297.19
2025-06-01 | 74.1081 | WML - Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 10806.88 | 10806.88
2025-06-01 | 74.1082 | WML - City of Clovis - Pump Station E New Pump 5 VFD Startup | 100.31 | 100.31
2025-06-01 | 74.1088 | WML - California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 485.31 | 485.31
2025-06-01 | 74.1089 | WML - San Jose Water - ASE Bell Modem Assistance | 533.44 | 533.44
2025-06-01 | 74.1104 | Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 28628 | 28628
2025-06-01 | 74.1108 | City of Davis - Programming and Panel Modifications at Turnout Sit | 32861 | 32861
2025-06-01 | 74.111 | WML - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 4596.42 | 4596.42
2025-06-01 | 74.1112 | Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 40013.3 | 40013.3
2025-06-01 | 74.1115 | UC Davis - WWTP Annual Instrument Calibrations | 5895.77 | 5895.77
2025-06-01 | 74.1117 | UC Davis - Wastewater Integration Service Contract | 995.63 | 995.63
2025-06-01 | 74.1122 | West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 25315 | 25315
2025-06-01 | 74.1123 | UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 7193 | 7193
2025-06-01 | 74.1129 | RMCSD - VEEAM SFTWR | 6899 | 6899
2025-06-01 | 74.1132 | UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 44530 | 44530
2025-06-01 | 74.1133 | UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 27435 | 27435
2025-06-01 | 74.1138 | City of Brentwood - SCADA System Upgrade | 1139524 | 1139524
2025-06-01 | 74.1139 | City of Brentwood - Brentwood, City of - On-Call Agreement | 4556.46 | 4556.46
2025-06-01 | 74.1143 | East Contra Costa Irrigation District - On-Call Contract | 1996.88 | 1996.88
2025-06-01 | 74.1144 | East Contra Costa Irrigation District - Fiber Optic Network Infrastructure - East Contra Costa Irrig | 1423.25 | 1423.25
2025-06-01 | 74.1151 | UC Davis - SCADA Assessment and Recommendations - UC Davis | 7898.75 | 7898.75
2025-06-01 | 75.1077 | AIC - SoCal Overhead 2025 | 94464 | 94464
2025-06-01 | 75.113 | AIC - Estimating 2025 | 8626.62 | 8626.62
2025-06-01 | 76.1054 | WML - W.M. Lyles - Riverside Public Works - Digester 5 Rehab | 4354.53 | 4354.53
2025-06-01 | 78.1016 | WML - Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 6761.45 | 6761.45
2025-06-01 | 78.1042 | WML - Trabuco Canyon Water Dist. - SCADA Integration Services | 12178.75 | 12178.75
2025-06-01 | 78.1049 | WML - East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 5670.47 | 5670.47
2025-06-01 | 78.1083 | WML - West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 5419.1 | 5419.1
2025-06-01 | 78.1084 | WML - South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 901.88 | 901.88
2025-06-01 | 78.1087 | WML - San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 401.25 | 401.25
2025-06-01 | 78.1136 | Irvine Rranch District - MWRP Fueling Facility CP-100 Programming | 28866 | 28866
2025-06-01 | 78.1137 | Irvine Ranch Water District - Michelson Water Recycling Plan | 201037 | 201037