## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-04-01 | 20.2520. | APC Office Admin/Overhead |  | 0 | -136018.04 | 2025-12-31
2025-04-01 | 20.2530. | APC Yard/Building |  | 0 | -33269.23 | 2025-12-31
2025-04-01 | 20.2540. | APC Warranty Work |  | 0 | 937.12 | 2025-12-31
2025-04-01 | 20.2550. | APC Legal |  | 0 | -2902.03 | 2025-12-31
2025-04-01 | 20.2560. | APC Estimating |  | 0 | -92550.81 | 2025-12-31
2025-04-01 | 20.2570. | APC Equipment |  | 0 | -10396.56 | 2025-12-31
2025-04-01 | 21.2106. | Sturgeon Electric - Ashlan Ave. Corridor |  | 105202 | -10000 | 2025-07-31
2025-04-01 | 21.2304. | City of Merced - Community Park 42 |  | 10454058 | 832037.5 | 2025-07-31
2025-04-01 | 21.2307. | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough |  | 5192802 | 843950.8 | 2025-05-31
2025-04-01 | 21.2310. | City of Porterville - Tule River Parkway Phase 3 |  | 3175038 | 240565.5 | 2025-05-31
2025-04-01 | 21.2312. | City of Fresno - Mariposa Plaza Renovation |  | 2732751.56 | 123876 | 2025-08-31
2025-04-01 | 21.2313. | City of Kerman - Kerman Northwest Park |  | 694995 | 119664 | 2025-08-31
2025-04-01 | 21.2314. | G.L. Associates Bruno - Clovis VA Parking Expansion |  | 1294297 | 0 | 2025-06-30
2025-04-01 | 21.2316. | WM Lyles - Groundwater Blending & Arsenic Treatment Project |  | 1592500 | 188622 | 2025-06-30
2025-04-01 | 21.2317. | City of Fresno - Connecting the Winchell |  | 1819928 | 249600 | 2025-05-31
2025-04-01 | 21.2322. | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite |  | 218864.46 | 70280.1069 | 2025-05-31
2025-04-01 | 21.2323. | WM Lyles - Water Treatment Plant Replacement |  | 1257787.22 | 92512 | 2026-08-31
2025-04-01 | 21.2401. | County of Tulare - M109 Over White River Bridge Replacement Project |  | 5296006.94 | 1503500 | 2025-05-31
2025-04-01 | 21.2403. | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements |  | 1999773 | 232472.5 | 2025-05-31
2025-04-01 | 21.2406. | City of Fresno - BPMP Phase II |  | 734313 | 280907 | 2025-04-30
2025-04-01 | 21.2407. | City of Fresno - South Peach Park Project |  | 9653846.35 | 0 | 2025-10-31
2025-04-01 | 21.2408. | A-C Electric Co. - Friant I.T.S. Phase 2 |  | 84275 | 0 | 2025-12-31
2025-04-01 | 21.2409. | City of Merced - G Street Bridge Railing Repair |  | 147100.21 | 49811 | 2025-05-31
2025-04-01 | 21.2410. | City of Fresno - Barstow and Bond Traffic Signal |  | 1260917 | 0 | 2025-09-30
2025-04-01 | 21.2411. | City of Merced - Bob Hart Square Expansion |  | 3300638 | 0 | 2025-07-31
2025-04-01 | 21.2412. | City of Merced - Main Street Directional (REBID) |  | 965804.7 | 0 | 2025-05-31
2025-04-01 | 21.2413. | NESM - Amazon ADA Improvements |  | 3651 | 569.42 | 2025-04-30
2025-04-01 | 21.2501. | C3 Electric - Lake and Sherwood Traffic Signal |  | 119230 | 22740 | 2025-05-31
2025-04-01 | 21.2502. | HPS Mechanical - Well 7 TCP Mitigation Project |  | 310807 | 0 | 2025-12-31
2025-04-01 | 21.2503. | City of Fresno - Dolores Huerta Park |  | 9950023.15 | 0 | 2026-05-31
2025-04-01 | 21.2504. | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project |  | 168405 | 0 | 2025-06-30
2025-04-01 | 21.2592. | WML Intercompany L&E |  | 3833.55 | 183.02 | 2025-12-31

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-04-01 | 20.2520. | APC Office Admin/Overhead |  | 136018.04
2025-04-01 | 20.2530. | APC Yard/Building |  | 33269.23
2025-04-01 | 20.2540. | APC Warranty Work |  | -937.12
2025-04-01 | 20.2550. | APC Legal |  | 2902.03
2025-04-01 | 20.2560. | APC Estimating |  | 92550.81
2025-04-01 | 20.2570. | APC Equipment |  | 10396.56
2025-04-01 | 21.2106. | Sturgeon Electric - Ashlan Ave. Corridor |  | 115202
2025-04-01 | 21.2304. | City of Merced - Community Park 42 |  | 9529058
2025-04-01 | 21.2307. | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough |  | 4345802
2025-04-01 | 21.2310. | City of Porterville - Tule River Parkway Phase 3 |  | 2860038
2025-04-01 | 21.2312. | City of Fresno - Mariposa Plaza Renovation |  | 2547751.56
2025-04-01 | 21.2313. | City of Kerman - Kerman Northwest Park |  | 559995
2025-04-01 | 21.2314. | G.L. Associates Bruno - Clovis VA Parking Expansion |  | 1184297
2025-04-01 | 21.2316. | WM Lyles - Groundwater Blending & Arsenic Treatment Project |  | 1382500
2025-04-01 | 21.2317. | City of Fresno - Connecting the Winchell |  | 1569928
2025-04-01 | 21.2322. | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite |  | 148181.46
2025-04-01 | 21.2323. | WM Lyles - Water Treatment Plant Replacement |  | 977787.22
2025-04-01 | 21.2401. | County of Tulare - M109 Over White River Bridge Replacement Project |  | 3746006.94
2025-04-01 | 21.2403. | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements |  | 1674773
2025-04-01 | 21.2406. | City of Fresno - BPMP Phase II |  | 453406
2025-04-01 | 21.2407. | City of Fresno - South Peach Park Project |  | 9203846.35
2025-04-01 | 21.2408. | A-C Electric Co. - Friant I.T.S. Phase 2 |  | 69775
2025-04-01 | 21.2409. | City of Merced - G Street Bridge Railing Repair |  | 97289.21
2025-04-01 | 21.2410. | City of Fresno - Barstow and Bond Traffic Signal |  | 1195917
2025-04-01 | 21.2411. | City of Merced - Bob Hart Square Expansion |  | 3110638
2025-04-01 | 21.2412. | City of Merced - Main Street Directional (REBID) |  | 885804.7
2025-04-01 | 21.2413. | NESM - Amazon ADA Improvements |  | 3081.58
2025-04-01 | 21.2501. | C3 Electric - Lake and Sherwood Traffic Signal |  | 79230
2025-04-01 | 21.2502. | HPS Mechanical - Well 7 TCP Mitigation Project |  | 275807
2025-04-01 | 21.2503. | City of Fresno - Dolores Huerta Park |  | 9500023.15
2025-04-01 | 21.2504. | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project |  | 145405
2025-04-01 | 21.2592. | WML Intercompany L&E |  | 3650.53