## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-08-01 | 21.2106 | Sturgeon Electric - Ashlan Ave. Corridor |  | 105202 | -10000 | 2025-07-31
2025-08-01 | 21.2304 | City of Merced - Community Park 42 |  | 10530003 | 926838 | 2025-07-31
2025-08-01 | 21.231 | City of Porterville - Tule River Parkway Phase 3 |  | 3480894.01 | 379282.5 | 2025-06-30
2025-08-01 | 21.2312 | City of Fresno - Mariposa Plaza Renovation |  | 2794794 | 119812 | 2025-08-31
2025-08-01 | 21.2313 | City of Kerman - Kerman Northwest Park |  | 694995 | 125712 | 2025-08-31
2025-08-01 | 21.2314 | G.L. Associates Bruno - Clovis VA Parking Expansion |  | 1294297 | 0 | 2025-06-30
2025-08-01 | 21.2323 | WM Lyles - Water Treatment Plant Replacement |  | 1257787.22 | 123464 | 2026-08-31
2025-08-01 | 21.2401 | County of Tulare - M109 Over White River Bridge Replacement Project |  | 5249337.16 | 1548279.4 | 2025-06-30
2025-08-01 | 21.2403 | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements |  | 2009535 | 324591.4 | 2025-06-30
2025-08-01 | 21.2407 | City of Fresno - South Peach Park Project |  | 9668743 | 145101 | 2025-10-31
2025-08-01 | 21.2408 | A-C Electric Co. - Friant I.T.S. Phase 2 |  | 84275 | 4702.35 | 2025-12-31
2025-08-01 | 21.2409 | City of Merced - G Street Bridge Railing Repair |  | 178520 | 38946.9273 | 2025-06-30
2025-08-01 | 21.241 | City of Fresno - Barstow and Bond Traffic Signal |  | 1291858 | 101706 | 2025-09-30
2025-08-01 | 21.2411 | City of Merced - Bob Hart Square Expansion |  | 3300638 | 122406 | 2025-07-31
2025-08-01 | 21.2412 | City of Merced - Main Street Directional (REBID) |  | 1246171 | 199212 | 2025-06-30
2025-08-01 | 21.2501 | C3 Electric - Lake and Sherwood Traffic Signal |  | 126006 | 8390.8968 | 2025-06-30
2025-08-01 | 21.2502 | HPS Mechanical - Well 7 TCP Mitigation Project |  | 310807 | 0 | 2025-12-31
2025-08-01 | 21.2503 | City of Fresno - Dolores Huerta Park |  | 9967206 | 0 | 2026-05-31
2025-08-01 | 21.2504 | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project |  | 168405 | 0 | 2025-06-30
2025-08-01 | 21.2505 | A-C Electric Co. - Reed Avenue and Reedley College Driveway Traffic Signal |  | 218115 | 0 | 2026-01-31
2025-08-01 | 21.2507 | City of Fresno - Radio Park Renovation |  | 9699827 | 0 | 2025-12-31
2025-08-01 | 21.2591 | LDI Intercompany L&E |  | 25874.2 | 2967.01 | 2025-12-31
2025-08-01 | 21.2592 | WML Intercompany L&E |  | 9009.56 | 569.17 | 2025-12-31
2025-08-01 | 21.2593 | NESM Intercompany L&E |  | 2034.2 | 138.34 | 2025-12-31
2025-08-01 | 20.252 | APC Office Admin/Overhead |  | 0 | -257598.77 | 2025-12-31
2025-08-01 | 20.253 | APC Yard/Building |  | 0 | -93223.66 | 2025-12-31
2025-08-01 | 20.254 | APC Warranty Work |  | 0 | -4975.72 | 2025-12-31
2025-08-01 | 20.255 | APC Legal |  | 0 | -7603.98 | 2025-12-31
2025-08-01 | 20.256 | APC Estimating |  | 0 | -214339.27 | 2025-12-31
2025-08-01 | 20.257 | APC Equipment |  | 0 | -20363.26 | 2025-12-31
2025-08-01 | 20.2571 | APC Yard |  | 0 | -20699.99 | 2025-12-31
2025-08-01 | 21.2307 | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough |  | 5192801.8 | 862136.01 | 2025-06-30
2025-08-01 | 21.2316 | WM Lyles - Groundwater Blending & Arsenic Treatment Project |  | 1603209.73 | 172112.29 | 2025-06-30
2025-08-01 | 21.2317 | City of Fresno - Connecting the Winchell |  | 1815311.42 | 255551.53 | 2025-06-30
2025-08-01 | 21.2322 | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite |  | 218864.46 | 70831.34 | 2025-06-30
2025-08-01 | 21.2406 | City of Fresno - BPMP Phase II |  | 734312.72 | 280244 | 2025-04-30
2025-08-01 | 21.2413 | NESM - Amazon ADA Improvements |  | 3650.84 | 569.26 | 2025-04-30
2025-08-01 | 21.2506 | Showtime Concrete, Inc. - Kaiser Permanente Cypress Charging Station |  | 33252 | 20381.02 | 2025-07-31

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-08-01 | 21.2106 | Sturgeon Electric - Ashlan Ave. Corridor |  | 115202
2025-08-01 | 21.2304 | City of Merced - Community Park 42 |  | 9540003
2025-08-01 | 21.231 | City of Porterville - Tule River Parkway Phase 3 |  | 3075894.01
2025-08-01 | 21.2312 | City of Fresno - Mariposa Plaza Renovation |  | 2654794
2025-08-01 | 21.2313 | City of Kerman - Kerman Northwest Park |  | 559995
2025-08-01 | 21.2314 | G.L. Associates Bruno - Clovis VA Parking Expansion |  | 1184297
2025-08-01 | 21.2323 | WM Lyles - Water Treatment Plant Replacement |  | 1027787.22
2025-08-01 | 21.2401 | County of Tulare - M109 Over White River Bridge Replacement Project |  | 3701057.76
2025-08-01 | 21.2403 | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements |  | 1680535
2025-08-01 | 21.2407 | City of Fresno - South Peach Park Project |  | 9338743
2025-08-01 | 21.2408 | A-C Electric Co. - Friant I.T.S. Phase 2 |  | 69775
2025-08-01 | 21.2409 | City of Merced - G Street Bridge Railing Repair |  | 128051
2025-08-01 | 21.241 | City of Fresno - Barstow and Bond Traffic Signal |  | 1071858
2025-08-01 | 21.2411 | City of Merced - Bob Hart Square Expansion |  | 3070638
2025-08-01 | 21.2412 | City of Merced - Main Street Directional (REBID) |  | 986171
2025-08-01 | 21.2501 | C3 Electric - Lake and Sherwood Traffic Signal |  | 117502
2025-08-01 | 21.2502 | HPS Mechanical - Well 7 TCP Mitigation Project |  | 270807
2025-08-01 | 21.2503 | City of Fresno - Dolores Huerta Park |  | 9527206
2025-08-01 | 21.2504 | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project |  | 145405
2025-08-01 | 21.2505 | A-C Electric Co. - Reed Avenue and Reedley College Driveway Traffic Signal |  | 189115
2025-08-01 | 21.2507 | City of Fresno - Radio Park Renovation |  | 9224827
2025-08-01 | 21.2591 | LDI Intercompany L&E |  | 22907.19
2025-08-01 | 21.2592 | WML Intercompany L&E |  | 8440.39
2025-08-01 | 21.2593 | NESM Intercompany L&E |  | 1895.86
2025-08-01 | 20.252 | APC Office Admin/Overhead |  | 257598.77
2025-08-01 | 20.253 | APC Yard/Building |  | 93223.66
2025-08-01 | 20.254 | APC Warranty Work |  | 4975.72
2025-08-01 | 20.255 | APC Legal |  | 7603.98
2025-08-01 | 20.256 | APC Estimating |  | 214339.27
2025-08-01 | 20.257 | APC Equipment |  | 20363.26
2025-08-01 | 20.2571 | APC Yard |  | 20699.99
2025-08-01 | 21.2307 | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough |  | 4330665.79
2025-08-01 | 21.2316 | WM Lyles - Groundwater Blending & Arsenic Treatment Project |  | 1431097.44
2025-08-01 | 21.2317 | City of Fresno - Connecting the Winchell |  | 1559759.89
2025-08-01 | 21.2322 | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite |  | 148033.12
2025-08-01 | 21.2406 | City of Fresno - BPMP Phase II |  | 454068.72
2025-08-01 | 21.2413 | NESM - Amazon ADA Improvements |  | 3081.58
2025-08-01 | 21.2506 | Showtime Concrete, Inc. - Kaiser Permanente Cypress Charging Station |  | 12870.98