## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-12-01 | 21.2106 | Sturgeon Electric - Ashlan Ave. Corridor | 120553.54 | 138609 | 860.6 | 2026-02-28
2025-12-01 | 21.2304 | City of Merced - Community Park 42 | 10996795.85 | 10996795.85 | 955128 | 2026-06-30
2025-12-01 | 21.231 | City of Porterville - Tule River Parkway Phase 3 | 3543296.49 | 3543296.49 | 404137 | 2026-01-31
2025-12-01 | 21.2312 | City of Fresno - Mariposa Plaza Renovation | 2832729.95 | 2832729.95 | 157930 | 2026-02-28
2025-12-01 | 21.2314 | G.L. Associates Bruno - Clovis VA Parking Expansion | 1294297 | 1294297 | 0 | TBD
2025-12-01 | 21.2323 | WM Lyles - Water Treatment Plant Replacement | 1912857.82 | 1912857.82 | 506428 | 2026-05-31
2025-12-01 | 21.2407 | City of Fresno - South Peach Park Project | 9700445.05 | 9700445.05 | 282981.5 | 2026-09-30
2025-12-01 | 21.2408 | A-C Electric Co. - Friant I.T.S. Phase 2 | 130099.7 | 130099.7 | 29812 | 2026-02-28
2025-12-01 | 21.241 | City of Fresno - Barstow and Bond Traffic Signal | 1320507 | 1320507 | 155660.4 | 2026-02-28
2025-12-01 | 21.2411 | City of Merced - Bob Hart Square Expansion | 3460630.45 | 3460630.45 | 166402 | 2026-08-31
2025-12-01 | 21.2412 | City of Merced - Main Street Directional (REBID) | 1289873 | 1289873 | 248547.6 | 2026-01-31
2025-12-01 | 21.2502 | HPS Mechanical - Well 7 TCP Mitigation Project | 332999.4 | 332999.4 | 0 | 2026-03-31
2025-12-01 | 21.2503 | City of Fresno - Dolores Huerta Park | 9987006.45 | 9987006.45 | 183540 | 2026-07-31
2025-12-01 | 21.2504 | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project | 168405 | 168405 | 0 | 2026-04-30
2025-12-01 | 21.2505 | A-C Electric Co. - Reed Avenue and Reedley College Driveway Traffic Signal | 218115 | 218115 | 0 | 2026-03-31
2025-12-01 | 21.2507 | City of Fresno - Radio Park Renovation | 9177239.8 | 9177239.8 | 0 | 2027-01-31
2025-12-01 | 21.2509 | City of Sanger - Bethel Avenue and Almond Avenue Traffic Signal Improvements | 699952 | 699952 | 0 | 2026-06-30
2025-12-01 | 20.2571 | APC Yard Improvements - Equipment Building | 0 |  | -10673.67 | 2026-01-31
2025-12-01 | 20.2572 | APC Yard Improvements - Ponding Basin | 0 |  | -1656.39 | 2026-03-31
2025-12-01 | 20.2573 | APC Yard Improvements - Equipment Shed | 0 |  | -347.51 | 2026-02-28
2025-12-01 | 20.2574 | APC Yard Improvements - Shop Storage | 0 |  | -2373.78 | 2026-01-31
2025-12-01 | 21.2307 | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough | 5192801.8 | 5192801.8 | 863269.01 | 2025-06-30
2025-12-01 | 21.2313 | City of Kerman - Kerman Northwest Park | 700013.94 | 700013.94 | 157867.49 | 2025-10-31
2025-12-01 | 21.2316 | WM Lyles - Groundwater Blending & Arsenic Treatment Project | 1603209.73 | 1603209.73 | 172112.29 | 2025-06-30
2025-12-01 | 21.2317 | City of Fresno - Connecting the Winchell | 1815311.42 | 1815311.42 | 255551.53 | 2025-06-30
2025-12-01 | 21.2322 | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite | 218864.46 | 218864.46 | 70831.34 | 2025-06-30
2025-12-01 | 21.2401 | County of Tulare - M109 Over White River Bridge Replacement Project | 5256236.75 | 5256236.75 | 1545733.48 | 2025-06-30
2025-12-01 | 21.2403 | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements | 2001595.3 | 2001595.3 | 338795.39 | 2025-06-30
2025-12-01 | 21.2406 | City of Fresno - BPMP Phase II | 734312.72 | 734312.72 | 280244 | 2025-04-30
2025-12-01 | 21.2409 | City of Merced - G Street Bridge Railing Repair | 178520 | 178520 | 50426.74 | 2025-06-30
2025-12-01 | 21.2413 | NESM - Amazon ADA Improvements | 3650.84 | 3650.84 | 569.26 | 2025-04-30
2025-12-01 | 21.2501 | C3 Electric - Lake and Sherwood Traffic Signal | 134976.95 | 134976.95 | 11248.57 | 2025-12-31
2025-12-01 | 21.2506 | Showtime Concrete, Inc. - Kaiser Permanente Cypress Charging Station | 33252 | 33252 | 20381.02 | 2025-07-31
2025-12-01 | 21.2508 | Showtime Concrete - Kaiser Selma Driveway Approaches | 21978 | 21978 | 14303.17 | 2025-10-31
2025-12-01 | 21.251 | Mid Cal Pipeline & Utilities Inc. - Craig Dr. Sewer | 56895.8 | 56895.8 | 20919.93 | 2025-12-31
2025-12-01 | 21.2591 | LDI Intercompany L&E | 25874.2 | 25874.2 | 2967.01 | 2025-12-31
2025-12-01 | 21.2592 | WML Intercompany L&E | 9009.56 | 9009.56 | 569.17 | 2025-12-31
2025-12-01 | 21.2593 | NESM Intercompany L&E | 2034.2 | 2034.2 | 138.34 | 2025-12-31
2025-12-01 | 20.252 | APC Office Admin/Overhead | 0 |  | -417362.06 | 2025-12-31
2025-12-01 | 20.253 | APC Yard/Building | 0 |  | -136442.7 | 2025-12-31
2025-12-01 | 20.254 | APC Warranty Work | 0 |  | -4786.46 | 2025-12-31
2025-12-01 | 20.255 | APC Legal | 0 |  | -7603.98 | 2025-12-31
2025-12-01 | 20.256 | APC Estimating | 0 |  | -345355.21 | 2025-12-31
2025-12-01 | 20.257 | APC Equipment | 0 |  | -28346.72 | 2025-12-31

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-12-01 | 21.2106 | Sturgeon Electric - Ashlan Ave. Corridor | 119553.54 | 137609
2025-12-01 | 21.2304 | City of Merced - Community Park 42 | 9976795.85 | 9976795.85
2025-12-01 | 21.231 | City of Porterville - Tule River Parkway Phase 3 | 3133296.49 | 3133296.49
2025-12-01 | 21.2312 | City of Fresno - Mariposa Plaza Renovation | 2662729.95 | 2662729.95
2025-12-01 | 21.2314 | G.L. Associates Bruno - Clovis VA Parking Expansion | 1184297 | 1184297
2025-12-01 | 21.2323 | WM Lyles - Water Treatment Plant Replacement | 1392857.82 | 1392857.82
2025-12-01 | 21.2407 | City of Fresno - South Peach Park Project | 9282945.05 | 9282945.05
2025-12-01 | 21.2408 | A-C Electric Co. - Friant I.T.S. Phase 2 | 90099.7 | 90099.7
2025-12-01 | 21.241 | City of Fresno - Barstow and Bond Traffic Signal | 1068507 | 1068507
2025-12-01 | 21.2411 | City of Merced - Bob Hart Square Expansion | 3270630.45 | 3270630.45
2025-12-01 | 21.2412 | City of Merced - Main Street Directional (REBID) | 1037873 | 1037873
2025-12-01 | 21.2502 | HPS Mechanical - Well 7 TCP Mitigation Project | 277999.4 | 277999.4
2025-12-01 | 21.2503 | City of Fresno - Dolores Huerta Park | 9527006.45 | 9527006.45
2025-12-01 | 21.2504 | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project | 145405 | 145405
2025-12-01 | 21.2505 | A-C Electric Co. - Reed Avenue and Reedley College Driveway Traffic Signal | 189115 | 189115
2025-12-01 | 21.2507 | City of Fresno - Radio Park Renovation | 8702239.8 | 8702239.8
2025-12-01 | 21.2509 | City of Sanger - Bethel Avenue and Almond Avenue Traffic Signal Improvements | 654952 | 654952
2025-12-01 | 20.2571 | APC Yard Improvements - Equipment Building | 10673.67 | 10673.67
2025-12-01 | 20.2572 | APC Yard Improvements - Ponding Basin | 1656.39 | 1656.39
2025-12-01 | 20.2573 | APC Yard Improvements - Equipment Shed | 347.51 | 347.51
2025-12-01 | 20.2574 | APC Yard Improvements - Shop Storage | 2373.78 | 2373.78
2025-12-01 | 21.2307 | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough | 4329532.79 | 4329532.79
2025-12-01 | 21.2313 | City of Kerman - Kerman Northwest Park | 542146.45 | 542146.45
2025-12-01 | 21.2316 | WM Lyles - Groundwater Blending & Arsenic Treatment Project | 1431097.44 | 1431097.44
2025-12-01 | 21.2317 | City of Fresno - Connecting the Winchell | 1559759.89 | 1559759.89
2025-12-01 | 21.2322 | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite | 148033.12 | 148033.12
2025-12-01 | 21.2401 | County of Tulare - M109 Over White River Bridge Replacement Project | 3710503.27 | 3710503.27
2025-12-01 | 21.2403 | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements | 1662799.91 | 1662799.91
2025-12-01 | 21.2406 | City of Fresno - BPMP Phase II | 454068.72 | 454068.72
2025-12-01 | 21.2409 | City of Merced - G Street Bridge Railing Repair | 128093.26 | 128093.26
2025-12-01 | 21.2413 | NESM - Amazon ADA Improvements | 3081.58 | 3081.58
2025-12-01 | 21.2501 | C3 Electric - Lake and Sherwood Traffic Signal | 123728.38 | 123728.38
2025-12-01 | 21.2506 | Showtime Concrete, Inc. - Kaiser Permanente Cypress Charging Station | 12870.98 | 12870.98
2025-12-01 | 21.2508 | Showtime Concrete - Kaiser Selma Driveway Approaches | 7674.83 | 7674.83
2025-12-01 | 21.251 | Mid Cal Pipeline & Utilities Inc. - Craig Dr. Sewer | 35975.87 | 35975.87
2025-12-01 | 21.2591 | LDI Intercompany L&E | 22907.19 | 22907.19
2025-12-01 | 21.2592 | WML Intercompany L&E | 8440.39 | 8440.39
2025-12-01 | 21.2593 | NESM Intercompany L&E | 1895.86 | 1895.86
2025-12-01 | 20.252 | APC Office Admin/Overhead | 417362.06 | 417362.06
2025-12-01 | 20.253 | APC Yard/Building | 136442.7 | 136442.7
2025-12-01 | 20.254 | APC Warranty Work | 4786.46 | 4786.46
2025-12-01 | 20.255 | APC Legal | 7603.98 | 7603.98
2025-12-01 | 20.256 | APC Estimating | 345355.21 | 345355.21
2025-12-01 | 20.257 | APC Equipment | 28346.72 | 28346.72