## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-07-01 | 21.2106 | Sturgeon Electric - Ashlan Ave. Corridor |  | 105202 | -10000 | 2025-07-31
2025-07-01 | 21.2304 | City of Merced - Community Park 42 |  | 10454058 | 933471 | 2025-07-31
2025-07-01 | 21.2307 | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough |  | 5192802 | 844373.3364 | 2025-06-30
2025-07-01 | 21.231 | City of Porterville - Tule River Parkway Phase 3 |  | 3384841.97 | 371400 | 2025-06-30
2025-07-01 | 21.2312 | City of Fresno - Mariposa Plaza Renovation |  | 2794794 | 121407 | 2025-08-31
2025-07-01 | 21.2313 | City of Kerman - Kerman Northwest Park |  | 694995 | 125658 | 2025-08-31
2025-07-01 | 21.2314 | G.L. Associates Bruno - Clovis VA Parking Expansion |  | 1294297 | 0 | 2025-06-30
2025-07-01 | 21.2316 | WM Lyles - Groundwater Blending & Arsenic Treatment Project |  | 1603209.73 | 169592 | 2025-06-30
2025-07-01 | 21.2322 | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite |  | 218864.46 | 70612.317 | 2025-06-30
2025-07-01 | 21.2323 | WM Lyles - Water Treatment Plant Replacement |  | 1257787.22 | 93688 | 2026-08-31
2025-07-01 | 21.2401 | County of Tulare - M109 Over White River Bridge Replacement Project |  | 5249337.75 | 1548647.21 | 2025-06-30
2025-07-01 | 21.2403 | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements |  | 2009535 | 322714.7146 | 2025-06-30
2025-07-01 | 21.2407 | City of Fresno - South Peach Park Project |  | 9668743 | 158440 | 2025-10-31
2025-07-01 | 21.2408 | A-C Electric Co. - Friant I.T.S. Phase 2 |  | 84275 | 0 | 2025-12-31
2025-07-01 | 21.2409 | City of Merced - G Street Bridge Railing Repair |  | 178520 | 39802.8774 | 2025-06-30
2025-07-01 | 21.241 | City of Fresno - Barstow and Bond Traffic Signal |  | 1260917 | 0 | 2025-09-30
2025-07-01 | 21.2411 | City of Merced - Bob Hart Square Expansion |  | 3300638 | 111202 | 2025-07-31
2025-07-01 | 21.2412 | City of Merced - Main Street Directional (REBID) |  | 1263028 | 186395 | 2025-06-30
2025-07-01 | 21.2501 | C3 Electric - Lake and Sherwood Traffic Signal |  | 119230 | 5666.5 | 2025-06-30
2025-07-01 | 21.2502 | HPS Mechanical - Well 7 TCP Mitigation Project |  | 310807 | 0 | 2025-12-31
2025-07-01 | 21.2503 | City of Fresno - Dolores Huerta Park |  | 9950023.15 | 0 | 2026-05-31
2025-07-01 | 21.2504 | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project |  | 168405 | 0 | 2025-06-30
2025-07-01 | 21.2505 | A-C Electric Co. - Reed Avenue and Reedley College Driveway Traffic Signal |  | 218115 | 0 | 2025-12-31
2025-07-01 | 21.2506 | Showtime Concrete, Inc. - Kaiser Permanente Cypress Charging Station |  | 33252 | 13383.0823 | 2025-07-31
2025-07-01 | 21.2591 | LDI Intercompany L&E |  | 25874.2 | 2967.01 | 2025-12-31
2025-07-01 | 21.2592 | WML Intercompany L&E |  | 4614.08 | 204.25 | 2025-12-31
2025-07-01 | 20.252 | APC Office Admin/Overhead |  | 0 | -230528.88 | 2025-12-31
2025-07-01 | 20.253 | APC Yard/Building |  | 0 | -78723.37 | 2025-12-31
2025-07-01 | 20.254 | APC Warranty Work |  | 0 | -8571.71 | 2025-12-31
2025-07-01 | 20.255 | APC Legal |  | 0 | -7603.98 | 2025-12-31
2025-07-01 | 20.256 | APC Estimating |  | 0 | -177756.35 | 2025-12-31
2025-07-01 | 20.257 | APC Equipment |  | 0 | -17687.99 | 2025-12-31
2025-07-01 | 20.2571 | APC Yard |  | 0 | -11565 | 2025-12-31
2025-07-01 | 21.2317 | City of Fresno - Connecting the Winchell |  | 1815311.42 | 210598.67 | 2025-06-30
2025-07-01 | 21.2406 | City of Fresno - BPMP Phase II |  | 734312.72 | 280244 | 2025-04-30
2025-07-01 | 21.2413 | NESM - Amazon ADA Improvements |  | 3650.84 | 569.26 | 2025-04-30

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-07-01 | 21.2106 | Sturgeon Electric - Ashlan Ave. Corridor |  | 115202
2025-07-01 | 21.2304 | City of Merced - Community Park 42 |  | 9464058
2025-07-01 | 21.2307 | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough |  | 4345548
2025-07-01 | 21.231 | City of Porterville - Tule River Parkway Phase 3 |  | 2984841.97
2025-07-01 | 21.2312 | City of Fresno - Mariposa Plaza Renovation |  | 2651794
2025-07-01 | 21.2313 | City of Kerman - Kerman Northwest Park |  | 559995
2025-07-01 | 21.2314 | G.L. Associates Bruno - Clovis VA Parking Expansion |  | 1184297
2025-07-01 | 21.2316 | WM Lyles - Groundwater Blending & Arsenic Treatment Project |  | 1433209.73
2025-07-01 | 21.2322 | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite |  | 148181.46
2025-07-01 | 21.2323 | WM Lyles - Water Treatment Plant Replacement |  | 977787.22
2025-07-01 | 21.2401 | County of Tulare - M109 Over White River Bridge Replacement Project |  | 3700690.54
2025-07-01 | 21.2403 | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements |  | 1680838
2025-07-01 | 21.2407 | City of Fresno - South Peach Park Project |  | 9243743
2025-07-01 | 21.2408 | A-C Electric Co. - Friant I.T.S. Phase 2 |  | 69775
2025-07-01 | 21.2409 | City of Merced - G Street Bridge Railing Repair |  | 126754
2025-07-01 | 21.241 | City of Fresno - Barstow and Bond Traffic Signal |  | 1135917
2025-07-01 | 21.2411 | City of Merced - Bob Hart Square Expansion |  | 3065638
2025-07-01 | 21.2412 | City of Merced - Main Street Directional (REBID) |  | 988028
2025-07-01 | 21.2501 | C3 Electric - Lake and Sherwood Traffic Signal |  | 112230
2025-07-01 | 21.2502 | HPS Mechanical - Well 7 TCP Mitigation Project |  | 270807
2025-07-01 | 21.2503 | City of Fresno - Dolores Huerta Park |  | 9500023.15
2025-07-01 | 21.2504 | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project |  | 145405
2025-07-01 | 21.2505 | A-C Electric Co. - Reed Avenue and Reedley College Driveway Traffic Signal |  | 189115
2025-07-01 | 21.2506 | Showtime Concrete, Inc. - Kaiser Permanente Cypress Charging Station |  | 15353
2025-07-01 | 21.2591 | LDI Intercompany L&E |  | 22907.19
2025-07-01 | 21.2592 | WML Intercompany L&E |  | 4409.83
2025-07-01 | 20.252 | APC Office Admin/Overhead |  | 230528.88
2025-07-01 | 20.253 | APC Yard/Building |  | 78723.37
2025-07-01 | 20.254 | APC Warranty Work |  | 8571.71
2025-07-01 | 20.255 | APC Legal |  | 7603.98
2025-07-01 | 20.256 | APC Estimating |  | 177756.35
2025-07-01 | 20.257 | APC Equipment |  | 17687.99
2025-07-01 | 20.2571 | APC Yard |  | 11565
2025-07-01 | 21.2317 | City of Fresno - Connecting the Winchell |  | 1604712.75
2025-07-01 | 21.2406 | City of Fresno - BPMP Phase II |  | 454068.72
2025-07-01 | 21.2413 | NESM - Amazon ADA Improvements |  | 3081.58