## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-06-01 | 21.2106 | Sturgeon Electric - Ashlan Ave. Corridor | 105202 | 105202 | -10000 | 2025-07-31
2025-06-01 | 21.2304 | City of Merced - Community Park 42 | 10454058 | 10454058 | 906652.5 | 2025-07-31
2025-06-01 | 21.2307 | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough | 5192802 | 5192802 | 844373.3364 | 2025-06-30
2025-06-01 | 21.231 | City of Porterville - Tule River Parkway Phase 3 | 3296397 | 3296397 | 298622 | 2025-06-30
2025-06-01 | 21.2312 | City of Fresno - Mariposa Plaza Renovation | 2794794 | 2794794 | 123163 | 2025-08-31
2025-06-01 | 21.2313 | City of Kerman - Kerman Northwest Park | 694995 | 694995 | 125604 | 2025-08-31
2025-06-01 | 21.2314 | G.L. Associates Bruno - Clovis VA Parking Expansion | 1294297 | 1294297 | 0 | 2025-06-30
2025-06-01 | 21.2316 | WM Lyles - Groundwater Blending & Arsenic Treatment Project | 1603209.73 | 1603209.73 | 168623 | 2025-06-30
2025-06-01 | 21.2322 | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite | 218864.46 | 218864.46 | 70280.1069 | 2025-06-30
2025-06-01 | 21.2323 | WM Lyles - Water Treatment Plant Replacement | 1257787.22 | 1257787.22 | 93352 | 2026-08-31
2025-06-01 | 21.2401 | County of Tulare - M109 Over White River Bridge Replacement Project | 5249337 | 5249337 | 1549380 | 2025-06-30
2025-06-01 | 21.2403 | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements | 2009535 | 2009535 | 315964.8 | 2025-06-30
2025-06-01 | 21.2407 | City of Fresno - South Peach Park Project | 9668743 | 9668743 | 0 | 2025-10-31
2025-06-01 | 21.2408 | A-C Electric Co. - Friant I.T.S. Phase 2 | 84275 | 84275 | 0 | 2025-12-31
2025-06-01 | 21.2409 | City of Merced - G Street Bridge Railing Repair | 178520 | 178520 | 39802.8774 | 2025-06-30
2025-06-01 | 21.241 | City of Fresno - Barstow and Bond Traffic Signal | 1260917 | 1260917 | 0 | 2025-09-30
2025-06-01 | 21.2411 | City of Merced - Bob Hart Square Expansion | 3300638 | 3300638 | 88785 | 2025-07-31
2025-06-01 | 21.2412 | City of Merced - Main Street Directional (REBID) | 1263028 | 1263028 | 153522 | 2025-06-30
2025-06-01 | 21.2501 | C3 Electric - Lake and Sherwood Traffic Signal | 119230 | 119230 | 9564 | 2025-06-30
2025-06-01 | 21.2502 | HPS Mechanical - Well 7 TCP Mitigation Project | 310807 | 310807 | 0 | 2025-12-31
2025-06-01 | 21.2503 | City of Fresno - Dolores Huerta Park | 9950023.15 | 9950023.15 | 0 | 2026-05-31
2025-06-01 | 21.2504 | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project | 168405 | 168405 | 0 | 2025-06-30
2025-06-01 | 21.2505 | A-C Electric Co. - Reed Avenue and Reedley College Driveway Traffic Signal | 218115 | 218115 | 0 | 2025-12-31
2025-06-01 | 21.2506 | Showtime Concrete, Inc. - Kaiser Permanente Cypress Charging Station | 33252 | 33252 | 0 | 2025-12-31
2025-06-01 | 21.2591 | LDI Intercompany L&E | 25874.2 | 25874.2 | 1272.21 | 2025-12-31
2025-06-01 | 21.2592 | WML Intercompany L&E | 4614.08 | 4614.08 | 204.25 | 2025-12-31
2025-06-01 | 20.252 | APC Office Admin/Overhead | 0 | 0 | -201961.56 | 2025-12-31
2025-06-01 | 20.253 | APC Yard/Building | 0 | 0 | -65336.32 | 2025-12-31
2025-06-01 | 20.254 | APC Warranty Work | 0 | 0 | -8461.02 | 2025-12-31
2025-06-01 | 20.255 | APC Legal | 0 | 0 | -7603.98 | 2025-12-31
2025-06-01 | 20.256 | APC Estimating | 0 | 0 | -138912.23 | 2025-12-31
2025-06-01 | 20.257 | APC Equipment | 0 | 0 | -16586.4 | 2025-12-31
2025-06-01 | 20.2571 | APC Yard | 0 | 0 | -4956 | 2025-12-31
2025-06-01 | 21.2317 | City of Fresno - Connecting the Winchell | 1815311.42 | 1815311.42 | 247614.13 | 2025-06-30
2025-06-01 | 21.2406 | City of Fresno - BPMP Phase II | 734312.72 | 734312.72 | 280244 | 2025-04-30
2025-06-01 | 21.2413 | NESM - Amazon ADA Improvements | 3650.84 | 3650.84 | 569.26 | 2025-04-30

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-06-01 | 21.2106 | Sturgeon Electric - Ashlan Ave. Corridor | 115202 | 115202
2025-06-01 | 21.2304 | City of Merced - Community Park 42 | 9479058 | 9479058
2025-06-01 | 21.2307 | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough | 4345548 | 4345548
2025-06-01 | 21.231 | City of Porterville - Tule River Parkway Phase 3 | 2956397 | 2956397
2025-06-01 | 21.2312 | City of Fresno - Mariposa Plaza Renovation | 2639794 | 2639794
2025-06-01 | 21.2313 | City of Kerman - Kerman Northwest Park | 559995 | 559995
2025-06-01 | 21.2314 | G.L. Associates Bruno - Clovis VA Parking Expansion | 1184297 | 1184297
2025-06-01 | 21.2316 | WM Lyles - Groundwater Blending & Arsenic Treatment Project | 1433209.73 | 1433209.73
2025-06-01 | 21.2322 | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite | 148181.46 | 148181.46
2025-06-01 | 21.2323 | WM Lyles - Water Treatment Plant Replacement | 977787.22 | 977787.22
2025-06-01 | 21.2401 | County of Tulare - M109 Over White River Bridge Replacement Project | 3699337 | 3699337
2025-06-01 | 21.2403 | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements | 1685535 | 1685535
2025-06-01 | 21.2407 | City of Fresno - South Peach Park Project | 9193743 | 9193743
2025-06-01 | 21.2408 | A-C Electric Co. - Friant I.T.S. Phase 2 | 69775 | 69775
2025-06-01 | 21.2409 | City of Merced - G Street Bridge Railing Repair | 126754 | 126754
2025-06-01 | 21.241 | City of Fresno - Barstow and Bond Traffic Signal | 1175917 | 1175917
2025-06-01 | 21.2411 | City of Merced - Bob Hart Square Expansion | 3075638 | 3075638
2025-06-01 | 21.2412 | City of Merced - Main Street Directional (REBID) | 993028 | 993028
2025-06-01 | 21.2501 | C3 Electric - Lake and Sherwood Traffic Signal | 107230 | 107230
2025-06-01 | 21.2502 | HPS Mechanical - Well 7 TCP Mitigation Project | 270807 | 270807
2025-06-01 | 21.2503 | City of Fresno - Dolores Huerta Park | 9500023.15 | 9500023.15
2025-06-01 | 21.2504 | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project | 145405 | 145405
2025-06-01 | 21.2505 | A-C Electric Co. - Reed Avenue and Reedley College Driveway Traffic Signal | 189115 | 189115
2025-06-01 | 21.2506 | Showtime Concrete, Inc. - Kaiser Permanente Cypress Charging Station | 26852 | 26852
2025-06-01 | 21.2591 | LDI Intercompany L&E | 24601.99 | 24601.99
2025-06-01 | 21.2592 | WML Intercompany L&E | 4409.83 | 4409.83
2025-06-01 | 20.252 | APC Office Admin/Overhead | 201961.56 | 201961.56
2025-06-01 | 20.253 | APC Yard/Building | 65336.32 | 65336.32
2025-06-01 | 20.254 | APC Warranty Work | 8461.02 | 8461.02
2025-06-01 | 20.255 | APC Legal | 7603.98 | 7603.98
2025-06-01 | 20.256 | APC Estimating | 138912.23 | 138912.23
2025-06-01 | 20.257 | APC Equipment | 16586.4 | 16586.4
2025-06-01 | 20.2571 | APC Yard | 4956 | 4956
2025-06-01 | 21.2317 | City of Fresno - Connecting the Winchell | 1567697.29 | 1567697.29
2025-06-01 | 21.2406 | City of Fresno - BPMP Phase II | 454068.72 | 454068.72
2025-06-01 | 21.2413 | NESM - Amazon ADA Improvements | 3081.58 | 3081.58