## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-11-01 | 21.2106 | Sturgeon Electric - Ashlan Ave. Corridor |  | 156074 | 639.6 | 2026-01-31
2025-11-01 | 21.2304 | City of Merced - Community Park 42 |  | 10996975.85 | 921000 | 2026-07-31
2025-11-01 | 21.231 | City of Porterville - Tule River Parkway Phase 3 |  | 3543296.49 | 334075 | 2026-01-31
2025-11-01 | 21.2312 | City of Fresno - Mariposa Plaza Renovation |  | 2872105.76 | 145216 | 2026-02-28
2025-11-01 | 21.2314 | G.L. Associates Bruno - Clovis VA Parking Expansion |  | 1294297 | 0 | TBD
2025-11-01 | 21.2323 | WM Lyles - Water Treatment Plant Replacement |  | 1903467.24 | 358997.5 | 2026-05-31
2025-11-01 | 21.2407 | City of Fresno - South Peach Park Project |  | 9668743 | 223153 | 2026-09-30
2025-11-01 | 21.2408 | A-C Electric Co. - Friant I.T.S. Phase 2 |  | 127178 | 22312 | 2026-02-28
2025-11-01 | 21.241 | City of Fresno - Barstow and Bond Traffic Signal |  | 1320507 | 146496 | 2026-01-31
2025-11-01 | 21.2411 | City of Merced - Bob Hart Square Expansion |  | 3335864.93 | 177985.6 | 2026-03-31
2025-11-01 | 21.2412 | City of Merced - Main Street Directional (REBID) |  | 1289873 | 247965.3 | 2025-12-31
2025-11-01 | 21.2501 | C3 Electric - Lake and Sherwood Traffic Signal |  | 134977.27 | 10847.1 | 2025-12-31
2025-11-01 | 21.2502 | HPS Mechanical - Well 7 TCP Mitigation Project |  | 332999 | 0 | 2026-03-31
2025-11-01 | 21.2503 | City of Fresno - Dolores Huerta Park |  | 9967206 | 0 | 2026-06-30
2025-11-01 | 21.2504 | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project |  | 168405 | 0 | 2026-01-31
2025-11-01 | 21.2505 | A-C Electric Co. - Reed Avenue and Reedley College Driveway Traffic Signal |  | 218115 | 0 | 2026-02-28
2025-11-01 | 21.2507 | City of Fresno - Radio Park Renovation |  | 9950023 | 0 | TBD
2025-11-01 | 21.2509 | City of Sanger - Bethel Avenue and Almond Avenue Traffic Signal Improvements |  | 699952 | 0 | TBD
2025-11-01 | 21.251 | Mid Cal Pipeline & Utilities Inc. - Craig Dr. Sewer |  | 56895.8 | 19804.08 | 2025-12-31
2025-11-01 | 21.2591 | LDI Intercompany L&E |  | 25874.2 | 2967.01 | 2025-12-31
2025-11-01 | 21.2592 | WML Intercompany L&E |  | 9009.56 | 569.17 | 2025-12-31
2025-11-01 | 21.2593 | NESM Intercompany L&E |  | 2034.2 | 138.34 | 2025-12-31
2025-11-01 | 20.252 | APC Office Admin/Overhead |  | 0 | -358368.19 | 2025-12-31
2025-11-01 | 20.253 | APC Yard/Building |  | 0 | -117566.78 | 2025-12-31
2025-11-01 | 20.254 | APC Warranty Work |  | 0 | -4786.46 | 2025-12-31
2025-11-01 | 20.255 | APC Legal |  | 0 | -7603.98 | 2025-12-31
2025-11-01 | 20.256 | APC Estimating |  | 0 | -304722.82 | 2025-12-31
2025-11-01 | 20.257 | APC Equipment |  | 0 | -26579.4 | 2025-12-31
2025-11-01 | 20.2571 | APC Yard Improvements - Equipment Building |  | 0 | -8002.08 | 2025-12-31
2025-11-01 | 20.2572 | APC Yard Improvements - Ponding Basin |  | 0 | -100 | 2026-01-31
2025-11-01 | 20.2573 | APC Yard Improvements - Equipment Shed |  | 0 | -37.5 | 2026-01-31
2025-11-01 | 20.2574 | APC Yard Improvements - Shop Storage |  | 0 | -830.14 | 2025-12-31
2025-11-01 | 21.2307 | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough |  | 5192801.8 | 863269.01 | 2025-06-30
2025-11-01 | 21.2313 | City of Kerman - Kerman Northwest Park |  | 700013.94 | 157867.49 | 2025-10-31
2025-11-01 | 21.2316 | WM Lyles - Groundwater Blending & Arsenic Treatment Project |  | 1603209.73 | 172112.29 | 2025-06-30
2025-11-01 | 21.2317 | City of Fresno - Connecting the Winchell |  | 1815311.42 | 255551.53 | 2025-06-30
2025-11-01 | 21.2322 | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite |  | 218864.46 | 70831.34 | 2025-06-30
2025-11-01 | 21.2401 | County of Tulare - M109 Over White River Bridge Replacement Project |  | 5256236.75 | 1545733.48 | 2025-06-30
2025-11-01 | 21.2403 | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements |  | 2001595.3 | 338795.39 | 2025-06-30
2025-11-01 | 21.2406 | City of Fresno - BPMP Phase II |  | 734312.72 | 280244 | 2025-04-30
2025-11-01 | 21.2409 | City of Merced - G Street Bridge Railing Repair |  | 178520 | 50426.74 | 2025-06-30
2025-11-01 | 21.2413 | NESM - Amazon ADA Improvements |  | 3650.84 | 569.26 | 2025-04-30
2025-11-01 | 21.2506 | Showtime Concrete, Inc. - Kaiser Permanente Cypress Charging Station |  | 33252 | 20381.02 | 2025-07-31
2025-11-01 | 21.2508 | Showtime Concrete - Kaiser Selma Driveway Approaches |  | 21978 | 14303.17 | 2025-10-31

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-11-01 | 21.2106 | Sturgeon Electric - Ashlan Ave. Corridor |  | 155074
2025-11-01 | 21.2304 | City of Merced - Community Park 42 |  | 9996975.85
2025-11-01 | 21.231 | City of Porterville - Tule River Parkway Phase 3 |  | 3193296.49
2025-11-01 | 21.2312 | City of Fresno - Mariposa Plaza Renovation |  | 2712105.76
2025-11-01 | 21.2314 | G.L. Associates Bruno - Clovis VA Parking Expansion |  | 1184297
2025-11-01 | 21.2323 | WM Lyles - Water Treatment Plant Replacement |  | 1478467.24
2025-11-01 | 21.2407 | City of Fresno - South Peach Park Project |  | 9313743
2025-11-01 | 21.2408 | A-C Electric Co. - Friant I.T.S. Phase 2 |  | 87178
2025-11-01 | 21.241 | City of Fresno - Barstow and Bond Traffic Signal |  | 1080507
2025-11-01 | 21.2411 | City of Merced - Bob Hart Square Expansion |  | 3127864.93
2025-11-01 | 21.2412 | City of Merced - Main Street Directional (REBID) |  | 1036873
2025-11-01 | 21.2501 | C3 Electric - Lake and Sherwood Traffic Signal |  | 123977.27
2025-11-01 | 21.2502 | HPS Mechanical - Well 7 TCP Mitigation Project |  | 287999
2025-11-01 | 21.2503 | City of Fresno - Dolores Huerta Park |  | 9507206
2025-11-01 | 21.2504 | A-C Electric Co. - Clovis Avenue Adaptive Traffic Signal Sychronization Project |  | 145405
2025-11-01 | 21.2505 | A-C Electric Co. - Reed Avenue and Reedley College Driveway Traffic Signal |  | 189115
2025-11-01 | 21.2507 | City of Fresno - Radio Park Renovation |  | 9475023
2025-11-01 | 21.2509 | City of Sanger - Bethel Avenue and Almond Avenue Traffic Signal Improvements |  | 654952
2025-11-01 | 21.251 | Mid Cal Pipeline & Utilities Inc. - Craig Dr. Sewer |  | 36695.8
2025-11-01 | 21.2591 | LDI Intercompany L&E |  | 22907.19
2025-11-01 | 21.2592 | WML Intercompany L&E |  | 8440.39
2025-11-01 | 21.2593 | NESM Intercompany L&E |  | 1895.86
2025-11-01 | 20.252 | APC Office Admin/Overhead |  | 358368.19
2025-11-01 | 20.253 | APC Yard/Building |  | 117566.78
2025-11-01 | 20.254 | APC Warranty Work |  | 4786.46
2025-11-01 | 20.255 | APC Legal |  | 7603.98
2025-11-01 | 20.256 | APC Estimating |  | 304722.82
2025-11-01 | 20.257 | APC Equipment |  | 26579.4
2025-11-01 | 20.2571 | APC Yard Improvements - Equipment Building |  | 8002.08
2025-11-01 | 20.2572 | APC Yard Improvements - Ponding Basin |  | 100
2025-11-01 | 20.2573 | APC Yard Improvements - Equipment Shed |  | 37.5
2025-11-01 | 20.2574 | APC Yard Improvements - Shop Storage |  | 830.14
2025-11-01 | 21.2307 | Madera County - Ave 25 Bridge Replacement Proj. at Ash Slough |  | 4329532.79
2025-11-01 | 21.2313 | City of Kerman - Kerman Northwest Park |  | 542146.45
2025-11-01 | 21.2316 | WM Lyles - Groundwater Blending & Arsenic Treatment Project |  | 1431097.44
2025-11-01 | 21.2317 | City of Fresno - Connecting the Winchell |  | 1559759.89
2025-11-01 | 21.2322 | A-C Electric Co. - Kaiser Fresno Modular MOB-Offsite |  | 148033.12
2025-11-01 | 21.2401 | County of Tulare - M109 Over White River Bridge Replacement Project |  | 3710503.27
2025-11-01 | 21.2403 | City of Fresno - Woodward & Roeding Tot Lots & ADA Accessibility Improvements |  | 1662799.91
2025-11-01 | 21.2406 | City of Fresno - BPMP Phase II |  | 454068.72
2025-11-01 | 21.2409 | City of Merced - G Street Bridge Railing Repair |  | 128093.26
2025-11-01 | 21.2413 | NESM - Amazon ADA Improvements |  | 3081.58
2025-11-01 | 21.2506 | Showtime Concrete, Inc. - Kaiser Permanente Cypress Charging Station |  | 12870.98
2025-11-01 | 21.2508 | Showtime Concrete - Kaiser Selma Driveway Approaches |  | 7674.83