## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-04-01 | 31.1059. | W.M. Lyles Co. - ECWAP |  | 243894.7665 | 11614.0365 | 2025-04-25
2025-04-01 | 32.2056. | Bernards Brothers - Fresno Co. West Annex Jail |  | 17006858 | -5800000 | 2025-05-01
2025-04-01 | 32.2230. | GL Associates Bruno - VCH, Food Service Renovations |  | 411100 | 0 | 2025-09-01
2025-04-01 | 32.2239. | CRMC - CMC 2030 Program Support |  | 105444 | 43538.76 | 2025-04-01
2025-04-01 | 32.2254. | VCH - CIP 662 Cooling Tower #2 Replacement |  | 1017300 | 212992.54 | 2025-04-01
2025-04-01 | 32.2255. | Kruger / VCH - ECHO Cardiology IDMP |  | 212000 | 23132.761 | 2025-10-01
2025-04-01 | 32.2257. | Kruger / VCH - Kruger - PICU IDMP Reno & Re-Pipe |  | 1177800 | 49735.8151 | 2025-07-01
2025-04-01 | 32.2258. | City of Dos Palos-Water Treatment Plant Replacement |  | 491273.39 | 0 | 2025-12-01
2025-04-01 | 32.2260. | VCH - CIP 669 MRI #3 |  | 422650 | 59385.6925 | 2025-05-01
2025-04-01 | 32.2262. | Middle River Power BESS - Henrietta |  | 354432.82 | 67840.1236 | 2025-06-01
2025-04-01 | 32.2263. | VCH - Cooling Tower #1 |  | 648500 | 0 | 2026-02-01
2025-04-01 | 35.5193. | McCarthy Bldg. Co. - Kaiser Fresno Acute Service Exp. |  | 1487948 | -25000 | 2025-06-01
2025-04-01 | 35.5260. | PG&E - Helms Switchyard Elevator Ventilation Upgrade |  | 639475 | 24779.0776 | 2025-07-01
2025-04-01 | 35.5282. | Seals Constr. - SAMC, Switchgear Fire Pump |  | 905339 | -100000 | 2025-05-01
2025-04-01 | 35.5288. | Seals Constr. - SCCCD, Applied Technology Ph. 1, Clovis CC |  | 10032118 | -1110000 | 2025-05-01
2025-04-01 | 35.5299. | David A Bush - Dinuba High School |  | 5279141 | 678943.64 | 2025-04-01
2025-04-01 | 35.5302. | H&R Facilities - Citrus, Sheet Metal and Piping Work |  | 3962019.16 | 27367.45 | 2025-04-01
2025-04-01 | 35.5319. | Zumwalt Construction - VCH, CT 64 Replacement |  | 530330 | -80000 | 2025-08-01
2025-04-01 | 35.5321. | FUSD - HVAC Design-Build |  | 39854946.44 | 9518355.3516 | 2025-12-01
2025-04-01 | 35.5323. | GL Assoc. Bruno - VCH, Lab Remodel (Design/Build) |  | 936700 | 0 | 2026-12-01
2025-04-01 | 35.5325. | Kaiser Foundation - FRS MC Cabinet Inst. Drying |  | 62777 | 724.3102 | 2025-06-01
2025-04-01 | 35.5327. | VCH - Sterilizer Room Mod. (GO219) |  | 259011.48 | 22688.09 | 2025-04-25
2025-04-01 | 35.5328. | VCH - RTAC-4 Design & Build |  | 4367300 | 136841.9486 | 2025-12-01
2025-04-01 | 35.5336. | VCH - Utility Relocation (CEP to K-Line Pit) |  | 3620048 | 35399.2735 | 2025-12-01
2025-04-01 | 35.5337. | VCH - CIP 673 Elevator Retrofit |  | 960900 | 0 | 2027-12-01
2025-04-01 | 35.5338. | Sanger Ed Complex-Ph 3 - ASM |  | 4250000 | 80400.3266 | 2025-12-01
2025-04-01 | 35.5339. | FUSD - Dailey Elementary Charter School - HVAC Improvements |  | 1086960 | 153555.26 | 2025-04-01
2025-04-01 | 35.5342. | VCH - Kruger - Simulation Area |  | 79300 | 5252.03 | 2025-04-01
2025-04-01 | 35.5343. | FUSD - Sunnyside High School Chiller Replacements |  | 489000 | 34669.6077 | 2025-06-01
2025-04-01 | 35.5344. | Kaiser - Clovis Main Corridor Restroom Refresh |  | 125900 | 1766.328 | 2025-07-01
2025-04-01 | 35.5346. | Harris Construction - Terry Bradley Educational Center, Increment 5 |  | 1169000 | 8536.63 | 2026-08-01
2025-04-01 | 35.5347. | GL Bruno - Home Care AC Redesign (VCH) |  | 826800 | 15705.9804 | 2025-12-01
2025-04-01 | 35.5348. | VCH CSA 22 System Improvements |  | 1680292 | 0 | 2026-06-01
2025-04-01 | 35.5349. | Construction Division - Administration OH 2025 FY |  | 0 | -939614.26 | 2025-12-01
2025-04-01 | 35.5350. | Construction Division - Pursuit OH 2025 FY |  | 0 | -319781.51 | 2025-12-01
2025-04-01 | 35.5351. | Construction Division - Engineering OH 2025 FY |  | 0 | -139073.79 | 2025-12-01
2025-04-01 | 35.5352. | Construction Division - Warranty for Closed Jobs 2025 FY |  | 0 | -59750.89 | 2025-12-01
2025-04-01 | 35.5353. | VCH - Small Jobs 2025 FY |  | 66474.21 | -55000 | 2025-12-01
2025-04-01 | 35.5354. | SAMC - Maintenance Work Repair 2025 |  | 344126.07 | 0 | 2025-12-01
2025-04-01 | 35.5355. | CMC Work 2025 FY |  | 70000 | -10000 | 2025-12-01
2025-04-01 | 35.5356. | Vegas Builds - DESIGN - Lyles Sacramento - Ramona Opportunity |  | 125428.75 | 115002.35 | 2025-04-01
2025-04-01 | 35.5357. | Kruger - VCH - Doctor's Lounge |  | 34900 | -1901 | 2025-07-01
2025-04-01 | 35.5358. | SAMC - 1 North Fluoroscopy Rooms 5-7 – Design and Engineerin |  | 25200 | 0 | 2025-12-01
2025-04-01 | 35.5359. | SAMC - Radiology Rooms 1,2,8 and 9 – Design and Engineering |  | 33600 | 0 | 2025-12-01
2025-04-01 | 35.5360. | CRMC- Bob Smittcamp Neurosciences Renovation |  | 4326950 | 0 | 2025-12-01
2025-04-01 | 35.5361. | VCH - Cell Therapy Lab Modifications |  | 2100 | 0 | 2025-12-01
2025-04-01 | 35.5362. | PG&E - Kerckhoff 2 Control Room Ventilation Study |  | 17400 | 472.7793 | 2025-08-01
2025-04-01 | 35.5363. | W.M. Lyles Co.- Aymium |  | 38484.6 | 482.4626 | 2025-12-01
2025-04-01 | 35.5364. | FUSD - Baird Middle School HVAC Equipment Replacement |  | 1279000 | 0 | 2025-10-01
2025-04-01 | 35.5366. | Swinerton - CMC Seismic Compliance Upgrades Project |  | 7000 | 0 | 2027-12-01
2025-04-01 | 35.5367. | CertainTeed - Office HVAC RFP |  | 2000 | 0 | 2025-12-01

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-04-01 | 31.1059. | W.M. Lyles Co. - ECWAP |  | 232280.73
2025-04-01 | 32.2056. | Bernards Brothers - Fresno Co. West Annex Jail |  | 22806858
2025-04-01 | 32.2230. | GL Associates Bruno - VCH, Food Service Renovations |  | 396100
2025-04-01 | 32.2239. | CRMC - CMC 2030 Program Support |  | 61905.24
2025-04-01 | 32.2254. | VCH - CIP 662 Cooling Tower #2 Replacement |  | 804307.46
2025-04-01 | 32.2255. | Kruger / VCH - ECHO Cardiology IDMP |  | 182000
2025-04-01 | 32.2257. | Kruger / VCH - Kruger - PICU IDMP Reno & Re-Pipe |  | 1107800
2025-04-01 | 32.2258. | City of Dos Palos-Water Treatment Plant Replacement |  | 469273.39
2025-04-01 | 32.2260. | VCH - CIP 669 MRI #3 |  | 347650
2025-04-01 | 32.2262. | Middle River Power BESS - Henrietta |  | 269432.82
2025-04-01 | 32.2263. | VCH - Cooling Tower #1 |  | 638500
2025-04-01 | 35.5193. | McCarthy Bldg. Co. - Kaiser Fresno Acute Service Exp. |  | 1512948
2025-04-01 | 35.5260. | PG&E - Helms Switchyard Elevator Ventilation Upgrade |  | 609475
2025-04-01 | 35.5282. | Seals Constr. - SAMC, Switchgear Fire Pump |  | 1005339
2025-04-01 | 35.5288. | Seals Constr. - SCCCD, Applied Technology Ph. 1, Clovis CC |  | 11142118
2025-04-01 | 35.5299. | David A Bush - Dinuba High School |  | 4600197.36
2025-04-01 | 35.5302. | H&R Facilities - Citrus, Sheet Metal and Piping Work |  | 3934651.71
2025-04-01 | 35.5319. | Zumwalt Construction - VCH, CT 64 Replacement |  | 610330
2025-04-01 | 35.5321. | FUSD - HVAC Design-Build |  | 29930386.44
2025-04-01 | 35.5323. | GL Assoc. Bruno - VCH, Lab Remodel (Design/Build) |  | 891700
2025-04-01 | 35.5325. | Kaiser Foundation - FRS MC Cabinet Inst. Drying |  | 60777
2025-04-01 | 35.5327. | VCH - Sterilizer Room Mod. (GO219) |  | 236323.39
2025-04-01 | 35.5328. | VCH - RTAC-4 Design & Build |  | 4117300
2025-04-01 | 35.5336. | VCH - Utility Relocation (CEP to K-Line Pit) |  | 3520048
2025-04-01 | 35.5337. | VCH - CIP 673 Elevator Retrofit |  | 930900
2025-04-01 | 35.5338. | Sanger Ed Complex-Ph 3 - ASM |  | 4040000
2025-04-01 | 35.5339. | FUSD - Dailey Elementary Charter School - HVAC Improvements |  | 933404.74
2025-04-01 | 35.5342. | VCH - Kruger - Simulation Area |  | 74047.97
2025-04-01 | 35.5343. | FUSD - Sunnyside High School Chiller Replacements |  | 454000
2025-04-01 | 35.5344. | Kaiser - Clovis Main Corridor Restroom Refresh |  | 120900
2025-04-01 | 35.5346. | Harris Construction - Terry Bradley Educational Center, Increment 5 |  | 1144000
2025-04-01 | 35.5347. | GL Bruno - Home Care AC Redesign (VCH) |  | 791800
2025-04-01 | 35.5348. | VCH CSA 22 System Improvements |  | 1660292
2025-04-01 | 35.5349. | Construction Division - Administration OH 2025 FY |  | 939614.26
2025-04-01 | 35.5350. | Construction Division - Pursuit OH 2025 FY |  | 319781.51
2025-04-01 | 35.5351. | Construction Division - Engineering OH 2025 FY |  | 139073.79
2025-04-01 | 35.5352. | Construction Division - Warranty for Closed Jobs 2025 FY |  | 59750.89
2025-04-01 | 35.5353. | VCH - Small Jobs 2025 FY |  | 121474.21
2025-04-01 | 35.5354. | SAMC - Maintenance Work Repair 2025 |  | 344126.07
2025-04-01 | 35.5355. | CMC Work 2025 FY |  | 80000
2025-04-01 | 35.5356. | Vegas Builds - DESIGN - Lyles Sacramento - Ramona Opportunity |  | 10426.4
2025-04-01 | 35.5357. | Kruger - VCH - Doctor's Lounge |  | 36801
2025-04-01 | 35.5358. | SAMC - 1 North Fluoroscopy Rooms 5-7 – Design and Engineerin |  | 24700
2025-04-01 | 35.5359. | SAMC - Radiology Rooms 1,2,8 and 9 – Design and Engineering |  | 33100
2025-04-01 | 35.5360. | CRMC- Bob Smittcamp Neurosciences Renovation |  | 4251950
2025-04-01 | 35.5361. | VCH - Cell Therapy Lab Modifications |  | 2100
2025-04-01 | 35.5362. | PG&E - Kerckhoff 2 Control Room Ventilation Study |  | 16400
2025-04-01 | 35.5363. | W.M. Lyles Co.- Aymium |  | 37984.92
2025-04-01 | 35.5364. | FUSD - Baird Middle School HVAC Equipment Replacement |  | 1239000
2025-04-01 | 35.5366. | Swinerton - CMC Seismic Compliance Upgrades Project |  | 7000
2025-04-01 | 35.5367. | CertainTeed - Office HVAC RFP |  | 2000