## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-12-01 | 32.2230 | GL Associates Bruno - VCH, Food Service Renovations | 507000 | 507000 | 0 | 2027-05-01
2025-12-01 | 32.2258 | City of Dos Palos-Water Treatment Plant Replacement | 494981.39 | 494981.39 | 171759.1417 | 2026-03-01
2025-12-01 | 32.2263 | VCH - Cooling Tower #1 | 1317830 | 1317830 | 23056.4496 | 2026-03-01
2025-12-01 | 35.5193 | McCarthy Bldg. Co. - Kaiser Fresno Acute Service Exp. | 1523719 | 1523719 | -160000 | 2026-02-01
2025-12-01 | 35.5260 | PG&E - Helms Switchyard Elevator Ventilation Upgrade | 1128719 | 1128719 | 323889.495 | 2026-02-01
2025-12-01 | 35.5319 | Zumwalt Construction - VCH, CT 64 Replacement | 530330 | 530330 | -100000 | 2026-07-01
2025-12-01 | 35.5323 | GL Assoc. Bruno - VCH, Lab Remodel (Design/Build) | 944692.93 | 944692.93 | 50541.6592 | 2026-12-01
2025-12-01 | 35.5325 | Kaiser Foundation - FRS MC Cabinet Inst. Drying | 112344 | 112344 | -30000 | 2026-02-01
2025-12-01 | 35.5336 | VCH - Utility Relocation (CEP to K-Line Pit) | 3720798 | 3720798 | 88222.3763 | 2026-06-01
2025-12-01 | 35.5337 | VCH - CIP 673 Elevator Retrofit | 960900 | 960900 | 24437.0401 | 2027-12-01
2025-12-01 | 35.5338 | Sanger Ed Complex-Ph 3 - ASM | 4232402 | 4232402 | -600000 | 2026-06-01
2025-12-01 | 35.5346 | Harris Construction - Terry Bradley Educational Center, Increment 5 | 1180355 | 1180355 | -90000 | 2026-08-01
2025-12-01 | 35.5358 | SAMC - 1 North Fluoroscopy Rooms 5-7 – Design and Engineerin | 25200 | 25200 | 10150.6324 | 2026-02-01
2025-12-01 | 35.5359 | SAMC - Radiology Rooms 1,2,8 and 9 – Design and Engineering | 33600 | 33600 | 10746.6129 | 2026-02-01
2025-12-01 | 35.5360 | CRMC- Bob Smittcamp Neurosciences Renovation | 4480637.17 | 4480637.17 | 135443.1452 | 2026-06-01
2025-12-01 | 35.5361 | VCH - Cell Therapy Lab Modifications | 280300 | 280300 | 61535.4631 | 2026-06-01
2025-12-01 | 35.5364 | FUSD - Baird Middle School HVAC Equipment Replacement | 1310859 | 1310859 | 147308.1794 | 2026-02-01
2025-12-01 | 35.5366 | Swinerton - CMC Seismic Compliance Upgrades Project | 2922020 | 2922020 | 172433.5477 | 2027-12-01
2025-12-01 | 35.5367 | CertainTeed - Office HVAC RFP | 26800 | 26800 | 927.392 | 2026-12-01
2025-12-01 | 35.5369 | Granite Construction - Faraday Microgrid (FR_VCH Solar CIP 646 Microgrid Energy Fac) | 254582 | 254582 | 0 | 2026-06-01
2025-12-01 | 35.5370 | FUSD - HVAC Replacements at 8 Various Sites - Bid No. 25-48 | 8753825 | 8753825 | 1488143.8 | 2026-02-01
2025-12-01 | 35.5371 | FUSD - Aynesworth and Calwa Elementary Schools | 2883856 | 2883856 | 184074.9601 | 2026-02-01
2025-12-01 | 35.5372 | Kaiser - NFSA 2023 CTP FRS MC Tissue Processor Lifecycle | 41000 | 41000 | 0 | 2026-02-01
2025-12-01 | 35.5374 | VCH - SPD Decontamination Sink (CIP 729) | 77800 | 77800 | 38628.777 | 2026-02-01
2025-12-01 | 35.5376 | Kaiser - Clovis MOB Medicine Refrigerators Battery Back Up Optimization | 49900 | 49900 | 0 | 2026-04-01
2025-12-01 | 35.5377 | Kruger - VCH Biosafety Cabinets | 9200 | 9200 | 3678.1786 | 2026-02-01
2025-12-01 | 35.5378 | FUSD - Ahwahnee Middle School Gym HVAC Upgrade | 644900 | 644900 | 0 | 2026-07-01
2025-12-01 | 35.5379 | Central USD - Bid 2425-1405 - Rebid Roosevelt Elementary School Café HVAC | 325000 | 325000 | 0 | 2026-07-01
2025-12-01 | 35.5380 | SCCC - Bid No. 2526-06- FCC Forum Hall Reroof & HVAC Replacement | 1157000 | 1157000 | 0 | 2026-07-01
2025-12-01 | 35.5381 | VCH - CIP 646 Waterline Relocate at Microgrid | 83030 | 83030 | 4137.0793 | 2026-02-01
2025-12-01 | 35.5382 | SCCCD - Auto Booth Seismic Flex Loop Install - West Fresno Center, F | 193900 | 193900 | 0 | 2026-03-01
2025-12-01 | 35.5383 | SCCCD - FCC - Bookstore Reroof & HVAC Replacment | 2138700 | 2138700 | 0 | 2026-07-01
2025-12-01 | 31.1059 | W.M. Lyles Co. - ECWAP | 243894.7665 | 243894.7665 | 11614.0365 | 2025-04-25
2025-12-01 | 32.2056 | Bernards Brothers - Fresno Co. West Annex Jail | 17116858 | 17116858 | -5579847.01 | 2025-12-01
2025-12-01 | 32.2239 | CRMC - CMC 2030 Program Support | 105444 | 105444 | 43538.76 | 2025-04-01
2025-12-01 | 32.2254 | VCH - CIP 662 Cooling Tower #2 Replacement | 1017300 | 1017300 | 220049.94 | 2025-04-01
2025-12-01 | 32.2255 | Kruger / VCH - ECHO Cardiology IDMP | 179650 | 179650 | 39082.35 | 2025-12-01
2025-12-01 | 32.2257 | Kruger / VCH - Kruger - PICU IDMP Reno & Re-Pipe | 1168969 | 1168969 | 263440.44 | 2025-11-01
2025-12-01 | 32.2260 | VCH - CIP 669 MRI #3 | 405950 | 405950 | 130677.52 | 2025-12-01
2025-12-01 | 32.2262 | Middle River Power BESS - Henrietta | 360762.82 | 360762.82 | 145260.09 | 2025-06-01
2025-12-01 | 35.5282 | Seals Constr. - SAMC, Switchgear Fire Pump | 886099 | 886099 | -109003.77 | 2025-09-26
2025-12-01 | 35.5288 | Seals Constr. - SCCCD, Applied Technology Ph. 1, Clovis CC | 10032117.5 | 10032117.5 | -1121576.85 | 2025-09-26
2025-12-01 | 35.5299 | David A Bush - Dinuba High School | 5279141 | 5279141 | 678943.64 | 2025-04-01
2025-12-01 | 35.5302 | H&R Facilities - Citrus, Sheet Metal and Piping Work | 3962019.16 | 3962019.16 | 27367.45 | 2025-04-01
2025-12-01 | 35.5321 | FUSD - HVAC Design-Build | 39854946.44 | 39854946.44 | 11171902.52 | 2025-12-01
2025-12-01 | 35.5327 | VCH - Sterilizer Room Mod. (GO219) | 259011.48 | 259011.48 | 22688.09 | 2025-04-25
2025-12-01 | 35.5328 | VCH - RTAC-4 Engineering/Design | 4650803 | 4650803 | 910291.46 | 2025-12-01
2025-12-01 | 35.5339 | FUSD - Dailey Elementary Charter School - HVAC Improvements | 1086960 | 1086960 | 140327.95 | 2025-04-01
2025-12-01 | 35.5342 | VCH - Kruger - Simulation Area | 79300 | 79300 | 5252.03 | 2025-04-01
2025-12-01 | 35.5343 | FUSD - Sunnyside High School Chiller Replacements | 532951 | 532951 | 51136.41 | 2025-10-01
2025-12-01 | 35.5344 | Kaiser - Clovis Main Corridor Restroom Refresh | 146990 | 146990 | 28733.47 | 2025-12-01
2025-12-01 | 35.5347 | GL Bruno - Home Care AC Redesign (VCH) | 807078 | 807078 | 178651.98 | 2025-10-01
2025-12-01 | 35.5348 | G.L. Associates Bruno - VCH CSA 22 System Improvements | 1463485.03 | 1463485.03 | 103667.6 | 2025-11-28
2025-12-01 | 35.5349 | Construction Division - Administration OH 2025 FY | 0 | 0 | -2411363.84 | 2025-12-01
2025-12-01 | 35.5350 | Construction Division - Pursuit OH 2025 FY | 0 | 0 | -845739.25 | 2025-12-01
2025-12-01 | 35.5351 | Construction Division - Engineering OH 2025 FY | 0 | 0 | -331849.41 | 2025-12-01
2025-12-01 | 35.5352 | Construction Division - Warranty for Closed Jobs 2025 FY | 0 | 0 | -71917.56 | 2025-12-01
2025-12-01 | 35.5353 | VCH - Small Jobs 2025 FY | 192488.64 | 192488.64 | -118210.46 | 2025-12-01
2025-12-01 | 35.5354 | SAMC - Maintenance Work Repair 2025 | 500401.4 | 500401.4 | 158969.92 | 2025-12-01
2025-12-01 | 35.5355 | CMC Work 2025 FY | 91979 | 91979 | -10198.7 | 2025-12-01
2025-12-01 | 35.5356 | Vegas Builds - DESIGN - Lyles Sacramento - Ramona Opportunity | 125428.75 | 125428.75 | 115002.35 | 2025-04-01
2025-12-01 | 35.5357 | Kruger - VCH - Doctor's Lounge | 34900 | 34900 | -2003.17 | 2025-07-01
2025-12-01 | 35.5362 | PG&E - Kerckhoff 2 Control Room Ventilation Study | 17400 | 17400 | 8962.94 | 2025-09-26
2025-12-01 | 35.5363 | W.M. Lyles Co.- Aymium | 2095818.51 | 2095818.51 | 94974.32 | 2025-11-28
2025-12-01 | 35.5365 | VCH- CIP693 Boiler Emission Upgrades #2 - Design Services | 22126 | 22126 | 8659.94 | 2025-12-01
2025-12-01 | 35.5368 | Kaiser - Clovis Rehab Services Conversion | 80454 | 80454 | 43488.1 | 2025-12-01
2025-12-01 | 35.5373 | Kruger - Valley Children's Hospital Small Jobs Fiscal Year 2 | 12793 | 12793 | 7354 | 2025-12-01
2025-12-01 | 35.5375 | VCH - Waiting Room 20148 (20153 etc.) | 211600 | 211600 | 109919.27 | 2025-12-01

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-12-01 | 32.2230 | GL Associates Bruno - VCH, Food Service Renovations | 467000 | 467000
2025-12-01 | 32.2258 | City of Dos Palos-Water Treatment Plant Replacement | 314981.39 | 314981.39
2025-12-01 | 32.2263 | VCH - Cooling Tower #1 | 1267830 | 1267830
2025-12-01 | 35.5193 | McCarthy Bldg. Co. - Kaiser Fresno Acute Service Exp. | 1683719 | 1683719
2025-12-01 | 35.5260 | PG&E - Helms Switchyard Elevator Ventilation Upgrade | 753719 | 753719
2025-12-01 | 35.5319 | Zumwalt Construction - VCH, CT 64 Replacement | 630330 | 630330
2025-12-01 | 35.5323 | GL Assoc. Bruno - VCH, Lab Remodel (Design/Build) | 854692.93 | 854692.93
2025-12-01 | 35.5325 | Kaiser Foundation - FRS MC Cabinet Inst. Drying | 142344 | 142344
2025-12-01 | 35.5336 | VCH - Utility Relocation (CEP to K-Line Pit) | 3520798 | 3520798
2025-12-01 | 35.5337 | VCH - CIP 673 Elevator Retrofit | 890900 | 890900
2025-12-01 | 35.5338 | Sanger Ed Complex-Ph 3 - ASM | 4832402 | 4832402
2025-12-01 | 35.5346 | Harris Construction - Terry Bradley Educational Center, Increment 5 | 1270355 | 1270355
2025-12-01 | 35.5358 | SAMC - 1 North Fluoroscopy Rooms 5-7 – Design and Engineerin | 10200 | 10200
2025-12-01 | 35.5359 | SAMC - Radiology Rooms 1,2,8 and 9 – Design and Engineering | 18600 | 18600
2025-12-01 | 35.5360 | CRMC- Bob Smittcamp Neurosciences Renovation | 4290637.17 | 4290637.17
2025-12-01 | 35.5361 | VCH - Cell Therapy Lab Modifications | 180300 | 180300
2025-12-01 | 35.5364 | FUSD - Baird Middle School HVAC Equipment Replacement | 1140859 | 1140859
2025-12-01 | 35.5366 | Swinerton - CMC Seismic Compliance Upgrades Project | 2522020 | 2522020
2025-12-01 | 35.5367 | CertainTeed - Office HVAC RFP | 24300 | 24300
2025-12-01 | 35.5369 | Granite Construction - Faraday Microgrid (FR_VCH Solar CIP 646 Microgrid Energy Fac) | 249582 | 249582
2025-12-01 | 35.5370 | FUSD - HVAC Replacements at 8 Various Sites - Bid No. 25-48 | 7153825 | 7153825
2025-12-01 | 35.5371 | FUSD - Aynesworth and Calwa Elementary Schools | 2683856 | 2683856
2025-12-01 | 35.5372 | Kaiser - NFSA 2023 CTP FRS MC Tissue Processor Lifecycle | 40000 | 40000
2025-12-01 | 35.5374 | VCH - SPD Decontamination Sink (CIP 729) | 27800 | 27800
2025-12-01 | 35.5376 | Kaiser - Clovis MOB Medicine Refrigerators Battery Back Up Optimization | 47900 | 47900
2025-12-01 | 35.5377 | Kruger - VCH Biosafety Cabinets | 4200 | 4200
2025-12-01 | 35.5378 | FUSD - Ahwahnee Middle School Gym HVAC Upgrade | 624400 | 624400
2025-12-01 | 35.5379 | Central USD - Bid 2425-1405 - Rebid Roosevelt Elementary School Café HVAC | 307000 | 307000
2025-12-01 | 35.5380 | SCCC - Bid No. 2526-06- FCC Forum Hall Reroof & HVAC Replacement | 1147000 | 1147000
2025-12-01 | 35.5381 | VCH - CIP 646 Waterline Relocate at Microgrid | 78030 | 78030
2025-12-01 | 35.5382 | SCCCD - Auto Booth Seismic Flex Loop Install - West Fresno Center, F | 163900 | 163900
2025-12-01 | 35.5383 | SCCCD - FCC - Bookstore Reroof & HVAC Replacment | 2128700 | 2128700
2025-12-01 | 31.1059 | W.M. Lyles Co. - ECWAP | 232280.73 | 232280.73
2025-12-01 | 32.2056 | Bernards Brothers - Fresno Co. West Annex Jail | 22696705.01 | 22696705.01
2025-12-01 | 32.2239 | CRMC - CMC 2030 Program Support | 61905.24 | 61905.24
2025-12-01 | 32.2254 | VCH - CIP 662 Cooling Tower #2 Replacement | 797250.06 | 797250.06
2025-12-01 | 32.2255 | Kruger / VCH - ECHO Cardiology IDMP | 140567.65 | 140567.65
2025-12-01 | 32.2257 | Kruger / VCH - Kruger - PICU IDMP Reno & Re-Pipe | 905528.56 | 905528.56
2025-12-01 | 32.2260 | VCH - CIP 669 MRI #3 | 275272.48 | 275272.48
2025-12-01 | 32.2262 | Middle River Power BESS - Henrietta | 215502.73 | 215502.73
2025-12-01 | 35.5282 | Seals Constr. - SAMC, Switchgear Fire Pump | 995102.77 | 995102.77
2025-12-01 | 35.5288 | Seals Constr. - SCCCD, Applied Technology Ph. 1, Clovis CC | 11153694.35 | 11153694.35
2025-12-01 | 35.5299 | David A Bush - Dinuba High School | 4600197.36 | 4600197.36
2025-12-01 | 35.5302 | H&R Facilities - Citrus, Sheet Metal and Piping Work | 3934651.71 | 3934651.71
2025-12-01 | 35.5321 | FUSD - HVAC Design-Build | 28683043.92 | 28683043.92
2025-12-01 | 35.5327 | VCH - Sterilizer Room Mod. (GO219) | 236323.39 | 236323.39
2025-12-01 | 35.5328 | VCH - RTAC-4 Engineering/Design | 3740511.54 | 3740511.54
2025-12-01 | 35.5339 | FUSD - Dailey Elementary Charter School - HVAC Improvements | 946632.05 | 946632.05
2025-12-01 | 35.5342 | VCH - Kruger - Simulation Area | 74047.97 | 74047.97
2025-12-01 | 35.5343 | FUSD - Sunnyside High School Chiller Replacements | 481814.59 | 481814.59
2025-12-01 | 35.5344 | Kaiser - Clovis Main Corridor Restroom Refresh | 118256.53 | 118256.53
2025-12-01 | 35.5347 | GL Bruno - Home Care AC Redesign (VCH) | 628426.02 | 628426.02
2025-12-01 | 35.5348 | G.L. Associates Bruno - VCH CSA 22 System Improvements | 1359817.43 | 1359817.43
2025-12-01 | 35.5349 | Construction Division - Administration OH 2025 FY | 2411363.84 | 2411363.84
2025-12-01 | 35.5350 | Construction Division - Pursuit OH 2025 FY | 845739.25 | 845739.25
2025-12-01 | 35.5351 | Construction Division - Engineering OH 2025 FY | 331849.41 | 331849.41
2025-12-01 | 35.5352 | Construction Division - Warranty for Closed Jobs 2025 FY | 71917.56 | 71917.56
2025-12-01 | 35.5353 | VCH - Small Jobs 2025 FY | 310699.1 | 310699.1
2025-12-01 | 35.5354 | SAMC - Maintenance Work Repair 2025 | 341431.48 | 341431.48
2025-12-01 | 35.5355 | CMC Work 2025 FY | 102177.7 | 102177.7
2025-12-01 | 35.5356 | Vegas Builds - DESIGN - Lyles Sacramento - Ramona Opportunity | 10426.4 | 10426.4
2025-12-01 | 35.5357 | Kruger - VCH - Doctor's Lounge | 36903.17 | 36903.17
2025-12-01 | 35.5362 | PG&E - Kerckhoff 2 Control Room Ventilation Study | 8437.06 | 8437.06
2025-12-01 | 35.5363 | W.M. Lyles Co.- Aymium | 2000844.19 | 2000844.19
2025-12-01 | 35.5365 | VCH- CIP693 Boiler Emission Upgrades #2 - Design Services | 13466.06 | 13466.06
2025-12-01 | 35.5368 | Kaiser - Clovis Rehab Services Conversion | 36965.9 | 36965.9
2025-12-01 | 35.5373 | Kruger - Valley Children's Hospital Small Jobs Fiscal Year 2 | 5439 | 5439
2025-12-01 | 35.5375 | VCH - Waiting Room 20148 (20153 etc.) | 101680.73 | 101680.73