## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-05-01 | 31.1059. | W.M. Lyles Co. - ECWAP |  | 243894.7665 | 11614.0365 | 2025-04-25
2025-05-01 | 32.2056. | Bernards Brothers - Fresno Co. West Annex Jail |  | 17006858 | -5800000 | 2025-12-01
2025-05-01 | 32.2230. | GL Associates Bruno - VCH, Food Service Renovations |  | 411100 | 0 | 2027-05-01
2025-05-01 | 32.2239. | CRMC - CMC 2030 Program Support |  | 105444 | 43538.76 | 2025-04-01
2025-05-01 | 32.2254. | VCH - CIP 662 Cooling Tower #2 Replacement |  | 1017300 | 220049.94 | 2025-04-01
2025-05-01 | 32.2255. | Kruger / VCH - ECHO Cardiology IDMP |  | 212000 | 23132.761 | 2025-12-01
2025-05-01 | 32.2257. | Kruger / VCH - Kruger - PICU IDMP Reno & Re-Pipe |  | 1177800 | 76222.0598 | 2025-11-01
2025-05-01 | 32.2258. | City of Dos Palos-Water Treatment Plant Replacement |  | 491273.39 | 17110.7482 | 2026-03-01
2025-05-01 | 32.2260. | VCH - CIP 669 MRI #3 |  | 422650 | 85316.1258 | 2025-06-01
2025-05-01 | 32.2262. | Middle River Power BESS - Henrietta |  | 360762.82 | 128864.7464 | 2025-06-01
2025-05-01 | 32.2263. | VCH - Cooling Tower #1 |  | 648500 | 0 | 2026-02-01
2025-05-01 | 35.5193. | McCarthy Bldg. Co. - Kaiser Fresno Acute Service Exp. |  | 1556837 | -5000 | 2025-07-01
2025-05-01 | 35.5260. | PG&E - Helms Switchyard Elevator Ventilation Upgrade |  | 702875 | 22455.4825 | 2025-12-01
2025-05-01 | 35.5282. | Seals Constr. - SAMC, Switchgear Fire Pump |  | 895425 | -100000 | 2025-07-01
2025-05-01 | 35.5288. | Seals Constr. - SCCCD, Applied Technology Ph. 1, Clovis CC |  | 10032118 | -1110000 | 2025-07-01
2025-05-01 | 35.5299. | David A Bush - Dinuba High School |  | 5279141 | 678943.64 | 2025-04-01
2025-05-01 | 35.5302. | H&R Facilities - Citrus, Sheet Metal and Piping Work |  | 3962019.16 | 27367.45 | 2025-04-01
2025-05-01 | 35.5319. | Zumwalt Construction - VCH, CT 64 Replacement |  | 530330 | -80000 | 2025-08-01
2025-05-01 | 35.5321. | FUSD - HVAC Design-Build |  | 39854946.44 | 9776775.7294 | 2025-12-01
2025-05-01 | 35.5323. | GL Assoc. Bruno - VCH, Lab Remodel (Design/Build) |  | 936700 | 19395.2714 | 2026-12-01
2025-05-01 | 35.5325. | Kaiser Foundation - FRS MC Cabinet Inst. Drying |  | 69405 | -5000 | 2025-09-01
2025-05-01 | 35.5327. | VCH - Sterilizer Room Mod. (GO219) |  | 259011.48 | 22688.09 | 2025-04-25
2025-05-01 | 35.5328. | VCH - RTAC-4 Design & Build |  | 4650803 | 138716.4166 | 2025-12-01
2025-05-01 | 35.5336. | VCH - Utility Relocation (CEP to K-Line Pit) |  | 3620048 | 79039.5825 | 2026-06-01
2025-05-01 | 35.5337. | VCH - CIP 673 Elevator Retrofit |  | 960900 | 0 | 2027-12-01
2025-05-01 | 35.5338. | Sanger Ed Complex-Ph 3 - ASM |  | 4253620 | 79209.5951 | 2025-12-01
2025-05-01 | 35.5339. | FUSD - Dailey Elementary Charter School - HVAC Improvements |  | 1086960 | 140272.99 | 2025-04-01
2025-05-01 | 35.5342. | VCH - Kruger - Simulation Area |  | 79300 | 5252.03 | 2025-04-01
2025-05-01 | 35.5343. | FUSD - Sunnyside High School Chiller Replacements |  | 532951 | 31796.1551 | 2025-06-01
2025-05-01 | 35.5344. | Kaiser - Clovis Main Corridor Restroom Refresh |  | 146990 | 1919.9616 | 2025-09-01
2025-05-01 | 35.5346. | Harris Construction - Terry Bradley Educational Center, Increment 5 |  | 1169000 | 2386.8497 | 2026-08-01
2025-05-01 | 35.5347. | GL Bruno - Home Care AC Redesign (VCH) |  | 831300 | 27822.3874 | 2025-12-01
2025-05-01 | 35.5348. | VCH CSA 22 System Improvements |  | 1680292 | 0 | 2025-12-01
2025-05-01 | 35.5349. | Construction Division - Administration OH 2025 FY |  | 0 | -1164534.58 | 2025-12-01
2025-05-01 | 35.5350. | Construction Division - Pursuit OH 2025 FY |  | 0 | -440864.45 | 2025-12-01
2025-05-01 | 35.5351. | Construction Division - Engineering OH 2025 FY |  | 0 | -176468.35 | 2025-12-01
2025-05-01 | 35.5352. | Construction Division - Warranty for Closed Jobs 2025 FY |  | 0 | -65074.94 | 2025-12-01
2025-05-01 | 35.5353. | VCH - Small Jobs 2025 FY |  | 72776.49 | -85000 | 2025-12-01
2025-05-01 | 35.5354. | SAMC - Maintenance Work Repair 2025 |  | 408351.06 | 0 | 2025-12-01
2025-05-01 | 35.5355. | CMC Work 2025 FY |  | 85000 | -10000 | 2025-12-01
2025-05-01 | 35.5356. | Vegas Builds - DESIGN - Lyles Sacramento - Ramona Opportunity |  | 125428.75 | 115002.35 | 2025-04-01
2025-05-01 | 35.5357. | Kruger - VCH - Doctor's Lounge |  | 34900 | -2003.17 | 2025-05-30
2025-05-01 | 35.5358. | SAMC - 1 North Fluoroscopy Rooms 5-7 – Design and Engineerin |  | 25200 | 0 | 2025-12-01
2025-05-01 | 35.5359. | SAMC - Radiology Rooms 1,2,8 and 9 – Design and Engineering |  | 33600 | 0 | 2025-12-01
2025-05-01 | 35.5360. | CRMC- Bob Smittcamp Neurosciences Renovation |  | 4390950 | 0 | 2025-12-01
2025-05-01 | 35.5361. | VCH - Cell Therapy Lab Modifications |  | 4500 | 0 | 2025-12-01
2025-05-01 | 35.5362. | PG&E - Kerckhoff 2 Control Room Ventilation Study |  | 17400 | 3248.2097 | 2025-08-01
2025-05-01 | 35.5363. | W.M. Lyles Co.- Aymium |  | 289666.7545 | 9864.3505 | 2025-12-01
2025-05-01 | 35.5364. | FUSD - Baird Middle School HVAC Equipment Replacement |  | 1279000 | 0 | 2025-10-01
2025-05-01 | 35.5366. | Swinerton - CMC Seismic Compliance Upgrades Project |  | 18250 | 99.6978 | 2027-12-01
2025-05-01 | 35.5367. | CertainTeed - Office HVAC RFP |  | 7900 | 99.4206 | 2025-12-01
2025-05-01 | 35.5369. | Granite Construction - Faraday Microgrid (FR_VCH Solar CIP 646 Microgrid Energy Fac) |  | 113700 | 0 | 2025-12-01
2025-05-01 | 35.5370. | FUSD - HVAC Replacements at 8 Various Sites - Bid No. 25-48 |  | 8743000 | 0 | 2026-02-01
2025-05-01 | 35.5371. | FUSD - Aynesworth and Calwa Elementary Schools |  | 2768000 | 0 | 2025-12-01

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-05-01 | 31.1059. | W.M. Lyles Co. - ECWAP |  | 232280.73
2025-05-01 | 32.2056. | Bernards Brothers - Fresno Co. West Annex Jail |  | 22806858
2025-05-01 | 32.2230. | GL Associates Bruno - VCH, Food Service Renovations |  | 391100
2025-05-01 | 32.2239. | CRMC - CMC 2030 Program Support |  | 61905.24
2025-05-01 | 32.2254. | VCH - CIP 662 Cooling Tower #2 Replacement |  | 797250.06
2025-05-01 | 32.2255. | Kruger / VCH - ECHO Cardiology IDMP |  | 182000
2025-05-01 | 32.2257. | Kruger / VCH - Kruger - PICU IDMP Reno & Re-Pipe |  | 1077800
2025-05-01 | 32.2258. | City of Dos Palos-Water Treatment Plant Replacement |  | 456273.39
2025-05-01 | 32.2260. | VCH - CIP 669 MRI #3 |  | 322650
2025-05-01 | 32.2262. | Middle River Power BESS - Henrietta |  | 225762.82
2025-05-01 | 32.2263. | VCH - Cooling Tower #1 |  | 603500
2025-05-01 | 35.5193. | McCarthy Bldg. Co. - Kaiser Fresno Acute Service Exp. |  | 1561837
2025-05-01 | 35.5260. | PG&E - Helms Switchyard Elevator Ventilation Upgrade |  | 672875
2025-05-01 | 35.5282. | Seals Constr. - SAMC, Switchgear Fire Pump |  | 995425
2025-05-01 | 35.5288. | Seals Constr. - SCCCD, Applied Technology Ph. 1, Clovis CC |  | 11142118
2025-05-01 | 35.5299. | David A Bush - Dinuba High School |  | 4600197.36
2025-05-01 | 35.5302. | H&R Facilities - Citrus, Sheet Metal and Piping Work |  | 3934651.71
2025-05-01 | 35.5319. | Zumwalt Construction - VCH, CT 64 Replacement |  | 610330
2025-05-01 | 35.5321. | FUSD - HVAC Design-Build |  | 29730386.44
2025-05-01 | 35.5323. | GL Assoc. Bruno - VCH, Lab Remodel (Design/Build) |  | 876700
2025-05-01 | 35.5325. | Kaiser Foundation - FRS MC Cabinet Inst. Drying |  | 74405
2025-05-01 | 35.5327. | VCH - Sterilizer Room Mod. (GO219) |  | 236323.39
2025-05-01 | 35.5328. | VCH - RTAC-4 Design & Build |  | 4400803
2025-05-01 | 35.5336. | VCH - Utility Relocation (CEP to K-Line Pit) |  | 3420048
2025-05-01 | 35.5337. | VCH - CIP 673 Elevator Retrofit |  | 910900
2025-05-01 | 35.5338. | Sanger Ed Complex-Ph 3 - ASM |  | 4063620
2025-05-01 | 35.5339. | FUSD - Dailey Elementary Charter School - HVAC Improvements |  | 946687.01
2025-05-01 | 35.5342. | VCH - Kruger - Simulation Area |  | 74047.97
2025-05-01 | 35.5343. | FUSD - Sunnyside High School Chiller Replacements |  | 497951
2025-05-01 | 35.5344. | Kaiser - Clovis Main Corridor Restroom Refresh |  | 141990
2025-05-01 | 35.5346. | Harris Construction - Terry Bradley Educational Center, Increment 5 |  | 1164000
2025-05-01 | 35.5347. | GL Bruno - Home Care AC Redesign (VCH) |  | 786300
2025-05-01 | 35.5348. | VCH CSA 22 System Improvements |  | 1660292
2025-05-01 | 35.5349. | Construction Division - Administration OH 2025 FY |  | 1164534.58
2025-05-01 | 35.5350. | Construction Division - Pursuit OH 2025 FY |  | 440864.45
2025-05-01 | 35.5351. | Construction Division - Engineering OH 2025 FY |  | 176468.35
2025-05-01 | 35.5352. | Construction Division - Warranty for Closed Jobs 2025 FY |  | 65074.94
2025-05-01 | 35.5353. | VCH - Small Jobs 2025 FY |  | 157776.49
2025-05-01 | 35.5354. | SAMC - Maintenance Work Repair 2025 |  | 408351.06
2025-05-01 | 35.5355. | CMC Work 2025 FY |  | 95000
2025-05-01 | 35.5356. | Vegas Builds - DESIGN - Lyles Sacramento - Ramona Opportunity |  | 10426.4
2025-05-01 | 35.5357. | Kruger - VCH - Doctor's Lounge |  | 36903.17
2025-05-01 | 35.5358. | SAMC - 1 North Fluoroscopy Rooms 5-7 – Design and Engineerin |  | 20200
2025-05-01 | 35.5359. | SAMC - Radiology Rooms 1,2,8 and 9 – Design and Engineering |  | 28600
2025-05-01 | 35.5360. | CRMC- Bob Smittcamp Neurosciences Renovation |  | 4315950
2025-05-01 | 35.5361. | VCH - Cell Therapy Lab Modifications |  | 4500
2025-05-01 | 35.5362. | PG&E - Kerckhoff 2 Control Room Ventilation Study |  | 12400
2025-05-01 | 35.5363. | W.M. Lyles Co.- Aymium |  | 279666.75
2025-05-01 | 35.5364. | FUSD - Baird Middle School HVAC Equipment Replacement |  | 1229000
2025-05-01 | 35.5366. | Swinerton - CMC Seismic Compliance Upgrades Project |  | 18150
2025-05-01 | 35.5367. | CertainTeed - Office HVAC RFP |  | 7800
2025-05-01 | 35.5369. | Granite Construction - Faraday Microgrid (FR_VCH Solar CIP 646 Microgrid Energy Fac) |  | 108700
2025-05-01 | 35.5370. | FUSD - HVAC Replacements at 8 Various Sites - Bid No. 25-48 |  | 8443000
2025-05-01 | 35.5371. | FUSD - Aynesworth and Calwa Elementary Schools |  | 2718000