## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-11-01 | 32.2056 | Bernards Brothers - Fresno Co. West Annex Jail |  | 17116858 | -5780000 | 2025-12-01
2025-11-01 | 32.2230 | GL Associates Bruno - VCH, Food Service Renovations |  | 507000 | 0 | 2027-05-01
2025-11-01 | 32.2255 | Kruger / VCH - ECHO Cardiology IDMP |  | 179650 | 37709.6414 | 2025-12-01
2025-11-01 | 32.2258 | City of Dos Palos-Water Treatment Plant Replacement |  | 491273.39 | 151882.4148 | 2026-03-01
2025-11-01 | 32.2260 | VCH - CIP 669 MRI #3 |  | 422650 | 122280.6164 | 2025-12-01
2025-11-01 | 32.2263 | VCH - Cooling Tower #1 |  | 1317830 | 23011.9898 | 2026-02-01
2025-11-01 | 35.5193 | McCarthy Bldg. Co. - Kaiser Fresno Acute Service Exp. |  | 1523719 | -110000 | 2025-12-01
2025-11-01 | 35.5260 | PG&E - Helms Switchyard Elevator Ventilation Upgrade |  | 1128719 | 129669.2799 | 2025-12-01
2025-11-01 | 35.5319 | Zumwalt Construction - VCH, CT 64 Replacement |  | 530330 | -100000 | 2025-12-01
2025-11-01 | 35.5321 | FUSD - HVAC Design-Build |  | 39854946.44 | 11106228.7219 | 2025-12-01
2025-11-01 | 35.5323 | GL Assoc. Bruno - VCH, Lab Remodel (Design/Build) |  | 944693 | 48381.9438 | 2026-12-01
2025-11-01 | 35.5325 | Kaiser Foundation - FRS MC Cabinet Inst. Drying |  | 112344 | -30000 | 2025-12-01
2025-11-01 | 35.5328 | VCH - RTAC-4 Engineering/Design |  | 4650803 | 896055.0743 | 2025-12-01
2025-11-01 | 35.5336 | VCH - Utility Relocation (CEP to K-Line Pit) |  | 3620048 | 90218.2063 | 2026-06-01
2025-11-01 | 35.5337 | VCH - CIP 673 Elevator Retrofit |  | 960900 | 18668.993 | 2027-12-01
2025-11-01 | 35.5338 | Sanger Ed Complex-Ph 3 - ASM |  | 4232402 | -300000 | 2025-12-01
2025-11-01 | 35.5344 | Kaiser - Clovis Main Corridor Restroom Refresh |  | 146990 | 18233.7318 | 2026-02-01
2025-11-01 | 35.5346 | Harris Construction - Terry Bradley Educational Center, Increment 5 |  | 1193232 | -30000 | 2026-08-01
2025-11-01 | 35.5349 | Construction Division - Administration OH 2025 FY |  |  | -2236089.18 | 2025-12-01
2025-11-01 | 35.5350 | Construction Division - Pursuit OH 2025 FY |  |  | -803135.31 | 2025-12-01
2025-11-01 | 35.5351 | Construction Division - Engineering OH 2025 FY |  |  | -296203.65 | 2025-12-01
2025-11-01 | 35.5352 | Construction Division - Warranty for Closed Jobs 2025 FY |  |  | -69990.81 | 2025-12-01
2025-11-01 | 35.5353 | VCH - Small Jobs 2025 FY |  | 164950 | -130000 | 2025-12-01
2025-11-01 | 35.5354 | SAMC - Maintenance Work Repair 2025 |  | 502341 | 120103.1979 | 2025-12-01
2025-11-01 | 35.5355 | CMC Work 2025 FY |  | 91007 | -15000 | 2025-12-01
2025-11-01 | 35.5358 | SAMC - 1 North Fluoroscopy Rooms 5-7 – Design and Engineerin |  | 25200 | 1708.5223 | 2025-12-01
2025-11-01 | 35.5359 | SAMC - Radiology Rooms 1,2,8 and 9 – Design and Engineering |  | 33600 | 3243.2213 | 2025-12-01
2025-11-01 | 35.5360 | CRMC- Bob Smittcamp Neurosciences Renovation |  | 4478938 | 99324.523 | 2026-06-01
2025-11-01 | 35.5361 | VCH - Cell Therapy Lab Modifications |  | 280300 | 19615.578 | 2026-06-01
2025-11-01 | 35.5364 | FUSD - Baird Middle School HVAC Equipment Replacement |  | 1309000 | 200902.9857 | 2025-12-01
2025-11-01 | 35.5365 | VCH- CIP693 Boiler Emission Upgrades #2 - Design Services |  | 18074 | 3168.9651 | 2025-12-01
2025-11-01 | 35.5366 | Swinerton - CMC Seismic Compliance Upgrades Project |  | 2909336 | 135948.3098 | 2027-12-01
2025-11-01 | 35.5367 | CertainTeed - Office HVAC RFP |  | 26800 | 927.392 | 2025-12-01
2025-11-01 | 35.5368 | Kaiser - Clovis Rehab Services Conversion |  | 80454 | 8020.7673 | 2025-12-01
2025-11-01 | 35.5369 | Granite Construction - Faraday Microgrid (FR_VCH Solar CIP 646 Microgrid Energy Fac) |  | 254582 | 0 | 2025-12-01
2025-11-01 | 35.5370 | FUSD - HVAC Replacements at 8 Various Sites - Bid No. 25-48 |  | 8743000 | 862992.5205 | 2026-02-01
2025-11-01 | 35.5371 | FUSD - Aynesworth and Calwa Elementary Schools |  | 2838000 | 204044.0415 | 2025-12-01
2025-11-01 | 35.5372 | Kaiser - NFSA 2023 CTP FRS MC Tissue Processor Lifecycle |  | 41000 | 0 | 2025-12-01
2025-11-01 | 35.5373 | Kruger - Valley Children's Hospital Small Jobs Fiscal Year 2 |  | 12793 | 0 | 2025-12-01
2025-11-01 | 35.5374 | VCH - SPD Decontamination Sink (CIP 729) |  | 77800 | 10169.3182 | 2026-01-01
2025-11-01 | 35.5375 | VCH - Waiting Room 20148 (20153 etc.) |  | 211600 | 14170.7576 | 2026-02-01
2025-11-01 | 35.5376 | Kaiser - Clovis MOB Medicine Refrigerators Battery Back Up Optimization |  | 49900 | 0 | 2026-04-01
2025-11-01 | 35.5377 | Kruger - VCH Biosafety Cabinets |  | 9200 | 0 | 2026-02-01
2025-11-01 | 35.5378 | FUSD - Ahwahnee Middle School Gym HVAC Upgrade |  | 644900 | 0 | 2026-07-01
2025-11-01 | 35.5379 | Central USD - Bid 2425-1405 - Rebid Roosevelt Elementary School Café HVAC |  | 325000 | 0 | 2026-07-01
2025-11-01 | 35.5380 | SCCC - Bid No. 2526-06- FCC Forum Hall Reroof & HVAC Replacement |  | 1157000 | 0 | 2026-07-01
2025-11-01 | 35.5381 | VCH - CIP 646 Waterline Relocate at Microgrid |  | 83030 | 0 | 2026-01-01
2025-11-01 | 31.1059 | W.M. Lyles Co. - ECWAP |  | 243894.7665 | 11614.0365 | 2025-04-25
2025-11-01 | 32.2239 | CRMC - CMC 2030 Program Support |  | 105444 | 43538.76 | 2025-04-01
2025-11-01 | 32.2254 | VCH - CIP 662 Cooling Tower #2 Replacement |  | 1017300 | 220049.94 | 2025-04-01
2025-11-01 | 32.2257 | Kruger / VCH - Kruger - PICU IDMP Reno & Re-Pipe |  | 1168969 | 263440.44 | 2025-11-01
2025-11-01 | 32.2262 | Middle River Power BESS - Henrietta |  | 360762.82 | 145260.09 | 2025-06-01
2025-11-01 | 35.5282 | Seals Constr. - SAMC, Switchgear Fire Pump |  | 886099 | -108508.92 | 2025-09-26
2025-11-01 | 35.5288 | Seals Constr. - SCCCD, Applied Technology Ph. 1, Clovis CC |  | 10032117.5 | -1117220.47 | 2025-09-26
2025-11-01 | 35.5299 | David A Bush - Dinuba High School |  | 5279141 | 678943.64 | 2025-04-01
2025-11-01 | 35.5302 | H&R Facilities - Citrus, Sheet Metal and Piping Work |  | 3962019.16 | 27367.45 | 2025-04-01
2025-11-01 | 35.5327 | VCH - Sterilizer Room Mod. (GO219) |  | 259011.48 | 22688.09 | 2025-04-25
2025-11-01 | 35.5339 | FUSD - Dailey Elementary Charter School - HVAC Improvements |  | 1086960 | 140327.95 | 2025-04-01
2025-11-01 | 35.5342 | VCH - Kruger - Simulation Area |  | 79300 | 5252.03 | 2025-04-01
2025-11-01 | 35.5343 | FUSD - Sunnyside High School Chiller Replacements |  | 532951 | 51136.41 | 2025-10-01
2025-11-01 | 35.5347 | GL Bruno - Home Care AC Redesign (VCH) |  | 807078 | 179131.61 | 2025-10-01
2025-11-01 | 35.5348 | G.L. Associates Bruno - VCH CSA 22 System Improvements |  | 1463485.03 | 103667.6 | 2025-11-28
2025-11-01 | 35.5356 | Vegas Builds - DESIGN - Lyles Sacramento - Ramona Opportunity |  | 125428.75 | 115002.35 | 2025-04-01
2025-11-01 | 35.5357 | Kruger - VCH - Doctor's Lounge |  | 34900 | -2003.17 | 2025-07-01
2025-11-01 | 35.5362 | PG&E - Kerckhoff 2 Control Room Ventilation Study |  | 17400 | 8962.94 | 2025-09-26
2025-11-01 | 35.5363 | W.M. Lyles Co.- Aymium |  | 2095818.51 | 94972.82 | 2025-11-28

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-11-01 | 32.2056 | Bernards Brothers - Fresno Co. West Annex Jail |  | 22896858
2025-11-01 | 32.2230 | GL Associates Bruno - VCH, Food Service Renovations |  | 467000
2025-11-01 | 32.2255 | Kruger / VCH - ECHO Cardiology IDMP |  | 141650
2025-11-01 | 32.2258 | City of Dos Palos-Water Treatment Plant Replacement |  | 321273.39
2025-11-01 | 32.2260 | VCH - CIP 669 MRI #3 |  | 292650
2025-11-01 | 32.2263 | VCH - Cooling Tower #1 |  | 1267830
2025-11-01 | 35.5193 | McCarthy Bldg. Co. - Kaiser Fresno Acute Service Exp. |  | 1633719
2025-11-01 | 35.5260 | PG&E - Helms Switchyard Elevator Ventilation Upgrade |  | 928719
2025-11-01 | 35.5319 | Zumwalt Construction - VCH, CT 64 Replacement |  | 630330
2025-11-01 | 35.5321 | FUSD - HVAC Design-Build |  | 28730386.44
2025-11-01 | 35.5323 | GL Assoc. Bruno - VCH, Lab Remodel (Design/Build) |  | 854693
2025-11-01 | 35.5325 | Kaiser Foundation - FRS MC Cabinet Inst. Drying |  | 142344
2025-11-01 | 35.5328 | VCH - RTAC-4 Engineering/Design |  | 3750803
2025-11-01 | 35.5336 | VCH - Utility Relocation (CEP to K-Line Pit) |  | 3420048
2025-11-01 | 35.5337 | VCH - CIP 673 Elevator Retrofit |  | 900900
2025-11-01 | 35.5338 | Sanger Ed Complex-Ph 3 - ASM |  | 4532402
2025-11-01 | 35.5344 | Kaiser - Clovis Main Corridor Restroom Refresh |  | 126990
2025-11-01 | 35.5346 | Harris Construction - Terry Bradley Educational Center, Increment 5 |  | 1223232
2025-11-01 | 35.5349 | Construction Division - Administration OH 2025 FY |  | 2236089.18
2025-11-01 | 35.5350 | Construction Division - Pursuit OH 2025 FY |  | 803135.31
2025-11-01 | 35.5351 | Construction Division - Engineering OH 2025 FY |  | 296203.65
2025-11-01 | 35.5352 | Construction Division - Warranty for Closed Jobs 2025 FY |  | 69990.81
2025-11-01 | 35.5353 | VCH - Small Jobs 2025 FY |  | 294950
2025-11-01 | 35.5354 | SAMC - Maintenance Work Repair 2025 |  | 372341
2025-11-01 | 35.5355 | CMC Work 2025 FY |  | 106007
2025-11-01 | 35.5358 | SAMC - 1 North Fluoroscopy Rooms 5-7 – Design and Engineerin |  | 20200
2025-11-01 | 35.5359 | SAMC - Radiology Rooms 1,2,8 and 9 – Design and Engineering |  | 26100
2025-11-01 | 35.5360 | CRMC- Bob Smittcamp Neurosciences Renovation |  | 4328938
2025-11-01 | 35.5361 | VCH - Cell Therapy Lab Modifications |  | 215300
2025-11-01 | 35.5364 | FUSD - Baird Middle School HVAC Equipment Replacement |  | 1074000
2025-11-01 | 35.5365 | VCH- CIP693 Boiler Emission Upgrades #2 - Design Services |  | 13074
2025-11-01 | 35.5366 | Swinerton - CMC Seismic Compliance Upgrades Project |  | 2509336
2025-11-01 | 35.5367 | CertainTeed - Office HVAC RFP |  | 24300
2025-11-01 | 35.5368 | Kaiser - Clovis Rehab Services Conversion |  | 65454
2025-11-01 | 35.5369 | Granite Construction - Faraday Microgrid (FR_VCH Solar CIP 646 Microgrid Energy Fac) |  | 249582
2025-11-01 | 35.5370 | FUSD - HVAC Replacements at 8 Various Sites - Bid No. 25-48 |  | 7593000
2025-11-01 | 35.5371 | FUSD - Aynesworth and Calwa Elementary Schools |  | 2578000
2025-11-01 | 35.5372 | Kaiser - NFSA 2023 CTP FRS MC Tissue Processor Lifecycle |  | 40000
2025-11-01 | 35.5373 | Kruger - Valley Children's Hospital Small Jobs Fiscal Year 2 |  | 10793
2025-11-01 | 35.5374 | VCH - SPD Decontamination Sink (CIP 729) |  | 52800
2025-11-01 | 35.5375 | VCH - Waiting Room 20148 (20153 etc.) |  | 171600
2025-11-01 | 35.5376 | Kaiser - Clovis MOB Medicine Refrigerators Battery Back Up Optimization |  | 47900
2025-11-01 | 35.5377 | Kruger - VCH Biosafety Cabinets |  | 8700
2025-11-01 | 35.5378 | FUSD - Ahwahnee Middle School Gym HVAC Upgrade |  | 624900
2025-11-01 | 35.5379 | Central USD - Bid 2425-1405 - Rebid Roosevelt Elementary School Café HVAC |  | 315000
2025-11-01 | 35.5380 | SCCC - Bid No. 2526-06- FCC Forum Hall Reroof & HVAC Replacement |  | 1147000
2025-11-01 | 35.5381 | VCH - CIP 646 Waterline Relocate at Microgrid |  | 78030
2025-11-01 | 31.1059 | W.M. Lyles Co. - ECWAP |  | 232280.73
2025-11-01 | 32.2239 | CRMC - CMC 2030 Program Support |  | 61905.24
2025-11-01 | 32.2254 | VCH - CIP 662 Cooling Tower #2 Replacement |  | 797250.06
2025-11-01 | 32.2257 | Kruger / VCH - Kruger - PICU IDMP Reno & Re-Pipe |  | 905528.56
2025-11-01 | 32.2262 | Middle River Power BESS - Henrietta |  | 215502.73
2025-11-01 | 35.5282 | Seals Constr. - SAMC, Switchgear Fire Pump |  | 994607.92
2025-11-01 | 35.5288 | Seals Constr. - SCCCD, Applied Technology Ph. 1, Clovis CC |  | 11149337.97
2025-11-01 | 35.5299 | David A Bush - Dinuba High School |  | 4600197.36
2025-11-01 | 35.5302 | H&R Facilities - Citrus, Sheet Metal and Piping Work |  | 3934651.71
2025-11-01 | 35.5327 | VCH - Sterilizer Room Mod. (GO219) |  | 236323.39
2025-11-01 | 35.5339 | FUSD - Dailey Elementary Charter School - HVAC Improvements |  | 946632.05
2025-11-01 | 35.5342 | VCH - Kruger - Simulation Area |  | 74047.97
2025-11-01 | 35.5343 | FUSD - Sunnyside High School Chiller Replacements |  | 481814.59
2025-11-01 | 35.5347 | GL Bruno - Home Care AC Redesign (VCH) |  | 627946.39
2025-11-01 | 35.5348 | G.L. Associates Bruno - VCH CSA 22 System Improvements |  | 1359817.43
2025-11-01 | 35.5356 | Vegas Builds - DESIGN - Lyles Sacramento - Ramona Opportunity |  | 10426.4
2025-11-01 | 35.5357 | Kruger - VCH - Doctor's Lounge |  | 36903.17
2025-11-01 | 35.5362 | PG&E - Kerckhoff 2 Control Room Ventilation Study |  | 8437.06
2025-11-01 | 35.5363 | W.M. Lyles Co.- Aymium |  | 2000845.69