## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-10-01 | 32.2056 | Bernards Brothers - Fresno Co. West Annex Jail |  | 17116858 | -5790000 | 2025-12-01
2025-10-01 | 32.2230 | GL Associates Bruno - VCH, Food Service Renovations |  | 411100 | 0 | 2027-05-01
2025-10-01 | 32.2255 | Kruger / VCH - ECHO Cardiology IDMP |  | 212000 | 27795.863 | 2025-12-01
2025-10-01 | 32.2258 | City of Dos Palos-Water Treatment Plant Replacement |  | 491273.39 | 81740.2972 | 2026-03-01
2025-10-01 | 32.2260 | VCH - CIP 669 MRI #3 |  | 422650 | 109144.8789 | 2025-12-01
2025-10-01 | 32.2263 | VCH - Cooling Tower #1 |  | 1317830 | 21860.1985 | 2026-02-01
2025-10-01 | 35.5193 | McCarthy Bldg. Co. - Kaiser Fresno Acute Service Exp. |  | 1556837 | -75000 | 2025-12-01
2025-10-01 | 35.5260 | PG&E - Helms Switchyard Elevator Ventilation Upgrade |  | 702875 | 27207.6954 | 2025-12-01
2025-10-01 | 35.5319 | Zumwalt Construction - VCH, CT 64 Replacement |  | 530330 | -100000 | 2025-12-01
2025-10-01 | 35.5321 | FUSD - HVAC Design-Build |  | 39854946.44 | 11023306.7242 | 2025-12-01
2025-10-01 | 35.5323 | GL Assoc. Bruno - VCH, Lab Remodel (Design/Build) |  | 936700 | 41556.4095 | 2026-12-01
2025-10-01 | 35.5325 | Kaiser Foundation - FRS MC Cabinet Inst. Drying |  | 97288 | -30000 | 2025-11-25
2025-10-01 | 35.5328 | VCH - RTAC-4 Engineering/Design |  | 4650803 | 907678.5982 | 2025-12-01
2025-10-01 | 35.5336 | VCH - Utility Relocation (CEP to K-Line Pit) |  | 3620048 | 89850.1349 | 2026-06-01
2025-10-01 | 35.5337 | VCH - CIP 673 Elevator Retrofit |  | 960900 | 0 | 2027-12-01
2025-10-01 | 35.5338 | Sanger Ed Complex-Ph 3 - ASM |  | 4253620 | -300000 | 2025-12-01
2025-10-01 | 35.5344 | Kaiser - Clovis Main Corridor Restroom Refresh |  | 146990 | 5842.7946 | 2025-11-25
2025-10-01 | 35.5346 | Harris Construction - Terry Bradley Educational Center, Increment 5 |  | 1169000 | 4587.8647 | 2026-08-01
2025-10-01 | 35.5348 | G.L. Associates Bruno - VCH CSA 22 System Improvements |  | 1463485.03 | 73451.4993 | 2025-12-01
2025-10-01 | 35.5349 | Construction Division - Administration OH 2025 FY |  |  | -2061073 | 2025-12-01
2025-10-01 | 35.5350 | Construction Division - Pursuit OH 2025 FY |  |  | -751640.17 | 2025-12-01
2025-10-01 | 35.5351 | Construction Division - Engineering OH 2025 FY |  |  | -282943.8 | 2025-12-01
2025-10-01 | 35.5352 | Construction Division - Warranty for Closed Jobs 2025 FY |  |  | -65762.13 | 2025-12-01
2025-10-01 | 35.5353 | VCH - Small Jobs 2025 FY |  | 130399.77 | -130000 | 2025-12-01
2025-10-01 | 35.5354 | SAMC - Maintenance Work Repair 2025 |  | 500401.4 | 85272.2992 | 2025-12-01
2025-10-01 | 35.5355 | CMC Work 2025 FY |  | 87389 | -15000 | 2025-12-01
2025-10-01 | 35.5358 | SAMC - 1 North Fluoroscopy Rooms 5-7 – Design and Engineerin |  | 25200 | 1708.5223 | 2025-12-01
2025-10-01 | 35.5359 | SAMC - Radiology Rooms 1,2,8 and 9 – Design and Engineering |  | 33600 | 1933.1311 | 2025-12-01
2025-10-01 | 35.5360 | CRMC- Bob Smittcamp Neurosciences Renovation |  | 4390950 | 79613.7765 | 2026-06-01
2025-10-01 | 35.5361 | VCH - Cell Therapy Lab Modifications |  | 280300 | 0 | 2026-06-01
2025-10-01 | 35.5363 | W.M. Lyles Co.- Aymium |  | 2100882.3145 | 68964.5182 | 2025-12-01
2025-10-01 | 35.5364 | FUSD - Baird Middle School HVAC Equipment Replacement |  | 1279000 | 167070.6135 | 2025-10-01
2025-10-01 | 35.5365 | VCH- CIP693 Boiler Emission Upgrades #2 - Design Services |  | 5000 | 0 | 2025-12-01
2025-10-01 | 35.5366 | Swinerton - CMC Seismic Compliance Upgrades Project |  | 2909336 | 0 | 2027-12-01
2025-10-01 | 35.5367 | CertainTeed - Office HVAC RFP |  | 26800 | 349.3895 | 2025-12-01
2025-10-01 | 35.5368 | Kaiser - Clovis Rehab Services Conversion |  | 77400 | 3122.765 | 2025-12-01
2025-10-01 | 35.5369 | Granite Construction - Faraday Microgrid (FR_VCH Solar CIP 646 Microgrid Energy Fac) |  | 254582 | 0 | 2025-12-01
2025-10-01 | 35.5370 | FUSD - HVAC Replacements at 8 Various Sites - Bid No. 25-48 |  | 8743000 | 711862.1051 | 2026-02-01
2025-10-01 | 35.5371 | FUSD - Aynesworth and Calwa Elementary Schools |  | 2768000 | 201916.0674 | 2025-12-01
2025-10-01 | 35.5372 | Kaiser - NFSA 2023 CTP FRS MC Tissue Processor Lifecycle |  | 41000 | 0 | 2025-12-01
2025-10-01 | 35.5374 | VCH - SPD Decontamination Sink (CIP 729) |  | 77800 | 0 | 2026-01-01
2025-10-01 | 35.5375 | VCH - Waiting Room 20148 (20153 etc.) |  | 211600 | 0 | 2026-02-01
2025-10-01 | 35.5376 | Kaiser - Clovis MOB Medicine Refrigerators Battery Back Up Optimization |  | 49900 | 0 | 2026-04-01
2025-10-01 | 31.1059 | W.M. Lyles Co. - ECWAP |  | 243894.7665 | 11614.0365 | 2025-04-25
2025-10-01 | 32.2239 | CRMC - CMC 2030 Program Support |  | 105444 | 43538.76 | 2025-04-01
2025-10-01 | 32.2254 | VCH - CIP 662 Cooling Tower #2 Replacement |  | 1017300 | 220049.94 | 2025-04-01
2025-10-01 | 32.2257 | Kruger / VCH - Kruger - PICU IDMP Reno & Re-Pipe |  | 1168969 | 263440.44 | 2025-11-01
2025-10-01 | 32.2262 | Middle River Power BESS - Henrietta |  | 360762.82 | 145260.09 | 2025-06-01
2025-10-01 | 35.5282 | Seals Constr. - SAMC, Switchgear Fire Pump |  | 886099 | -108335.94 | 2025-09-26
2025-10-01 | 35.5288 | Seals Constr. - SCCCD, Applied Technology Ph. 1, Clovis CC |  | 10032117.5 | -1117220.47 | 2025-09-26
2025-10-01 | 35.5299 | David A Bush - Dinuba High School |  | 5279141 | 678943.64 | 2025-04-01
2025-10-01 | 35.5302 | H&R Facilities - Citrus, Sheet Metal and Piping Work |  | 3962019.16 | 27367.45 | 2025-04-01
2025-10-01 | 35.5327 | VCH - Sterilizer Room Mod. (GO219) |  | 259011.48 | 22688.09 | 2025-04-25
2025-10-01 | 35.5339 | FUSD - Dailey Elementary Charter School - HVAC Improvements |  | 1086960 | 140327.95 | 2025-04-01
2025-10-01 | 35.5342 | VCH - Kruger - Simulation Area |  | 79300 | 5252.03 | 2025-04-01
2025-10-01 | 35.5343 | FUSD - Sunnyside High School Chiller Replacements |  | 532951 | 51136.41 | 2025-10-01
2025-10-01 | 35.5347 | GL Bruno - Home Care AC Redesign (VCH) |  | 807078 | 179131.61 | 2025-10-01
2025-10-01 | 35.5356 | Vegas Builds - DESIGN - Lyles Sacramento - Ramona Opportunity |  | 125428.75 | 115002.35 | 2025-04-01
2025-10-01 | 35.5357 | Kruger - VCH - Doctor's Lounge |  | 34900 | -2003.17 | 2025-07-01
2025-10-01 | 35.5362 | PG&E - Kerckhoff 2 Control Room Ventilation Study |  | 17400 | 8962.94 | 2025-09-26

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-10-01 | 32.2056 | Bernards Brothers - Fresno Co. West Annex Jail |  | 22906858
2025-10-01 | 32.2230 | GL Associates Bruno - VCH, Food Service Renovations |  | 381100
2025-10-01 | 32.2255 | Kruger / VCH - ECHO Cardiology IDMP |  | 177000
2025-10-01 | 32.2258 | City of Dos Palos-Water Treatment Plant Replacement |  | 381273.39
2025-10-01 | 32.2260 | VCH - CIP 669 MRI #3 |  | 302650
2025-10-01 | 32.2263 | VCH - Cooling Tower #1 |  | 1267830
2025-10-01 | 35.5193 | McCarthy Bldg. Co. - Kaiser Fresno Acute Service Exp. |  | 1631837
2025-10-01 | 35.5260 | PG&E - Helms Switchyard Elevator Ventilation Upgrade |  | 667875
2025-10-01 | 35.5319 | Zumwalt Construction - VCH, CT 64 Replacement |  | 630330
2025-10-01 | 35.5321 | FUSD - HVAC Design-Build |  | 28790386.44
2025-10-01 | 35.5323 | GL Assoc. Bruno - VCH, Lab Remodel (Design/Build) |  | 856700
2025-10-01 | 35.5325 | Kaiser Foundation - FRS MC Cabinet Inst. Drying |  | 127288
2025-10-01 | 35.5328 | VCH - RTAC-4 Engineering/Design |  | 3725803
2025-10-01 | 35.5336 | VCH - Utility Relocation (CEP to K-Line Pit) |  | 3420048
2025-10-01 | 35.5337 | VCH - CIP 673 Elevator Retrofit |  | 910900
2025-10-01 | 35.5338 | Sanger Ed Complex-Ph 3 - ASM |  | 4553620
2025-10-01 | 35.5344 | Kaiser - Clovis Main Corridor Restroom Refresh |  | 139490
2025-10-01 | 35.5346 | Harris Construction - Terry Bradley Educational Center, Increment 5 |  | 1164000
2025-10-01 | 35.5348 | G.L. Associates Bruno - VCH CSA 22 System Improvements |  | 1388485.03
2025-10-01 | 35.5349 | Construction Division - Administration OH 2025 FY |  | 2061073
2025-10-01 | 35.5350 | Construction Division - Pursuit OH 2025 FY |  | 751640.17
2025-10-01 | 35.5351 | Construction Division - Engineering OH 2025 FY |  | 282943.8
2025-10-01 | 35.5352 | Construction Division - Warranty for Closed Jobs 2025 FY |  | 65762.13
2025-10-01 | 35.5353 | VCH - Small Jobs 2025 FY |  | 260399.77
2025-10-01 | 35.5354 | SAMC - Maintenance Work Repair 2025 |  | 400401.4
2025-10-01 | 35.5355 | CMC Work 2025 FY |  | 102389
2025-10-01 | 35.5358 | SAMC - 1 North Fluoroscopy Rooms 5-7 – Design and Engineerin |  | 20200
2025-10-01 | 35.5359 | SAMC - Radiology Rooms 1,2,8 and 9 – Design and Engineering |  | 28600
2025-10-01 | 35.5360 | CRMC- Bob Smittcamp Neurosciences Renovation |  | 4265950
2025-10-01 | 35.5361 | VCH - Cell Therapy Lab Modifications |  | 260300
2025-10-01 | 35.5363 | W.M. Lyles Co.- Aymium |  | 2030882.3145
2025-10-01 | 35.5364 | FUSD - Baird Middle School HVAC Equipment Replacement |  | 1079000
2025-10-01 | 35.5365 | VCH- CIP693 Boiler Emission Upgrades #2 - Design Services |  | 4750
2025-10-01 | 35.5366 | Swinerton - CMC Seismic Compliance Upgrades Project |  | 2509336
2025-10-01 | 35.5367 | CertainTeed - Office HVAC RFP |  | 25800
2025-10-01 | 35.5368 | Kaiser - Clovis Rehab Services Conversion |  | 69900
2025-10-01 | 35.5369 | Granite Construction - Faraday Microgrid (FR_VCH Solar CIP 646 Microgrid Energy Fac) |  | 249582
2025-10-01 | 35.5370 | FUSD - HVAC Replacements at 8 Various Sites - Bid No. 25-48 |  | 7743000
2025-10-01 | 35.5371 | FUSD - Aynesworth and Calwa Elementary Schools |  | 2508000
2025-10-01 | 35.5372 | Kaiser - NFSA 2023 CTP FRS MC Tissue Processor Lifecycle |  | 40000
2025-10-01 | 35.5374 | VCH - SPD Decontamination Sink (CIP 729) |  | 75800
2025-10-01 | 35.5375 | VCH - Waiting Room 20148 (20153 etc.) |  | 205600
2025-10-01 | 35.5376 | Kaiser - Clovis MOB Medicine Refrigerators Battery Back Up Optimization |  | 47900
2025-10-01 | 31.1059 | W.M. Lyles Co. - ECWAP |  | 232280.73
2025-10-01 | 32.2239 | CRMC - CMC 2030 Program Support |  | 61905.24
2025-10-01 | 32.2254 | VCH - CIP 662 Cooling Tower #2 Replacement |  | 797250.06
2025-10-01 | 32.2257 | Kruger / VCH - Kruger - PICU IDMP Reno & Re-Pipe |  | 905528.56
2025-10-01 | 32.2262 | Middle River Power BESS - Henrietta |  | 215502.73
2025-10-01 | 35.5282 | Seals Constr. - SAMC, Switchgear Fire Pump |  | 994434.94
2025-10-01 | 35.5288 | Seals Constr. - SCCCD, Applied Technology Ph. 1, Clovis CC |  | 11149337.97
2025-10-01 | 35.5299 | David A Bush - Dinuba High School |  | 4600197.36
2025-10-01 | 35.5302 | H&R Facilities - Citrus, Sheet Metal and Piping Work |  | 3934651.71
2025-10-01 | 35.5327 | VCH - Sterilizer Room Mod. (GO219) |  | 236323.39
2025-10-01 | 35.5339 | FUSD - Dailey Elementary Charter School - HVAC Improvements |  | 946632.05
2025-10-01 | 35.5342 | VCH - Kruger - Simulation Area |  | 74047.97
2025-10-01 | 35.5343 | FUSD - Sunnyside High School Chiller Replacements |  | 481814.59
2025-10-01 | 35.5347 | GL Bruno - Home Care AC Redesign (VCH) |  | 627946.39
2025-10-01 | 35.5356 | Vegas Builds - DESIGN - Lyles Sacramento - Ramona Opportunity |  | 10426.4
2025-10-01 | 35.5357 | Kruger - VCH - Doctor's Lounge |  | 36903.17
2025-10-01 | 35.5362 | PG&E - Kerckhoff 2 Control Room Ventilation Study |  | 8437.06