## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2024-12-01 | 51.1108. | City of Stockton - RWCF Phase 2A/2B | 92554957.54 | 93788263 | 858269 | 2025-06-30
2024-12-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) | 0 | 0 | 3470130.75 | 2025-06-30
2024-12-01 | 51.1129. | Union Sanit. Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin | 121965840.84 | 121965840.84 | 7950623.3602 | 2027-06-25
2024-12-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 369231.26 | 369231.26 | 17359.5806 | 2025-03-31
2024-12-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements | 5586995 | 5586995 | 758905.7861 | 2025-01-31
2024-12-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 | 1246905.44 | 1246905.44 | 27243.5887 | 2025-06-30
2024-12-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 | 1031404.75 | 1031404.75 | 77778.0991 | 2025-01-01
2024-12-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 67202.17 | 67202.17 | 4426.359 | 2025-01-31
2024-12-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project | 4071084.11 | 4071084.11 | 79920.2987 | 2025-03-31
2024-12-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion | 1991231 | 1991231 | 226011.7629 | 2025-01-31
2024-12-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project | 5436308 | 5436308 | 90331.4512 | 2026-12-20
2024-12-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility | 63489353 | 63489353 | 510849.9358 | 2025-10-01
2024-12-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2488947.44 | 2488947.44 | 128284.5352 | 2026-01-31
2024-12-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2452136.56 | 2452136.56 | 166471.8295 | 2025-03-31
2024-12-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 10658200 | 10658200 | 0 | 2026-11-25
2024-12-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project | 19450000 | 19450000 | 0 | 2026-06-30
2024-12-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement | 549548.83 | 549548.83 | 12859.3892 | 2025-01-31
2024-12-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 12462240 | 12462240 | 0 | 2025-10-31
2024-12-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out | 0 | 0 | 571197.48 | 2025-10-01
2024-12-01 | 51.1102. | Delta Diablo - Pump Station | 10872631.63 | 10872631.63 | 1146690.87 | 2024-04-30
2024-12-01 | 51.1114. | City of Roseville - Pleasant Grove WWTP | 59281827.3 | 59281827.3 | -4033945.99 | 2023-09-30
2024-12-01 | 51.1124. | SVCSD - Treatment Plant Headworks Rehabilitation | 3112418.16 | 3112418.16 | 292612.75 | 2024-04-30
2024-12-01 | 51.1125. | Sac. Reg. Cnty - Highlands Sewer Relief Proj.- Pump Stn. S015 & S016 | 5050105.8 | 5050105.8 | -158909.07 | 2024-12-31
2024-12-01 | 51.1140. | Reeve-Knight Construction Co. - Darling Ingredients Wastewater Trtmnt Sys. Expansion #3 | 2444953.22 | 2444953.22 | 653487.8 | 2024-12-31
2024-12-01 | 51.1142. | City of Yuba City - Lift Station No. 2 Rehabilitation | 552813.37 | 552813.37 | 85112.93 | 2024-04-30
2024-12-01 | 51.1148. | Rocklin Area Overhead 2024 | 0 | 0 | -1417610.71 | 2024-12-31
2024-12-01 | 51.1149. | Rocklin Area Estimating 2024 | 0 | 0 | -510550.96 | 2024-12-31
2024-12-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 915332.49 | 1049183 | 0 | 2025-02-06
2024-12-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out | 0 | 0 | 264189.76 | 2025-02-06
2024-12-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System | 1251553 | 1251553 | 223974.5063 | 2025-03-31
2024-12-01 | 52.8567. | City of Modesto - Grayson Well 69 | 3059859 | 3059859 | -83000 | 2025-01-31
2024-12-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 12551954 | 12551954 | 1757780.0079 | 2025-06-30
2024-12-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 5082998 | 5082998 | 329989.1327 | 2025-05-31
2024-12-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 5734385.5 | 5734385.5 | 197224.7538 | 2025-03-30
2024-12-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 3022534.45 | 3022534.45 | 73003.7005 | 2025-03-01
2024-12-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 | 13631102.77 | 13631102.77 | 277972.0115 | 2026-03-11
2024-12-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 2276400 | 2276400 | 204319.7111 | 2025-05-31
2024-12-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic | 25633500 | 25633500 | 1208391.7577 | 2025-08-31
2024-12-01 | 52.8640. | City of Dos Palos - WTP Replacement Project | 36559246.77 | 36559246.77 | 703966.8389 | 2026-04-17
2024-12-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station | 1253547 | 1253547 | 170698.8374 | 2025-01-31
2024-12-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1789732.45 | 1789732.45 | 148751 | 2025-01-31
2024-12-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1641800 | 1641800 | 42676.9508 | 2025-06-17
2024-12-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 | 313740 | 313740 | 26868.8653 | 2025-01-31
2024-12-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 | 305900 | 305900 | 0 | 2025-02-28
2024-12-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 | 253700 | 253700 | 10404.4356 | 2025-01-31
2024-12-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install | 279244 | 279244 | 15534.5836 | 2025-01-31
2024-12-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 550900 | 550900 | 0 | 2025-06-30
2024-12-01 | 52.8678. | City of Chowcilla - Well 15 & Generator Improvement Projects | 1190560 | 1190560 | 0 | 2025-11-30
2024-12-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M | 6514.21 | 6514.21 | 0 | 2025-03-31
2024-12-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 23957 | 23957 | 15372.2567 | 2025-12-31
2024-12-01 | 52.8575. | City of Fresno - RWRF Waste Gas Flare Improvements | 6656329.13 | 6656329.13 | 643457.78 | 2024-12-31
2024-12-01 | 52.8576. | City of Ceres - Well 16 GAC Chamber | 1035854.13 | 1035854.13 | 227897.41 | 2024-05-24
2024-12-01 | 52.8595. | Richgrove Community Services Dist. - Water Well & Storage Tank | 10276979 | 10276979 | 1423833.21 | 2024-09-30
2024-12-01 | 52.8611. | City of Orange Cove - WWTP Secondary Clarifier & RAS Pump Station Imp. | 1169240 | 1169240 | 72984 | 2024-01-31
2024-12-01 | 52.8627. | Provost and Prichard Engineering Group - Root Creek Water District Road 40 General Repairs | 1082277.02 | 1082277.02 | 75448.89 | 2024-03-22
2024-12-01 | 52.8632. | City of Visalia - Water Conservation Plant Digester #04 Pipe | 541741 | 541741 | 65861.35 | 2024-04-30
2024-12-01 | 52.8644. | County of Fresno - Septic Tank Pipe Repair | 15603.51 | 15603.51 | 4195.93 | 2023-11-30
2024-12-01 | 52.8648. | City of Reedley - Sewer Trunk Line & Headworks Improvement | 3698210.93 | 3698210.93 | 939993.06 | 2024-12-31
2024-12-01 | 52.8650. | Fresno Area Overhead 2024 | 0 | 0 | -1040751.99 | 2024-12-31
2024-12-01 | 52.8651. | Fresno Area Estimating 2024 | 0 | 0 | -351378.83 | 2024-12-31
2024-12-01 | 52.8653. | WEBCOR Construction - Fire Line & Appurtenances Removal | 30672.9 | 30672.9 | 3555.73 | 2024-03-31
2024-12-01 | 52.8654. | New England Sheet Metal and Mechanical Co. - VCH - Emergency Underground Water Repair | 13722.04 | 13722.04 | 1186.69 | 2024-03-31
2024-12-01 | 52.8655. | County of Fresno - DIST 38 Sewer Line Repair | 23106.17 | 23106.17 | 7406.73 | 2024-03-31
2024-12-01 | 52.8656. | County of Fresno - DIST 38 Water Service Connection | 13493.83 | 13493.83 | 4513.44 | 2024-03-31
2024-12-01 | 52.8657. | County of Fresno - DIST 34 Excavate and Expose Pipeline | 5873.5 | 5873.5 | 1325.77 | 2024-03-31
2024-12-01 | 52.8659. | Western Hills Water Dist. - Excavate & Assist in Repair | 288683.94 | 288683.94 | 32437.87 | 2024-03-01
2024-12-01 | 52.8660. | City of Sanger WWTP - Trickle Filter Rehabilitation T&M | 76645 | 76645 | 11980.36 | 2024-05-31
2024-12-01 | 52.8661. | New England Sheet Metal and Mechanical Co. - VCH 8" Sewer Line | 3400 | 3400 | 1090.11 | 2024-03-31
2024-12-01 | 52.8664. | San Lorenzo Mutual Water Co. - 16in Pipeline Emergency Repair | 23267.25 | 23267.25 | 3710.7 | 2024-05-30
2024-12-01 | 52.8665. | Lakeside Ditch Co. - Cross Creek Radial Gate Repair | 23005.52 | 23005.52 | 1819.03 | 2024-08-22
2024-12-01 | 52.8666. | Lakeside Ditch Co. - Lakeside East Branch-Main Radial Gate Repair | 62720.73 | 62720.73 | 5019.41 | 2024-10-11
2024-12-01 | 52.8669. | City of Dinuba - City of Dinuba WWTP- Rake Replacement | 15949.53 | 15949.53 | 3397.66 | 2024-07-31
2024-12-01 | 52.8671. | County of Fresno - DIST 39A-B Emergency Waterline Repair | 4628.09 | 4628.09 | 430.66 | 2024-07-23
2024-12-01 | 52.8672. | County of Fresno - DIST CSA-47 Emergency Waterline Repair | 3709.29 | 3709.29 | 486.82 | 2024-08-01
2024-12-01 | 52.8673. | Tooleville Mutual Water Co. - Tooleville Waterline Repair (T&M) | 21471.45 | 21471.45 | 2859.37 | 2024-12-31
2024-12-01 | 52.8675. | California Water Service Co. - Tesoro Viejo WTP Conduit Install | 12500 | 12500 | 2665.79 | 2024-08-31
2024-12-01 | 52.8676. | County of Fresno - DIST 47-Water - Emergency Repair | 15118.5 | 15118.5 | 1533.22 | 2024-08-20
2024-12-01 | 52.8679. | Brower GSA Ranch LLC - Lindsay LDI Work | 47485.21 | 47485.21 | 6437.45 | 2024-12-31
2024-12-01 | 52.8681. | Provost and Prichard Engineering Group, Inc. - Sugar Leaf Emergency Water Line Repair (T&M) | 10628.16 | 10628.16 | 1585.95 | 2024-12-11
2024-12-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 1038540 | 1038540 | 0 | 2025-11-30
2024-12-01 | 53.2001. | East Bay Area Overhead 2024 | 0 | 0 | -278701.26 | 2024-12-31
2024-12-01 | 53.2002. | East Bay Area Estimating 2024 | 0 | 0 | -68437.31 | 2024-12-31
2024-12-01 | 53.2003. | City of Brentwood - Brentwood Solid Waste Organics Diversion Project | 1166600 | 1166600 | -95243.3 | 2024-12-01
2024-12-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 93909.8 | 93909.8 | 10966.87 | 2025-12-31
2024-12-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 55447829.25 | 55447829.25 | 10372751.5815 | 2025-12-31
2024-12-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 7371036.33 | 8037939.28 | 551994.3651 | 2025-12-31
2024-12-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 24154131.07 | 24157761.07 | 3076351.4492 | 2025-12-31
2024-12-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements | 2337754.68 | 2337754.68 | 140849.7535 | 2025-08-31
2024-12-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 1743970 | 1743970 | 69196.4543 | 2025-04-30
2024-12-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station | 1471328 | 1471328 | 0 | 2025-06-01
2024-12-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 223896.9 | 223896.9 | 0 | 2025-01-31
2024-12-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 907297.99 | 907297.99 | 71013.0668 | 2025-02-28
2024-12-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 340270.46 | 340270.46 | 34249.05 | 2025-12-31
2024-12-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3203768.8 | 3203768.8 | -15000 | 2025-02-11
2024-12-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 434950 | 434950 | 35686.2378 | 2025-02-28
2024-12-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 14176 | 14176 | 669.81 | 2025-12-31
2024-12-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 4300 | 4300 | 2986.55 | 2025-12-31
2024-12-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3823848.71 | 3823848.71 | 62853.4158 | 2025-06-01
2024-12-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 8787721.04 | 8787721.04 | 197714.5111 | 2025-12-31
2024-12-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 85064.63 | 85064.63 | 0 | 2025-01-31
2024-12-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 324900 | 324900 | 10642.1273 | 2025-03-31
2024-12-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 166980.44 | 166980.44 | 14888.68 | 2025-03-01
2024-12-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 24811393.79 | 24811393.79 | 0 | 2026-10-07
2024-12-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 4082300 | 4082300 | 0 | 2026-10-30
2024-12-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 162416 | 162416 | 54179.7977 | 2025-01-31
2024-12-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1195200 | 1195200 | 0 | 2025-03-07
2024-12-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 174865 | 174865 | 41394.1127 | 2025-01-31
2024-12-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 6881300 | 6881300 | 0 | 2026-03-26
2024-12-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 294600 | 294600 | 4519.6837 | 2025-02-28
2024-12-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 | 10110.6 | 10110.6 | 0 | 2025-03-31
2024-12-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 136808.3 | 153298.79 | 11095.2671 | 2025-01-31
2024-12-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 1117.5 | 1117.5 | 0 | 2025-03-31
2024-12-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 14274.54 | 14274.54 | 1923.43 | 2025-01-31
2024-12-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 1815.23 | 1815.23 | 0 | 2025-03-31
2024-12-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 1283004 | 1283004 | 0 | 2025-06-30
2024-12-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 889.66 | 889.66 | 0 | 2025-03-31
2024-12-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1147640 | 1147640 | 15917.5507 | 2025-09-01
2024-12-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1144.88 | 1144.88 | 0 | 2025-03-31
2024-12-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 162458.93 | 400000 | 18050.9922 | 2025-01-25
2024-12-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 777.55 | 777.55 | 0 | 2025-03-31
2024-12-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 1263.33 | 1263.33 | 0 | 2025-03-31
2024-12-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1225220 | 1225220 | 0 | 2026-05-31
2024-12-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 1602.33 | 1602.33 | 0 | 2025-03-31
2024-12-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 15697.91 | 15697.91 | 2044.29 | 2025-01-31
2024-12-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project | 30413570 | 30413570 | 0 | 2027-01-05
2024-12-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 889.64 | 889.64 | 0 | 2025-03-31
2024-12-01 | 54.9020. | City of Camarillo - North Pleasant Valley Desalter Project | 42431509.16 | 42431509.16 | 3081679.91 | 2025-12-01
2024-12-01 | 54.9210. | Lamont Public Utility District - Well 13 Replacement | 3729423.63 | 3729423.63 | 58233.84 | 2024-07-31
2024-12-01 | 54.9211. | Semitropic Water Storage Dist. - Leonard System Extension Project | 14859049.96 | 14859049.96 | -751219.05 | 2024-10-01
2024-12-01 | 54.9232. | Kern Water Bank Authority - Well 20D01 | 102831.78 | 102831.78 | 9998.21 | 2024-04-01
2024-12-01 | 54.9234. | Kern Water Bank Authority - Well 9D01 | 287784.74 | 287784.74 | 17332.03 | 2024-05-01
2024-12-01 | 54.9236. | Kern Water Bank Authority - Well 12J01 | 118054.3 | 118054.3 | 9916.63 | 2024-04-01
2024-12-01 | 54.9243. | Shafter-Wasco Irrigation Dist. - Farmer Co-Op Pipeline | 1487079 | 1487079 | 9181.08 | 2024-11-30
2024-12-01 | 54.9275. | City of Bakersfield - WWTP No. 3 DAF Tank & Polymer Feed System Rehab - Phase 2 | 1135663.85 | 1135663.85 | 134623.07 | 2024-12-31
2024-12-01 | 54.9286. | Kern Water Bank Authority - Well 30S/25E-03L02 | 215335.93 | 215335.93 | 22838.83 | 2024-10-01
2024-12-01 | 54.9288. | Kern Water Bank Authority - Well 30S/26E-07N02 | 122474.4 | 122474.4 | 15129.17 | 2024-07-01
2024-12-01 | 54.9290. | County of Santa Barbara-Public Works - Laguna CSD Dutard Road Culvert #1 Maintenance | 87672.9 | 87672.9 | 45463.47 | 2024-06-01
2024-12-01 | 54.9291. | Cawelo Water District - Poso Creek 2023 Storm Damage Repair | 336808.77 | 336808.77 | 33226.74 | 2024-03-01
2024-12-01 | 54.9296. | Semitropic Water Storage Dist. - XYZ PIPE NETWORK EXTENSION PROJECT - AMENDMENT NO. 25 | 32595.74 | 32595.74 | 2095.56 | 2024-12-01
2024-12-01 | 54.9297. | Bakersfield Area Overhead 2024 | 0 |  | -1227667.28 | 2024-12-31
2024-12-01 | 54.9298. | Bakersfield Area Estimating 2024 | 0 |  | -516192.65 | 2024-12-31
2024-12-01 | 54.9299. | Granite Construction Co. - Chumash WTP/WWTP | 24270.75 | 24270.75 | 19542.33 | 2024-08-01
2024-12-01 | 54.9300. | California Water Service Co. - Northeast Plant Pipe and Pump Replacement | 46534.26 | 46534.26 | 7325.51 | 2024-04-01
2024-12-01 | 54.9301. | California Water Service Co. - Northwest Plant Basin Cleaning | 52852.04 | 52852.04 | 6890.85 | 2024-04-01
2024-12-01 | 54.9305. | Semitropic Water Storage Dist. - East West Canal Cleaning | 141876.84 | 141876.84 | 14039.28 | 2024-12-01
2024-12-01 | 54.9306. | Lyles Utility Construction, LLC - Annual Maintenance Job 2024 Fiscal Year | 25500.97 | 25500.97 | 2966.46 | 2024-12-01
2024-12-01 | 54.9307. | Shafter-Wasco Irrigation Dist. - Jack Avenue Turnout | 40854.49 | 40854.49 | 5581.7 | 2024-04-01
2024-12-01 | 54.9308. | City of Bakersfield - Stine Road Hydrant Repair | 99366.46 | 99366.46 | 10755.05 | 2024-07-01
2024-12-01 | 54.9310. | Kern Water Bank Authority - Pond Valve Repairs | 28930.02 | 28930.02 | 3334.01 | 2024-04-01
2024-12-01 | 54.9311. | City of Bakersfield - Rosedale Lowes Hydrant Repair | 5240.97 | 5240.97 | 627.12 | 2024-04-01
2024-12-01 | 54.9312. | Kern Water Bank Authority - Emergency Pump Station Repairs | 33568.76 | 33568.76 | 3759.66 | 2024-04-01
2024-12-01 | 54.9314. | Kleinfelder, Inc. - Test Pit Excavations | 16400 | 16400 | 3752.81 | 2024-03-01
2024-12-01 | 54.9315. | Cawelo Water Dist. - Emergency Pump Station Pipe Repair | 27981.66 | 27981.66 | 4167.92 | 2024-04-01
2024-12-01 | 54.9316. | East Niles Community Service Dist. - Concrete Foundations at New Office | 23225.38 | 23225.38 | 3891.49 | 2024-07-01
2024-12-01 | 54.9317. | Shafter-Wasco Irrigation Dist. - Emergency Burbank St Repair | 16619.27 | 16619.27 | 2326.4 | 2024-04-01
2024-12-01 | 54.9318. | Kern Water Bank Authority - Aqueduct Siphon Pipe Repair | 3919.5 | 3919.5 | 604.26 | 2024-07-01
2024-12-01 | 54.9319. | Semitropic Water Storage Dist. - Kimberlina RCP Repairs | 70433.1 | 70433.1 | 9479.88 | 2024-07-01
2024-12-01 | 54.9320. | Semitropic Water Storage Dist. - Schuster Road PCCP Repair | 21614.24 | 21614.24 | 3688.2 | 2024-07-01
2024-12-01 | 54.9322. | Kern Water Bank Authority - Emergency Pump Station Repairs | 17390.61 | 17390.61 | 2090.93 | 2024-07-01
2024-12-01 | 54.9324. | Kern Water Bank Authority - Pump Station Trash Rack Removal | 2518.29 | 2518.29 | 329.42 | 2024-07-01
2024-12-01 | 54.9325. | Semitropic Water Storage Dist. - Wildwood Pipe Repair | 49679.1 | 49679.1 | 7164.01 | 2024-10-31
2024-12-01 | 54.9326. | Kern Water Bank Authority - Siphon Pipe Cleaning | 30547.5 | 30547.5 | 3230.67 | 2024-10-31
2024-12-01 | 54.9327. | California Water Service Co. - Valve & Sluice Gate Repair | 2909.8 | 2909.8 | 509.59 | 2024-10-31
2024-12-01 | 54.9328. | Kern County Water Agency - Removal of Precipitated Solids from Drying Bed Nos. 8 and 9 | 44000 | 44000 | 10671.32 | 2024-10-31
2024-12-01 | 54.9331. | Laguna County Sanitation Dist. - WWTP Flooding Repairs 2024 | 30194.03 | 30194.03 | 9100.03 | 2024-12-24
2024-12-01 | 54.9332. | Kern Water Bank Authority - Emergency Actuator Repair | 4984.85 | 4984.85 | 684.88 | 2024-07-01
2024-12-01 | 54.9334. | County of Santa Barbara-Public Works - Laguna CSD - Orcutt Bluffs SS Replacement | 135100 | 135100 | 53132.65 | 2024-07-31
2024-12-01 | 54.9335. | Kern Water Bank Authority - Strand Pump Rehabilitation | 51409.79 | 51409.79 | 5243.14 | 2024-10-31
2024-12-01 | 54.9339. | Cawelo Water Dist. - Famoso Spreading Ground Repairs - Phase 3 | 423595.9 | 423595.9 | 46752.02 | 2024-12-01
2024-12-01 | 54.9340. | Shafter-Wasco Irrigation Dist. - Dresser Ave. Pipe Removal Project | 85300.86 | 85300.86 | 11638.71 | 2024-10-31
2024-12-01 | 54.9344. | Cawelo Water Dist. - Famoso Spreading Ground Material Purchases | 17708.7 | 17708.7 | 2195.29 | 2024-10-24
2024-12-01 | 54.9345. | East Niles Community Service Dist. - Breckenridge Electrical Pads | 24232.94 | 24232.94 | 3513.1 | 2024-10-31
2024-12-01 | 54.9346. | East Niles Community Service Dist. - Kern Citrus Pipe Repair | 18944.23 | 18944.23 | 2943.81 | 2024-10-31
2024-12-01 | 54.9348. | Semitropic Water Storage Dist. - Gromer Avenue Road Repair | 15578.23 | 15578.23 | 2104.39 | 2024-12-31
2024-12-01 | 54.9352. | Arvin Edison Water Storage Dist. - Canal Liner Repairs | 252359.72 | 252359.72 | 28047.19 | 2025-01-31
2024-12-01 | 54.9359. | Arvin Edison Water Storage Dist. - Fairfax & 58 Manhole Repair | 35186.03 | 35186.03 | 5041.2 | 2024-12-31
2024-12-01 | 55.1090. | LA Dept of Water and Power - Silverlake | 4974161.54 | 5200000 | 1463888.1686 | 2025-06-01
2024-12-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Exp. & Solids Treat. Facility | 341062067.71 | 341062067.71 | 7900000 | 2026-06-01
2024-12-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6580352.53 | 6580352.53 | 350000 | 2025-03-01
2024-12-01 | 55.1200. | East County Advanced Water Purification Project - Package 1 | 140379771 | 177974141 | 0 | 2027-02-02
2024-12-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out | 0 | 0 | 5995115.13 | 2027-02-02
2024-12-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project | 16115717.28 | 16115717.28 | 647450.7063 | 2026-01-01
2024-12-01 | 55.1204. | East County Advanced Water Purification Project - Package 3 | 39787580 | 40662397 | 0 | 2027-02-02
2024-12-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out | 0 | 0 | 1917801.19 | 2027-02-02
2024-12-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 40814118.62 | 40922930.09 | 3399354.1719 | 2025-05-01
2024-12-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement | 2273682.69 | 2273682.69 | 480252.0335 | 2025-03-31
2024-12-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements | 4072535 | 4072535 | 627907.3954 | 2025-03-31
2024-12-01 | 55.1233. | Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 84758.64 | 84758.64 | 8428.84 | 2025-03-31
2024-12-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 | 34207.53 | 34207.53 | 8107.48 | 2026-12-31
2024-12-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 5542665 | 5542665 | 0 | 2026-01-31
2024-12-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 147718400 | 147718400 | 0 | 2029-02-01
2024-12-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 202000 | 202000 | 101052.1598 | 2025-03-31
2024-12-01 | 55.1173. | City of Beaumont - WWTP | 62589044.57 | 62589044.57 | 4427392.31 | 2024-01-31
2024-12-01 | 55.1193. | Rialto Bioenergy Facility, LLC - RBF PyroBioMethane Project | 19224499.81 | 19224499.81 | 1022991.01 | 2023-07-31
2024-12-01 | 55.1236. | Southern Contracting Co. - City of Palm Springs Lighting Project | 605641.1 | 605641.1 | 20687.01 | 2024-04-01
2024-12-01 | 55.1240. | Murrieta Area Overhead 2024 | 0 |  | -1156437.83 | 2024-12-31
2024-12-01 | 55.1241. | Murrieta Area Estimating 2024 | 0 |  | -833941.37 | 2024-12-31
2024-12-01 | 55.1242. | Victor Valley Wastewater Reclamation Authority - VVWRA - 6in Filtrate Pipe | 24908.17 | 24908.17 | -575.9 | 2024-02-28
2024-12-01 | 55.1243. | Victor Valley Wastewater Reclamation Authority - VVWRA - 6in Filtrate Pipe PHS 2 | 23414.5 | 23414.5 | -856.08 | 2024-02-28
2024-12-01 | 55.1244. | Victor Valley Wastewater Reclamation Authority - Civil Works for Pipe Supports | 17023.41 | 17023.41 | 6954.69 | 2024-01-24
2024-12-01 | 55.1245. | Victor Valley Wastewater Reclamation Authority - Side Stream Air Project | 165261.09 | 165261.09 | 87807.22 | 2024-05-01
2024-12-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 2999485 | 2999485 | 96385.4118 | 2024-12-31
2024-12-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 40106224.63 | 40106224.63 | 0 | 2026-03-25
2024-12-01 | 57.0001. | San Diego Area Overhead 2024 | 0 | 0 | -14122.99 | 2024-12-31
2024-12-01 | 57.0002. | San Diego Area Estimating 2024 | 0 | 0 | -98216 | 2024-12-31
2024-12-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 22085905 | 22085905 | 0 | 2026-06-01
2024-12-01 | 58.0001. | Los Angeles Area Overhead 2024 | 0 | 0 | -54188.26 | 2024-12-31
2024-12-01 | 58.0002. | Los Angeles Area Estimating 2024 | 0 | 0 | -44984.62 | 2024-12-31
2024-12-01 | 56.1002. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 185000 | 185000 | 50745.2395 | 2025-03-31
2024-12-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 296656 | 296656 | 64460.9863 | 2025-06-30
2024-12-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 373425 | 373425 | 51359.9627 | 2025-09-30
2024-12-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 135000 | 135000 | 0 | 2025-06-30
2024-12-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 19314 | 19314 | 3177.441 | 2025-03-31
2024-12-01 | 56.1008. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 55000 | 55000 | 23094.0224 | 2025-03-31
2024-12-01 | 56.1010.01. | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 9569 | 9569 | 619.6471 | 2025-03-31
2024-12-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 160000 | 160000 | 29395.3303 | 2025-06-30
2024-12-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 71814.5 | 71814.5 | 14743.36 | 2025-12-31
2024-12-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 73222 | 73222 | 19016.5728 | 2025-12-31
2024-12-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 145000 | 145000 | 31982.9546 | 2025-06-30
2024-12-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 168000 | 168000 | 0 | 2025-12-31
2024-12-01 | 56.1021. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 244760 | 244760 | 38878.5393 | 2025-06-30
2024-12-01 | 56.1022. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 88093.56 | 88093.56 | 0 | 2025-12-31
2024-12-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 216655 | 216655 | 40095.3125 | 2025-06-30
2024-12-01 | 56.1030. | Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 795000 | 795000 | 0 | 2025-09-30
2024-12-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 85000 | 85000 | 0 | 2025-09-30
2024-12-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 276000 | 276000 | 0 | 2025-12-31
2024-12-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 2362.5 | 2362.5 | 338.12 | 2025-12-31
2024-12-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 95000 | 95000 | 6303.4542 | 2025-12-31
2024-12-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 375000 | 375000 | 0 | 2025-12-31
2024-12-01 | 56.1041. | Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 49013 | 49013 | 7002.238 | 2025-06-30
2024-12-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services | 217870 | 217870 | 34822.2181 | 2025-09-30
2024-12-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 325000 | 325000 | 0 | 2025-12-31
2024-12-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 66000 | 66000 | 0 | 2025-09-30
2024-12-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 2395000 | 2395000 | 0 | 2026-12-31
2024-12-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 200000 | 200000 | 0 | 2025-09-30
2024-12-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 295000 | 295000 | 74409.071 | 2025-06-30
2024-12-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 3780000 | 3780000 | 0 | 2026-12-31
2024-12-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 124975 | 124975 | 16220.5398 | 2025-09-30
2024-12-01 | 56.1052. | San Jose Water - Williams Back ATS Replacement | 8887 | 8887 | 369.0936 | 2025-03-31
2024-12-01 | 56.1053. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 35000 | 35000 | 0 | 2025-06-30
2024-12-01 | 56.1054. | W.M. Lyles - Riverside Public Works - Digester 5 Rehab | 215000 | 215000 | 0 | 2026-03-31
2024-12-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 119765.1 | 119765.1 | 0 | 2025-09-30
2024-12-01 | 56.1056. | Irvine Ranch Water District - Michelson Water Recycling Plan | 326800 | 326800 | 0 | 2026-09-30
2024-12-01 | 56.1057. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 450000 | 450000 | 0 | 2026-06-30
2024-12-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 380000 | 380000 | 0 | 2025-12-31
2024-12-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 400000 | 400000 | 0 | 2026-03-31
2024-12-01 | 56.1061. | San Jose Water - PLC System Assessment | 11269 | 11269 | 5163.8304 | 2025-03-31
2024-12-01 | 56.1062. | SCADA System Upgrade - City of Brentwood | 1785125 | 1785125 | 0 | 2025-12-31
2024-12-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 108000 | 108000 | 0 | 2026-03-31
2024-12-01 | 56.1064. | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 405900 | 405900 | 69496.4896 | 2025-06-30
2024-12-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 227000 | 227000 | 0 | 2025-09-30
2024-12-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 595000 | 595000 | 0 | 2025-12-31
2024-12-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 478000 | 478000 | 0 | 2026-06-30
2024-12-01 | 56.1071. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 34000 | 34000 | 0 | 2025-06-30
2024-12-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 48420 | 48420 | 0 | 2025-09-30
2024-12-01 | 56.1074. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 12650 | 12650 | 1239.6881 | 2025-06-30
2024-12-01 | 56.1076. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 19200 | 19200 | 0 | 2025-03-31
2024-12-01 | 56.1001. | San Jose Water Co. - Batista PLC Control Panel Upgrade | 97350 | 97350 | 55516.24 | 2024-04-30
2024-12-01 | 56.1006. | System Integration Overhead 2024 | 0 |  | -8057307.54 | 2024-12-31
2024-12-01 | 56.1009. | Al Fresco Landscaping Inc. - East Garrison Marina On-Site Assessment - County of Monterey | 3000 | 3000 | 648.75 | 2024-04-30
2024-12-01 | 56.1009.01. | Al Fresco Landscaping Inc. - East Garrison On-Site Eq. Reconfig. - County of Monterey | 45865 | 45865 | 23386.21 | 2024-09-30
2024-12-01 | 56.1011. | City of Atwater - Well VFD Reconfiguration | 1000 | 1000 | 532.5 | 2024-04-30
2024-12-01 | 56.1012. | California Water Service Co. - SSF-1 - Wildfire Booster Pump Station | 42207.31 | 42207.31 | 424.26 | 2024-12-31
2024-12-01 | 56.1013. | Placer County Water Agency - Raw Water PLC Control Panels - PCWA | 67250 | 67250 | 12424.38 | 2024-12-31
2024-12-01 | 56.1014. | Collins Electric - SWWTP On-Site Support Services | 34070 | 34070 | 15279.37 | 2024-12-31
2024-12-01 | 56.1020. | East Contra Costa Irrigation Dist. - Time & Material Contract - East Contra Costa Irrigation Dist | 10472.75 | 10472.75 | 4849.94 | 2024-08-31
2024-12-01 | 56.1024. | Templeton Community Services Dist. - Instrumentation Calibration Services | 7642 | 7642 | 5320.91 | 2024-08-31
2024-12-01 | 56.1026. | City of Tracy Public Works - Annual Flow Calibrations | 12500 | 12500 | -2290.16 | 2024-08-31
2024-12-01 | 56.1027. | Young Electric Co. - PLC & SCADA Assessment at Caldecott Tunnel - 04-1X260 | 9600 | 9600 | 5788.22 | 2024-08-31
2024-12-01 | 56.1028. | Shape Incorporated - Flow Meter Purchase | 6265 | 6265 | 680.81 | 2024-08-31
2024-12-01 | 56.1029. | San Gabriel Valley Water Co. - WNOU Plant Flow Meter Assessment | 5000 | 5000 | 2590.42 | 2024-08-31
2024-12-01 | 56.1031. | Winton Water & Sanitary Dist. - Buhach Well Site Troubleshooting | 2272.5 | 2272.5 | 1669.91 | 2024-08-31
2024-12-01 | 56.1034. | Fair Oaks Water Dist. - Fair Oaks, City of - Lemon Street PRV Station RTU 13 | 1315 | 1315 | 1147.81 | 2024-08-31
2024-12-01 | 56.1035. | California Water Service Co. - Salinas Station 47 Assessment | 3670 | 3670 | 1519.37 | 2024-08-31
2024-12-01 | 56.1040. | San Jose Water Co - Belgatos Booster Station | 27695 | 27695 | 6553.22 | 2024-12-31
2024-12-01 | 56.1044. | San Jose Water Co - Saratoga Startup Support | 62300 | 62300 | 17772.5 | 2024-12-31
2024-12-01 | 56.1045. | Fusion Electic. Imc - Copperopolis - Copper Cove Flowmeter Cables | 4569 | 4569 | 1622.48 | 2024-08-31
2024-12-01 | 56.1058. | South Orange County Wastewater Authority - As Needed Profess | 3125 | 3125 | 970.8 | 2024-12-31
2024-12-01 | 56.1070. | UC Davis - Sand Filter PLC Troubleshooting | 1964.5 | 1964.5 | 542.12 | 2024-12-31
2024-12-01 | 50.0528. | W.M. Lyles Co. - General Overhead | 0 | 0 | -2950997.47 | 2024-12-31
2024-12-01 | 50.0529. | W.M. Lyles Co. - General Estimating | 0 | 0 | -98218.84 | 2024-12-31
2024-12-01 | 50.0531. | American Paving | 324.93 | 324.93 | 0 | 2024-12-31
2024-12-01 | 50.0532. | Lyles Services Co. | 43574.5 | 43574.5 | 0 | 2024-12-31
2024-12-01 | 50.0534. | Lyles Utility Construction, LLC | 19849.84 | 19849.84 | 952.11 | 2024-12-31

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2024-12-01 | 51.1108. | City of Stockton - RWCF Phase 2A/2B | 91989325.72 | 92929994
2024-12-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) | -3470130.75 | -3530000
2024-12-01 | 51.1129. | Union Sanit. Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin | 109965840.84 | 109965840.84
2024-12-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 349231.26 | 349231.26
2024-12-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements | 4736995 | 4736995
2024-12-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 | 1133265.44 | 1133265.44
2024-12-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 | 938629.75 | 938629.75
2024-12-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 62359.17 | 62359.17
2024-12-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project | 3969084.11 | 3969084.11
2024-12-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion | 1761231 | 1761231
2024-12-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project | 5096164 | 5096164
2024-12-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility | 57741915 | 57741915
2024-12-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2318947.44 | 2318947.44
2024-12-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2269699.56 | 2269699.56
2024-12-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 10061352 | 10061352
2024-12-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project | 18328291 | 18328291
2024-12-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement | 486351.83 | 486351.83
2024-12-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 11986906 | 11986906
2024-12-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out | -1250000 | -1250000
2024-12-01 | 51.1102. | Delta Diablo - Pump Station | 9725940.76 | 9725940.76
2024-12-01 | 51.1114. | City of Roseville - Pleasant Grove WWTP | 63315773.29 | 63315773.29
2024-12-01 | 51.1124. | SVCSD - Treatment Plant Headworks Rehabilitation | 2819805.41 | 2819805.41
2024-12-01 | 51.1125. | Sac. Reg. Cnty - Highlands Sewer Relief Proj.- Pump Stn. S015 & S016 | 5209014.87 | 5209014.87
2024-12-01 | 51.1140. | Reeve-Knight Construction Co. - Darling Ingredients Wastewater Trtmnt Sys. Expansion #3 | 1791465.42 | 1791465.42
2024-12-01 | 51.1142. | City of Yuba City - Lift Station No. 2 Rehabilitation | 467700.44 | 467700.44
2024-12-01 | 51.1148. | Rocklin Area Overhead 2024 | 1417610.71 | 1417610.71
2024-12-01 | 51.1149. | Rocklin Area Estimating 2024 | 510550.96 | 510550.96
2024-12-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 985056.51 | 1049183
2024-12-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out | -264189.76 | -265000
2024-12-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System | 1021553 | 1021553
2024-12-01 | 52.8567. | City of Modesto - Grayson Well 69 | 3142859 | 3142859
2024-12-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 10711954 | 10711954
2024-12-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 4662998 | 4662998
2024-12-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 5454385.5 | 5454385.5
2024-12-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 2927534.45 | 2927534.45
2024-12-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 | 12941102.77 | 12941102.77
2024-12-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 1996400 | 1996400
2024-12-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic | 24133500 | 24133500
2024-12-01 | 52.8640. | City of Dos Palos - WTP Replacement Project | 34685923.77 | 34685923.77
2024-12-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station | 1068547 | 1068547
2024-12-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1633152.45 | 1633152.45
2024-12-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1485937 | 1485937
2024-12-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 | 286740 | 286740
2024-12-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 | 276215 | 276215
2024-12-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 | 233630 | 233630
2024-12-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install | 257584 | 257584
2024-12-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 518191 | 518191
2024-12-01 | 52.8678. | City of Chowcilla - Well 15 & Generator Improvement Projects | 1130367 | 1130367
2024-12-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M | 6514.21 | 6514.21
2024-12-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 6957 | 6957
2024-12-01 | 52.8575. | City of Fresno - RWRF Waste Gas Flare Improvements | 6012871.35 | 6012871.35
2024-12-01 | 52.8576. | City of Ceres - Well 16 GAC Chamber | 807956.72 | 807956.72
2024-12-01 | 52.8595. | Richgrove Community Services Dist. - Water Well & Storage Tank | 8853145.79 | 8853145.79
2024-12-01 | 52.8611. | City of Orange Cove - WWTP Secondary Clarifier & RAS Pump Station Imp. | 1096256 | 1096256
2024-12-01 | 52.8627. | Provost and Prichard Engineering Group - Root Creek Water District Road 40 General Repairs | 1006828.13 | 1006828.13
2024-12-01 | 52.8632. | City of Visalia - Water Conservation Plant Digester #04 Pipe | 475879.65 | 475879.65
2024-12-01 | 52.8644. | County of Fresno - Septic Tank Pipe Repair | 11407.58 | 11407.58
2024-12-01 | 52.8648. | City of Reedley - Sewer Trunk Line & Headworks Improvement | 2758217.87 | 2758217.87
2024-12-01 | 52.8650. | Fresno Area Overhead 2024 | 1040751.99 | 1040751.99
2024-12-01 | 52.8651. | Fresno Area Estimating 2024 | 351378.83 | 351378.83
2024-12-01 | 52.8653. | WEBCOR Construction - Fire Line & Appurtenances Removal | 27117.17 | 27117.17
2024-12-01 | 52.8654. | New England Sheet Metal and Mechanical Co. - VCH - Emergency Underground Water Repair | 12535.35 | 12535.35
2024-12-01 | 52.8655. | County of Fresno - DIST 38 Sewer Line Repair | 15699.44 | 15699.44
2024-12-01 | 52.8656. | County of Fresno - DIST 38 Water Service Connection | 8980.39 | 8980.39
2024-12-01 | 52.8657. | County of Fresno - DIST 34 Excavate and Expose Pipeline | 4547.73 | 4547.73
2024-12-01 | 52.8659. | Western Hills Water Dist. - Excavate & Assist in Repair | 256246.07 | 256246.07
2024-12-01 | 52.8660. | City of Sanger WWTP - Trickle Filter Rehabilitation T&M | 64664.64 | 64664.64
2024-12-01 | 52.8661. | New England Sheet Metal and Mechanical Co. - VCH 8" Sewer Line | 2309.89 | 2309.89
2024-12-01 | 52.8664. | San Lorenzo Mutual Water Co. - 16in Pipeline Emergency Repair | 19556.55 | 19556.55
2024-12-01 | 52.8665. | Lakeside Ditch Co. - Cross Creek Radial Gate Repair | 21186.49 | 21186.49
2024-12-01 | 52.8666. | Lakeside Ditch Co. - Lakeside East Branch-Main Radial Gate Repair | 57701.32 | 57701.32
2024-12-01 | 52.8669. | City of Dinuba - City of Dinuba WWTP- Rake Replacement | 12551.87 | 12551.87
2024-12-01 | 52.8671. | County of Fresno - DIST 39A-B Emergency Waterline Repair | 4197.43 | 4197.43
2024-12-01 | 52.8672. | County of Fresno - DIST CSA-47 Emergency Waterline Repair | 3222.47 | 3222.47
2024-12-01 | 52.8673. | Tooleville Mutual Water Co. - Tooleville Waterline Repair (T&M) | 18612.08 | 18612.08
2024-12-01 | 52.8675. | California Water Service Co. - Tesoro Viejo WTP Conduit Install | 9834.21 | 9834.21
2024-12-01 | 52.8676. | County of Fresno - DIST 47-Water - Emergency Repair | 13585.28 | 13585.28
2024-12-01 | 52.8679. | Brower GSA Ranch LLC - Lindsay LDI Work | 41047.76 | 41047.76
2024-12-01 | 52.8681. | Provost and Prichard Engineering Group, Inc. - Sugar Leaf Emergency Water Line Repair (T&M) | 9042.21 | 9042.21
2024-12-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 1010333 | 1010333
2024-12-01 | 53.2001. | East Bay Area Overhead 2024 | 278701.26 | 278701.26
2024-12-01 | 53.2002. | East Bay Area Estimating 2024 | 68437.31 | 68437.31
2024-12-01 | 53.2003. | City of Brentwood - Brentwood Solid Waste Organics Diversion Project | 1261843.3 | 1261843.3
2024-12-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 82942.93 | 82942.93
2024-12-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 45072829.25 | 45072829.25
2024-12-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 7371036.33 | 7477939.28
2024-12-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 21046229.25 | 21076923.07
2024-12-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements | 2187754.68 | 2187754.68
2024-12-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 1658970 | 1658970
2024-12-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station | 1398716 | 1398716
2024-12-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 223896.9 | 223896.9
2024-12-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 832297.99 | 832297.99
2024-12-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 306021.41 | 306021.41
2024-12-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3218768.8 | 3218768.8
2024-12-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 364950 | 364950
2024-12-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 13506.19 | 13506.19
2024-12-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 1313.45 | 1313.45
2024-12-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3703932.71 | 3703932.71
2024-12-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 7967721.04 | 7967721.04
2024-12-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 85064.63 | 85064.63
2024-12-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 306900 | 306900
2024-12-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 152091.76 | 152091.76
2024-12-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 23452991.79 | 23452991.79
2024-12-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 3922300 | 3922300
2024-12-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 107416 | 107416
2024-12-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1141484 | 1141484
2024-12-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 129865 | 129865
2024-12-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 6239300 | 6239300
2024-12-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 282600 | 282600
2024-12-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 | 10110.6 | 10110.6
2024-12-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 136808.3 | 141798.79
2024-12-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 1117.5 | 1117.5
2024-12-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 12351.11 | 12351.11
2024-12-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 1815.23 | 1815.23
2024-12-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 1180798 | 1180798
2024-12-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 889.66 | 889.66
2024-12-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1093306 | 1093306
2024-12-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1144.88 | 1144.88
2024-12-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 162458.93 | 360000
2024-12-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 777.55 | 777.55
2024-12-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 1263.33 | 1263.33
2024-12-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1162246 | 1162246
2024-12-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 1602.33 | 1602.33
2024-12-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 13653.62 | 13653.62
2024-12-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project | 28042707 | 28042707
2024-12-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 889.64 | 889.64
2024-12-01 | 54.9020. | City of Camarillo - North Pleasant Valley Desalter Project | 39349829.25 | 39349829.25
2024-12-01 | 54.9210. | Lamont Public Utility District - Well 13 Replacement | 3671189.79 | 3671189.79
2024-12-01 | 54.9211. | Semitropic Water Storage Dist. - Leonard System Extension Project | 15610269.01 | 15610269.01
2024-12-01 | 54.9232. | Kern Water Bank Authority - Well 20D01 | 92833.57 | 92833.57
2024-12-01 | 54.9234. | Kern Water Bank Authority - Well 9D01 | 270452.71 | 270452.71
2024-12-01 | 54.9236. | Kern Water Bank Authority - Well 12J01 | 108137.67 | 108137.67
2024-12-01 | 54.9243. | Shafter-Wasco Irrigation Dist. - Farmer Co-Op Pipeline | 1477897.92 | 1477897.92
2024-12-01 | 54.9275. | City of Bakersfield - WWTP No. 3 DAF Tank & Polymer Feed System Rehab - Phase 2 | 1001040.78 | 1001040.78
2024-12-01 | 54.9286. | Kern Water Bank Authority - Well 30S/25E-03L02 | 192497.1 | 192497.1
2024-12-01 | 54.9288. | Kern Water Bank Authority - Well 30S/26E-07N02 | 107345.23 | 107345.23
2024-12-01 | 54.9290. | County of Santa Barbara-Public Works - Laguna CSD Dutard Road Culvert #1 Maintenance | 42209.43 | 42209.43
2024-12-01 | 54.9291. | Cawelo Water District - Poso Creek 2023 Storm Damage Repair | 303582.03 | 303582.03
2024-12-01 | 54.9296. | Semitropic Water Storage Dist. - XYZ PIPE NETWORK EXTENSION PROJECT - AMENDMENT NO. 25 | 30500.18 | 30500.18
2024-12-01 | 54.9297. | Bakersfield Area Overhead 2024 | 1227667.28 | 1227667.28
2024-12-01 | 54.9298. | Bakersfield Area Estimating 2024 | 516192.65 | 516192.65
2024-12-01 | 54.9299. | Granite Construction Co. - Chumash WTP/WWTP | 4728.42 | 4728.42
2024-12-01 | 54.9300. | California Water Service Co. - Northeast Plant Pipe and Pump Replacement | 39208.75 | 39208.75
2024-12-01 | 54.9301. | California Water Service Co. - Northwest Plant Basin Cleaning | 45961.19 | 45961.19
2024-12-01 | 54.9305. | Semitropic Water Storage Dist. - East West Canal Cleaning | 127837.56 | 127837.56
2024-12-01 | 54.9306. | Lyles Utility Construction, LLC - Annual Maintenance Job 2024 Fiscal Year | 22534.51 | 22534.51
2024-12-01 | 54.9307. | Shafter-Wasco Irrigation Dist. - Jack Avenue Turnout | 35272.79 | 35272.79
2024-12-01 | 54.9308. | City of Bakersfield - Stine Road Hydrant Repair | 88611.41 | 88611.41
2024-12-01 | 54.9310. | Kern Water Bank Authority - Pond Valve Repairs | 25596.01 | 25596.01
2024-12-01 | 54.9311. | City of Bakersfield - Rosedale Lowes Hydrant Repair | 4613.85 | 4613.85
2024-12-01 | 54.9312. | Kern Water Bank Authority - Emergency Pump Station Repairs | 29809.1 | 29809.1
2024-12-01 | 54.9314. | Kleinfelder, Inc. - Test Pit Excavations | 12647.19 | 12647.19
2024-12-01 | 54.9315. | Cawelo Water Dist. - Emergency Pump Station Pipe Repair | 23813.74 | 23813.74
2024-12-01 | 54.9316. | East Niles Community Service Dist. - Concrete Foundations at New Office | 19333.89 | 19333.89
2024-12-01 | 54.9317. | Shafter-Wasco Irrigation Dist. - Emergency Burbank St Repair | 14292.87 | 14292.87
2024-12-01 | 54.9318. | Kern Water Bank Authority - Aqueduct Siphon Pipe Repair | 3315.24 | 3315.24
2024-12-01 | 54.9319. | Semitropic Water Storage Dist. - Kimberlina RCP Repairs | 60953.22 | 60953.22
2024-12-01 | 54.9320. | Semitropic Water Storage Dist. - Schuster Road PCCP Repair | 17926.04 | 17926.04
2024-12-01 | 54.9322. | Kern Water Bank Authority - Emergency Pump Station Repairs | 15299.68 | 15299.68
2024-12-01 | 54.9324. | Kern Water Bank Authority - Pump Station Trash Rack Removal | 2188.87 | 2188.87
2024-12-01 | 54.9325. | Semitropic Water Storage Dist. - Wildwood Pipe Repair | 42515.09 | 42515.09
2024-12-01 | 54.9326. | Kern Water Bank Authority - Siphon Pipe Cleaning | 27316.83 | 27316.83
2024-12-01 | 54.9327. | California Water Service Co. - Valve & Sluice Gate Repair | 2400.21 | 2400.21
2024-12-01 | 54.9328. | Kern County Water Agency - Removal of Precipitated Solids from Drying Bed Nos. 8 and 9 | 33328.68 | 33328.68
2024-12-01 | 54.9331. | Laguna County Sanitation Dist. - WWTP Flooding Repairs 2024 | 21094 | 21094
2024-12-01 | 54.9332. | Kern Water Bank Authority - Emergency Actuator Repair | 4299.97 | 4299.97
2024-12-01 | 54.9334. | County of Santa Barbara-Public Works - Laguna CSD - Orcutt Bluffs SS Replacement | 81967.35 | 81967.35
2024-12-01 | 54.9335. | Kern Water Bank Authority - Strand Pump Rehabilitation | 46166.65 | 46166.65
2024-12-01 | 54.9339. | Cawelo Water Dist. - Famoso Spreading Ground Repairs - Phase 3 | 376843.88 | 376843.88
2024-12-01 | 54.9340. | Shafter-Wasco Irrigation Dist. - Dresser Ave. Pipe Removal Project | 73662.15 | 73662.15
2024-12-01 | 54.9344. | Cawelo Water Dist. - Famoso Spreading Ground Material Purchases | 15513.41 | 15513.41
2024-12-01 | 54.9345. | East Niles Community Service Dist. - Breckenridge Electrical Pads | 20719.84 | 20719.84
2024-12-01 | 54.9346. | East Niles Community Service Dist. - Kern Citrus Pipe Repair | 16000.42 | 16000.42
2024-12-01 | 54.9348. | Semitropic Water Storage Dist. - Gromer Avenue Road Repair | 13473.84 | 13473.84
2024-12-01 | 54.9352. | Arvin Edison Water Storage Dist. - Canal Liner Repairs | 224312.53 | 224312.53
2024-12-01 | 54.9359. | Arvin Edison Water Storage Dist. - Fairfax & 58 Manhole Repair | 30144.83 | 30144.83
2024-12-01 | 55.1090. | LA Dept of Water and Power - Silverlake | 3617796.45 | 3702028.55
2024-12-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Exp. & Solids Treat. Facility | 333162067.71 | 333162067.71
2024-12-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6230352.53 | 6230352.53
2024-12-01 | 55.1200. | East County Advanced Water Purification Project - Package 1 | 142200053.22 | 177974141
2024-12-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out | -5995115.13 | -8100000
2024-12-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project | 14940308.28 | 14940308.28
2024-12-01 | 55.1204. | East County Advanced Water Purification Project - Package 3 | 40078338.41 | 40662397
2024-12-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out | -1917801.19 | -2500000
2024-12-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 36564118.62 | 36672930.09
2024-12-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement | 1764713.69 | 1764713.69
2024-12-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements | 3422535 | 3422535
2024-12-01 | 55.1233. | Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 76329.8 | 76329.8
2024-12-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 | 26100.05 | 26100.05
2024-12-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 5142665 | 5142665
2024-12-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 139897192 | 139897192
2024-12-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 63696 | 63696
2024-12-01 | 55.1173. | City of Beaumont - WWTP | 58161652.26 | 58161652.26
2024-12-01 | 55.1193. | Rialto Bioenergy Facility, LLC - RBF PyroBioMethane Project | 18201508.8 | 18201508.8
2024-12-01 | 55.1236. | Southern Contracting Co. - City of Palm Springs Lighting Project | 584954.09 | 584954.09
2024-12-01 | 55.1240. | Murrieta Area Overhead 2024 | 1156437.83 | 1156437.83
2024-12-01 | 55.1241. | Murrieta Area Estimating 2024 | 833941.37 | 833941.37
2024-12-01 | 55.1242. | Victor Valley Wastewater Reclamation Authority - VVWRA - 6in Filtrate Pipe | 25484.07 | 25484.07
2024-12-01 | 55.1243. | Victor Valley Wastewater Reclamation Authority - VVWRA - 6in Filtrate Pipe PHS 2 | 24270.58 | 24270.58
2024-12-01 | 55.1244. | Victor Valley Wastewater Reclamation Authority - Civil Works for Pipe Supports | 10068.72 | 10068.72
2024-12-01 | 55.1245. | Victor Valley Wastewater Reclamation Authority - Side Stream Air Project | 77453.87 | 77453.87
2024-12-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 2709865 | 2709865
2024-12-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 37896367.63 | 37896367.63
2024-12-01 | 57.0001. | San Diego Area Overhead 2024 | 14122.99 | 14122.99
2024-12-01 | 57.0002. | San Diego Area Estimating 2024 | 98216 | 98216
2024-12-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 20764841 | 20764841
2024-12-01 | 58.0001. | Los Angeles Area Overhead 2024 | 54188.26 | 54188.26
2024-12-01 | 58.0002. | Los Angeles Area Estimating 2024 | 44984.62 | 44984.62
2024-12-01 | 56.1002. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 127961 | 127961
2024-12-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 209558 | 209558
2024-12-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 279521 | 279521
2024-12-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 70578 | 70578
2024-12-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 15806 | 15806
2024-12-01 | 56.1008. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 31267 | 31267
2024-12-01 | 56.1010.01. | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 7647 | 7647
2024-12-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 123684 | 123684
2024-12-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 57071.14 | 57071.14
2024-12-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 50665 | 50665
2024-12-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 52462 | 52462
2024-12-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 137169 | 137169
2024-12-01 | 56.1021. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 182399 | 182399
2024-12-01 | 56.1022. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 88093.56 | 88093.56
2024-12-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 159577 | 159577
2024-12-01 | 56.1030. | Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 692696 | 692696
2024-12-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 76106 | 76106
2024-12-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 206207 | 206207
2024-12-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 2024.38 | 2024.38
2024-12-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 85203 | 85203
2024-12-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 340493 | 340493
2024-12-01 | 56.1041. | Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 27735 | 27735
2024-12-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services | 156172 | 156172
2024-12-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 290493 | 290493
2024-12-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 56439 | 56439
2024-12-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 2151599 | 2151599
2024-12-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 75007 | 75007
2024-12-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 186274 | 186274
2024-12-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 3340726 | 3340726
2024-12-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 88433 | 88433
2024-12-01 | 56.1052. | San Jose Water - Williams Back ATS Replacement | 8365 | 8365
2024-12-01 | 56.1053. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 20193 | 20193
2024-12-01 | 56.1054. | W.M. Lyles - Riverside Public Works - Digester 5 Rehab | 157227 | 157227
2024-12-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 101821.1 | 101821.1
2024-12-01 | 56.1056. | Irvine Ranch Water District - Michelson Water Recycling Plan | 197595 | 197595
2024-12-01 | 56.1057. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 383141 | 383141
2024-12-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 304484 | 304484
2024-12-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 307643 | 307643
2024-12-01 | 56.1061. | San Jose Water - PLC System Assessment | 5589 | 5589
2024-12-01 | 56.1062. | SCADA System Upgrade - City of Brentwood | 1149774 | 1149774
2024-12-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 92421 | 92421
2024-12-01 | 56.1064. | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 260418 | 260418
2024-12-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 209493 | 209493
2024-12-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 464755 | 464755
2024-12-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 409155 | 409155
2024-12-01 | 56.1071. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 7711 | 7711
2024-12-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 37323 | 37323
2024-12-01 | 56.1074. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 10689 | 10689
2024-12-01 | 56.1076. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 14594 | 14594
2024-12-01 | 56.1001. | San Jose Water Co. - Batista PLC Control Panel Upgrade | 41833.76 | 41833.76
2024-12-01 | 56.1006. | System Integration Overhead 2024 | 8057307.54 | 8057307.54
2024-12-01 | 56.1009. | Al Fresco Landscaping Inc. - East Garrison Marina On-Site Assessment - County of Monterey | 2351.25 | 2351.25
2024-12-01 | 56.1009.01. | Al Fresco Landscaping Inc. - East Garrison On-Site Eq. Reconfig. - County of Monterey | 22478.79 | 22478.79
2024-12-01 | 56.1011. | City of Atwater - Well VFD Reconfiguration | 467.5 | 467.5
2024-12-01 | 56.1012. | California Water Service Co. - SSF-1 - Wildfire Booster Pump Station | 41783.05 | 41783.05
2024-12-01 | 56.1013. | Placer County Water Agency - Raw Water PLC Control Panels - PCWA | 54825.62 | 54825.62
2024-12-01 | 56.1014. | Collins Electric - SWWTP On-Site Support Services | 18790.63 | 18790.63
2024-12-01 | 56.1020. | East Contra Costa Irrigation Dist. - Time & Material Contract - East Contra Costa Irrigation Dist | 5622.81 | 5622.81
2024-12-01 | 56.1024. | Templeton Community Services Dist. - Instrumentation Calibration Services | 2321.09 | 2321.09
2024-12-01 | 56.1026. | City of Tracy Public Works - Annual Flow Calibrations | 14790.16 | 14790.16
2024-12-01 | 56.1027. | Young Electric Co. - PLC & SCADA Assessment at Caldecott Tunnel - 04-1X260 | 3811.78 | 3811.78
2024-12-01 | 56.1028. | Shape Incorporated - Flow Meter Purchase | 5584.19 | 5584.19
2024-12-01 | 56.1029. | San Gabriel Valley Water Co. - WNOU Plant Flow Meter Assessment | 2409.58 | 2409.58
2024-12-01 | 56.1031. | Winton Water & Sanitary Dist. - Buhach Well Site Troubleshooting | 602.59 | 602.59
2024-12-01 | 56.1034. | Fair Oaks Water Dist. - Fair Oaks, City of - Lemon Street PRV Station RTU 13 | 167.19 | 167.19
2024-12-01 | 56.1035. | California Water Service Co. - Salinas Station 47 Assessment | 2150.63 | 2150.63
2024-12-01 | 56.1040. | San Jose Water Co - Belgatos Booster Station | 21141.78 | 21141.78
2024-12-01 | 56.1044. | San Jose Water Co - Saratoga Startup Support | 44527.5 | 44527.5
2024-12-01 | 56.1045. | Fusion Electic. Imc - Copperopolis - Copper Cove Flowmeter Cables | 2946.52 | 2946.52
2024-12-01 | 56.1058. | South Orange County Wastewater Authority - As Needed Profess | 2154.2 | 2154.2
2024-12-01 | 56.1070. | UC Davis - Sand Filter PLC Troubleshooting | 1422.38 | 1422.38
2024-12-01 | 50.0528. | W.M. Lyles Co. - General Overhead | 2950997.47 | 2950997.47
2024-12-01 | 50.0529. | W.M. Lyles Co. - General Estimating | 98218.84 | 98218.84
2024-12-01 | 50.0531. | American Paving | 324.93 | 324.93
2024-12-01 | 50.0532. | Lyles Services Co. | 43574.5 | 43574.5
2024-12-01 | 50.0534. | Lyles Utility Construction, LLC | 18897.73 | 18897.73