## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-06-01 | 51.1108. | JV w/AECOM - Stockton - RWCF Phase 2A/2B | 93864441.26 | 94026998 | 858269 | 2025-07-30
2025-06-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) | 0 | 0 | 3463215.24 | 2025-07-30
2025-06-01 | 51.1129. | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications | 122305869.84 | 122305869.84 | 8796198.171 | 2027-06-25
2025-06-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 373737.9 | 373737.9 | 42449.2259 | 2025-07-30
2025-06-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements | 5620852 | 5620852 | 786140.5727 | 2025-07-30
2025-06-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 | 1246905.44 | 1246905.44 | 69994.7312 | 2025-07-30
2025-06-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 | 1117331.42 | 1117331.42 | -2500 | 2025-07-30
2025-06-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 67202.17 | 67202.17 | 4426.359 | 2025-07-30
2025-06-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project | 3979878.31 | 3979878.31 | 127979.7284 | 2025-07-30
2025-06-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project | 14969567 | 14969567 | 178356.1774 | 2026-12-20
2025-06-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility | 60275337 | 60275337 | 2742477.6369 | 2025-10-01
2025-06-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2623267 | 2623267 | 158150.8933 | 2026-01-31
2025-06-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2486231.58 | 2486231.58 | 233008.2349 | 2025-07-30
2025-06-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 10658200 | 10658200 | 0 | 2026-11-25
2025-06-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project | 19450000 | 19450000 | 310138.7572 | 2026-06-30
2025-06-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement | 549548.83 | 549548.83 | 80123.2238 | 2025-07-30
2025-06-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 13363835 | 13363835 | 319505.2002 | 2025-12-15
2025-06-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out | 0 | 0 | 1297744.54 | 2025-10-01
2025-06-01 | 51.1156. | Rocklin Overhead 2025 | 0 | 0 | -575452.68 | 2025-12-31
2025-06-01 | 51.1157. | Rocklin Estimating 2025 | 0 | 0 | -316562.26 | 2025-12-31
2025-06-01 | 51.1158. | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 32282 | 32282 | 0 | 2025-07-30
2025-06-01 | 51.1159. | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 1199000 | 1199000 | 564.1295 | 2026-03-15
2025-06-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion | 1991231.37 | 1991231.37 | 233098.8 | 2025-06-25
2025-06-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 1134038.13 | 1174183 | 0 | 2025-07-30
2025-06-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out | 0 | 0 | 293290.03 | 2025-07-30
2025-06-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System | 1259398 | 1259398 | 228697.8498 | 2025-07-31
2025-06-01 | 52.8567. | City of Modesto - Grayson Well 69 | 3059858.99 | 3059858.99 | -70086 | 2025-07-30
2025-06-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 12551954 | 12551954 | 1794336.5526 | 2025-08-31
2025-06-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 5095690.97 | 5095690.97 | 410557.9604 | 2025-07-30
2025-06-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 5899872 | 5899872 | 269392.8392 | 2025-07-30
2025-06-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 2515889 | 2515889 | 101437.7195 | 2025-08-31
2025-06-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 | 13727995 | 13727995 | 474916.6106 | 2026-03-11
2025-06-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 2510000 | 2510000 | 279220.0795 | 2025-07-31
2025-06-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic | 25799094 | 25799094 | 1547951.7378 | 2025-08-31
2025-06-01 | 52.8640. | City of Dos Palos - WTP Replacement Project | 37051511.29 | 37051511.29 | 1099633.279 | 2026-04-17
2025-06-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station | 1290184 | 1290184 | 243006.9465 | 2025-07-31
2025-06-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1863066 | 1863066 | 152000 | 2025-07-30
2025-06-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1641800 | 1641800 | 180952.464 | 2025-08-31
2025-06-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 | 328500 | 328500 | 23359.77 | 2025-07-30
2025-06-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 | 325522 | 325522 | 23375.9869 | 2025-08-31
2025-06-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 576850 | 576850 | 39670.6917 | 2025-09-30
2025-06-01 | 52.8678. | City of Chowchilla - Well 15 & Generator Improvement Projects | 1240321 | 1240321 | 20853.4412 | 2025-12-31
2025-06-01 | 52.8682. | Fresno Overhead 2025 | 0 | 0 | -498447.1 | 2025-12-31
2025-06-01 | 52.8683. | Fresno Estimating 2025 | 0 | 0 | -180482.49 | 2025-12-31
2025-06-01 | 52.8684. | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 30579.25 | 30579.25 | 0 | 2025-08-29
2025-06-01 | 52.8685. | Malaga County Water Dist. - Malaga County Water District | 426800 | 426800 | 0 | 2025-09-30
2025-06-01 | 52.8687. | California Water Service Co. - Salinas Station 205 | 831511 | 831511 | 37985.3431 | 2025-08-31
2025-06-01 | 52.8688. | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 132492.2 | 132492.2 | 16292.2 | 2025-08-31
2025-06-01 | 52.8692. | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 44658.46 | 44658.46 | 3802.79 | 2025-08-31
2025-06-01 | 52.8693. | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 1136503 | 1136503 | 23328.5075 | 2025-09-22
2025-06-01 | 52.8697. | City of Tulare - Industrial WWTP Dewatering Improvements | 1388000 | 1388000 | 0 | 2026-07-22
2025-06-01 | 52.8699. | City of Hanford - WWTP Repair T&M | 3001 | 3001 | 114.0705 | 2025-07-30
2025-06-01 | 52.8700. | Lyles Services Co. - LSC GO Misc. Work | 5000 | 5000 | 325.0582 | 2025-12-31
2025-06-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 | 274166.01 | 274166.01 | 6883.96 | 2025-06-30
2025-06-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install | 279244 | 279244 | 28155.8 | 2025-01-31
2025-06-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M | 29838.25 | 29838.25 | 3749.92 | 2025-06-30
2025-06-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 23957 | 23957 | 16567.28 | 2025-12-31
2025-06-01 | 52.8689. | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 16665.83 | 16665.83 | 570.25 | 2025-05-31
2025-06-01 | 52.8690. | City of Dinuba - WWTP Rake Replacement | 14151.97 | 14151.97 | 996.14 | 2025-05-02
2025-06-01 | 52.8691. | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 11302.84 | 11302.84 | 3015.02 | 2025-06-30
2025-06-01 | 52.8694. | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 43047.45 | 43047.45 | 4505.46 | 2025-04-30
2025-06-01 | 52.8695. | Lyles Services Co. - LSC GO Trash Enclosure | 13769 | 13769 | 744.63 | 2025-06-30
2025-06-01 | 52.8696. | American Paving Co. - Hot Tap for APC- Tule River Parkway | 1059.22 | 1059.22 | 171.57 | 2025-05-31
2025-06-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 1038540 | 1038540 | 37185.5137 | 2025-11-30
2025-06-01 | 53.2005. | East Bay Overhead 2025 | 0 | 0 | -164346.29 | 2025-12-31
2025-06-01 | 53.2006. | East Bay Estimating 2026 | 0 | 0 | -282142.77 | 2025-12-31
2025-06-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 105085.45 | 105085.45 | 10966.87 | 2025-12-31
2025-06-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 55719995 | 55719995 | 10372751.5815 | 2025-08-30
2025-06-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 9313752.09 | 9313752.09 | 551994.3651 | 2025-07-30
2025-06-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements | 2472164 | 2472164 | 159438.0972 | 2025-09-15
2025-06-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equipping Project | 1777852 | 1777852 | 77796.0454 | 2025-09-30
2025-06-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station | 1471328 | 1471328 | 0 | 2025-09-30
2025-06-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 223896.47 | 223896.47 | 951.112 | 2025-07-30
2025-06-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 907297.99 | 907297.99 | 68000 | 2025-08-30
2025-06-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3203768.8 | 3203768.8 | 14650.368 | 2025-07-30
2025-06-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 462022 | 462022 | 48820.5793 | 2025-07-28
2025-06-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 20000 | 20000 | 694.5672 | 2026-12-01
2025-06-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3930346 | 3930346 | 92997.5508 | 2025-08-25
2025-06-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 8787721.04 | 8787721.04 | 364661.0099 | 2025-12-31
2025-06-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 324900 | 324900 | 13494.2176 | 2025-07-30
2025-06-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 25063572.79 | 25063572.79 | 396590.5975 | 2026-08-17
2025-06-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 4082300 | 4082300 | 0 | 2026-10-30
2025-06-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1213797 | 1213797 | 131966.4672 | 2025-07-30
2025-06-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 6881300 | 6881300 | 290608.5078 | 2026-05-31
2025-06-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 1294830 | 1294830 | 156022.6009 | 2025-08-31
2025-06-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1147640 | 1147640 | 24208.3952 | 2025-09-01
2025-06-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1225220 | 1225220 | 0 | 2026-05-31
2025-06-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project | 30413570 | 30413570 | 0 | 2027-01-05
2025-06-01 | 54.9371. | Bakersfield Overhead 2025 | 0 | 0 | -622467.54 | 2025-12-31
2025-06-01 | 54.9372. | Bakersfield Estimating 2025 | 0 | 0 | -328988.36 | 2025-12-31
2025-06-01 | 54.9373. | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 1524766 | 1524766 | 0 | 2026-03-01
2025-06-01 | 54.9382. | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 110700 | 110700 | 4505.5362 | 2025-12-31
2025-06-01 | 54.9384. | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 75000 | 75000 | 3443.2447 | 2025-07-30
2025-06-01 | 54.9385. | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 111263 | 111263 | 2932.4057 | 2025-07-30
2025-06-01 | 54.9386. | Kern Valley State Prison - Arsenic Pipe Leak Repair | 96086 | 96086 | 20708.3 | 2025-07-30
2025-06-01 | 54.9387. | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 25000 | 25000 | 2112.4056 | 2025-07-30
2025-06-01 | 54.9389. | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 299780 | 299780 | 0 | 2025-09-30
2025-06-01 | 54.9390. | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 80000 | 80000 | 1102.8726 | 2025-07-30
2025-06-01 | 54.9391. | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 400000 | 400000 | 0 | 2025-07-31
2025-06-01 | 54.9392. | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 223000 | 223000 | 4360.2899 | 2025-07-31
2025-06-01 | 54.9394. | City of Arvin - Haven Drive Lateral Repair | 16000 | 16000 | 935.97 | 2025-07-30
2025-06-01 | 54.9395. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 1528900 | 1528900 | 0 | 2026-02-28
2025-06-01 | 54.9397. | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 3690645 | 3690645 | 0 | 2026-03-01
2025-06-01 | 54.9398. | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 14300 | 14300 | 1085.485 | 2025-07-01
2025-06-01 | 54.9399. | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 24775 | 24775 | 0 | 2025-07-30
2025-06-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 24160002.44 | 24160002.44 | 3105829.59 | 2025-03-01
2025-06-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 340270.46 | 340270.46 | 34249.05 | 2025-12-31
2025-06-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 4300 | 4300 | 2986.55 | 2025-12-31
2025-06-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 110661.47 | 110661.47 | 24353.21 | 2025-03-31
2025-06-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 427464.77 | 427464.77 | 58649.48 | 2025-03-01
2025-06-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 175884.64 | 175884.64 | 56698.53 | 2025-01-31
2025-06-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 199161.5 | 199161.5 | 75015.2 | 2025-01-31
2025-06-01 | 54.9347. | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 7100 | 7100 | 3872.3 | 2025-02-28
2025-06-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 290129 | 290129 | 92239.69 | 2025-02-28
2025-06-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 | 116193.81 | 116193.81 | 11750.75 | 2025-03-31
2025-06-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 153298.79 | 153298.79 | 16490.49 | 2025-01-31
2025-06-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 2008.42 | 2008.42 | 890.92 | 2025-03-31
2025-06-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 9571.2 | 9571.2 | 1340.37 | 2025-01-31
2025-06-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 2806.42 | 2806.42 | 991.19 | 2025-03-31
2025-06-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 1760.42 | 1760.42 | 870.76 | 2025-03-31
2025-06-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1855.92 | 1855.92 | 711.04 | 2025-03-31
2025-06-01 | 54.9361. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 108668.35 | 108668.35 | 8076.44 | 2025-03-30
2025-06-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 425035.04 | 425035.04 | 49433.8 | 2025-01-25
2025-06-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 1855.92 | 1855.92 | 1078.37 | 2025-03-31
2025-06-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 2216.42 | 2216.42 | 953.09 | 2025-03-31
2025-06-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 2540.42 | 2540.42 | 938.09 | 2025-03-31
2025-06-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 15697.91 | 15697.91 | 2044.29 | 2025-01-31
2025-06-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 1760.42 | 1760.42 | 870.78 | 2025-03-31
2025-06-01 | 54.9374. | City of Santa Maria - WWTP Trickling Filter Repairs | 32962 | 32962 | 12975.55 | 2025-03-31
2025-06-01 | 54.9375. | City of Santa Maria - WWTP Clarifier Repairs | 8232.73 | 8232.73 | 3687.25 | 2025-03-13
2025-06-01 | 54.9379. | Semitropic Water Storage Dist. - Delta System Pipe Repair | 41679.77 | 41679.77 | 5567.82 | 2025-02-28
2025-06-01 | 54.9380. | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 22446.19 | 22446.19 | 4381.47 | 2025-03-25
2025-06-01 | 54.9381. | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 58900 | 58900 | 30024.62 | 2025-03-30
2025-06-01 | 54.9383. | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 17542.44 | 17542.44 | 1782.68 | 2025-12-30
2025-06-01 | 54.9388. | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 7454.07 | 7454.07 | 918.66 | 2025-07-01
2025-06-01 | 54.9393. | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 31523.02 | 31523.02 | 6105.3 | 2025-06-30
2025-06-01 | 55.1090. | JV w/Webcor & Obayashi - Silverlake - LADWP | 5099451.37 | 5300000 | 1464039.2408 | 2025-07-25
2025-06-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility | 341247032 | 341247032 | 5748986 | 2027-06-01
2025-06-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6651803.53 | 6651803.53 | 300000 | 2025-07-01
2025-06-01 | 55.1200. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 | 171115950 | 195685221 | 0 | 2027-04-02
2025-06-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out | 0 | 0 | 6961158.46 | 2027-04-02
2025-06-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project | 16115717.28 | 16115717.28 | 670837.5569 | 2026-08-01
2025-06-01 | 55.1204. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 | 46351308 | 47052523 | 0 | 2027-02-26
2025-06-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out | 0 | 0 | 2133979.08 | 2027-02-26
2025-06-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 41043874.76 | 41043874.76 | 4281280.3867 | 2025-07-21
2025-06-01 | 55.1233. | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 104043 | 104043 | 8428.84 | 2025-07-30
2025-06-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 | 223325 | 223325 | 8107 | 2026-12-31
2025-06-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 5600482 | 5600482 | 0 | 2026-04-01
2025-06-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 147718400 | 147718400 | 0 | 2029-02-01
2025-06-01 | 55.1252. | Murrieta Overhead 2025 | 0 | 0 | -975097.07 | 2025-12-31
2025-06-01 | 55.1253. | Murrieta Estimating 2025 | 0 | 0 | -282141.3 | 2025-12-31
2025-06-01 | 55.1254. | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 471896 | 471896 | 0 | 2025-07-30
2025-06-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement | 2273682.69 | 2273682.69 | 608537.39 | 2025-03-31
2025-06-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements | 4046200 | 4046200 | 725363.31 | 2025-03-31
2025-06-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 184557.17 | 184557.17 | 136263.23 | 2025-03-31
2025-06-01 | 55.1251. | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 322982.96 | 322982.96 | 39300.11 | 2025-04-25
2025-06-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 3583401 | 3583401 | 148243.1572 | 2025-07-30
2025-06-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 40106224.63 | 40106224.63 | 0 | 2026-03-25
2025-06-01 | 57.0005. | San Diego Overhead 2025 | 0 | 0 | -17058.05 | 2025-12-31
2025-06-01 | 57.0006. | San Diego Estimating 2025 | 0 | 0 | -4432.92 | 2025-12-31
2025-06-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 22085905 | 22085905 | 0 | 2026-06-01
2025-06-01 | 58.0004. | Los Angeles Overhead 2025 | 0 | 0 | -53275.6 | 2025-12-31
2025-06-01 | 58.0005. | Los Angeles Estimating 2025 | 0 | 0 | -12730.8 | 2025-12-31
2025-06-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 311191 | 311191 | 74976.7551 | 2025-09-30
2025-06-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 373425 | 373425 | 71178.5215 | 2025-09-30
2025-06-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 135000 | 135000 | 15725.5302 | 2025-09-30
2025-06-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 19314 | 19314 | 1861.3347 | 2025-09-30
2025-06-01 | 56.1010. | Placer County Water Agency -PCWA Time & Material Contract | 49250 | 49250 | 14136.5945 | 2025-09-30
2025-06-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 160000 | 160000 | 26970.641 | 2025-12-31
2025-06-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 140764.5 | 140764.5 | 45153.77 | 2025-12-31
2025-06-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 73222 | 73222 | 15442.2466 | 2025-12-31
2025-06-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 145000 | 145000 | 56904.3117 | 2025-12-31
2025-06-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 184435 | 184435 | 26638.5755 | 2025-12-31
2025-06-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 220390 | 220390 | 58109.351 | 2025-07-30
2025-06-01 | 56.1030. | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 611831.14 | 611831.14 | 0 | 2025-09-30
2025-06-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 85000 | 85000 | 0 | 2025-12-31
2025-06-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 276000 | 276000 | 24698.1604 | 2026-03-31
2025-06-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 15788.5 | 15788.5 | 10246.62 | 2025-12-31
2025-06-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 95000 | 95000 | 4524.7784 | 2025-12-31
2025-06-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 375000 | 375000 | 40177.4908 | 2025-12-31
2025-06-01 | 56.1041. | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 20016.78 | 20016.78 | 0 | 2025-09-30
2025-06-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services | 277565 | 277565 | 61126.6953 | 2025-09-30
2025-06-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 325000 | 325000 | 0 | 2026-03-31
2025-06-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 66000 | 66000 | 8325.8902 | 2025-09-30
2025-06-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 2395000 | 2395000 | 0 | 2026-12-31
2025-06-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 200000 | 200000 | 60507.1128 | 2025-09-30
2025-06-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 308725 | 308725 | 46675.4058 | 2025-12-31
2025-06-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 3780000 | 3780000 | 0 | 2026-12-31
2025-06-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 126535.19 | 126535.19 | 28244.3424 | 2025-09-30
2025-06-01 | 56.1054. | W.M. Lyles - Riverside Public Works - Digester 5 Rehab | 215000 | 215000 | 13988.8206 | 2026-03-31
2025-06-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 120891 | 120891 | 10910.5098 | 2025-09-30
2025-06-01 | 56.1056. | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan | 98280.63 | 98280.63 | 0 | 2026-09-30
2025-06-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 380000 | 380000 | 25549.706 | 2026-03-31
2025-06-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 400000 | 400000 | 0 | 2026-09-30
2025-06-01 | 56.1062. | AIC - SCADA System Upgrade - City of Brentwood | 406588.07 | 406588.07 | 0 | 2025-12-31
2025-06-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 108000 | 108000 | 3941.0609 | 2026-03-31
2025-06-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 227000 | 227000 | 12241.0195 | 2025-09-30
2025-06-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 595000 | 595000 | 31992.863 | 2025-12-31
2025-06-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 478000 | 478000 | 0 | 2026-06-30
2025-06-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 48420 | 48420 | 5563.6133 | 2025-12-31
2025-06-01 | 56.1073. | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 122210 | 122210 | 0 | 2026-03-31
2025-06-01 | 56.1075. | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 950000 | 950000 | 0 | 2025-12-31
2025-06-01 | 56.1077. | System Integration Overhead 2025 | 0 | 0 | -4370293.76 | 2025-12-31
2025-06-01 | 56.1078. | City of Napa - On-Call Control Systems Integrator Services | 13795 | 13795 | 6677.81 | 2025-12-31
2025-06-01 | 56.1079. | San Jose Water Co - Montevina PLC Upgrade | 405000 | 405000 | 0 | 2025-12-31
2025-06-01 | 56.1080. | San Jose Water Co - PLC System Assessment | 359469 | 359469 | 68128.44 | 2025-09-30
2025-06-01 | 56.1081. | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 179690 | 179690 | 3538.2351 | 2025-09-30
2025-06-01 | 56.1082. | City of Clovis - Pump Station E New Pump 5 VFD Startup | 19800 | 19800 | 4278.6419 | 2025-09-30
2025-06-01 | 56.1083. | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 717010 | 717010 | 0 | 2026-06-30
2025-06-01 | 56.1084. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 6000 | 6000 | 1008.311 | 2025-12-31
2025-06-01 | 56.1085. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 80000 | 80000 | 0 | 2026-06-30
2025-06-01 | 56.1086. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 376000 | 376000 | 0 | 2026-06-30
2025-06-01 | 56.1087. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 49369 | 49369 | 4938.7803 | 2025-12-31
2025-06-01 | 56.1088. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 127235 | 127235 | 0 | 2026-03-31
2025-06-01 | 56.1102. | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 19815.94 | 19815.94 | 0 | 2025-12-31
2025-06-01 | 56.1103. | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 55592.31 | 55592.31 | 0 | 2025-12-31
2025-06-01 | 56.1104. | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 9500.31 | 9500.31 | 0 | 2025-09-30
2025-06-01 | 56.1105. | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 23646.28 | 23646.28 | 0 | 2026-03-31
2025-06-01 | 56.1106. | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 54250.3 | 54250.3 | 0 | 2025-12-31
2025-06-01 | 56.1107. | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 3429.06 | 3429.06 | 0 | 2025-12-31
2025-06-01 | 56.1108. | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 20729.84 | 20729.84 | 0 | 2025-09-30
2025-06-01 | 56.1109. | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 13870.31 | 13870.31 | 0 | 2026-03-31
2025-06-01 | 56.1110. | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 4596.42 | 4596.42 | 0 | 2025-07-30
2025-06-01 | 56.1111. | AIC - California American Water - Luzern Well Treatment Design | 17135.01 | 17135.01 | 0 | 2026-03-31
2025-06-01 | 56.1112. | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 27241.58 | 27241.58 | 0 | 2025-12-31
2025-06-01 | 56.1113. | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 49158.44 | 49158.44 | 0 | 2026-12-31
2025-06-01 | 56.1115. | AIC - UC Davis - WWTP Annual Instrument Calibrations | 5895.77 | 5895.77 | 0 | 2025-07-30
2025-06-01 | 56.1119. | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 22184.06 | 22184.06 | 0 | 2026-09-30
2025-06-01 | 56.1120. | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 1045.63 | 1045.63 | 0 | 2026-03-31
2025-06-01 | 56.1121. | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 21399.38 | 21399.38 | 0 | 2026-06-30
2025-06-01 | 56.1122. | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 5864.38 | 5864.38 | 0 | 2025-09-30
2025-06-01 | 56.1123. | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 3772.82 | 3772.82 | 0 | 2025-09-30
2025-06-01 | 56.1124. | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 28100 | 28100 | 0 | 2026-12-31
2025-06-01 | 56.1125. | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 14229.38 | 14229.38 | 0 | 2025-12-31
2025-06-01 | 56.1126. | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 9526.88 | 9526.88 | 0 | 2026-03-31
2025-06-01 | 56.1127. | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 6519.07 | 6519.07 | 0 | 2026-12-31
2025-06-01 | 56.1128. | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 4793.13 | 4793.13 | 0 | 2025-12-31
2025-06-01 | 56.1129. | AIC - RMCSD - VEEAM SFTWR | 133.75 | 133.75 | 0 | 2025-09-30
2025-06-01 | 56.1130. | System Integration Division Estimating 2025 | 0 | 0 | -267.5 | 2025-12-31
2025-06-01 | 56.1131. | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 2388.75 | 2388.75 | 0 | 2026-03-31
2025-06-01 | 56.1132. | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 585 | 585 | 0 | 2025-09-30
2025-06-01 | 56.1133. | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 2827.5 | 2827.5 | 0 | 2025-09-30
2025-06-01 | 56.1134. | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 965.51 | 965.51 | 0 | 2025-12-31
2025-06-01 | 56.1135. | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 112.5 | 112.5 | 0 | 2025-12-31
2025-06-01 | 56.1141. | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 2827.5 | 2827.5 | 0 | 2026-03-31
2025-06-01 | 56.1002. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 185000 | 185000 | 70514.18 | 2025-04-01
2025-06-01 | 56.1008. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 55000 | 55000 | 24448.08 | 2025-03-31
2025-06-01 | 56.1010.01. | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 9569 | 9569 | 2471.9 | 2025-03-31
2025-06-01 | 56.1021. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 244760 | 244760 | 128007.48 | 2025-06-30
2025-06-01 | 56.1022. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 0 | 0 | 0 | 2025-03-31
2025-06-01 | 56.1052. | San Jose Water - Williams Back ATS Replacement | 8887 | 8887 | 2486.06 | 2025-04-01
2025-06-01 | 56.1053. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 35000 | 35000 | 15035.22 | 2025-04-01
2025-06-01 | 56.1057. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 0 | 0 | 0 | 2025-04-01
2025-06-01 | 56.1061. | San Jose Water - PLC System Assessment | 11269 | 11269 | 5686.34 | 2025-03-31
2025-06-01 | 56.1064. | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 435153 | 435153 | 233861.6 | 2025-05-01
2025-06-01 | 56.1069. | City of Brentwood - Brentwood, City of - On-Call Agreement | 2525 | 2525 | -1296.46 | 2025-06-30
2025-06-01 | 56.1071. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 34000 | 34000 | 30403.44 | 2025-06-30
2025-06-01 | 56.1074. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 12650 | 12650 | 2008.14 | 2025-04-01
2025-06-01 | 56.1076. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 19200 | 19200 | 7622.23 | 2025-03-31
2025-06-01 | 50.0541. | W.M. Lyles Co. - General Overhead | 0 | 0 | -1633185.01 | 2025-12-31
2025-06-01 | 50.0542. | W.M. Lyles Co. - General Estimating | 0 | 0 | -30707.93 | 2025-12-31
2025-06-01 | 50.0543. | American Paving | 7051.01 | 7051.01 | 0 | 2025-12-31
2025-06-01 | 50.0544. | Lyles Services Co. | 3880.42 | 3880.42 | 0 | 2025-12-31
2025-06-01 | 50.0545. | New England Sheet Metal and Mechanical Co. | 1037.94 | 1037.94 | 0 | 2025-12-31
2025-06-01 | 50.0546. | Lyles Utility Construction, LLC | 11254.28 | 11254.28 | 788.66 | 2025-12-31
2025-06-01 | 50.0551. | Advanced Integration & Controls | 274.42 | 274.42 | 0 | 2025-12-31

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-06-01 | 51.1108. | JV w/AECOM - Stockton - RWCF Phase 2A/2B | 93101935.31 | 93168729
2025-06-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) | -3463215.24 | -3530000
2025-06-01 | 51.1129. | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications | 110305869.84 | 110305869.84
2025-06-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 329649.9 | 329649.9
2025-06-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements | 4770852 | 4770852
2025-06-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 | 1133265.44 | 1133265.44
2025-06-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 | 1119831.42 | 1119831.42
2025-06-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 62359.17 | 62359.17
2025-06-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project | 3849878.31 | 3849878.31
2025-06-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project | 14412567 | 14412567
2025-06-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility | 53275337 | 53275337
2025-06-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2453267 | 2453267
2025-06-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2251231.58 | 2251231.58
2025-06-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 10061352 | 10061352
2025-06-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project | 18328291 | 18328291
2025-06-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement | 442548.83 | 442548.83
2025-06-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 12809391 | 12809391
2025-06-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out | -1800000 | -1800000
2025-06-01 | 51.1156. | Rocklin Overhead 2025 | 575452.68 | 575452.68
2025-06-01 | 51.1157. | Rocklin Estimating 2025 | 316562.26 | 316562.26
2025-06-01 | 51.1158. | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 32282 | 32282
2025-06-01 | 51.1159. | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 1079240 | 1079240
2025-06-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion | 1758132.57 | 1758132.57
2025-06-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 1152035.99 | 1174183
2025-06-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out | -293290.03 | -293392.63
2025-06-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System | 1029398 | 1029398
2025-06-01 | 52.8567. | City of Modesto - Grayson Well 69 | 3129944.99 | 3129944.99
2025-06-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 10691954 | 10691954
2025-06-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 4645690.97 | 4645690.97
2025-06-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 5534872 | 5534872
2025-06-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 2410889 | 2410889
2025-06-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 | 13025995 | 13025995
2025-06-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 2230000 | 2230000
2025-06-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic | 24149094 | 24149094
2025-06-01 | 52.8640. | City of Dos Palos - WTP Replacement Project | 35178188.29 | 35178188.29
2025-06-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station | 1045184 | 1045184
2025-06-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1703066 | 1703066
2025-06-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1416800 | 1416800
2025-06-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 | 305140.23 | 305140.23
2025-06-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 | 295722 | 295722
2025-06-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 516850 | 516850
2025-06-01 | 52.8678. | City of Chowchilla - Well 15 & Generator Improvement Projects | 1180128 | 1180128
2025-06-01 | 52.8682. | Fresno Overhead 2025 | 498447.1 | 498447.1
2025-06-01 | 52.8683. | Fresno Estimating 2025 | 180482.49 | 180482.49
2025-06-01 | 52.8684. | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 25272.25 | 25272.25
2025-06-01 | 52.8685. | Malaga County Water Dist. - Malaga County Water District | 402983 | 402983
2025-06-01 | 52.8687. | California Water Service Co. - Salinas Station 205 | 750089 | 750089
2025-06-01 | 52.8688. | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 116200 | 116200
2025-06-01 | 52.8692. | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 40855.67 | 40855.67
2025-06-01 | 52.8693. | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 1036503 | 1036503
2025-06-01 | 52.8697. | City of Tulare - Industrial WWTP Dewatering Improvements | 1325482 | 1325482
2025-06-01 | 52.8699. | City of Hanford - WWTP Repair T&M | 2851 | 2851
2025-06-01 | 52.8700. | Lyles Services Co. - LSC GO Misc. Work | 4650 | 4650
2025-06-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 | 267282.05 | 267282.05
2025-06-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install | 251088.2 | 251088.2
2025-06-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M | 26088.33 | 26088.33
2025-06-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 7389.72 | 7389.72
2025-06-01 | 52.8689. | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 16095.58 | 16095.58
2025-06-01 | 52.8690. | City of Dinuba - WWTP Rake Replacement | 13155.83 | 13155.83
2025-06-01 | 52.8691. | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 8287.82 | 8287.82
2025-06-01 | 52.8694. | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 38541.99 | 38541.99
2025-06-01 | 52.8695. | Lyles Services Co. - LSC GO Trash Enclosure | 13024.37 | 13024.37
2025-06-01 | 52.8696. | American Paving Co. - Hot Tap for APC- Tule River Parkway | 887.65 | 887.65
2025-06-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 938540 | 938540
2025-06-01 | 53.2005. | East Bay Overhead 2025 | 164346.29 | 164346.29
2025-06-01 | 53.2006. | East Bay Estimating 2026 | 282142.77 | 282142.77
2025-06-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 94118.58 | 94118.58
2025-06-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 45344995 | 45344995
2025-06-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 8753752.09 | 8753752.09
2025-06-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements | 2310164 | 2310164
2025-06-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equipping Project | 1697852 | 1697852
2025-06-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station | 1398716 | 1398716
2025-06-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 222896.47 | 222896.47
2025-06-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 839297.99 | 839297.99
2025-06-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3188768.8 | 3188768.8
2025-06-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 387022 | 387022
2025-06-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 19300 | 19300
2025-06-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3810346 | 3810346
2025-06-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 7967721.04 | 7967721.04
2025-06-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 306900 | 306900
2025-06-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 23463572.79 | 23463572.79
2025-06-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 3922300 | 3922300
2025-06-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1078797 | 1078797
2025-06-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 6181300 | 6181300
2025-06-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 944830 | 944830
2025-06-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1122640 | 1122640
2025-06-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1162246 | 1162246
2025-06-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project | 28042727 | 28042727
2025-06-01 | 54.9371. | Bakersfield Overhead 2025 | 622467.54 | 622467.54
2025-06-01 | 54.9372. | Bakersfield Estimating 2025 | 328988.36 | 328988.36
2025-06-01 | 54.9373. | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 1393326 | 1393326
2025-06-01 | 54.9382. | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 101157 | 101157
2025-06-01 | 54.9384. | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 71500 | 71500
2025-06-01 | 54.9385. | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 101263 | 101263
2025-06-01 | 54.9386. | Kern Valley State Prison - Arsenic Pipe Leak Repair | 75377.7 | 75377.7
2025-06-01 | 54.9387. | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 22500 | 22500
2025-06-01 | 54.9389. | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 329780 | 329780
2025-06-01 | 54.9390. | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 78000 | 78000
2025-06-01 | 54.9391. | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 392000 | 392000
2025-06-01 | 54.9392. | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 217000 | 217000
2025-06-01 | 54.9394. | City of Arvin - Haven Drive Lateral Repair | 15000 | 15000
2025-06-01 | 54.9395. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 1388900 | 1388900
2025-06-01 | 54.9397. | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 3390645 | 3390645
2025-06-01 | 54.9398. | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 12598 | 12598
2025-06-01 | 54.9399. | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 21939 | 21939
2025-06-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 21054172.85 | 21054172.85
2025-06-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 306021.41 | 306021.41
2025-06-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 1313.45 | 1313.45
2025-06-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 86308.26 | 86308.26
2025-06-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 368815.29 | 368815.29
2025-06-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 119186.11 | 119186.11
2025-06-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 124146.3 | 124146.3
2025-06-01 | 54.9347. | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 3227.7 | 3227.7
2025-06-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 197889.31 | 197889.31
2025-06-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 | 104443.06 | 104443.06
2025-06-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 136808.3 | 136808.3
2025-06-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 1117.5 | 1117.5
2025-06-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 8230.83 | 8230.83
2025-06-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 1815.23 | 1815.23
2025-06-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 889.66 | 889.66
2025-06-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1144.88 | 1144.88
2025-06-01 | 54.9361. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 100591.91 | 100591.91
2025-06-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 375601.24 | 375601.24
2025-06-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 777.55 | 777.55
2025-06-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 1263.33 | 1263.33
2025-06-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 1602.33 | 1602.33
2025-06-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 13653.62 | 13653.62
2025-06-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 889.64 | 889.64
2025-06-01 | 54.9374. | City of Santa Maria - WWTP Trickling Filter Repairs | 19986.45 | 19986.45
2025-06-01 | 54.9375. | City of Santa Maria - WWTP Clarifier Repairs | 4545.48 | 4545.48
2025-06-01 | 54.9379. | Semitropic Water Storage Dist. - Delta System Pipe Repair | 36111.95 | 36111.95
2025-06-01 | 54.9380. | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 18064.72 | 18064.72
2025-06-01 | 54.9381. | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 28875.38 | 28875.38
2025-06-01 | 54.9383. | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 15759.76 | 15759.76
2025-06-01 | 54.9388. | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 6535.41 | 6535.41
2025-06-01 | 54.9393. | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 25417.72 | 25417.72
2025-06-01 | 55.1090. | JV w/Webcor & Obayashi - Silverlake - LADWP | 3719985.62 | 3803207.8
2025-06-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility | 335498046 | 335498046
2025-06-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6351803.53 | 6351803.53
2025-06-01 | 55.1200. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 | 172121844.83 | 195685221
2025-06-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out | -6961158.46 | -8100000
2025-06-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project | 14940308.28 | 14940308.28
2025-06-01 | 55.1204. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 | 46652703.95 | 47052523
2025-06-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out | -2133979.08 | -2500000
2025-06-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 36543874.76 | 36543874.76
2025-06-01 | 55.1233. | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 95614 | 95614
2025-06-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 | 215218 | 215218
2025-06-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 5120482 | 5120482
2025-06-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 139897192 | 139897192
2025-06-01 | 55.1252. | Murrieta Overhead 2025 | 975097.07 | 975097.07
2025-06-01 | 55.1253. | Murrieta Estimating 2025 | 282141.3 | 282141.3
2025-06-01 | 55.1254. | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 441896 | 441896
2025-06-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement | 1665145.3 | 1665145.3
2025-06-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements | 3320836.69 | 3320836.69
2025-06-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 48293.94 | 48293.94
2025-06-01 | 55.1251. | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 283682.85 | 283682.85
2025-06-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 3293781 | 3293781
2025-06-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 37896367.63 | 37896367.63
2025-06-01 | 57.0005. | San Diego Overhead 2025 | 17058.05 | 17058.05
2025-06-01 | 57.0006. | San Diego Estimating 2025 | 4432.92 | 4432.92
2025-06-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 20761280 | 20761280
2025-06-01 | 58.0004. | Los Angeles Overhead 2025 | 53275.6 | 53275.6
2025-06-01 | 58.0005. | Los Angeles Estimating 2025 | 12730.8 | 12730.8
2025-06-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 224344 | 224344
2025-06-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 282723 | 282723
2025-06-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 70781 | 70781
2025-06-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 17360 | 17360
2025-06-01 | 56.1010. | Placer County Water Agency -PCWA Time & Material Contract | 32860 | 32860
2025-06-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 130544 | 130544
2025-06-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 95610.73 | 95610.73
2025-06-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 54275 | 54275
2025-06-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 52159 | 52159
2025-06-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 144452 | 144452
2025-06-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 156228 | 156228
2025-06-01 | 56.1030. | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 611831.14 | 611831.14
2025-06-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 76078 | 76078
2025-06-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 208781 | 208781
2025-06-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 5541.88 | 5541.88
2025-06-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 88907 | 88907
2025-06-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 324159 | 324159
2025-06-01 | 56.1041. | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 20016.78 | 20016.78
2025-06-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services | 197695 | 197695
2025-06-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 285000 | 285000
2025-06-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 54674 | 54674
2025-06-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 2144469 | 2144469
2025-06-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 86075 | 86075
2025-06-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 249407 | 249407
2025-06-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 3341376 | 3341376
2025-06-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 94942.19 | 94942.19
2025-06-01 | 56.1054. | W.M. Lyles - Riverside Public Works - Digester 5 Rehab | 156482 | 156482
2025-06-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 98200 | 98200
2025-06-01 | 56.1056. | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan | 98280.63 | 98280.63
2025-06-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 308910 | 308910
2025-06-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 310028 | 310028
2025-06-01 | 56.1062. | AIC - SCADA System Upgrade - City of Brentwood | 406588.07 | 406588.07
2025-06-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 93240 | 93240
2025-06-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 212228 | 212228
2025-06-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 456653 | 456653
2025-06-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 408349 | 408349
2025-06-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 37411 | 37411
2025-06-01 | 56.1073. | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 99706 | 99706
2025-06-01 | 56.1075. | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 773000 | 773000
2025-06-01 | 56.1077. | System Integration Overhead 2025 | 4370293.76 | 4370293.76
2025-06-01 | 56.1078. | City of Napa - On-Call Control Systems Integrator Services | 7117.19 | 7117.19
2025-06-01 | 56.1079. | San Jose Water Co - Montevina PLC Upgrade | 287944 | 287944
2025-06-01 | 56.1080. | San Jose Water Co - PLC System Assessment | 219022 | 219022
2025-06-01 | 56.1081. | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 166944 | 166944
2025-06-01 | 56.1082. | City of Clovis - Pump Station E New Pump 5 VFD Startup | 11476 | 11476
2025-06-01 | 56.1083. | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 652967 | 652967
2025-06-01 | 56.1084. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 4485 | 4485
2025-06-01 | 56.1085. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 66334 | 66334
2025-06-01 | 56.1086. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 295345 | 295345
2025-06-01 | 56.1087. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 42956 | 42956
2025-06-01 | 56.1088. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 95411 | 95411
2025-06-01 | 56.1102. | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 19815.94 | 19815.94
2025-06-01 | 56.1103. | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 55592.31 | 55592.31
2025-06-01 | 56.1104. | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 9500.31 | 9500.31
2025-06-01 | 56.1105. | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 23646.28 | 23646.28
2025-06-01 | 56.1106. | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 54250.3 | 54250.3
2025-06-01 | 56.1107. | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 3429.06 | 3429.06
2025-06-01 | 56.1108. | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 20729.84 | 20729.84
2025-06-01 | 56.1109. | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 13870.31 | 13870.31
2025-06-01 | 56.1110. | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 4596.42 | 4596.42
2025-06-01 | 56.1111. | AIC - California American Water - Luzern Well Treatment Design | 17135.01 | 17135.01
2025-06-01 | 56.1112. | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 27241.58 | 27241.58
2025-06-01 | 56.1113. | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 49158.44 | 49158.44
2025-06-01 | 56.1115. | AIC - UC Davis - WWTP Annual Instrument Calibrations | 5895.77 | 5895.77
2025-06-01 | 56.1119. | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 22184.06 | 22184.06
2025-06-01 | 56.1120. | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 1045.63 | 1045.63
2025-06-01 | 56.1121. | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 21399.38 | 21399.38
2025-06-01 | 56.1122. | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 5864.38 | 5864.38
2025-06-01 | 56.1123. | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 3772.82 | 3772.82
2025-06-01 | 56.1124. | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 28100 | 28100
2025-06-01 | 56.1125. | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 14229.38 | 14229.38
2025-06-01 | 56.1126. | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 9526.88 | 9526.88
2025-06-01 | 56.1127. | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 6519.07 | 6519.07
2025-06-01 | 56.1128. | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 4793.13 | 4793.13
2025-06-01 | 56.1129. | AIC - RMCSD - VEEAM SFTWR | 133.75 | 133.75
2025-06-01 | 56.1130. | System Integration Division Estimating 2025 | 267.5 | 267.5
2025-06-01 | 56.1131. | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 2388.75 | 2388.75
2025-06-01 | 56.1132. | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 585 | 585
2025-06-01 | 56.1133. | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 2827.5 | 2827.5
2025-06-01 | 56.1134. | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 965.51 | 965.51
2025-06-01 | 56.1135. | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 112.5 | 112.5
2025-06-01 | 56.1141. | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 2827.5 | 2827.5
2025-06-01 | 56.1002. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 114485.82 | 114485.82
2025-06-01 | 56.1008. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 30551.92 | 30551.92
2025-06-01 | 56.1010.01. | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 7097.1 | 7097.1
2025-06-01 | 56.1021. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 116752.52 | 116752.52
2025-06-01 | 56.1022. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 0 | 0
2025-06-01 | 56.1052. | San Jose Water - Williams Back ATS Replacement | 6400.94 | 6400.94
2025-06-01 | 56.1053. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 19964.78 | 19964.78
2025-06-01 | 56.1057. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 0 | 0
2025-06-01 | 56.1061. | San Jose Water - PLC System Assessment | 5582.66 | 5582.66
2025-06-01 | 56.1064. | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 201291.4 | 201291.4
2025-06-01 | 56.1069. | City of Brentwood - Brentwood, City of - On-Call Agreement | 3821.46 | 3821.46
2025-06-01 | 56.1071. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 3596.56 | 3596.56
2025-06-01 | 56.1074. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 10641.86 | 10641.86
2025-06-01 | 56.1076. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 11577.77 | 11577.77
2025-06-01 | 50.0541. | W.M. Lyles Co. - General Overhead | 1633185.01 | 1633185.01
2025-06-01 | 50.0542. | W.M. Lyles Co. - General Estimating | 30707.93 | 30707.93
2025-06-01 | 50.0543. | American Paving | 7051.01 | 7051.01
2025-06-01 | 50.0544. | Lyles Services Co. | 3880.42 | 3880.42
2025-06-01 | 50.0545. | New England Sheet Metal and Mechanical Co. | 1037.94 | 1037.94
2025-06-01 | 50.0546. | Lyles Utility Construction, LLC | 10465.62 | 10465.62
2025-06-01 | 50.0551. | Advanced Integration & Controls | 274.42 | 274.42