## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-05-01 | 51.1108. | JV w/AECOM - Stockton - RWCF Phase 2A/2B |  | 93946637 | 858269 | 2025-06-30
2025-05-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) |  | 0 | 3463225.29 | 2025-06-30
2025-05-01 | 51.1129. | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications |  | 122305869.84 | 8633263.4211 | 2027-06-25
2025-05-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement |  | 369231.26 | 18176.8745 | 2025-06-01
2025-05-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements |  | 5620852 | 774587.2088 | 2025-06-30
2025-05-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 |  | 1246905.44 | 66308.019 | 2025-06-30
2025-05-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 |  | 1091453 | -2500 | 2025-06-01
2025-05-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 |  | 67202.17 | 4426.359 | 2025-06-01
2025-05-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project |  | 3979878.31 | 127979.7284 | 2025-06-01
2025-05-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project |  | 14969567 | 115757.2927 | 2026-12-20
2025-05-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility |  | 60275337 | 2154418.0224 | 2025-10-01
2025-05-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project |  | 2623267 | 149443.8381 | 2026-01-31
2025-05-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 |  | 2486231.58 | 231255.5877 | 2025-06-01
2025-05-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade |  | 10658200 | 0 | 2026-11-25
2025-05-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project |  | 19450000 | 0 | 2026-06-30
2025-05-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement |  | 549548.83 | 80123.2238 | 2025-06-01
2025-05-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 |  | 13079230 | 235396.3359 | 2025-12-15
2025-05-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out |  | 0 | 1159300.31 | 2025-10-01
2025-05-01 | 51.1156. | Rocklin Overhead 2025 |  | 0 | -500674.73 | 2025-12-31
2025-05-01 | 51.1157. | Rocklin Estimating 2025 |  | 0 | -254383.65 | 2025-12-31
2025-05-01 | 51.1158. | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric |  | 32282 | 0 | 2025-12-31
2025-05-01 | 51.1159. | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement |  | 1199000 | 564.1295 | 2026-03-15
2025-05-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion |  | 1991231.37 | 233098.8 | 2025-05-01
2025-05-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 |  | 1174183 | 0 | 2025-06-01
2025-05-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out |  | 0 | 293392.63 | 2025-06-01
2025-05-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System |  | 1259398 | 226413.7648 | 2025-07-31
2025-05-01 | 52.8567. | City of Modesto - Grayson Well 69 |  | 3059858.99 | -76000 | 2025-06-01
2025-05-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 |  | 12551954 | 1793597.2968 | 2025-08-31
2025-05-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation |  | 5084967 | 376976.4505 | 2025-06-30
2025-05-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. |  | 5899872 | 254397.9381 | 2025-06-30
2025-05-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements |  | 2515889 | 100697.2886 | 2025-06-30
2025-05-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 |  | 13727995 | 451996.9744 | 2026-03-11
2025-05-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project |  | 2276400 | 268089.7349 | 2025-07-31
2025-05-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic |  | 25799094 | 1494492.4224 | 2025-08-31
2025-05-01 | 52.8640. | City of Dos Palos - WTP Replacement Project |  | 37051511.29 | 1037954.4014 | 2026-04-17
2025-05-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station |  | 1288134 | 243307.8617 | 2025-06-30
2025-05-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site |  | 1863066 | 152000 | 2025-06-30
2025-05-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project |  | 1641800 | 71869.3392 | 2025-08-31
2025-05-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 |  | 328500 | 23359.66 | 2025-06-01
2025-05-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 |  | 328552 | 23107.1833 | 2025-08-31
2025-05-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 |  | 296477.1 | 6500 | 2025-06-01
2025-05-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements |  | 556882 | 22460.2714 | 2025-08-31
2025-05-01 | 52.8678. | City of Chowchilla - Well 15 & Generator Improvement Projects |  | 1190560 | 12402.4566 | 2025-12-31
2025-05-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M |  | 28500 | 2883.5459 | 2025-06-30
2025-05-01 | 52.8682. | Fresno Overhead 2025 |  | 0 | -435377.71 | 2025-12-31
2025-05-01 | 52.8683. | Fresno Estimating 2025 |  | 0 | -144093.42 | 2025-12-31
2025-05-01 | 52.8685. | Malaga County Water Dist. - Malaga County Water District |  | 426800 | 0 | 2025-09-30
2025-05-01 | 52.8687. | California Water Service Co. - Salinas Station 205 |  | 831511 | 30531.6831 | 2025-07-25
2025-05-01 | 52.8688. | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits |  | 132992.2 | 16580.7169 | 2025-06-30
2025-05-01 | 52.8691. | County of Fresno - Quail Lakes Repair at Bodega Bay Rd |  | 9127 | 999.93 | 2025-06-01
2025-05-01 | 52.8692. | New England Sheet Metal and Mechanical Co. - Clovis South T&M |  | 44658.46 | 3802.79 | 2025-06-30
2025-05-01 | 52.8693. | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections |  | 1136503 | 0 | 2025-09-30
2025-05-01 | 52.8694. | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair |  | 25500 | 1985.3864 | 2025-06-01
2025-05-01 | 52.8695. | Lyles Services Co. - LSC GO Trash Enclosure |  | 13500 | 397.6907 | 2025-06-01
2025-05-01 | 52.8697. | City of Tulare - Industrial WWTP Dewatering Improvements |  | 1388000 | 0 | 2026-07-22
2025-05-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install |  | 279244 | 28155.8 | 2025-01-31
2025-05-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair |  | 23957 | 16567.28 | 2025-01-31
2025-05-01 | 52.8689. | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M |  | 16665.83 | 570.25 | 2025-04-01
2025-05-01 | 52.8690. | City of Dinuba - WWTP Rake Replacement |  | 14151.97 | 996.14 | 2025-05-02
2025-05-01 | 52.8696. | American Paving Co. - Hot Tap for APC- Tule River Parkway |  | 1059.22 | 171.57 | 2025-05-31
2025-05-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project |  | 1038540 | 21459.9165 | 2025-11-30
2025-05-01 | 53.2005. | East Bay Overhead 2025 |  | 0 | -142458.6 | 2025-12-31
2025-05-01 | 53.2006. | East Bay Estimating 2026 |  | 0 | -205447.08 | 2025-12-31
2025-05-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 |  | 104529.95 | 10966.87 | 2025-12-31
2025-05-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade |  | 55581160 | 10372751.5815 | 2025-06-30
2025-05-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project |  | 9239736 | 551994.3651 | 2025-06-01
2025-05-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements |  | 2472164 | 151678.8734 | 2025-09-15
2025-05-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equiping Project |  | 1743970 | 84053.936 | 2025-09-30
2025-05-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station |  | 1471328 | 0 | 2025-09-30
2025-05-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification |  | 223896.47 | 951.112 | 2025-06-01
2025-05-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement |  | 907297.99 | 74120.7561 | 2025-06-30
2025-05-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation |  | 3203768.8 | -15000 | 2025-06-01
2025-05-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement |  | 462022 | 44250.6165 | 2025-07-28
2025-05-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting |  | 14176 | 669.81 | 2025-12-31
2025-05-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr |  | 3930346 | 77994.7107 | 2025-07-16
2025-05-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project |  | 8787721.04 | 328048.2461 | 2025-12-31
2025-05-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair |  | 110661.47 | 6759.8229 | 2025-06-01
2025-05-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep |  | 324900 | 13053.4891 | 2025-06-01
2025-05-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project |  | 390000 | 19935.9616 | 2025-06-01
2025-05-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility |  | 25048834 | 314917.125 | 2026-08-17
2025-05-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project |  | 4082300 | 0 | 2026-10-30
2025-05-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements |  | 1195200 | 118094.8141 | 2025-06-30
2025-05-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 |  | 6881300 | 267337.27 | 2026-05-31
2025-05-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 |  | 110000 | 9836.962 | 2025-06-01
2025-05-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond |  | 1294830 | 140596.8037 | 2025-08-31
2025-05-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout |  | 1147640 | 24175.0648 | 2025-09-01
2025-05-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement |  | 1225220 | 0 | 2026-05-31
2025-05-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project |  | 30413570 | 0 | 2027-01-05
2025-05-01 | 54.9371. | Bakersfield Overhead 2025 |  | 0 | -539602.18 | 2025-12-31
2025-05-01 | 54.9372. | Bakersfield Estimating 2025 |  | 0 | -275567.82 | 2025-12-31
2025-05-01 | 54.9373. | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement |  | 1524766 | 0 | 2026-03-01
2025-05-01 | 54.9374. | City of Santa Maria - WWTP Trickling Filter Repairs |  | 46890 | 7753.6448 | 2025-06-01
2025-05-01 | 54.9382. | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement |  | 110700 | 0 | 2025-12-31
2025-05-01 | 54.9384. | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair |  | 75000 | 3443.2447 | 2025-06-01
2025-05-01 | 54.9385. | Westside Water Authority - Pump Station A - Electrical Controls and Civil |  | 111263 | 2924.5875 | 2025-06-01
2025-05-01 | 54.9386. | Kern Valley State Prison - Arsenic Pipe Leak Repair |  | 96086 | 2783.0611 | 2025-06-30
2025-05-01 | 54.9387. | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications |  | 25000 | 2089.2211 | 2025-06-30
2025-05-01 | 54.9388. | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation |  | 7454.07 | 226.8376 | 2025-07-01
2025-05-01 | 54.9389. | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project |  | 299780 | 0 | 2025-09-30
2025-05-01 | 54.9390. | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads |  | 44568.57 | 986.2382 | 2025-06-01
2025-05-01 | 54.9391. | Arvin Edison Water Storage Dist. - HQ Concrete R&R |  | 266000 | 0 | 2025-07-31
2025-05-01 | 54.9392. | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs |  | 223000 | 1706.7472 | 2025-07-31
2025-05-01 | 54.9393. | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs |  | 15000 | 941.5429 | 2025-06-30
2025-05-01 | 54.9394. | City of Arvin - Haven Drive Lateral Repair |  | 16000 | 935.97 | 2025-06-30
2025-05-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict |  | 24160002.44 | 3105829.59 | 2025-03-01
2025-05-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 |  | 340270.46 | 34249.05 | 2025-03-01
2025-05-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting |  | 4300 | 2986.55 | 2025-03-01
2025-05-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement |  | 175884.64 | 56698.53 | 2025-01-31
2025-05-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace |  | 199161.5 | 75015.2 | 2025-01-31
2025-05-01 | 54.9347. | City of Guadalupe - Effluent Pump Station Flow Meter Installation |  | 7100 | 3872.3 | 2025-04-01
2025-05-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A |  | 290129 | 92239.69 | 2025-04-01
2025-05-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement |  | 153298.79 | 16490.49 | 2025-01-31
2025-05-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 |  | 2008.42 | 890.92 | 2025-03-31
2025-05-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair |  | 9571.2 | 1340.37 | 2025-01-31
2025-05-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 |  | 2806.42 | 991.19 | 2025-03-31
2025-05-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 |  | 1760.42 | 870.76 | 2025-03-31
2025-05-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 |  | 1855.92 | 711.04 | 2025-03-31
2025-05-01 | 54.9361. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair |  | 108668.35 | 8076.44 | 2025-05-01
2025-05-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line |  | 425035.04 | 49433.8 | 2025-01-25
2025-05-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 |  | 1855.92 | 1078.37 | 2025-03-31
2025-05-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 |  | 2216.42 | 953.09 | 2025-03-31
2025-05-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 |  | 2540.42 | 938.09 | 2025-03-31
2025-05-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair |  | 15697.91 | 2044.29 | 2025-01-31
2025-05-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 |  | 1760.42 | 870.78 | 2025-03-31
2025-05-01 | 54.9375. | City of Santa Maria - WWTP Clarifier Repairs |  | 8232.73 | 3687.25 | 2025-03-13
2025-05-01 | 54.9379. | Semitropic Water Storage Dist. - Delta System Pipe Repair |  | 41679.77 | 5567.82 | 2025-02-28
2025-05-01 | 54.9380. | Cawelo Water Dist. - CWD Pump Station Pipe Repair |  | 22446.19 | 4381.47 | 2025-03-25
2025-05-01 | 54.9381. | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement |  | 58900 | 30024.62 | 2025-03-30
2025-05-01 | 54.9383. | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 |  | 17542.44 | 1782.68 | 2025-05-01
2025-05-01 | 55.1090. | JV w/Webcor & Obayashi - Silverlake - LADWP |  | 5300000 | 1463888.1686 | 2025-07-25
2025-05-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility |  | 341250325.7 | 5984167 | 2027-06-01
2025-05-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements |  | 6651803.53 | 300000 | 2025-07-01
2025-05-01 | 55.1200. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 |  | 195236114 | 0 | 2027-04-02
2025-05-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out |  | 0 | 6802289.77 | 2027-04-02
2025-05-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project |  | 16115717.28 | 668919.6861 | 2026-08-01
2025-05-01 | 55.1204. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 |  | 45839550 | 0 | 2026-11-26
2025-05-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out |  | 0 | 2098084.43 | 2026-11-26
2025-05-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project |  | 41043874.76 | 4191477.2039 | 2025-07-21
2025-05-01 | 55.1233. | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) |  | 104043 | 8428.84 | 2025-06-01
2025-05-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 |  | 223325 | 8107 | 2026-12-31
2025-05-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation |  | 5600482 | 0 | 2026-02-01
2025-05-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 |  | 147718400 | 0 | 2029-02-01
2025-05-01 | 55.1252. | Murrieta Overhead 2025 |  | 0 | -825211.2 | 2025-12-31
2025-05-01 | 55.1253. | Murrieta Estimating 2025 |  | 0 | -236986.46 | 2025-12-31
2025-05-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement |  | 2273682.69 | 608537.39 | 2025-03-31
2025-05-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements |  | 4046200 | 725363.31 | 2025-03-31
2025-05-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair |  | 184557.17 | 136263.23 | 2025-03-31
2025-05-01 | 55.1251. | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade |  | 322982.96 | 39300.11 | 2025-04-25
2025-05-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 |  | 3583401 | 140634.6013 | 2025-06-01
2025-05-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project |  | 40106224.63 | 0 | 2026-03-25
2025-05-01 | 57.0005. | San Diego Overhead 2025 |  | 0 | -15091.75 | 2025-12-31
2025-05-01 | 57.0006. | San Diego Estimating 2025 |  | 0 | -4432.92 | 2025-12-31
2025-05-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement |  | 22085905 | 0 | 2026-06-01
2025-05-01 | 58.0004. | Los Angeles Overhead 2025 |  | 0 | -39196.15 | 2025-12-31
2025-05-01 | 58.0005. | Los Angeles Estimating 2025 |  | 0 | -10080 | 2025-12-31
2025-05-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment |  | 311191 | 74976.7551 | 2025-09-30
2025-05-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station |  | 373425 | 71165.0504 | 2025-09-30
2025-05-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold |  | 135000 | 15711.4037 | 2025-09-30
2025-05-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield |  | 19314 | 1861.3347 | 2025-09-30
2025-05-01 | 56.1010. | Placer County Water Agency -PCWA Time & Material Contract |  | 49250 | 14136.5945 | 2025-09-30
2025-05-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga |  | 160000 | 26970.641 | 2025-12-31
2025-05-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District |  | 131948 | 36469.42 | 2025-12-31
2025-05-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport |  | 73222 | 15442.2466 | 2025-12-31
2025-05-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas |  | 145000 | 56904.3117 | 2025-12-31
2025-05-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. |  | 184435 | 25788.1548 | 2025-12-31
2025-05-01 | 56.1021. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 |  | 244760 | 88537.6866 | 2025-06-30
2025-05-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade |  | 220390 | 57411.1332 | 2025-06-30
2025-05-01 | 56.1030. | Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject |  | 795000 | 95861.4877 | 2025-09-30
2025-05-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods |  | 85000 | 0 | 2025-12-31
2025-05-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 |  | 276000 | 24698.1604 | 2026-03-31
2025-05-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services |  | 12638.5 | 7096.62 | 2025-12-31
2025-05-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 |  | 95000 | 4374.0204 | 2025-12-31
2025-05-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station |  | 375000 | 40144.9278 | 2025-12-31
2025-05-01 | 56.1041. | Irvin Rranch District - MWRP Fueling Facility CP-100 Programming |  | 49013 | 13970.6945 | 2025-09-30
2025-05-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services |  | 277565 | 61126.6953 | 2025-09-30
2025-05-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh |  | 325000 | 0 | 2026-03-31
2025-05-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods |  | 66000 | 8033.526 | 2025-09-30
2025-05-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 |  | 2395000 | 0 | 2026-12-31
2025-05-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement |  | 200000 | 57793.8249 | 2025-09-30
2025-05-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 |  | 308725 | 46675.4058 | 2025-12-31
2025-05-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat |  | 3780000 | 0 | 2026-12-31
2025-05-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives |  | 126535.19 | 28244.3424 | 2025-09-30
2025-05-01 | 56.1054. | W.M. Lyles - Riverside Public Works - Digester 5 Rehab |  | 215000 | 12912.6424 | 2026-03-31
2025-05-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project |  | 120891 | 10910.5098 | 2025-09-30
2025-05-01 | 56.1056. | Irvine Ranch Water District - Michelson Water Recycling Plan |  | 326800 | 61481.5525 | 2026-09-30
2025-05-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou |  | 380000 | 24005.683 | 2026-03-31
2025-05-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar |  | 400000 | 0 | 2026-09-30
2025-05-01 | 56.1062. | SCADA System Upgrade - City of Brentwood |  | 1785125 | 229245.0387 | 2025-12-31
2025-05-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project |  | 108000 | 3893.3727 | 2026-03-31
2025-05-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact |  | 227000 | 8240.9848 | 2025-09-30
2025-05-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather |  | 595000 | 30707.485 | 2025-12-31
2025-05-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto |  | 478000 | 0 | 2026-06-30
2025-05-01 | 56.1069. | City of Brentwood - Brentwood, City of - On-Call Agreement |  | 2525 | -1296.46 | 2025-12-31
2025-05-01 | 56.1071. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard |  | 34000 | 11939.3363 | 2025-09-30
2025-05-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri |  | 48420 | 0 | 2025-12-31
2025-05-01 | 56.1073. | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W |  | 122210 | 0 | 2026-03-31
2025-05-01 | 56.1075. | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF |  | 950000 | 0 | 2025-12-31
2025-05-01 | 56.1077. | System Integration Overhead 2025 |  | 0 | -4322821.23 | 2025-12-31
2025-05-01 | 56.1078. | City of Napa - On-Call Control Systems Integrator Services |  | 13795 | 6677.81 | 2025-12-31
2025-05-01 | 56.1079. | San Jose Water Co - Montevina PLC Upgrade |  | 405000 | 0 | 2025-12-31
2025-05-01 | 56.1080. | San Jose Water Co - PLC System Assessment |  | 359469 | 67851.1909 | 2025-09-30
2025-05-01 | 56.1081. | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA |  | 179690 | 3534.1504 | 2025-09-30
2025-05-01 | 56.1082. | City of Clovis - Pump Station E New Pump 5 VFD Startup |  | 19800 | 4239.6549 | 2025-09-30
2025-05-01 | 56.1083. | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM |  | 717010 | 0 | 2026-06-30
2025-05-01 | 56.1084. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut |  | 4500 | 1435.0395 | 2025-12-31
2025-05-01 | 56.1085. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service |  | 80000 | 0 | 2026-06-30
2025-05-01 | 56.1086. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service |  | 376000 | 0 | 2026-06-30
2025-05-01 | 56.1087. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters |  | 49369 | 4000.8784 | 2025-12-31
2025-05-01 | 56.1088. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo |  | 127235 | 0 | 2026-03-31
2025-05-01 | 56.1102. | San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal |  | 181657 | 0 | 2025-12-31
2025-05-01 | 56.1103. | Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District |  | 128000 | 11485.9961 | 2025-12-31
2025-05-01 | 56.1104. | Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric |  | 48860 | 6714.0657 | 2025-09-30
2025-05-01 | 56.1105. | Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun |  | 180000 | 0 | 2026-03-31
2025-05-01 | 56.1106. | Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - |  | 464000 | 0 | 2025-12-31
2025-05-01 | 56.1107. | San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W |  | 485000 | 0 | 2025-12-31
2025-05-01 | 56.1108. | City of Davis - Programming and Panel Modifications at Turnout Sit |  | 45200 | 7336.2472 | 2025-09-30
2025-05-01 | 56.1109. | Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U |  | 123000 | 0 | 2026-03-31
2025-05-01 | 56.1110. | Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M |  | 9960 | 5363.58 | 2025-06-30
2025-05-01 | 56.1111. | California American Water - Luzern Well Treatment Design |  | 180000 | 0 | 2026-03-31
2025-05-01 | 56.1112. | Westside Water Authority - Pump Station A On-Site Support - Westside Water Au |  | 36965 | 2297.6181 | 2025-12-31
2025-05-01 | 56.1113. | Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr |  | 1800000 | 0 | 2026-12-31
2025-05-01 | 56.1115. | UC Davis - WWTP Annual Instrument Calibrations |  | 12725 | 6829.23 | 2025-06-30
2025-05-01 | 56.1119. | SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit |  | 59545 | 0 | 2026-09-30
2025-05-01 | 56.1120. | Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio |  | 50000 | 0 | 2026-03-31
2025-05-01 | 56.1121. | San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro |  | 1325000 | 0 | 2026-06-30
2025-05-01 | 56.1122. | West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit |  | 30300 | 1036.6555 | 2025-09-30
2025-05-01 | 56.1123. | UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis |  | 12450 | 2757.3634 | 2025-09-30
2025-05-01 | 56.1124. | Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of |  | 2822000 | 0 | 2026-12-31
2025-05-01 | 56.1125. | Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation |  | 198000 | 0 | 2025-12-31
2025-05-01 | 56.1126. | Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat |  | 225000 | 0 | 2026-03-31
2025-05-01 | 56.1127. | Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co |  | 734780 | 0 | 2026-12-31
2025-05-01 | 56.1128. | Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase |  | 214000 | 0 | 2025-12-31
2025-05-01 | 56.1129. | RMCSD - VEEAM SFTWR |  | 9820 | 0 | 2025-09-30
2025-05-01 | 56.113. | System Integration Division Estimating 2025 |  | 0 | -267.5 | 2025-12-31
2025-05-01 | 56.1131. | North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame |  | 105895 | 0 | 2026-03-31
2025-05-01 | 56.1132. | UC Davis - CABA Well Pump Station Rehabilitation – UC Davis |  | 49530 | 0 | 2025-09-30
2025-05-01 | 56.1133. | UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis |  | 34935 | 0 | 2025-09-30
2025-05-01 | 56.1134. | Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc |  | 4646 | 3761.01 | 2025-12-31
2025-05-01 | 56.1135. | San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa |  | 163000 | 0 | 2025-12-31
2025-05-01 | 56.1141. | Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos |  | 32150 | 0 | 2026-03-31
2025-05-01 | 56.1002. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency |  | 185000 | 70514.18 | 2025-04-01
2025-05-01 | 56.1008. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers |  | 55000 | 24448.08 | 2025-03-31
2025-05-01 | 56.1010.01. | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels |  | 9569 | 2471.9 | 2025-03-31
2025-05-01 | 56.1022. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz |  | 0 | 0 | 2025-03-31
2025-05-01 | 56.1052. | San Jose Water - Williams Back ATS Replacement |  | 8887 | 2486.06 | 2025-04-01
2025-05-01 | 56.1053. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un |  | 35000 | 15035.22 | 2025-04-01
2025-05-01 | 56.1057. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant |  | 0 | 0 | 2025-04-01
2025-05-01 | 56.1061. | San Jose Water - PLC System Assessment |  | 11269 | 5686.34 | 2025-03-31
2025-05-01 | 56.1064. | South Orange County Water Agency - CTP & JBL SCADA Upgrade |  | 435153 | 233861.6 | 2025-05-01
2025-05-01 | 56.1074. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley |  | 12650 | 2008.14 | 2025-04-01
2025-05-01 | 56.1076. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement |  | 19200 | 7622.23 | 2025-03-31
2025-05-01 | 50.0541. | W.M. Lyles Co. - General Overhead |  | 0 | -1347443.11 | 2025-12-31
2025-05-01 | 50.0542. | W.M. Lyles Co. - General Estimating |  | 0 | -24803.44 | 2025-12-31
2025-05-01 | 50.0543. | American Paving |  | 7051.01 | 0 | 2025-12-31
2025-05-01 | 50.0544. | Lyles Services Co. |  | 3464.39 | 0 | 2025-12-31
2025-05-01 | 50.0545. | New England Sheet Metal and Mechanical Co. |  | 1037.94 | 0 | 2025-12-31
2025-05-01 | 50.0546. | Lyles Utility Construction, LLC |  | 11254.28 | 788.66 | 2025-12-31

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-05-01 | 51.1108. | JV w/AECOM - Stockton - RWCF Phase 2A/2B |  | 93088368
2025-05-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) |  | -3530000
2025-05-01 | 51.1129. | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications |  | 110305869.84
2025-05-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement |  | 349231.26
2025-05-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements |  | 4770852
2025-05-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 |  | 1133265.44
2025-05-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 |  | 1093953
2025-05-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 |  | 62359.17
2025-05-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project |  | 3849878.31
2025-05-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project |  | 14412567
2025-05-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility |  | 53275337
2025-05-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project |  | 2453267
2025-05-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 |  | 2251231.58
2025-05-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade |  | 10061352
2025-05-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project |  | 18328291
2025-05-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement |  | 442548.83
2025-05-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 |  | 12603896
2025-05-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out |  | -1800000
2025-05-01 | 51.1156. | Rocklin Overhead 2025 |  | 500674.73
2025-05-01 | 51.1157. | Rocklin Estimating 2025 |  | 254383.65
2025-05-01 | 51.1158. | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric |  | 32282
2025-05-01 | 51.1159. | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement |  | 1079240
2025-05-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion |  | 1758132.57
2025-05-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 |  | 1174183
2025-05-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out |  | -293392.63
2025-05-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System |  | 1029398
2025-05-01 | 52.8567. | City of Modesto - Grayson Well 69 |  | 3135858.99
2025-05-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 |  | 10691954
2025-05-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation |  | 4664967
2025-05-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. |  | 5549872
2025-05-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements |  | 2410889
2025-05-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 |  | 13025995
2025-05-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project |  | 1996400
2025-05-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic |  | 24174094
2025-05-01 | 52.8640. | City of Dos Palos - WTP Replacement Project |  | 35178188.29
2025-05-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station |  | 1043134
2025-05-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site |  | 1703066
2025-05-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project |  | 1456800
2025-05-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 |  | 305140.34
2025-05-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 |  | 298752
2025-05-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 |  | 289977.1
2025-05-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements |  | 516882
2025-05-01 | 52.8678. | City of Chowchilla - Well 15 & Generator Improvement Projects |  | 1130367
2025-05-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M |  | 25295
2025-05-01 | 52.8682. | Fresno Overhead 2025 |  | 435377.71
2025-05-01 | 52.8683. | Fresno Estimating 2025 |  | 144093.42
2025-05-01 | 52.8685. | Malaga County Water Dist. - Malaga County Water District |  | 402983
2025-05-01 | 52.8687. | California Water Service Co. - Salinas Station 205 |  | 750089
2025-05-01 | 52.8688. | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits |  | 116362.2
2025-05-01 | 52.8691. | County of Fresno - Quail Lakes Repair at Bodega Bay Rd |  | 8127.07
2025-05-01 | 52.8692. | New England Sheet Metal and Mechanical Co. - Clovis South T&M |  | 40855.67
2025-05-01 | 52.8693. | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections |  | 1066503
2025-05-01 | 52.8694. | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair |  | 23500
2025-05-01 | 52.8695. | Lyles Services Co. - LSC GO Trash Enclosure |  | 13100
2025-05-01 | 52.8697. | City of Tulare - Industrial WWTP Dewatering Improvements |  | 1325482
2025-05-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install |  | 251088.2
2025-05-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair |  | 7389.72
2025-05-01 | 52.8689. | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M |  | 16095.58
2025-05-01 | 52.8690. | City of Dinuba - WWTP Rake Replacement |  | 13155.83
2025-05-01 | 52.8696. | American Paving Co. - Hot Tap for APC- Tule River Parkway |  | 887.65
2025-05-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project |  | 938540
2025-05-01 | 53.2005. | East Bay Overhead 2025 |  | 142458.6
2025-05-01 | 53.2006. | East Bay Estimating 2026 |  | 205447.08
2025-05-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 |  | 93563.08
2025-05-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade |  | 45206160
2025-05-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project |  | 8679736
2025-05-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements |  | 2317164
2025-05-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equiping Project |  | 1658970
2025-05-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station |  | 1398716
2025-05-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification |  | 222896.47
2025-05-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement |  | 829297.99
2025-05-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation |  | 3218768.8
2025-05-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement |  | 392022
2025-05-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting |  | 13506.19
2025-05-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr |  | 3810346
2025-05-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project |  | 7967721.04
2025-05-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair |  | 102661.47
2025-05-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep |  | 306900
2025-05-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project |  | 370000
2025-05-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility |  | 23498834
2025-05-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project |  | 3922300
2025-05-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements |  | 1060200
2025-05-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 |  | 6206300
2025-05-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 |  | 100000
2025-05-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond |  | 944830
2025-05-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout |  | 1122640
2025-05-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement |  | 1162246
2025-05-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project |  | 28042727
2025-05-01 | 54.9371. | Bakersfield Overhead 2025 |  | 539602.18
2025-05-01 | 54.9372. | Bakersfield Estimating 2025 |  | 275567.82
2025-05-01 | 54.9373. | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement |  | 1393326
2025-05-01 | 54.9374. | City of Santa Maria - WWTP Trickling Filter Repairs |  | 33665
2025-05-01 | 54.9382. | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement |  | 101157
2025-05-01 | 54.9384. | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair |  | 71500
2025-05-01 | 54.9385. | Westside Water Authority - Pump Station A - Electrical Controls and Civil |  | 101263
2025-05-01 | 54.9386. | Kern Valley State Prison - Arsenic Pipe Leak Repair |  | 91086
2025-05-01 | 54.9387. | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications |  | 22500
2025-05-01 | 54.9388. | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation |  | 7044.07
2025-05-01 | 54.9389. | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project |  | 329780
2025-05-01 | 54.9390. | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads |  | 43568.57
2025-05-01 | 54.9391. | Arvin Edison Water Storage Dist. - HQ Concrete R&R |  | 262000
2025-05-01 | 54.9392. | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs |  | 219000
2025-05-01 | 54.9393. | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs |  | 14000
2025-05-01 | 54.9394. | City of Arvin - Haven Drive Lateral Repair |  | 15000
2025-05-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict |  | 21054172.85
2025-05-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 |  | 306021.41
2025-05-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting |  | 1313.45
2025-05-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement |  | 119186.11
2025-05-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace |  | 124146.3
2025-05-01 | 54.9347. | City of Guadalupe - Effluent Pump Station Flow Meter Installation |  | 3227.7
2025-05-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A |  | 197889.31
2025-05-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement |  | 136808.3
2025-05-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 |  | 1117.5
2025-05-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair |  | 8230.83
2025-05-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 |  | 1815.23
2025-05-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 |  | 889.66
2025-05-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 |  | 1144.88
2025-05-01 | 54.9361. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair |  | 100591.91
2025-05-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line |  | 375601.24
2025-05-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 |  | 777.55
2025-05-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 |  | 1263.33
2025-05-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 |  | 1602.33
2025-05-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair |  | 13653.62
2025-05-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 |  | 889.64
2025-05-01 | 54.9375. | City of Santa Maria - WWTP Clarifier Repairs |  | 4545.48
2025-05-01 | 54.9379. | Semitropic Water Storage Dist. - Delta System Pipe Repair |  | 36111.95
2025-05-01 | 54.9380. | Cawelo Water Dist. - CWD Pump Station Pipe Repair |  | 18064.72
2025-05-01 | 54.9381. | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement |  | 28875.38
2025-05-01 | 54.9383. | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 |  | 15759.76
2025-05-01 | 55.1090. | JV w/Webcor & Obayashi - Silverlake - LADWP |  | 3803207.8
2025-05-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility |  | 335266158.7
2025-05-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements |  | 6351803.53
2025-05-01 | 55.1200. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 |  | 195236114
2025-05-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out |  | -8100000
2025-05-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project |  | 14940308.28
2025-05-01 | 55.1204. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 |  | 45839550
2025-05-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out |  | -2500000
2025-05-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project |  | 36543874.76
2025-05-01 | 55.1233. | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) |  | 95614
2025-05-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 |  | 215218
2025-05-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation |  | 5120482
2025-05-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 |  | 139897192
2025-05-01 | 55.1252. | Murrieta Overhead 2025 |  | 825211.2
2025-05-01 | 55.1253. | Murrieta Estimating 2025 |  | 236986.46
2025-05-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement |  | 1665145.3
2025-05-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements |  | 3320836.69
2025-05-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair |  | 48293.94
2025-05-01 | 55.1251. | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade |  | 283682.85
2025-05-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 |  | 3293781
2025-05-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project |  | 37896367.63
2025-05-01 | 57.0005. | San Diego Overhead 2025 |  | 15091.75
2025-05-01 | 57.0006. | San Diego Estimating 2025 |  | 4432.92
2025-05-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement |  | 20761280
2025-05-01 | 58.0004. | Los Angeles Overhead 2025 |  | 39196.15
2025-05-01 | 58.0005. | Los Angeles Estimating 2025 |  | 10080
2025-05-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment |  | 224344
2025-05-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station |  | 282723
2025-05-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold |  | 70781
2025-05-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield |  | 17360
2025-05-01 | 56.1010. | Placer County Water Agency -PCWA Time & Material Contract |  | 32860
2025-05-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga |  | 130544
2025-05-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District |  | 95478.58
2025-05-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport |  | 54275
2025-05-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas |  | 52159
2025-05-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. |  | 144452
2025-05-01 | 56.1021. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 |  | 139186
2025-05-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade |  | 156228
2025-05-01 | 56.1030. | Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject |  | 686904
2025-05-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods |  | 76078
2025-05-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 |  | 208781
2025-05-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services |  | 5541.88
2025-05-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 |  | 88907
2025-05-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station |  | 324159
2025-05-01 | 56.1041. | Irvin Rranch District - MWRP Fueling Facility CP-100 Programming |  | 28866
2025-05-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services |  | 197695
2025-05-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh |  | 285000
2025-05-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods |  | 54674
2025-05-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 |  | 2144469
2025-05-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement |  | 86075
2025-05-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 |  | 249407
2025-05-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat |  | 3341376
2025-05-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives |  | 94942.19
2025-05-01 | 56.1054. | W.M. Lyles - Riverside Public Works - Digester 5 Rehab |  | 156482
2025-05-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project |  | 98200
2025-05-01 | 56.1056. | Irvine Ranch Water District - Michelson Water Recycling Plan |  | 201037
2025-05-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou |  | 308910
2025-05-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar |  | 310028
2025-05-01 | 56.1062. | SCADA System Upgrade - City of Brentwood |  | 1139524
2025-05-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project |  | 93240
2025-05-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact |  | 212228
2025-05-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather |  | 456653
2025-05-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto |  | 408349
2025-05-01 | 56.1069. | City of Brentwood - Brentwood, City of - On-Call Agreement |  | 3821.46
2025-05-01 | 56.1071. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard |  | 7871
2025-05-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri |  | 37411
2025-05-01 | 56.1073. | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W |  | 99706
2025-05-01 | 56.1075. | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF |  | 773000
2025-05-01 | 56.1077. | System Integration Overhead 2025 |  | 4322821.23
2025-05-01 | 56.1078. | City of Napa - On-Call Control Systems Integrator Services |  | 7117.19
2025-05-01 | 56.1079. | San Jose Water Co - Montevina PLC Upgrade |  | 287944
2025-05-01 | 56.1080. | San Jose Water Co - PLC System Assessment |  | 219022
2025-05-01 | 56.1081. | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA |  | 166944
2025-05-01 | 56.1082. | City of Clovis - Pump Station E New Pump 5 VFD Startup |  | 11476
2025-05-01 | 56.1083. | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM |  | 652967
2025-05-01 | 56.1084. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut |  | 3039
2025-05-01 | 56.1085. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service |  | 66334
2025-05-01 | 56.1086. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service |  | 295345
2025-05-01 | 56.1087. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters |  | 42956
2025-05-01 | 56.1088. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo |  | 95411
2025-05-01 | 56.1102. | San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal |  | 138625
2025-05-01 | 56.1103. | Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District |  | 103701
2025-05-01 | 56.1104. | Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric |  | 28628
2025-05-01 | 56.1105. | Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun |  | 130981
2025-05-01 | 56.1106. | Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - |  | 312631
2025-05-01 | 56.1107. | San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W |  | 418395
2025-05-01 | 56.1108. | City of Davis - Programming and Panel Modifications at Turnout Sit |  | 32861
2025-05-01 | 56.1109. | Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U |  | 112265
2025-05-01 | 56.1110. | Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M |  | 4596.42
2025-05-01 | 56.1111. | California American Water - Luzern Well Treatment Design |  | 144956
2025-05-01 | 56.1112. | Westside Water Authority - Pump Station A On-Site Support - Westside Water Au |  | 34076
2025-05-01 | 56.1113. | Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr |  | 1629439
2025-05-01 | 56.1115. | UC Davis - WWTP Annual Instrument Calibrations |  | 5895.77
2025-05-01 | 56.1119. | SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit |  | 47941
2025-05-01 | 56.1120. | Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio |  | 40662
2025-05-01 | 56.1121. | San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro |  | 1174927
2025-05-01 | 56.1122. | West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit |  | 25315
2025-05-01 | 56.1123. | UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis |  | 7193
2025-05-01 | 56.1124. | Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of |  | 2306698
2025-05-01 | 56.1125. | Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation |  | 165468
2025-05-01 | 56.1126. | Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat |  | 188110
2025-05-01 | 56.1127. | Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co |  | 648296
2025-05-01 | 56.1128. | Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase |  | 158018
2025-05-01 | 56.1129. | RMCSD - VEEAM SFTWR |  | 6899
2025-05-01 | 56.1130. | System Integration Division Estimating 2025 |  | 267.5
2025-05-01 | 56.1131. | North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame |  | 72836
2025-05-01 | 56.1132. | UC Davis - CABA Well Pump Station Rehabilitation – UC Davis |  | 44530
2025-05-01 | 56.1133. | UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis |  | 27435
2025-05-01 | 56.1134. | Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc |  | 884.99
2025-05-01 | 56.1135. | San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa |  | 110078
2025-05-01 | 56.1141. | Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos |  | 26782.9038
2025-05-01 | 56.1002. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency |  | 114485.82
2025-05-01 | 56.1008. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers |  | 30551.92
2025-05-01 | 56.1010.01. | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels |  | 7097.1
2025-05-01 | 56.1022. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz |  | 0
2025-05-01 | 56.1052. | San Jose Water - Williams Back ATS Replacement |  | 6400.94
2025-05-01 | 56.1053. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un |  | 19964.78
2025-05-01 | 56.1057. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant |  | 0
2025-05-01 | 56.1061. | San Jose Water - PLC System Assessment |  | 5582.66
2025-05-01 | 56.1064. | South Orange County Water Agency - CTP & JBL SCADA Upgrade |  | 201291.4
2025-05-01 | 56.1074. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley |  | 10641.86
2025-05-01 | 56.1076. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement |  | 11577.77
2025-05-01 | 50.0541. | W.M. Lyles Co. - General Overhead |  | 1347443.11
2025-05-01 | 50.0542. | W.M. Lyles Co. - General Estimating |  | 24803.44
2025-05-01 | 50.0543. | American Paving |  | 7051.01
2025-05-01 | 50.0544. | Lyles Services Co. |  | 3464.39
2025-05-01 | 50.0545. | New England Sheet Metal and Mechanical Co. |  | 1037.94
2025-05-01 | 50.0546. | Lyles Utility Construction, LLC |  | 10465.62