## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-10-01 | 51.1108. | JV w/AECOM - Stockton - RWCF Phase 2A/2B |  | 94172998 | 858269 | 2025-11-30
2025-10-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) |  | 0 | 3463004.11 | 2025-11-30
2025-10-01 | 51.1129. | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications |  | 126413057 | 8997122.3673 | 2027-06-25
2025-10-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements |  | 5772260 | 1157811.7613 | 2025-11-30
2025-10-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 |  | 1259243 | 96297.1867 | 2025-11-30
2025-10-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 |  | 1120182.07 | -47522.08 | 2025-11-30
2025-10-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 |  | 67202.17 | 4427.344 | 2025-11-30
2025-10-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project |  | 14969567 | 652347.9051 | 2026-12-20
2025-10-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility |  | 60980234 | 13898570.3249 | 2025-11-30
2025-10-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade |  | 10658200 | 203122.2113 | 2026-11-25
2025-10-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project |  | 19495325 | 818026.766 | 2026-06-30
2025-10-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement |  | 549548.83 | 81887.8675 | 2025-11-30
2025-10-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 |  | 13363835 | 803148.4566 | 2025-12-15
2025-10-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out |  | 0 | 1744225.3 | 2025-11-30
2025-10-01 | 51.1156. | Rocklin Overhead 2025 |  | 0 | -1044821.84 | 2025-12-31
2025-10-01 | 51.1157. | Rocklin Estimating 2025 |  | 0 | -514947.49 | 2025-12-31
2025-10-01 | 51.1158. | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric |  | 49098.67 | 0 | 2025-12-31
2025-10-01 | 51.1159. | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement |  | 1199000 | 0 | 2026-03-15
2025-10-01 | 51.1160. | City of Galt Public Works - Industrial WWTP Expansion |  | 1757000 | 0 | 2026-09-20
2025-10-01 | 51.1161. | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project |  | 10848599 | 0 | 2026-12-10
2025-10-01 | 51.1162. | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project |  | 6029750 | 0 | 2027-10-21
2025-10-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement |  | 372738 | 40882.72 | 2025-09-30
2025-10-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project |  | 3967189.79 | 132095.06 | 2025-09-30
2025-10-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion |  | 1991231.37 | 233098.8 | 2025-06-25
2025-10-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project |  | 2742860.08 | 195842.13 | 2025-10-31
2025-10-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 |  | 2486231.58 | 246796.44 | 2025-09-30
2025-10-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 |  | 1174183 | 0 | 2025-11-30
2025-10-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out |  | 0 | 293353.69 | 2025-11-30
2025-10-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System |  | 1259398 | 228697.8498 | 2025-12-31
2025-10-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 |  | 12582099 | 1870179.3289 | 2025-11-30
2025-10-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. |  | 5899872 | 344289.998 | 2025-11-30
2025-10-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements |  | 2561263 | 119687.635 | 2025-11-30
2025-10-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 |  | 13892772.64 | 565999.3694 | 2026-03-11
2025-10-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project |  | 3642197 | 291459.4668 | 2025-12-31
2025-10-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic |  | 25799094 | 1616852.2843 | 2025-11-12
2025-10-01 | 52.8640. | City of Dos Palos - WTP Replacement Project |  | 37884482 | 1493552.5538 | 2026-04-17
2025-10-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site |  | 1870914.99 | 233831.3878 | 2025-11-30
2025-10-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project |  | 1641800 | 238489.7774 | 2025-11-12
2025-10-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 |  | 346522 | 32534.5017 | 2025-11-30
2025-10-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements |  | 777484.38 | 83140.7099 | 2025-11-30
2025-10-01 | 52.8678. | City of Chowcilla - Well 15 & Generator Improvement Projects |  | 1240321 | 29958.9574 | 2026-01-31
2025-10-01 | 52.8682. | Fresno Overhead 2025 |  | 0 | -881266.35 | 2025-12-31
2025-10-01 | 52.8683. | Fresno Estimating 2025 |  | 0 | -303806.13 | 2025-12-31
2025-10-01 | 52.8684. | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) |  | 50000 | 3705.2567 | 2025-11-30
2025-10-01 | 52.8685. | Malaga County Water Dist. - Malaga County Water District |  | 442074 | 20278.8185 | 2025-11-30
2025-10-01 | 52.8687. | California Water Service Co. - Salinas Station 205 |  | 831511 | 75089.6517 | 2025-11-30
2025-10-01 | 52.8692. | New England Sheet Metal and Mechanical Co. - Clovis South T&M |  | 55135.37 | 5452.88 | 2025-11-30
2025-10-01 | 52.8693. | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections |  | 1136503 | 358951.8033 | 2025-11-30
2025-10-01 | 52.8697. | City of Tulare - Industrial WWTP Dewatering Improvements Pro |  | 1388000 | 24733.8971 | 2026-07-22
2025-10-01 | 52.8700. | Lyles Services Co. - LSC GO Misc. Work |  | 5000 | 334.6549 | 2025-12-31
2025-10-01 | 52.8704. | City of Visalia - Solids Handling Improvements Project |  | 13744000 | 0 | 2026-12-04
2025-10-01 | 52.8705. | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster |  | 775000 | 0 | 2026-01-31
2025-10-01 | 52.8707. | County of Fresno - Westside Water Tank and Pump Station |  | 4192700 | 0 | 2026-07-12
2025-10-01 | 52.8708. | County of Fresno - CSA 44A Wastewater Improvements |  | 363833 | 0 | 2026-02-28
2025-10-01 | 52.8709. | County of Fresno - 47.1 Water |  | 14000 | 946.6415 | 2025-11-30
2025-10-01 | 52.8710. | City of Dinuba - WWTP Bar Screen Motor Bracket Repair |  | 5000 | 385.6911 | 2025-11-30
2025-10-01 | 52.8567. | City of Modesto - Grayson Well 69 |  | 3059858.99 | -68164.94 | 2025-08-31
2025-10-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation |  | 5095690.97 | 523187.74 | 2025-08-31
2025-10-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station |  | 1290184 | 250807.92 | 2025-09-11
2025-10-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 |  | 314085.77 | 23359.66 | 2025-07-31
2025-10-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 |  | 274166.01 | 6883.96 | 2025-06-30
2025-10-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install |  | 279244 | 28155.8 | 2025-03-31
2025-10-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M |  | 29838.25 | 3749.92 | 2025-06-30
2025-10-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair |  | 23957 | 16451.74 | 2025-03-31
2025-10-01 | 52.8688. | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits |  | 132492.2 | 15519.45 | 2025-10-31
2025-10-01 | 52.8689. | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M |  | 16665.83 | 570.25 | 2025-04-30
2025-10-01 | 52.8690. | City of Dinuba - WWTP Rake Replacement |  | 14151.97 | 996.14 | 2025-05-02
2025-10-01 | 52.8691. | County of Fresno - Quail Lakes Repair at Bodega Bay Rd |  | 11302.84 | 3015.02 | 2025-06-30
2025-10-01 | 52.8694. | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair |  | 43047.45 | 4505.46 | 2025-06-30
2025-10-01 | 52.8695. | Lyles Services Co. - LSC GO Trash Enclosure |  | 13769 | 744.63 | 2025-06-30
2025-10-01 | 52.8696. | American Paving Co. - Hot Tap for APC- Tule River Parkway |  | 1059.22 | 171.57 | 2025-05-31
2025-10-01 | 52.8699. | City of Hanford - WWTP Repair T&M |  | 3001.12 | 52.21 | 2025-08-31
2025-10-01 | 52.8701. | County of Fresno - 47 Water |  | 13433.85 | 1247.66 | 2025-07-31
2025-10-01 | 52.8702. | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M |  | 5626.78 | 901.5 | 2025-08-31
2025-10-01 | 52.8703. | County of Fresno - CSA 47 Egret Point Water Line Repair |  | 14402.18 | 2171.92 | 2025-09-30
2025-10-01 | 52.8706. | City of Hanford - WWTP Weld Repair T&M 2 |  | 2868.6 | 432.82 | 2025-09-30
2025-10-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project |  | 1173753.47 | 169877.4649 | 2025-11-30
2025-10-01 | 53.2005. | East Bay Overhead 2025 |  | 0 | -224999.23 | 2025-12-31
2025-10-01 | 53.2006. | East Bay Estimating 2026 |  | 0 | -303815.55 | 2025-12-31
2025-10-01 | 53.2007. | Union Sanitary Dist. - Phase 1B Secondary Clarifiers |  | 324530134 | 0 | 2031-01-31
2025-10-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 |  | 114667.83 | 10966.87 | 2025-12-25
2025-10-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade |  | 55712110 | 10372751.5815 | 2025-11-30
2025-10-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project |  | 9447507 | 560240.6328 | 2025-11-30
2025-10-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equiping Project |  | 1777852 | 60000 | 2025-11-30
2025-10-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station |  | 1471328 | 15983.8052 | 2025-11-30
2025-10-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement |  | 907298 | 65000 | 2025-11-30
2025-10-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 |  | 2295240 | 34260.1682 | 2025-12-25
2025-10-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement |  | 462022 | 57709.7794 | 2026-02-28
2025-10-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr |  | 3968669 | 134557.683 | 2025-11-30
2025-10-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project |  | 8787721 | 569286.4756 | 2025-12-25
2025-10-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep |  | 324900 | 17960.2 | 2025-11-30
2025-10-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility |  | 25173720 | 714938.8435 | 2025-11-30
2025-10-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project |  | 4082300 | 61357.3057 | 2026-10-26
2025-10-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements |  | 1282279 | 182196.7484 | 2025-11-30
2025-10-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 |  | 6881300 | 419829.5624 | 2026-05-31
2025-10-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond |  | 1298330 | 190794.2569 | 2025-11-30
2025-10-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement |  | 1225220 | 61631.1576 | 2026-05-31
2025-10-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project |  | 30413570 | 0 | 2027-04-01
2025-10-01 | 54.9371. | Bakersfield Overhead 2025 |  | 0 | -1099954.01 | 2025-12-31
2025-10-01 | 54.9372. | Bakersfield Estimating 2025 |  | 0 | -509754.56 | 2025-12-31
2025-10-01 | 54.9373. | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement |  | 1524766 | 0 | 2026-03-01
2025-10-01 | 54.9382. | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement |  | 143799 | 17073.6452 | 2025-11-30
2025-10-01 | 54.9385. | Westside Water Authority - Pump Station A - Electrical Controls and Civil |  | 105446 | 2419.8642 | 2025-11-30
2025-10-01 | 54.9389. | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project |  | 299780 | -30000 | 2025-11-30
2025-10-01 | 54.9391. | Arvin Edison Water Storage Dist. - HQ Concrete R&R |  | 550000 | 19316.5185 | 2025-11-30
2025-10-01 | 54.9392. | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs |  | 223000 | 6751.9761 | 2025-11-30
2025-10-01 | 54.9395. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project |  | 1528900 | 0 | 2026-02-28
2025-10-01 | 54.9396. | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction |  | 951469 | 0 | 2026-04-01
2025-10-01 | 54.9397. | Cawelo Water Dist. - Friant-Kern Canal Pump Station |  | 3690645 | 0 | 2026-03-26
2025-10-01 | 54.9403. | Lost Hills Utility Dist. - WTP Improvements |  | 381600 | 0 | 2026-02-18
2025-10-01 | 54.9404. | Cawelo Water Dist. - Reuse of Produced Water |  | 3720000 | 0 | 2025-12-25
2025-10-01 | 54.9405. | Semitropic Water Storage Dist. - Pump Platform Replacement Project |  | 942000 | 0 | 2026-03-30
2025-10-01 | 54.9408. | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line |  | 3777777 | 0 | 2026-06-01
2025-10-01 | 54.9411. | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation |  | 103000 | 19241.8622 | 2025-11-01
2025-10-01 | 54.9412. | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork |  | 60000 | 4445.06 | 2025-11-25
2025-10-01 | 54.9413. | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork |  | 60000 | 3214.5244 | 2025-11-25
2025-10-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict |  | 24160002.44 | 3141570.22 | 2025-03-01
2025-10-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements |  | 2472164.05 | 186096.35 | 2025-09-25
2025-10-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification |  | 223896.47 | 3141.96 | 2025-07-31
2025-10-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation |  | 3216240.01 | 63002.61 | 2025-08-01
2025-10-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting |  | 44560 | 19462.75 | 2025-08-01
2025-10-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting |  | 4300 | 2986.55 | 2025-03-31
2025-10-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair |  | 110661.47 | 16178.26 | 2025-06-30
2025-10-01 | 54.9329. | Kern Water Bank Authority - Valve Replacement Parts |  | 18201.12 | 1734.4 | 2025-10-31
2025-10-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project |  | 427464.77 | 58649.48 | 2025-06-30
2025-10-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement |  | 175884.64 | 56698.53 | 2025-03-31
2025-10-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace |  | 199161.5 | 75015.2 | 2025-03-31
2025-10-01 | 54.9347. | City of Guadalupe - Effluent Pump Station Flow Meter Installation |  | 7100 | 3872.3 | 2025-04-30
2025-10-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A |  | 290129 | 92239.69 | 2025-04-30
2025-10-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 |  | 129965.06 | 22339.88 | 2025-06-30
2025-10-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement |  | 153298.79 | 16490.49 | 2025-04-30
2025-10-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 |  | 2008.42 | 890.92 | 2025-03-31
2025-10-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair |  | 9571.2 | 1340.37 | 2025-03-31
2025-10-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 |  | 2806.42 | 991.19 | 2025-03-31
2025-10-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 |  | 1760.42 | 870.76 | 2025-03-31
2025-10-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout |  | 1147640 | 22240.17 | 2025-10-31
2025-10-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 |  | 1855.92 | 711.04 | 2025-03-31
2025-10-01 | 54.9361. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair |  | 108668.35 | 1593.48 | 2025-05-31
2025-10-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line |  | 425035.04 | 49433.8 | 2025-03-31
2025-10-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 |  | 1855.92 | 1078.37 | 2025-03-31
2025-10-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 |  | 2216.42 | 953.09 | 2025-03-31
2025-10-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 |  | 2540.42 | 938.09 | 2025-03-31
2025-10-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair |  | 15697.91 | 2044.29 | 2025-03-31
2025-10-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 |  | 1760.42 | 870.78 | 2025-03-31
2025-10-01 | 54.9374. | City of Santa Maria - WWTP Trickling Filter Repairs |  | 32962 | 12975.55 | 2025-06-30
2025-10-01 | 54.9375. | City of Santa Maria - WWTP Clarifier Repairs |  | 8232.73 | 3687.25 | 2025-03-31
2025-10-01 | 54.9379. | Semitropic Water Storage Dist. - Delta System Pipe Repair |  | 41679.77 | 5567.82 | 2025-03-31
2025-10-01 | 54.9380. | Cawelo Water Dist. - CWD Pump Station Pipe Repair |  | 22446.19 | 4381.47 | 2025-03-31
2025-10-01 | 54.9381. | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement |  | 58900 | 30024.62 | 2025-04-30
2025-10-01 | 54.9383. | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 |  | 17542.44 | 1782.68 | 2025-05-31
2025-10-01 | 54.9384. | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair |  | 79531.98 | 9191.41 | 2025-07-31
2025-10-01 | 54.9386. | Kern Valley State Prison - Arsenic Pipe Leak Repair |  | 96086 | 20301.26 | 2025-07-31
2025-10-01 | 54.9387. | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications |  | 22619.54 | 3607.89 | 2025-08-31
2025-10-01 | 54.9388. | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation |  | 7454.07 | 918.66 | 2025-06-30
2025-10-01 | 54.9390. | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads |  | 101491.67 | 5162.18 | 2025-08-31
2025-10-01 | 54.9393. | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs |  | 31523.02 | 3983.2 | 2025-06-30
2025-10-01 | 54.9394. | City of Arvin - Haven Drive Lateral Repair |  | 15966.99 | 1927.44 | 2025-08-31
2025-10-01 | 54.9398. | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation |  | 14300 | 6107.21 | 2025-09-30
2025-10-01 | 54.9399. | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement |  | 24775 | 13483.41 | 2025-08-31
2025-10-01 | 54.9400. | Arvin Edison Water Storage Dist. - FFPP Core Drilling |  | 800.69 | 29.37 | 2025-07-31
2025-10-01 | 54.9401. | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R |  | 247539.61 | 11227.04 | 2025-10-31
2025-10-01 | 54.9407. | Semitropic Water Storage Dist. - North Plant Emergency Repair |  | 31296.85 | 5629.51 | 2025-10-31
2025-10-01 | 54.9409. | Nipomo CSD Osage Emergency Waterline Repair |  | 20123.71 | 2712 | 2025-10-31
2025-10-01 | 54.9410. | SWID - Burbank St. Repair |  | 8241.55 | 1275.9 | 2025-10-31
2025-10-01 | 55.1090. | JV w/Webcor & Obayashi - Silverlake - LADWP |  | 5300000 | 1493927.8618 | 2025-12-25
2025-10-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility |  | 341457735.73 | 5210498 | 2027-07-01
2025-10-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements |  | 6651803.53 | 250000 | 2025-11-30
2025-10-01 | 55.1200. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 |  | 195902148 | 0 | 2027-04-02
2025-10-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out |  | 0 | 7584540.4 | 2027-04-02
2025-10-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project |  | 16115717 | 712051.7283 | 2026-08-01
2025-10-01 | 55.1204. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 |  | 54018182 | 0 | 2027-02-26
2025-10-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out |  | 0 | 2288167.25 | 2027-02-26
2025-10-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project |  | 41346178 | 4309044.6308 | 2026-02-28
2025-10-01 | 55.1233. | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) |  | 104447 | 8429.1 | 2025-11-30
2025-10-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation |  | 5782651.52 | 317310.7184 | 2026-03-01
2025-10-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 |  | 147718400 | 0 | 2029-02-01
2025-10-01 | 55.1252. | Murrieta Overhead 2025 |  | 0 | -1662182.29 | 2025-12-31
2025-10-01 | 55.1253. | Murrieta Estimating 2025 |  | 0 | -444897.31 | 2025-12-31
2025-10-01 | 55.1254. | JV w/City of Banning - Wastewater Treatment Plant Recycled Water |  | 471896 | 0 | 2026-05-25
2025-10-01 | 55.1255. | City of Riverside - RWQCP Emergency Repair |  | 1246.72 | 0 | 2025-12-31
2025-10-01 | 55.1256. | Anaergia Technologies LLC - City of Riverside - OPS |  | 2888100 | 0 | 2026-02-01
2025-10-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement |  | 2273682.69 | 608537.39 | 2025-05-31
2025-10-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements |  | 4046200 | 724343.64 | 2025-03-31
2025-10-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 |  | 34207.53 | 2206.22 | 2025-09-30
2025-10-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair |  | 184557.17 | 136263.23 | 2025-03-31
2025-10-01 | 55.1251. | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade |  | 322982.96 | 38761.1 | 2025-05-31
2025-10-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 |  | 38165419.5 | 96390.2947 | 2027-04-01
2025-10-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project |  | 40106224.63 | 0 | 2026-03-25
2025-10-01 | 57.0005. | San Diego Overhead 2025 |  | 0 | -69675.68 | 2025-12-31
2025-10-01 | 57.0006. | San Diego Estimating 2025 |  | 0 | -10411.32 | 2025-12-31
2025-10-01 | 57.0007. | Anaergia Technologies, LLC - East County Package 5 - Phase 1B |  | 162630 | -32235.1 | 2025-11-30
2025-10-01 | 57.0008. | Imperial Irrigation Dist. - El Centro Generating Station WWTP |  | 2876047 | 0 | 2026-11-01
2025-10-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement |  | 22085905 | 499821.8624 | 2026-06-01
2025-10-01 | 58.0004. | Los Angeles Overhead 2025 |  | 0 | -132532.5 | 2025-12-31
2025-10-01 | 58.0005. | Los Angeles Estimating 2025 |  | 0 | -28106.32 | 2025-12-31
2025-10-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment |  | 322651 | 77709.3978 | 2025-12-31
2025-10-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station |  | 373425 | 76622.6316 | 2025-12-31
2025-10-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold |  | 135000 | 50249.6318 | 2026-03-31
2025-10-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield |  | 19314 | 23.9695 | 2025-12-31
2025-10-01 | 56.1010. | Placer County Water Agency -PCWA Time & Material Contract |  | 49250 | 14145.31 | 2026-12-31
2025-10-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga |  | 230000 | 18742.3465 | 2026-03-31
2025-10-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport |  | 127868 | 9969.0868 | 2025-12-31
2025-10-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas |  | 153913 | 50779.1259 | 2026-03-31
2025-10-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. |  | 193845 | 35315.304 | 2025-12-31
2025-10-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods |  | 85000 | 1668.7562 | 2026-03-31
2025-10-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 |  | 276000 | 26619.689 | 2026-03-31
2025-10-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services |  | 52876 | 6843.9742 | 2025-12-31
2025-10-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 |  | 95000 | 4310.1925 | 2026-03-31
2025-10-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station |  | 375000 | 31031.7981 | 2025-12-31
2025-10-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services |  | 277565 | 45819.7839 | 2026-03-31
2025-10-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh |  | 336610 | 6277.0761 | 2026-03-31
2025-10-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods |  | 77120 | -1227 | 2025-12-31
2025-10-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 |  | 2394758 | 130058.9896 | 2026-12-31
2025-10-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement |  | 200000 | 38134.18 | 2025-12-31
2025-10-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 |  | 308725 | 46233.9251 | 2026-03-31
2025-10-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat |  | 3792559 | 115692.394 | 2026-12-31
2025-10-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives |  | 129975 | 22813.6781 | 2025-12-31
2025-10-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project |  | 120891 | 21247.2479 | 2026-03-31
2025-10-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou |  | 395209 | 43214.4881 | 2026-06-30
2025-10-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar |  | 404663 | 23237.4167 | 2026-09-30
2025-10-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project |  | 108000 | 9193.5284 | 2026-06-30
2025-10-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact |  | 226401 | 16147.5732 | 2025-12-31
2025-10-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather |  | 595000 | 109459.572 | 2025-12-31
2025-10-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto |  | 478000 | 0 | 2026-09-30
2025-10-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri |  | 65960 | 5111.8892 | 2026-03-31
2025-10-01 | 56.1073. | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W |  | 122210 | 9918.5842 | 2026-03-31
2025-10-01 | 56.1075. | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF |  | 950000 | 0 | 2026-06-30
2025-10-01 | 56.1077. | System Integration Overhead 2025 |  | 0 | -4372493.41 | 2025-12-25
2025-10-01 | 56.1078. | City of Napa - On-Call Control Systems Integrator Services |  | 146650.24 | 0 | 2026-03-31
2025-10-01 | 56.1081. | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA |  | 179690 | 10761.6121 | 2025-12-31
2025-10-01 | 56.1083. | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM |  | 717010 | 14897.0844 | 2026-06-30
2025-10-01 | 56.1085. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service |  | 80000 | 0 | 2026-06-30
2025-10-01 | 56.1086. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service |  | 376000 | 0 | 2026-06-30
2025-10-01 | 56.1087. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters |  | 49369 | 5767.3948 | 2026-03-31
2025-10-01 | 56.1088. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo |  | 127235 | 9253.9555 | 2026-03-31
2025-10-01 | 56.1002. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency |  | 185000 | 70514.18 | 2025-04-30
2025-10-01 | 56.1008. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers |  | 55000 | 24448.08 | 2025-03-31
2025-10-01 | 56.1010.01 | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels |  | 9569 | 2471.9 | 2025-03-31
2025-10-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District |  | 150064.25 | 39980.63 | 2025-09-09
2025-10-01 | 56.1021. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 |  | 244760 | 128007.48 | 2025-06-30
2025-10-01 | 56.1022. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz |  | 0 |  | 2024-12-31
2025-10-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade |  | 220390 | 69885.27 | 2025-09-30
2025-10-01 | 56.1030. | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject |  | 612078.64 | 0 | 2025-09-30
2025-10-01 | 56.1041. | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming |  | 20016.78 | 0 | 2025-07-31
2025-10-01 | 56.1052. | San Jose Water - Williams Back ATS Replacement |  | 8887 | 2486.06 | 2025-04-30
2025-10-01 | 56.1053. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un |  | 35000 | 15035.22 | 2025-03-31
2025-10-01 | 56.1054. | AIC - Riverside Public Works - Digester 5 Rehab |  | 37648.03 | 0 | 2025-09-30
2025-10-01 | 56.1056. | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan |  | 98280.63 | 0 | 2025-07-31
2025-10-01 | 56.1057. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant |  | 0 |  | 2025-04-30
2025-10-01 | 56.1061. | San Jose Water - PLC System Assessment |  | 11269 | 5686.34 | 2025-03-31
2025-10-01 | 56.1062. | AIC - SCADA System Upgrade - City of Brentwood |  | 409988.07 | 0 | 2025-07-31
2025-10-01 | 56.1064. | South Orange County Water Agency - CTP & JBL SCADA Upgrade |  | 435153 | 232886.6 | 2025-05-31
2025-10-01 | 56.1069. | City of Brentwood - Brentwood, City of - On-Call Agreement |  | 2525 | -1296.46 | 2025-06-30
2025-10-01 | 56.1071. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard |  | 34000 | 30403.44 | 2025-06-30
2025-10-01 | 56.1074. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley |  | 12650 | 2008.14 | 2025-03-31
2025-10-01 | 56.1076. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement |  | 19200 | 7622.23 | 2025-03-31
2025-10-01 | 56.1079. | AIC - San Jose Water Co - Montevina PLC Upgrade |  | 29235.63 | 0 | 2025-07-31
2025-10-01 | 56.1080. | AIC - San Jose Water Co - PLC System Assessment |  | 359469 | 0 | 2025-07-31
2025-10-01 | 56.1082. | City of Clovis - Pump Station E New Pump 5 VFD Startup |  | 19800 | -783.04 | 2025-09-09
2025-10-01 | 56.1084. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut |  | 8000 | 3771.87 | 2025-09-09
2025-10-01 | 56.1102. | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal |  | 19815.94 | 0 | 2025-07-31
2025-10-01 | 56.1103. | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District |  | 55855.24 | 0 | 2025-07-31
2025-10-01 | 56.1104. | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric |  | 9500.31 | 0 | 2025-07-31
2025-10-01 | 56.1105. | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun |  | 30502.53 | 0 | 2025-07-31
2025-10-01 | 56.1106. | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - |  | 54742.18 | 0 | 2025-07-31
2025-10-01 | 56.1107. | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W |  | 3429.06 | 0 | 2025-07-31
2025-10-01 | 56.1108. | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit |  | 20729.84 | 0 | 2025-07-31
2025-10-01 | 56.1109. | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U |  | 14772.26 | 0 | 2025-07-31
2025-10-01 | 56.1110. | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M |  | 4596.42 | 0 | 2025-07-31
2025-10-01 | 56.1111. | AIC - California American Water - Luzern Well Treatment Design |  | 17210.01 | 0 | 2025-07-31
2025-10-01 | 56.1112. | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au |  | 27241.58 | 0 | 2025-07-31
2025-10-01 | 56.1113. | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr |  | 49233.44 | 0 | 2025-07-31
2025-10-01 | 56.1115. | AIC - UC Davis - WWTP Annual Instrument Calibrations |  | 5895.77 | 0 | 2025-04-30
2025-10-01 | 56.1119. | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit |  | 22184.06 | 0 | 2025-07-31
2025-10-01 | 56.1120. | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio |  | 1045.63 | 0 | 2025-07-31
2025-10-01 | 56.1121. | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro |  | 22824.38 | 0 | 2025-07-31
2025-10-01 | 56.1122. | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit |  | 6289.38 | 0 | 2025-07-31
2025-10-01 | 56.1123. | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis |  | 3772.82 | 0 | 2025-07-31
2025-10-01 | 56.1124. | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of |  | 28950 | 0 | 2025-07-31
2025-10-01 | 56.1125. | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation |  | 14229.38 | 0 | 2025-07-31
2025-10-01 | 56.1126. | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat |  | 9526.88 | 0 | 2025-07-31
2025-10-01 | 56.1127. | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co |  | 6519.07 | 0 | 2025-07-31
2025-10-01 | 56.1128. | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase |  | 4793.13 | 0 | 2025-07-31
2025-10-01 | 56.1129. | AIC - RMCSD - VEEAM SFTWR |  | 133.75 | 0 | 2025-07-31
2025-10-01 | 56.1130. | System Integration Division Estimating 2025 |  | 0 | -267.5 | 2025-07-31
2025-10-01 | 56.1131. | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame |  | 2388.75 | 0 | 2025-07-31
2025-10-01 | 56.1132. | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis |  | 585 | 0 | 2025-07-31
2025-10-01 | 56.1133. | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis |  | 2827.5 | 0 | 2025-07-31
2025-10-01 | 56.1134. | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc |  | 965.51 | 0 | 2025-07-31
2025-10-01 | 56.1135. | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa |  | 112.5 | 0 | 2025-07-31
2025-10-01 | 56.1141. | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos |  | 2827.5 | 0 | 2025-07-31
2025-10-01 | 50.0541. | W.M. Lyles Co. - General Overhead |  | 0 | -2869307.34 | 2025-07-31
2025-10-01 | 50.0542. | W.M. Lyles Co. - General Estimating |  | 0 | -77832.23 | 2025-12-31
2025-10-01 | 50.0543. | American Paving |  | 7051.01 | 0 | 2025-12-31
2025-10-01 | 50.0544. | Lyles Services Co. |  | 6433.57 | 0 | 2025-12-31
2025-10-01 | 50.0545. | New England Sheet Metal and Mechanical Co. |  | 2226.16 | 0 | 2025-12-31
2025-10-01 | 50.0546. | Lyles Utility Construction, LLC |  | 11256.72 | 788.66 | 2025-12-31
2025-10-01 | 50.0551. | Advanced Integration & Controls |  | 5093.69 | 0 | 2025-12-31

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-10-01 | 51.1108. | JV w/AECOM - Stockton - RWCF Phase 2A/2B |  | 93314729
2025-10-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) |  | -3530000
2025-10-01 | 51.1129. | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications |  | 115163057
2025-10-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements |  | 4588654
2025-10-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 |  | 1145603
2025-10-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 |  | 1167704.15
2025-10-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 |  | 62358.17
2025-10-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project |  | 13839618
2025-10-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility |  | 45380234
2025-10-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade |  | 10079352
2025-10-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project |  | 18202915
2025-10-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement |  | 441244.83
2025-10-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 |  | 12492090
2025-10-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out |  | -1800000
2025-10-01 | 51.1156. | Rocklin Overhead 2025 |  | 1044821.84
2025-10-01 | 51.1157. | Rocklin Estimating 2025 |  | 514947.49
2025-10-01 | 51.1158. | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric |  | 49098.67
2025-10-01 | 51.1159. | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement |  | 1079240
2025-10-01 | 51.1160. | City of Galt Public Works - Industrial WWTP Expansion |  | 1690000
2025-10-01 | 51.1161. | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project |  | 10261252
2025-10-01 | 51.1162. | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project |  | 5845263
2025-10-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement |  | 331855.28
2025-10-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project |  | 3835094.73
2025-10-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion |  | 1758132.57
2025-10-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project |  | 2547017.95
2025-10-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 |  | 2239435.14
2025-10-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 |  | 1174183
2025-10-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out |  | -293392.63
2025-10-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System |  | 1029398
2025-10-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 |  | 10657099
2025-10-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. |  | 5499872
2025-10-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements |  | 2441263
2025-10-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 |  | 13190772.64
2025-10-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project |  | 3332197
2025-10-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic |  | 24149094
2025-10-01 | 52.8640. | City of Dos Palos - WTP Replacement Project |  | 36011159
2025-10-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site |  | 1636593.92
2025-10-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project |  | 1381800
2025-10-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 |  | 313722
2025-10-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements |  | 689484.38
2025-10-01 | 52.8678. | City of Chowcilla - Well 15 & Generator Improvement Projects |  | 1162321
2025-10-01 | 52.8682. | Fresno Overhead 2025 |  | 881266.35
2025-10-01 | 52.8683. | Fresno Estimating 2025 |  | 303806.13
2025-10-01 | 52.8684. | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) |  | 45000
2025-10-01 | 52.8685. | Malaga County Water Dist. - Malaga County Water District |  | 414074
2025-10-01 | 52.8687. | California Water Service Co. - Salinas Station 205 |  | 750089
2025-10-01 | 52.8692. | New England Sheet Metal and Mechanical Co. - Clovis South T&M |  | 49682.49
2025-10-01 | 52.8693. | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections |  | 736503
2025-10-01 | 52.8697. | City of Tulare - Industrial WWTP Dewatering Improvements Pro |  | 1325482
2025-10-01 | 52.8700. | Lyles Services Co. - LSC GO Misc. Work |  | 4650
2025-10-01 | 52.8704. | City of Visalia - Solids Handling Improvements Project |  | 13491127
2025-10-01 | 52.8705. | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster |  | 719260
2025-10-01 | 52.8707. | County of Fresno - Westside Water Tank and Pump Station |  | 3961077
2025-10-01 | 52.8708. | County of Fresno - CSA 44A Wastewater Improvements |  | 333757
2025-10-01 | 52.8709. | County of Fresno - 47.1 Water |  | 13000
2025-10-01 | 52.8710. | City of Dinuba - WWTP Bar Screen Motor Bracket Repair |  | 4500
2025-10-01 | 52.8567. | City of Modesto - Grayson Well 69 |  | 3128023.93
2025-10-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation |  | 4572503.23
2025-10-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station |  | 1039376.08
2025-10-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 |  | 290726.11
2025-10-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 |  | 267282.05
2025-10-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install |  | 251088.2
2025-10-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M |  | 26088.33
2025-10-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair |  | 7505.26
2025-10-01 | 52.8688. | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits |  | 116972.75
2025-10-01 | 52.8689. | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M |  | 16095.58
2025-10-01 | 52.8690. | City of Dinuba - WWTP Rake Replacement |  | 13155.83
2025-10-01 | 52.8691. | County of Fresno - Quail Lakes Repair at Bodega Bay Rd |  | 8287.82
2025-10-01 | 52.8694. | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair |  | 38541.99
2025-10-01 | 52.8695. | Lyles Services Co. - LSC GO Trash Enclosure |  | 13024.37
2025-10-01 | 52.8696. | American Paving Co. - Hot Tap for APC- Tule River Parkway |  | 887.65
2025-10-01 | 52.8699. | City of Hanford - WWTP Repair T&M |  | 2948.91
2025-10-01 | 52.8701. | County of Fresno - 47 Water |  | 12186.19
2025-10-01 | 52.8702. | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M |  | 4725.28
2025-10-01 | 52.8703. | County of Fresno - CSA 47 Egret Point Water Line Repair |  | 12230.26
2025-10-01 | 52.8706. | City of Hanford - WWTP Weld Repair T&M 2 |  | 2435.78
2025-10-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project |  | 997053.47
2025-10-01 | 53.2005. | East Bay Overhead 2025 |  | 224999.23
2025-10-01 | 53.2006. | East Bay Estimating 2026 |  | 303815.55
2025-10-01 | 53.2007. | Union Sanitary Dist. - Phase 1B Secondary Clarifiers |  | 291530134
2025-10-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 |  | 103700.83
2025-10-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade |  | 45337110
2025-10-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project |  | 8837507
2025-10-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equiping Project |  | 1717852
2025-10-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station |  | 1426328
2025-10-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement |  | 842298
2025-10-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 |  | 2260991
2025-10-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement |  | 387022
2025-10-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr |  | 3813669
2025-10-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project |  | 7957721
2025-10-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep |  | 306900
2025-10-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility |  | 23273720
2025-10-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project |  | 3922300
2025-10-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements |  | 1094757
2025-10-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 |  | 6031300
2025-10-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond |  | 913330
2025-10-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement |  | 1135220
2025-10-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project |  | 28042727
2025-10-01 | 54.9371. | Bakersfield Overhead 2025 |  | 1099954.01
2025-10-01 | 54.9372. | Bakersfield Estimating 2025 |  | 509754.56
2025-10-01 | 54.9373. | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement |  | 1393326
2025-10-01 | 54.9382. | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement |  | 123799
2025-10-01 | 54.9385. | Westside Water Authority - Pump Station A - Electrical Controls and Civil |  | 97820
2025-10-01 | 54.9389. | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project |  | 329780
2025-10-01 | 54.9391. | Arvin Edison Water Storage Dist. - HQ Concrete R&R |  | 530000
2025-10-01 | 54.9392. | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs |  | 216000
2025-10-01 | 54.9395. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project |  | 1498900
2025-10-01 | 54.9396. | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction |  | 941923
2025-10-01 | 54.9397. | Cawelo Water Dist. - Friant-Kern Canal Pump Station |  | 3390645
2025-10-01 | 54.9403. | Lost Hills Utility Dist. - WTP Improvements |  | 338101
2025-10-01 | 54.9404. | Cawelo Water Dist. - Reuse of Produced Water |  | 3585392
2025-10-01 | 54.9405. | Semitropic Water Storage Dist. - Pump Platform Replacement Project |  | 822000
2025-10-01 | 54.9408. | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line |  | 3537777
2025-10-01 | 54.9411. | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation |  | 78000
2025-10-01 | 54.9412. | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork |  | 54000
2025-10-01 | 54.9413. | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork |  | 54000
2025-10-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict |  | 21018432.22
2025-10-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements |  | 2286067.7
2025-10-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification |  | 220754.51
2025-10-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation |  | 3153237.4
2025-10-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting |  | 25097.25
2025-10-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting |  | 1313.45
2025-10-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair |  | 94483.21
2025-10-01 | 54.9329. | Kern Water Bank Authority - Valve Replacement Parts |  | 16466.72
2025-10-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project |  | 368815.29
2025-10-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement |  | 119186.11
2025-10-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace |  | 124146.3
2025-10-01 | 54.9347. | City of Guadalupe - Effluent Pump Station Flow Meter Installation |  | 3227.7
2025-10-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A |  | 197889.31
2025-10-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 |  | 107625.18
2025-10-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement |  | 136808.3
2025-10-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 |  | 1117.5
2025-10-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair |  | 8230.83
2025-10-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 |  | 1815.23
2025-10-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 |  | 889.66
2025-10-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout |  | 1125399.83
2025-10-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 |  | 1144.88
2025-10-01 | 54.9361. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair |  | 107074.87
2025-10-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line |  | 375601.24
2025-10-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 |  | 777.55
2025-10-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 |  | 1263.33
2025-10-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 |  | 1602.33
2025-10-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair |  | 13653.62
2025-10-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 |  | 889.64
2025-10-01 | 54.9374. | City of Santa Maria - WWTP Trickling Filter Repairs |  | 19986.45
2025-10-01 | 54.9375. | City of Santa Maria - WWTP Clarifier Repairs |  | 4545.48
2025-10-01 | 54.9379. | Semitropic Water Storage Dist. - Delta System Pipe Repair |  | 36111.95
2025-10-01 | 54.9380. | Cawelo Water Dist. - CWD Pump Station Pipe Repair |  | 18064.72
2025-10-01 | 54.9381. | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement |  | 28875.38
2025-10-01 | 54.9383. | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 |  | 15759.76
2025-10-01 | 54.9384. | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair |  | 70340.57
2025-10-01 | 54.9386. | Kern Valley State Prison - Arsenic Pipe Leak Repair |  | 75784.74
2025-10-01 | 54.9387. | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications |  | 19011.65
2025-10-01 | 54.9388. | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation |  | 6535.41
2025-10-01 | 54.9390. | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads |  | 96329.49
2025-10-01 | 54.9393. | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs |  | 27539.82
2025-10-01 | 54.9394. | City of Arvin - Haven Drive Lateral Repair |  | 14039.55
2025-10-01 | 54.9398. | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation |  | 8192.79
2025-10-01 | 54.9399. | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement |  | 11291.59
2025-10-01 | 54.9400. | Arvin Edison Water Storage Dist. - FFPP Core Drilling |  | 771.32
2025-10-01 | 54.9401. | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R |  | 236312.57
2025-10-01 | 54.9407. | Semitropic Water Storage Dist. - North Plant Emergency Repair |  | 25667.34
2025-10-01 | 54.9409. | Nipomo CSD Osage Emergency Waterline Repair |  | 17411.71
2025-10-01 | 54.9410. | SWID - Burbank St. Repair |  | 6965.65
2025-10-01 | 55.1090. | JV w/Webcor & Obayashi - Silverlake - LADWP |  | 3803027.8
2025-10-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility |  | 336247237.73
2025-10-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements |  | 6401803.53
2025-10-01 | 55.1200. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 |  | 195902148
2025-10-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out |  | -8100000
2025-10-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project |  | 14940308
2025-10-01 | 55.1204. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 |  | 54018182
2025-10-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out |  | -2500000
2025-10-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project |  | 36996178
2025-10-01 | 55.1233. | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) |  | 96017.9
2025-10-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation |  | 5057651.52
2025-10-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 |  | 139897192
2025-10-01 | 55.1252. | Murrieta Overhead 2025 |  | 1662182.29
2025-10-01 | 55.1253. | Murrieta Estimating 2025 |  | 444897.31
2025-10-01 | 55.1254. | JV w/City of Banning - Wastewater Treatment Plant Recycled Water |  | 471896
2025-10-01 | 55.1255. | City of Riverside - RWQCP Emergency Repair |  | 1246.72
2025-10-01 | 55.1256. | Anaergia Technologies LLC - City of Riverside - OPS |  | 2713100
2025-10-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement |  | 1665145.3
2025-10-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements |  | 3321856.36
2025-10-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 |  | 32001.31
2025-10-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair |  | 48293.94
2025-10-01 | 55.1251. | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade |  | 284221.86
2025-10-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 |  | 35758333.5
2025-10-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project |  | 37896367.63
2025-10-01 | 57.0005. | San Diego Overhead 2025 |  | 69675.68
2025-10-01 | 57.0006. | San Diego Estimating 2025 |  | 10411.32
2025-10-01 | 57.0007. | Anaergia Technologies, LLC - East County Package 5 - Phase 1B |  | 194865.1
2025-10-01 | 57.0008. | Imperial Irrigation Dist. - El Centro Generating Station WWTP |  | 2743982
2025-10-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement |  | 20782993
2025-10-01 | 58.0004. | Los Angeles Overhead 2025 |  | 132532.5
2025-10-01 | 58.0005. | Los Angeles Estimating 2025 |  | 28106.32
2025-10-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment |  | 238777
2025-10-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station |  | 280455
2025-10-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold |  | 68025
2025-10-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield |  | 19290
2025-10-01 | 56.1010. | Placer County Water Agency -PCWA Time & Material Contract |  | 35104.69
2025-10-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga |  | 200544
2025-10-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport |  | 108921
2025-10-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas |  | 61072
2025-10-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. |  | 153862
2025-10-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods |  | 77828
2025-10-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 |  | 212166
2025-10-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services |  | 37451
2025-10-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 |  | 90115
2025-10-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station |  | 341174
2025-10-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services |  | 218288
2025-10-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh |  | 320183
2025-10-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods |  | 78347
2025-10-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 |  | 2144227
2025-10-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement |  | 160090.08
2025-10-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 |  | 253873
2025-10-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat |  | 3353935
2025-10-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives |  | 104630
2025-10-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project |  | 93977
2025-10-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou |  | 328582
2025-10-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar |  | 324797
2025-10-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project |  | 93968
2025-10-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact |  | 208839.38
2025-10-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather |  | 457763
2025-10-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto |  | 416472
2025-10-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri |  | 56905
2025-10-01 | 56.1073. | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W |  | 103557
2025-10-01 | 56.1075. | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF |  | 773000
2025-10-01 | 56.1077. | System Integration Overhead 2025 |  | 4372493.41
2025-10-01 | 56.1078. | City of Napa - On-Call Control Systems Integrator Services |  | 103076.74
2025-10-01 | 56.1081. | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA |  | 167611
2025-10-01 | 56.1083. | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM |  | 658177
2025-10-01 | 56.1085. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service |  | 67051
2025-10-01 | 56.1086. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service |  | 297677
2025-10-01 | 56.1087. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters |  | 43026
2025-10-01 | 56.1088. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo |  | 96803
2025-10-01 | 56.1002. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency |  | 114485.82
2025-10-01 | 56.1008. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers |  | 30551.92
2025-10-01 | 56.1010.01 | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels |  | 7097.1
2025-10-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District |  | 110083.62
2025-10-01 | 56.1021. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 |  | 116752.52
2025-10-01 | 56.1022. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz |  | 0
2025-10-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade |  | 150504.73
2025-10-01 | 56.1030. | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject |  | 612078.64
2025-10-01 | 56.1041. | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming |  | 20016.78
2025-10-01 | 56.1052. | San Jose Water - Williams Back ATS Replacement |  | 6400.94
2025-10-01 | 56.1053. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un |  | 19964.78
2025-10-01 | 56.1054. | AIC - Riverside Public Works - Digester 5 Rehab |  | 37648.03
2025-10-01 | 56.1056. | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan |  | 98280.63
2025-10-01 | 56.1057. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant |  | 0
2025-10-01 | 56.1061. | San Jose Water - PLC System Assessment |  | 5582.66
2025-10-01 | 56.1062. | AIC - SCADA System Upgrade - City of Brentwood |  | 409988.07
2025-10-01 | 56.1064. | South Orange County Water Agency - CTP & JBL SCADA Upgrade |  | 202266.4
2025-10-01 | 56.1069. | City of Brentwood - Brentwood, City of - On-Call Agreement |  | 3821.46
2025-10-01 | 56.1071. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard |  | 3596.56
2025-10-01 | 56.1074. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley |  | 10641.86
2025-10-01 | 56.1076. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement |  | 11577.77
2025-10-01 | 56.1079. | AIC - San Jose Water Co - Montevina PLC Upgrade |  | 29235.63
2025-10-01 | 56.1080. | AIC - San Jose Water Co - PLC System Assessment |  | 359469
2025-10-01 | 56.1082. | City of Clovis - Pump Station E New Pump 5 VFD Startup |  | 20583.04
2025-10-01 | 56.1084. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut |  | 4228.13
2025-10-01 | 56.1102. | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal |  | 19815.94
2025-10-01 | 56.1103. | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District |  | 55855.24
2025-10-01 | 56.1104. | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric |  | 9500.31
2025-10-01 | 56.1105. | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun |  | 30502.53
2025-10-01 | 56.1106. | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - |  | 54742.18
2025-10-01 | 56.1107. | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W |  | 3429.06
2025-10-01 | 56.1108. | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit |  | 20729.84
2025-10-01 | 56.1109. | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U |  | 14772.26
2025-10-01 | 56.1110. | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M |  | 4596.42
2025-10-01 | 56.1111. | AIC - California American Water - Luzern Well Treatment Design |  | 17210.01
2025-10-01 | 56.1112. | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au |  | 27241.58
2025-10-01 | 56.1113. | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr |  | 49233.44
2025-10-01 | 56.1115. | AIC - UC Davis - WWTP Annual Instrument Calibrations |  | 5895.77
2025-10-01 | 56.1119. | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit |  | 22184.06
2025-10-01 | 56.1120. | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio |  | 1045.63
2025-10-01 | 56.1121. | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro |  | 22824.38
2025-10-01 | 56.1122. | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit |  | 6289.38
2025-10-01 | 56.1123. | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis |  | 3772.82
2025-10-01 | 56.1124. | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of |  | 28950
2025-10-01 | 56.1125. | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation |  | 14229.38
2025-10-01 | 56.1126. | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat |  | 9526.88
2025-10-01 | 56.1127. | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co |  | 6519.07
2025-10-01 | 56.1128. | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase |  | 4793.13
2025-10-01 | 56.1129. | AIC - RMCSD - VEEAM SFTWR |  | 133.75
2025-10-01 | 56.1130. | System Integration Division Estimating 2025 |  | 267.5
2025-10-01 | 56.1131. | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame |  | 2388.75
2025-10-01 | 56.1132. | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis |  | 585
2025-10-01 | 56.1133. | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis |  | 2827.5
2025-10-01 | 56.1134. | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc |  | 965.51
2025-10-01 | 56.1135. | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa |  | 112.5
2025-10-01 | 56.1141. | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos |  | 2827.5
2025-10-01 | 50.0541. | W.M. Lyles Co. - General Overhead |  | 2869307.34
2025-10-01 | 50.0542. | W.M. Lyles Co. - General Estimating |  | 77832.23
2025-10-01 | 50.0543. | American Paving |  | 7051.01
2025-10-01 | 50.0544. | Lyles Services Co. |  | 6433.57
2025-10-01 | 50.0545. | New England Sheet Metal and Mechanical Co. |  | 2226.16
2025-10-01 | 50.0546. | Lyles Utility Construction, LLC |  | 10468.06
2025-10-01 | 50.0551. | Advanced Integration & Controls |  | 5093.69