## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-09-01 | 51.1108. | JV w/AECOM - Stockton - RWCF Phase 2A/2B | 94010128.45 | 94158998 | 858269 | 2025-11-30
2025-09-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) | 0 | 0 | 3462979.66 | 2025-11-30
2025-09-01 | 51.1129. | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications | 126413057 | 126413057 | 9103990.1453 | 2027-06-25
2025-09-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements | 5772260 | 5772260 | 924762.8305 | 2025-11-30
2025-09-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 | 1259243 | 1259243 | 90048.2004 | 2025-11-30
2025-09-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 | 1117331.42 | 1117331.42 | -50372.73 | 2025-11-30
2025-09-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 67202.17 | 67202.17 | 4426.359 | 2025-11-30
2025-09-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project | 14969567 | 14969567 | 426740.6364 | 2026-12-20
2025-09-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility | 60980234 | 60980234 | 10939610.0169 | 2025-11-30
2025-09-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2742860.08 | 2742860.08 | 193176.4005 | 2026-01-31
2025-09-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 10658200 | 10658200 | 134072.8451 | 2026-11-25
2025-09-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project | 19495325 | 19495325 | 675278.7674 | 2026-06-30
2025-09-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement | 549548.83 | 549548.83 | 80123.2238 | 2025-11-30
2025-09-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 13363835 | 13363835 | 623995.8489 | 2025-12-15
2025-09-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out | 0 | 0 | 1672471.41 | 2025-11-30
2025-09-01 | 51.1156. | Rocklin Overhead 2025 | 0 | 0 | -911585.97 | 2025-12-31
2025-09-01 | 51.1157. | Rocklin Estimating 2025 | 0 | 0 | -467065.88 | 2025-12-31
2025-09-01 | 51.1158. | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 32282 | 32282 | 0 | 2025-12-31
2025-09-01 | 51.1159. | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 1199000 | 1199000 | 0 | 2026-03-15
2025-09-01 | 51.1160. | City of Galt Public Works - Industrial WWTP Expansion | 1757000 | 1757000 | 0 | 2026-09-20
2025-09-01 | 51.1161. | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | 10848599 | 10848599 | 0 | 2026-12-10
2025-09-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 372738 | 372738 | 40882.72 | 2025-09-30
2025-09-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project | 3967189.79 | 3967189.79 | 121085.88 | 2025-09-30
2025-09-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion | 1991231.37 | 1991231.37 | 233098.8 | 2025-06-25
2025-09-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2486231.58 | 2486231.58 | 246796.44 | 2025-09-30
2025-09-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 1134038.13 | 1174183 | 0 | 2025-11-30
2025-09-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out | 0 | 0 | 293353.69 | 2025-11-30
2025-09-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System | 1259398 | 1259398 | 228697.8498 | 2025-12-31
2025-09-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 12582099 | 12582099 | 1818144.1805 | 2025-11-30
2025-09-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 5899872 | 5899872 | 334431.5325 | 2025-11-30
2025-09-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 2556854 | 2556854 | 107287.034 | 2025-11-30
2025-09-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 | 13892772.64 | 13892772.64 | 535398.0622 | 2026-03-11
2025-09-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 3315820 | 3315820 | 305182.2661 | 2025-11-30
2025-09-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic | 25799094 | 25799094 | 1584639.6692 | 2025-11-12
2025-09-01 | 52.8640. | City of Dos Palos - WTP Replacement Project | 37884482 | 37884482 | 1380944.4951 | 2026-04-17
2025-09-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1868949.39 | 1868949.39 | 234321.07 | 2025-11-30
2025-09-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1641800 | 1641800 | 236791.2123 | 2025-11-12
2025-09-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 | 325522 | 325522 | 28265.783 | 2025-11-30
2025-09-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 741756 | 741756 | 77059.3067 | 2025-11-30
2025-09-01 | 52.8678. | City of Chowcilla - Well 15 & Generator Improvement Projects | 1240321 | 1240321 | 30036.299 | 2025-12-31
2025-09-01 | 52.8682. | Fresno Overhead 2025 | 0 | 0 | -764121.89 | 2025-12-31
2025-09-01 | 52.8683. | Fresno Estimating 2025 | 0 | 0 | -282753.04 | 2025-12-31
2025-09-01 | 52.8684. | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 42452.62 | 42452.62 | 2130.4037 | 2025-11-30
2025-09-01 | 52.8685. | Malaga County Water Dist. - Malaga County Water District | 426800 | 426800 | 14692.8714 | 2025-11-30
2025-09-01 | 52.8687. | California Water Service Co. - Salinas Station 205 | 831511 | 831511 | 67954.9424 | 2025-11-30
2025-09-01 | 52.8688. | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 135000 | 135000 | 16251.2618 | 2025-11-30
2025-09-01 | 52.8692. | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 60000 | 60000 | 4841.1303 | 2025-11-30
2025-09-01 | 52.8693. | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 1136503 | 1136503 | 209466.3964 | 2025-11-30
2025-09-01 | 52.8697. | City of Tulare - Industrial WWTP Dewatering Improvements Pro | 1388000 | 1388000 | 0 | 2026-07-22
2025-09-01 | 52.8700. | Lyles Services Co. - LSC GO Misc. Work | 5000 | 5000 | 334.6549 | 2025-12-31
2025-09-01 | 52.8704. | City of Visalia - Solids Handling Improvements Project | 13744000 | 13744000 | 0 | 2026-12-04
2025-09-01 | 52.8705. | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | 775000 | 775000 | 0 | 2025-12-31
2025-09-01 | 52.8707. | County of Fresno - Westside Water Tank and Pump Station | 4192700 | 4192700 | 0 | 2026-07-12
2025-09-01 | 52.8567. | City of Modesto - Grayson Well 69 | 3059858.99 | 3059858.99 | -68164.94 | 2025-08-31
2025-09-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 5095690.97 | 5095690.97 | 523187.74 | 2025-08-31
2025-09-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station | 1290184 | 1290184 | 250904.93 | 2025-09-11
2025-09-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 | 314085.77 | 314085.77 | 23359.66 | 2025-07-31
2025-09-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 | 274166.01 | 274166.01 | 6883.96 | 2025-06-30
2025-09-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install | 279244 | 279244 | 28155.8 | 2025-03-31
2025-09-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M | 29838.25 | 29838.25 | 3749.92 | 2025-06-30
2025-09-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 23957 | 23957 | 16567.28 | 2025-03-31
2025-09-01 | 52.8689. | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 16665.83 | 16665.83 | 570.25 | 2025-04-30
2025-09-01 | 52.8690. | City of Dinuba - WWTP Rake Replacement | 14151.97 | 14151.97 | 996.14 | 2025-05-02
2025-09-01 | 52.8691. | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 11302.84 | 11302.84 | 3015.02 | 2025-06-30
2025-09-01 | 52.8694. | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 43047.45 | 43047.45 | 4505.46 | 2025-06-30
2025-09-01 | 52.8695. | Lyles Services Co. - LSC GO Trash Enclosure | 13769 | 13769 | 744.63 | 2025-06-30
2025-09-01 | 52.8696. | American Paving Co. - Hot Tap for APC- Tule River Parkway | 1059.22 | 1059.22 | 171.57 | 2025-05-31
2025-09-01 | 52.8699. | City of Hanford - WWTP Repair T&M | 3001.12 | 3001.12 | 52.21 | 2025-08-31
2025-09-01 | 52.8701. | County of Fresno - 47 Water | 13433.85 | 13433.85 | 1247.66 | 2025-07-31
2025-09-01 | 52.8702. | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M | 5626.78 | 5626.78 | 901.5 | 2025-08-31
2025-09-01 | 52.8703. | County of Fresno - CSA 47 Egret Point Water Line Repair | 14402.18 | 14402.18 | 2934.16 | 2025-09-30
2025-09-01 | 52.8706. | City of Hanford - WWTP Weld Repair T&M 2 | 2868.6 | 2868.6 | 432.82 | 2025-09-30
2025-09-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 1173753.47 | 1173753.47 | 153684.1944 | 2025-11-30
2025-09-01 | 53.2005. | East Bay Overhead 2025 | 0 | 0 | -217661.3 | 2025-12-31
2025-09-01 | 53.2006. | East Bay Estimating 2026 | 0 | 0 | -300540.15 | 2025-12-31
2025-09-01 | 53.2007. | Union Sanitary Dist. - Phase 1B Secondary Clarifiers | 324530134 | 324530134 | 0 | 2031-01-31
2025-09-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 113001.33 | 113001.33 | 10966.87 | 2025-12-25
2025-09-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 55712110 | 55712110 | 10372751.5815 | 2025-11-30
2025-09-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 9447507 | 9447507 | 559707.0808 | 2025-11-30
2025-09-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 1777852 | 1777852 | 65000 | 2025-11-30
2025-09-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station | 1471328 | 1471328 | 15726.6057 | 2025-11-30
2025-09-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 907298 | 907298 | 65000 | 2025-11-30
2025-09-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 2295240 | 2295240 | 34257.1005 | 2025-12-25
2025-09-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 462022 | 462022 | 54357.5204 | 2026-02-28
2025-09-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3968669 | 3968669 | 131286.0371 | 2025-11-30
2025-09-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 8787721 | 8787721 | 520403.8382 | 2025-12-25
2025-09-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 324900 | 324900 | 13600.7132 | 2025-11-30
2025-09-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 25106976 | 25106976 | 611335.5753 | 2025-11-30
2025-09-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 4082300 | 4082300 | 42598.5925 | 2025-11-30
2025-09-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1282279 | 1282279 | 185604.6979 | 2025-11-30
2025-09-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 6881300 | 6881300 | 397688.687 | 2026-05-31
2025-09-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 1298330 | 1298330 | 189191.267 | 2025-11-30
2025-09-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1147640 | 1147640 | 20976.8839 | 2025-11-30
2025-09-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1225220 | 1225220 | 18764.2322 | 2026-05-31
2025-09-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project | 30413570 | 30413570 | 0 | 2027-01-05
2025-09-01 | 54.9371. | Bakersfield Overhead 2025 | 0 | 0 | -1000983.54 | 2025-12-31
2025-09-01 | 54.9372. | Bakersfield Estimating 2025 | 0 | 0 | -462255.27 | 2025-12-31
2025-09-01 | 54.9373. | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 1524766 | 1524766 | 0 | 2026-03-01
2025-09-01 | 54.9382. | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 131876 | 131876 | 12245.2483 | 2025-11-30
2025-09-01 | 54.9385. | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 105446 | 105446 | 3252.1017 | 2025-11-30
2025-09-01 | 54.9389. | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 299780 | 299780 | 0 | 2025-11-30
2025-09-01 | 54.9391. | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 500000 | 500000 | 12135.2992 | 2025-11-30
2025-09-01 | 54.9392. | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 223000 | 223000 | 6742.8838 | 2025-11-30
2025-09-01 | 54.9395. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 1528900 | 1528900 | 0 | 2026-02-28
2025-09-01 | 54.9396. | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | 951469 | 951469 | 0 | 2026-04-01
2025-09-01 | 54.9397. | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 3690645 | 3690645 | 0 | 2026-03-01
2025-09-01 | 54.9401. | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R | 250000 | 250000 | 7654.0794 | 2025-11-25
2025-09-01 | 54.9403. | Lost Hills Utility Dist. - WTP Improvements | 381600 | 381600 | 0 | 2026-02-18
2025-09-01 | 54.9404. | Cawelo Water Dist. - Reuse of Produced Water | 3720000 | 3720000 | 0 | 2025-12-25
2025-09-01 | 54.9405. | Semitropic Water Storage Dist. - Pump Platform Replacement Project | 942000 | 942000 | 0 | 2026-03-30
2025-09-01 | 54.9407. | Semitropic Water Storage Dist. - North Plant Emergency Repair | 40000 | 40000 | 2661.6889 | 2025-12-01
2025-09-01 | 54.9409. | Nipomo CSD Osage Emergency Waterline Repair | 20123.71 | 20123.71 | 2742.4348 | 2025-12-01
2025-09-01 | 54.9410. | SWID - Burbank St. Repair | 35000 | 35000 | 0 | 2025-12-01
2025-09-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 24160002.44 | 24160002.44 | 3104992.72 | 2025-03-01
2025-09-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements | 2472164.05 | 2472164.05 | 186096.35 | 2025-09-25
2025-09-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 223896.47 | 223896.47 | 3141.96 | 2025-07-31
2025-09-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3216240.01 | 3216240.01 | 62865.22 | 2025-08-01
2025-09-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 44560 | 44560 | 19462.75 | 2025-08-01
2025-09-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 4300 | 4300 | 2986.55 | 2025-03-31
2025-09-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 110661.47 | 110661.47 | 16178.26 | 2025-06-30
2025-09-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 427464.77 | 427464.77 | 58649.48 | 2025-06-30
2025-09-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 175884.64 | 175884.64 | 56698.53 | 2025-03-31
2025-09-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 199161.5 | 199161.5 | 75015.2 | 2025-03-31
2025-09-01 | 54.9347. | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 7100 | 7100 | 3872.3 | 2025-04-30
2025-09-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 290129 | 290129 | 92239.69 | 2025-04-30
2025-09-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 | 129965.06 | 129965.06 | 21621.38 | 2025-06-30
2025-09-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 153298.79 | 153298.79 | 16490.49 | 2025-04-30
2025-09-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 2008.42 | 2008.42 | 890.92 | 2025-03-31
2025-09-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 9571.2 | 9571.2 | 1340.37 | 2025-03-31
2025-09-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 2806.42 | 2806.42 | 991.19 | 2025-03-31
2025-09-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 1760.42 | 1760.42 | 870.76 | 2025-03-31
2025-09-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1855.92 | 1855.92 | 711.04 | 2025-03-31
2025-09-01 | 54.9361. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 108668.35 | 108668.35 | 1593.48 | 2025-05-31
2025-09-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 425035.04 | 425035.04 | 49433.8 | 2025-03-31
2025-09-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 1855.92 | 1855.92 | 1078.37 | 2025-03-31
2025-09-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 2216.42 | 2216.42 | 953.09 | 2025-03-31
2025-09-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 2540.42 | 2540.42 | 938.09 | 2025-03-31
2025-09-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 15697.91 | 15697.91 | 2044.29 | 2025-03-31
2025-09-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 1760.42 | 1760.42 | 870.78 | 2025-03-31
2025-09-01 | 54.9374. | City of Santa Maria - WWTP Trickling Filter Repairs | 32962 | 32962 | 12975.55 | 2025-06-30
2025-09-01 | 54.9375. | City of Santa Maria - WWTP Clarifier Repairs | 8232.73 | 8232.73 | 3687.25 | 2025-03-31
2025-09-01 | 54.9379. | Semitropic Water Storage Dist. - Delta System Pipe Repair | 41679.77 | 41679.77 | 5567.82 | 2025-03-31
2025-09-01 | 54.9380. | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 22446.19 | 22446.19 | 4381.47 | 2025-03-31
2025-09-01 | 54.9381. | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 58900 | 58900 | 30024.62 | 2025-04-30
2025-09-01 | 54.9383. | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 17542.44 | 17542.44 | 1782.68 | 2025-05-31
2025-09-01 | 54.9384. | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 79531.98 | 79531.98 | 9191.41 | 2025-07-31
2025-09-01 | 54.9386. | Kern Valley State Prison - Arsenic Pipe Leak Repair | 96086 | 96086 | 20324.3 | 2025-07-31
2025-09-01 | 54.9387. | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 22619.54 | 22619.54 | 3607.89 | 2025-08-31
2025-09-01 | 54.9388. | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 7454.07 | 7454.07 | 918.66 | 2025-06-30
2025-09-01 | 54.9390. | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 101491.67 | 101491.67 | 5162.18 | 2025-08-31
2025-09-01 | 54.9393. | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 31523.02 | 31523.02 | 4278.92 | 2025-06-30
2025-09-01 | 54.9394. | City of Arvin - Haven Drive Lateral Repair | 15966.99 | 15966.99 | 1927.44 | 2025-08-31
2025-09-01 | 54.9398. | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 14300 | 14300 | 6107.21 | 2025-09-30
2025-09-01 | 54.9399. | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 24775 | 24775 | 13483.41 | 2025-08-31
2025-09-01 | 54.9400. | Arvin Edison Water Storage Dist. - FFPP Core Drilling | 800.69 | 800.69 | 29.37 | 2025-07-31
2025-09-01 | 55.1090. | JV w/Webcor & Obayashi - Silverlake - LADWP | 5138788.35 | 5300000 | 1484349.2582 | 2025-11-30
2025-09-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility | 341293578.73 | 341293578.73 | 5210498 | 2027-06-01
2025-09-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6651803.53 | 6651803.53 | 250000 | 2025-11-30
2025-09-01 | 55.1200. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 | 186423681 | 195902148 | 0 | 2027-04-02
2025-09-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out | 0 | 0 | 7455309.51 | 2027-04-02
2025-09-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project | 16115717 | 16115717 | 701415.168 | 2026-08-01
2025-09-01 | 55.1204. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 | 51420607 | 51675607 | 0 | 2027-02-26
2025-09-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out | 0 | 0 | 2245865.32 | 2027-02-26
2025-09-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 41185764.34 | 41185764.34 | 4262083.8462 | 2025-11-30
2025-09-01 | 55.1233. | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 104043 | 104043 | 8428.84 | 2025-11-30
2025-09-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 5782651.52 | 5782651.52 | 255825.8763 | 2026-03-01
2025-09-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 147718400 | 147718400 | 0 | 2029-02-01
2025-09-01 | 55.1252. | Murrieta Overhead 2025 | 0 | 0 | -1467373.49 | 2025-12-31
2025-09-01 | 55.1253. | Murrieta Estimating 2025 | 0 | 0 | -397825.87 | 2025-12-31
2025-09-01 | 55.1254. | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 471896 | 471896 | 0 | 2026-05-25
2025-09-01 | 55.1255. | City of Riverside - RWQCP Emergency Repair | 1246.72 | 1246.72 | 0 | 2025-12-31
2025-09-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement | 2273682.69 | 2273682.69 | 608537.39 | 2025-05-31
2025-09-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements | 4046200 | 4046200 | 724343.64 | 2025-03-31
2025-09-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 | 34207.53 | 34207.53 | 4433.64 | 2025-09-30
2025-09-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 184557.17 | 184557.17 | 136263.23 | 2025-03-31
2025-09-01 | 55.1251. | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 322982.96 | 322982.96 | 38761.1 | 2025-05-31
2025-09-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 38144758 | 38144758 | 96384.6807 | 2027-04-01
2025-09-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 40106224.63 | 40106224.63 | 0 | 2026-03-25
2025-09-01 | 57.0005. | San Diego Overhead 2025 | 0 | 0 | -52860.36 | 2025-12-31
2025-09-01 | 57.0006. | San Diego Estimating 2025 | 0 | 0 | -4432.92 | 2025-12-31
2025-09-01 | 57.0007. | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | 153858.36 | 153858.36 | -32235 | 2025-11-30
2025-09-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 22085905 | 22085905 | 465999.4409 | 2026-06-01
2025-09-01 | 58.0004. | Los Angeles Overhead 2025 | 0 | 0 | -100764.69 | 2025-12-31
2025-09-01 | 58.0005. | Los Angeles Estimating 2025 | 0 | 0 | -14225.4 | 2025-12-31
2025-09-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 311191 | 311191 | 74267.3632 | 2025-12-31
2025-09-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 373425 | 373425 | 75759.3305 | 2025-12-31
2025-09-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 135000 | 135000 | 50249.6318 | 2026-03-31
2025-09-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 19314 | 19314 | 23.4617 | 2025-12-31
2025-09-01 | 56.1010. | Placer County Water Agency -PCWA Time & Material Contract | 49250 | 49250 | 15061.87 | 2026-12-31
2025-09-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 160000 | 160000 | 28528.3246 | 2026-03-31
2025-09-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 73222 | 73222 | 15849.2013 | 2025-12-31
2025-09-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 145000 | 145000 | 57981.1883 | 2026-03-31
2025-09-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 184435 | 184435 | 37193.0999 | 2025-12-31
2025-09-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 85000 | 85000 | 1448.6283 | 2026-03-31
2025-09-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 276000 | 276000 | 26321.4083 | 2026-03-31
2025-09-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 22876 | 22876 | 8081.45 | 2025-12-31
2025-09-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 95000 | 95000 | 3886.9248 | 2026-03-31
2025-09-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 375000 | 375000 | 30672.6263 | 2025-12-31
2025-09-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services | 277565 | 277565 | 45692.664 | 2026-03-31
2025-09-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 325000 | 325000 | 4838.3318 | 2026-03-31
2025-09-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 77120 | 77120 | -405.8 | 2025-12-31
2025-09-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 2377335 | 2377335 | 118245.6883 | 2026-12-31
2025-09-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 200000 | 200000 | 56910.96 | 2025-12-31
2025-09-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 308725 | 308725 | 45879.0452 | 2026-03-31
2025-09-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 3780000 | 3780000 | 106422.7781 | 2026-12-31
2025-09-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 136535.19 | 136535.19 | 24583.1466 | 2025-12-31
2025-09-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 120891 | 120891 | 19688.6459 | 2026-03-31
2025-09-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 380000 | 380000 | 41427.4327 | 2026-06-30
2025-09-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 400000 | 400000 | 19728.6893 | 2026-09-30
2025-09-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 108000 | 108000 | 8072.9535 | 2026-06-30
2025-09-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 226401 | 226401 | 16118.6685 | 2025-12-31
2025-09-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 595000 | 595000 | 85990.7178 | 2025-12-31
2025-09-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 478000 | 478000 | 0 | 2026-09-30
2025-09-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 48420 | 48420 | 6227.7951 | 2026-03-31
2025-09-01 | 56.1073. | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 122210 | 122210 | 6715.4769 | 2026-03-31
2025-09-01 | 56.1075. | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 950000 | 950000 | 0 | 2026-06-30
2025-09-01 | 56.1077. | System Integration Overhead 2025 | 0 | 0 | -4379101.41 | 2025-12-25
2025-09-01 | 56.1078. | City of Napa - On-Call Control Systems Integrator Services | 19627 | 19627 | 6677.56 | 2026-03-31
2025-09-01 | 56.1081. | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 179690 | 179690 | 10380.474 | 2025-12-31
2025-09-01 | 56.1083. | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 717010 | 717010 | 0 | 2026-06-30
2025-09-01 | 56.1085. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 80000 | 80000 | 0 | 2026-06-30
2025-09-01 | 56.1086. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 376000 | 376000 | 0 | 2026-06-30
2025-09-01 | 56.1087. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 49369 | 49369 | 5767.3948 | 2025-12-31
2025-09-01 | 56.1088. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 127235 | 127235 | 0 | 2026-03-31
2025-09-01 | 56.1002. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 185000 | 185000 | 70514.18 | 2025-04-30
2025-09-01 | 56.1008. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 55000 | 55000 | 24448.08 | 2025-03-31
2025-09-01 | 56.1010.01 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 9569 | 9569 | 2471.9 | 2025-03-31
2025-09-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 150064.25 | 150064.25 | 41175.01 | 2025-09-09
2025-09-01 | 56.1021. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 244760 | 244760 | 128007.48 | 2025-06-30
2025-09-01 | 56.1022. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 0 | 0 | 0 | 2024-12-31
2025-09-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 220390 | 220390 | 69885.27 | 2025-09-30
2025-09-01 | 56.1030. | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 612078.64 | 612078.64 | 0 | 2025-09-30
2025-09-01 | 56.1041. | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 20016.78 | 20016.78 | 0 | 2025-07-31
2025-09-01 | 56.1052. | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 8887 | 8887 | 2486.06 | 2025-04-30
2025-09-01 | 56.1053. | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 35000 | 35000 | 15035.22 | 2025-03-31
2025-09-01 | 56.1054. | W.M. Lyles - Riverside Public Works - Digester 5 Rehab | 37648.03 | 37648.03 | 0 | 2025-09-30
2025-09-01 | 56.1056. | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 98280.63 | 98280.63 | 0 | 2025-07-31
2025-09-01 | 56.1057. | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 0 | 0 | 0 | 2025-04-30
2025-09-01 | 56.1061. | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 11269 | 11269 | 5686.34 | 2025-03-31
2025-09-01 | 56.1062. | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 409988.07 | 409988.07 | 0 | 2025-07-31
2025-09-01 | 56.1064. | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 435153 | 435153 | 233081.6 | 2025-05-31
2025-09-01 | 56.1069. | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 2525 | 2525 | -1296.46 | 2025-06-30
2025-09-01 | 56.1071. | AIC - California American Water - Luzern Well Treatment Design | 34000 | 34000 | 30403.44 | 2025-06-30
2025-09-01 | 56.1074. | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 12650 | 12650 | 2008.14 | 2025-03-31
2025-09-01 | 56.1076. | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 19200 | 19200 | 7622.23 | 2025-03-31
2025-09-01 | 56.1079. | AIC - UC Davis - WWTP Annual Instrument Calibrations | 29235.63 | 29235.63 | 0 | 2025-07-31
2025-09-01 | 56.1080. | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 359469 | 359469 | 0 | 2025-07-31
2025-09-01 | 56.1082. | City of Clovis - Pump Station E New Pump 5 VFD Startup | 19800 | 19800 | -673.42 | 2025-09-09
2025-09-01 | 56.1084. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 8000 | 8000 | 3771.87 | 2025-09-09
2025-09-01 | 56.1102. | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 19815.94 | 19815.94 | 0 | 2025-07-31
2025-09-01 | 56.1103. | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 55855.24 | 55855.24 | 0 | 2025-07-31
2025-09-01 | 56.1104. | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 9500.31 | 9500.31 | 0 | 2025-07-31
2025-09-01 | 56.1105. | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 30502.53 | 30502.53 | 0 | 2025-07-31
2025-09-01 | 56.1106. | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 54742.18 | 54742.18 | 0 | 2025-07-31
2025-09-01 | 56.1107. | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 3429.06 | 3429.06 | 0 | 2025-07-31
2025-09-01 | 56.1108. | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 20729.84 | 20729.84 | 0 | 2025-07-31
2025-09-01 | 56.1109. | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 14772.26 | 14772.26 | 0 | 2025-07-31
2025-09-01 | 56.1110. | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 4596.42 | 4596.42 | 0 | 2025-07-31
2025-09-01 | 56.1111. | AIC - RMCSD - VEEAM SFTWR | 17210.01 | 17210.01 | 0 | 2025-07-31
2025-09-01 | 56.1112. | System Integration Division Estimating 2025 | 27241.58 | 27241.58 | 0 | 2025-07-31
2025-09-01 | 56.1113. | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 49233.44 | 49233.44 | 0 | 2025-07-31
2025-09-01 | 56.1115. | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 5895.77 | 5895.77 | 0 | 2025-04-30
2025-09-01 | 56.1119. | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 22184.06 | 22184.06 | 0 | 2025-07-31
2025-09-01 | 56.1120. | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 1045.63 | 1045.63 | 0 | 2025-07-31
2025-09-01 | 56.1121. | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 22824.38 | 22824.38 | 0 | 2025-07-31
2025-09-01 | 56.1122. | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 6289.38 | 6289.38 | 0 | 2025-07-31
2025-09-01 | 56.1123. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 3772.82 | 3772.82 | 0 | 2025-07-31
2025-09-01 | 56.1124. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 28950 | 28950 | 0 | 2025-07-31
2025-09-01 | 56.1125. | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 14229.38 | 14229.38 | 0 | 2025-07-31
2025-09-01 | 56.1126. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 9526.88 | 9526.88 | 0 | 2025-07-31
2025-09-01 | 56.1127. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 6519.07 | 6519.07 | 0 | 2025-07-31
2025-09-01 | 56.1128. | San Jose Water - Williams Back ATS Replacement | 4793.13 | 4793.13 | 0 | 2025-07-31
2025-09-01 | 56.1129. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 133.75 | 133.75 | 0 | 2025-07-31
2025-09-01 | 56.1130. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 0 |  | -267.5 | 2025-07-31
2025-09-01 | 56.1131. | San Jose Water - PLC System Assessment | 2388.75 | 2388.75 | 0 | 2025-07-31
2025-09-01 | 56.1132. | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 585 | 585 | 0 | 2025-07-31
2025-09-01 | 56.1133. | City of Brentwood - Brentwood, City of - On-Call Agreement | 2827.5 | 2827.5 | 0 | 2025-07-31
2025-09-01 | 56.1134. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 965.51 | 965.51 | 0 | 2025-07-31
2025-09-01 | 56.1135. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 112.5 | 112.5 | 0 | 2025-07-31
2025-09-01 | 56.1141. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 2827.5 | 2827.5 | 0 | 2025-07-31
2025-09-01 | 50.0541. | W.M. Lyles Co. - General Overhead | 0 | 0 | -2536129.82 | 2025-07-31
2025-09-01 | 50.0542. | W.M. Lyles Co. - General Estimating | 0 | 0 | -77816.23 | 2025-12-31
2025-09-01 | 50.0543. | American Paving | 7051.01 | 7051.01 | 0 | 2025-12-31
2025-09-01 | 50.0544. | Lyles Services Co. | 5977.43 | 5977.43 | 0 | 2025-12-31
2025-09-01 | 50.0545. | New England Sheet Metal and Mechanical Co. | 2096.11 | 2096.11 | 0 | 2025-12-31
2025-09-01 | 50.0546. | Lyles Utility Construction, LLC | 11256.72 | 11256.72 | 788.66 | 2025-12-31
2025-09-01 | 50.0551. | Advanced Integration & Controls | 1002.38 | 1002.38 | 0 | 2025-12-31

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-09-01 | 51.1108. | JV w/AECOM - Stockton - RWCF Phase 2A/2B | 93232905.07 | 93300729
2025-09-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) | -3462979.66 | -3530000
2025-09-01 | 51.1129. | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications | 114413057 | 114413057
2025-09-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements | 4786125 | 4786125
2025-09-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 | 1145603 | 1145603
2025-09-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 | 1167704.15 | 1167704.15
2025-09-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 62359.17 | 62359.17
2025-09-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project | 14116123 | 14116123
2025-09-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility | 47480234 | 47480234
2025-09-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2547860.08 | 2547860.08
2025-09-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 10061352 | 10061352
2025-09-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project | 18283140 | 18283140
2025-09-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement | 442548.83 | 442548.83
2025-09-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 12642378 | 12642378
2025-09-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out | -1800000 | -1800000
2025-09-01 | 51.1156. | Rocklin Overhead 2025 | 911585.97 | 911585.97
2025-09-01 | 51.1157. | Rocklin Estimating 2025 | 467065.88 | 467065.88
2025-09-01 | 51.1158. | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 32282 | 32282
2025-09-01 | 51.1159. | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 1079240 | 1079240
2025-09-01 | 51.1160. | City of Galt Public Works - Industrial WWTP Expansion | 1669787 | 1669787
2025-09-01 | 51.1161. | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | 10261252 | 10261252
2025-09-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 331855.28 | 331855.28
2025-09-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project | 3846103.91 | 3846103.91
2025-09-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion | 1758132.57 | 1758132.57
2025-09-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2239435.14 | 2239435.14
2025-09-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 1152291.77 | 1174183
2025-09-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out | -293353.69 | -293392.63
2025-09-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System | 1029398 | 1029398
2025-09-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 10702099 | 10702099
2025-09-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 5509872 | 5509872
2025-09-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 2446854 | 2446854
2025-09-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 | 13190772.64 | 13190772.64
2025-09-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 3005820 | 3005820
2025-09-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic | 24149094 | 24149094
2025-09-01 | 52.8640. | City of Dos Palos - WTP Replacement Project | 36011159 | 36011159
2025-09-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1634628.32 | 1634628.32
2025-09-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1381800 | 1381800
2025-09-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 | 295722 | 295722
2025-09-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 655756 | 655756
2025-09-01 | 52.8678. | City of Chowcilla - Well 15 & Generator Improvement Projects | 1162321 | 1162321
2025-09-01 | 52.8682. | Fresno Overhead 2025 | 764121.89 | 764121.89
2025-09-01 | 52.8683. | Fresno Estimating 2025 | 282753.04 | 282753.04
2025-09-01 | 52.8684. | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 35952.62 | 35952.62
2025-09-01 | 52.8685. | Malaga County Water Dist. - Malaga County Water District | 402983 | 402983
2025-09-01 | 52.8687. | California Water Service Co. - Salinas Station 205 | 750089 | 750089
2025-09-01 | 52.8688. | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 118708 | 118708
2025-09-01 | 52.8692. | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 54500 | 54500
2025-09-01 | 52.8693. | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 836503 | 836503
2025-09-01 | 52.8697. | City of Tulare - Industrial WWTP Dewatering Improvements Pro | 1325482 | 1325482
2025-09-01 | 52.8700. | Lyles Services Co. - LSC GO Misc. Work | 4650 | 4650
2025-09-01 | 52.8704. | City of Visalia - Solids Handling Improvements Project | 13491127 | 13491127
2025-09-01 | 52.8705. | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | 719260 | 719260
2025-09-01 | 52.8707. | County of Fresno - Westside Water Tank and Pump Station | 3961077 | 3961077
2025-09-01 | 52.8567. | City of Modesto - Grayson Well 69 | 3128023.93 | 3128023.93
2025-09-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 4572503.23 | 4572503.23
2025-09-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station | 1039279.07 | 1039279.07
2025-09-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 | 290726.11 | 290726.11
2025-09-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 | 267282.05 | 267282.05
2025-09-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install | 251088.2 | 251088.2
2025-09-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M | 26088.33 | 26088.33
2025-09-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 7389.72 | 7389.72
2025-09-01 | 52.8689. | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 16095.58 | 16095.58
2025-09-01 | 52.8690. | City of Dinuba - WWTP Rake Replacement | 13155.83 | 13155.83
2025-09-01 | 52.8691. | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 8287.82 | 8287.82
2025-09-01 | 52.8694. | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 38541.99 | 38541.99
2025-09-01 | 52.8695. | Lyles Services Co. - LSC GO Trash Enclosure | 13024.37 | 13024.37
2025-09-01 | 52.8696. | American Paving Co. - Hot Tap for APC- Tule River Parkway | 887.65 | 887.65
2025-09-01 | 52.8699. | City of Hanford - WWTP Repair T&M | 2948.91 | 2948.91
2025-09-01 | 52.8701. | County of Fresno - 47 Water | 12186.19 | 12186.19
2025-09-01 | 52.8702. | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M | 4725.28 | 4725.28
2025-09-01 | 52.8703. | County of Fresno - CSA 47 Egret Point Water Line Repair | 11468.02 | 11468.02
2025-09-01 | 52.8706. | City of Hanford - WWTP Weld Repair T&M 2 | 2435.78 | 2435.78
2025-09-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 1011723.47 | 1011723.47
2025-09-01 | 53.2005. | East Bay Overhead 2025 | 217661.3 | 217661.3
2025-09-01 | 53.2006. | East Bay Estimating 2026 | 300540.15 | 300540.15
2025-09-01 | 53.2007. | Union Sanitary Dist. - Phase 1B Secondary Clarifiers | 291530134 | 291530134
2025-09-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 102034.33 | 102034.33
2025-09-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 45337110 | 45337110
2025-09-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 8837507 | 8837507
2025-09-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 1712852 | 1712852
2025-09-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station | 1426328 | 1426328
2025-09-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 842298 | 842298
2025-09-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 2260991 | 2260991
2025-09-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 387022 | 387022
2025-09-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3813669 | 3813669
2025-09-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 7957721 | 7957721
2025-09-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 306900 | 306900
2025-09-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 23316976 | 23316976
2025-09-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 3922300 | 3922300
2025-09-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1096279 | 1096279
2025-09-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 6056300 | 6056300
2025-09-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 913330 | 913330
2025-09-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1126640 | 1126640
2025-09-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1162246 | 1162246
2025-09-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project | 28042727 | 28042727
2025-09-01 | 54.9371. | Bakersfield Overhead 2025 | 1000983.54 | 1000983.54
2025-09-01 | 54.9372. | Bakersfield Estimating 2025 | 462255.27 | 462255.27
2025-09-01 | 54.9373. | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 1393326 | 1393326
2025-09-01 | 54.9382. | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 111876 | 111876
2025-09-01 | 54.9385. | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 95446 | 95446
2025-09-01 | 54.9389. | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 329780 | 329780
2025-09-01 | 54.9391. | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 484000 | 484000
2025-09-01 | 54.9392. | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 216000 | 216000
2025-09-01 | 54.9395. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 1388900 | 1388900
2025-09-01 | 54.9396. | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | 941923 | 941923
2025-09-01 | 54.9397. | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 3390645 | 3390645
2025-09-01 | 54.9401. | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R | 241750 | 241750
2025-09-01 | 54.9403. | Lost Hills Utility Dist. - WTP Improvements | 338101 | 338101
2025-09-01 | 54.9404. | Cawelo Water Dist. - Reuse of Produced Water | 3585392 | 3585392
2025-09-01 | 54.9405. | Semitropic Water Storage Dist. - Pump Platform Replacement Project | 822000 | 822000
2025-09-01 | 54.9407. | Semitropic Water Storage Dist. - North Plant Emergency Repair | 36000 | 36000
2025-09-01 | 54.9409. | Nipomo CSD Osage Emergency Waterline Repair | 17181.71 | 17181.71
2025-09-01 | 54.9410. | SWID - Burbank St. Repair | 31500 | 31500
2025-09-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 21055009.72 | 21055009.72
2025-09-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements | 2286067.7 | 2286067.7
2025-09-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 220754.51 | 220754.51
2025-09-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3153374.79 | 3153374.79
2025-09-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 25097.25 | 25097.25
2025-09-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 1313.45 | 1313.45
2025-09-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 94483.21 | 94483.21
2025-09-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 368815.29 | 368815.29
2025-09-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 119186.11 | 119186.11
2025-09-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 124146.3 | 124146.3
2025-09-01 | 54.9347. | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 3227.7 | 3227.7
2025-09-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 197889.31 | 197889.31
2025-09-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 | 108343.68 | 108343.68
2025-09-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 136808.3 | 136808.3
2025-09-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 1117.5 | 1117.5
2025-09-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 8230.83 | 8230.83
2025-09-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 1815.23 | 1815.23
2025-09-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 889.66 | 889.66
2025-09-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1144.88 | 1144.88
2025-09-01 | 54.9361. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 107074.87 | 107074.87
2025-09-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 375601.24 | 375601.24
2025-09-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 777.55 | 777.55
2025-09-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 1263.33 | 1263.33
2025-09-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 1602.33 | 1602.33
2025-09-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 13653.62 | 13653.62
2025-09-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 889.64 | 889.64
2025-09-01 | 54.9374. | City of Santa Maria - WWTP Trickling Filter Repairs | 19986.45 | 19986.45
2025-09-01 | 54.9375. | City of Santa Maria - WWTP Clarifier Repairs | 4545.48 | 4545.48
2025-09-01 | 54.9379. | Semitropic Water Storage Dist. - Delta System Pipe Repair | 36111.95 | 36111.95
2025-09-01 | 54.9380. | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 18064.72 | 18064.72
2025-09-01 | 54.9381. | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 28875.38 | 28875.38
2025-09-01 | 54.9383. | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 15759.76 | 15759.76
2025-09-01 | 54.9384. | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 70340.57 | 70340.57
2025-09-01 | 54.9386. | Kern Valley State Prison - Arsenic Pipe Leak Repair | 75761.7 | 75761.7
2025-09-01 | 54.9387. | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 19011.65 | 19011.65
2025-09-01 | 54.9388. | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 6535.41 | 6535.41
2025-09-01 | 54.9390. | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 96329.49 | 96329.49
2025-09-01 | 54.9393. | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 27244.1 | 27244.1
2025-09-01 | 54.9394. | City of Arvin - Haven Drive Lateral Repair | 14039.55 | 14039.55
2025-09-01 | 54.9398. | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 8192.79 | 8192.79
2025-09-01 | 54.9399. | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 11291.59 | 11291.59
2025-09-01 | 54.9400. | Arvin Edison Water Storage Dist. - FFPP Core Drilling | 771.32 | 771.32
2025-09-01 | 55.1090. | JV w/Webcor & Obayashi - Silverlake - LADWP | 3770959.47 | 3803027.8
2025-09-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility | 336083080.73 | 336083080.73
2025-09-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6401803.53 | 6401803.53
2025-09-01 | 55.1200. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 | 186416226.63 | 195902148
2025-09-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out | -7455309.51 | -8100000
2025-09-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project | 14940308 | 14940308
2025-09-01 | 55.1204. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 | 51420970.83 | 51675607
2025-09-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out | -2245865.32 | -2500000
2025-09-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 36835764.34 | 36835764.34
2025-09-01 | 55.1233. | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 95614 | 95614
2025-09-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 5082651.52 | 5082651.52
2025-09-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 139897192 | 139897192
2025-09-01 | 55.1252. | Murrieta Overhead 2025 | 1467373.49 | 1467373.49
2025-09-01 | 55.1253. | Murrieta Estimating 2025 | 397825.87 | 397825.87
2025-09-01 | 55.1254. | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 471896 | 471896
2025-09-01 | 55.1255. | City of Riverside - RWQCP Emergency Repair | 1246.72 | 1246.72
2025-09-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement | 1665145.3 | 1665145.3
2025-09-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements | 3321856.36 | 3321856.36
2025-09-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 | 29773.89 | 29773.89
2025-09-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 48293.94 | 48293.94
2025-09-01 | 55.1251. | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 284221.86 | 284221.86
2025-09-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 35819403 | 35819403
2025-09-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 37896367.63 | 37896367.63
2025-09-01 | 57.0005. | San Diego Overhead 2025 | 52860.36 | 52860.36
2025-09-01 | 57.0006. | San Diego Estimating 2025 | 4432.92 | 4432.92
2025-09-01 | 57.0007. | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | 186093.36 | 186093.36
2025-09-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 20782993 | 20782993
2025-09-01 | 58.0004. | Los Angeles Overhead 2025 | 100764.69 | 100764.69
2025-09-01 | 58.0005. | Los Angeles Estimating 2025 | 14225.4 | 14225.4
2025-09-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 227317 | 227317
2025-09-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 280455 | 280455
2025-09-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 68025 | 68025
2025-09-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 19290 | 19290
2025-09-01 | 56.1010. | Placer County Water Agency -PCWA Time & Material Contract | 34188.13 | 34188.13
2025-09-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 130544 | 130544
2025-09-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 54275 | 54275
2025-09-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 52159 | 52159
2025-09-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 144452 | 144452
2025-09-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 77828 | 77828
2025-09-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 212166 | 212166
2025-09-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 14794.55 | 14794.55
2025-09-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 90115 | 90115
2025-09-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 341174 | 341174
2025-09-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services | 218288 | 218288
2025-09-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 308573 | 308573
2025-09-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 77525.8 | 77525.8
2025-09-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 2126804 | 2126804
2025-09-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 140000 | 140000
2025-09-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 253873 | 253873
2025-09-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 3341376 | 3341376
2025-09-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 106190.19 | 106190.19
2025-09-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 95477 | 95477
2025-09-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 309373 | 309373
2025-09-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 315257 | 315257
2025-09-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 95468 | 95468
2025-09-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 208839.38 | 208839.38
2025-09-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 457763 | 457763
2025-09-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 411520 | 411520
2025-09-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 39365 | 39365
2025-09-01 | 56.1073. | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 102413 | 102413
2025-09-01 | 56.1075. | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 773000 | 773000
2025-09-01 | 56.1077. | System Integration Overhead 2025 | 4379101.41 | 4379101.41
2025-09-01 | 56.1078. | City of Napa - On-Call Control Systems Integrator Services | 12949.44 | 12949.44
2025-09-01 | 56.1081. | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 167611 | 167611
2025-09-01 | 56.1083. | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 652967 | 652967
2025-09-01 | 56.1085. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 66810 | 66810
2025-09-01 | 56.1086. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 296403 | 296403
2025-09-01 | 56.1087. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 43026 | 43026
2025-09-01 | 56.1088. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 96282 | 96282
2025-09-01 | 56.1002. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 114485.82 | 114485.82
2025-09-01 | 56.1008. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 30551.92 | 30551.92
2025-09-01 | 56.1010.01 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 7097.1 | 7097.1
2025-09-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 108889.24 | 108889.24
2025-09-01 | 56.1021. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 116752.52 | 116752.52
2025-09-01 | 56.1022. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 0 | 0
2025-09-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 150504.73 | 150504.73
2025-09-01 | 56.1030. | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 612078.64 | 612078.64
2025-09-01 | 56.1041. | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 20016.78 | 20016.78
2025-09-01 | 56.1052. | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 6400.94 | 6400.94
2025-09-01 | 56.1053. | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 19964.78 | 19964.78
2025-09-01 | 56.1054. | W.M. Lyles - Riverside Public Works - Digester 5 Rehab | 37648.03 | 37648.03
2025-09-01 | 56.1056. | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 98280.63 | 98280.63
2025-09-01 | 56.1057. | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 0 | 0
2025-09-01 | 56.1061. | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 5582.66 | 5582.66
2025-09-01 | 56.1062. | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 409988.07 | 409988.07
2025-09-01 | 56.1064. | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 202071.4 | 202071.4
2025-09-01 | 56.1069. | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 3821.46 | 3821.46
2025-09-01 | 56.1071. | AIC - California American Water - Luzern Well Treatment Design | 3596.56 | 3596.56
2025-09-01 | 56.1074. | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 10641.86 | 10641.86
2025-09-01 | 56.1076. | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 11577.77 | 11577.77
2025-09-01 | 56.1079. | AIC - UC Davis - WWTP Annual Instrument Calibrations | 29235.63 | 29235.63
2025-09-01 | 56.1080. | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 359469 | 359469
2025-09-01 | 56.1082. | City of Clovis - Pump Station E New Pump 5 VFD Startup | 20473.42 | 20473.42
2025-09-01 | 56.1084. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 4228.13 | 4228.13
2025-09-01 | 56.1102. | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 19815.94 | 19815.94
2025-09-01 | 56.1103. | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 55855.24 | 55855.24
2025-09-01 | 56.1104. | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 9500.31 | 9500.31
2025-09-01 | 56.1105. | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 30502.53 | 30502.53
2025-09-01 | 56.1106. | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 54742.18 | 54742.18
2025-09-01 | 56.1107. | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 3429.06 | 3429.06
2025-09-01 | 56.1108. | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 20729.84 | 20729.84
2025-09-01 | 56.1109. | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 14772.26 | 14772.26
2025-09-01 | 56.1110. | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 4596.42 | 4596.42
2025-09-01 | 56.1111. | AIC - RMCSD - VEEAM SFTWR | 17210.01 | 17210.01
2025-09-01 | 56.1112. | System Integration Division Estimating 2025 | 27241.58 | 27241.58
2025-09-01 | 56.1113. | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 49233.44 | 49233.44
2025-09-01 | 56.1115. | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 5895.77 | 5895.77
2025-09-01 | 56.1119. | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 22184.06 | 22184.06
2025-09-01 | 56.1120. | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 1045.63 | 1045.63
2025-09-01 | 56.1121. | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 22824.38 | 22824.38
2025-09-01 | 56.1122. | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 6289.38 | 6289.38
2025-09-01 | 56.1123. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 3772.82 | 3772.82
2025-09-01 | 56.1124. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 28950 | 28950
2025-09-01 | 56.1125. | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 14229.38 | 14229.38
2025-09-01 | 56.1126. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 9526.88 | 9526.88
2025-09-01 | 56.1127. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 6519.07 | 6519.07
2025-09-01 | 56.1128. | San Jose Water - Williams Back ATS Replacement | 4793.13 | 4793.13
2025-09-01 | 56.1129. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 133.75 | 133.75
2025-09-01 | 56.1130. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 267.5 | 267.5
2025-09-01 | 56.1131. | San Jose Water - PLC System Assessment | 2388.75 | 2388.75
2025-09-01 | 56.1132. | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 585 | 585
2025-09-01 | 56.1133. | City of Brentwood - Brentwood, City of - On-Call Agreement | 2827.5 | 2827.5
2025-09-01 | 56.1134. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 965.51 | 965.51
2025-09-01 | 56.1135. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 112.5 | 112.5
2025-09-01 | 56.1141. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 2827.5 | 2827.5
2025-09-01 | 50.0541. | W.M. Lyles Co. - General Overhead | 2536129.82 | 2536129.82
2025-09-01 | 50.0542. | W.M. Lyles Co. - General Estimating | 77816.23 | 77816.23
2025-09-01 | 50.0543. | American Paving | 7051.01 | 7051.01
2025-09-01 | 50.0544. | Lyles Services Co. | 5977.43 | 5977.43
2025-09-01 | 50.0545. | New England Sheet Metal and Mechanical Co. | 2096.11 | 2096.11
2025-09-01 | 50.0546. | Lyles Utility Construction, LLC | 10468.06 | 10468.06
2025-09-01 | 50.0551. | Advanced Integration & Controls | 1002.38 | 1002.38