## GAAP Columns
Col Letter | Column Header Name | Data Source | Formula or Logic | Editable? | If Edited, What Happens? | Known Issue? | Nicole's Notes | Status
A | Job Number | Vista | bJCJM.Contract (RTRIM) | No |  |  |  | Verified
B | Job Description | Vista | bJCCM.Description | No |  |  |  | Verified
C | Project Manager | Vista | bJCMP.Name via bJCJM.ProjectMgr | No |  |  |  | Verified
D | Exclude All (UI Toggle) | UI/System | COLExAll — narrow column, collapses/expands all division grouping rows | No | Do not use for data — UI control only |  |  | System/UI
E | Current Contract Amount | Calculated | bJCCM.OrigContractAmt + SUM(bJCID.ContractAmt WHERE JCTransType='CO', status=Interfaced) | No |  | Comes from JC in Vista - bJCCM. Approved COs only (not PCOs). |  | Verified
F | PM Projected Revenue | Vista | bJCCM.ContractAmt (if no JCOR override), else bJCOR projected value | No | This is the PNP baseline before any overrides. | When no approved COs, use bJCCM.ContractAmt; otherwise use bJCOR projected value. |  | Verified
G | Close Flag | Approval | COLClose — 'C' when user marks WIP entry closed for this cycle | Yes | Phase 2: closes the WIP row for this cycle |  |  | Phase 2
H | Op's Done | Approval | COLDone — 'Y' when Ops / Division Manager approves | Yes | Phase 2: Ops approval flag |  |  | Phase 2
I | GAAP Done | Approval | COLGAAPDone — 'Y' when GAAP/Accounting approves | Yes | Phase 2: GAAP approval flag (separate from Ops Done) |  |  | Phase 2
J | GAAP Override Revenue Projection | Override (WipDb) | PM/DM/President tiered override of projected revenue | Yes | Bold = Plugged ('Y'). Stored to LCGWIPDetailGAAP. Delta vs PNP revenue is shown. | Tiered override: PM enters first, DM reviews, President can override. Phase 2. |  | Phase 2
K | GAAP Override Revenue Notes (hidden) | Override (WipDb) | Full notes text for override rev — hidden system column | No | System column, not visible to user |  |  | Hidden/System
L | GAAP Override Revenue Notes Display | Override (WipDb) | COLOvrRevProjNotes2 — shortened/display version of override notes | Yes | Stored to LCGWIPDetailGAAP |  |  | Phase 2
M | PM Projected Cost | Vista | SUM(bJCCD.ProjCost) WHERE JCTransType=PF AND CostType=99 | No |  | PNP Projected Cost is bJCCD.ProjCost WHERE JCTransType=PF. Also check bJCOR for overrides. |  | Verified
N | GAAP Override Cost Projection | Override (WipDb) | PM/DM/President override of projected cost | Yes | Bold = Plugged ('Y'). Stored to LCGWIPDetailGAAP. |  |  | Phase 2
O | GAAP Override Cost Notes (hidden) | Override (WipDb) | Full notes text — hidden system column | No | System column, not visible to user |  |  | Hidden/System
P | GAAP Override Cost Notes Display | Override (WipDb) | COLOvrCostProjNotes2 — shortened/display version of cost override notes | Yes | Stored to LCGWIPDetailGAAP |  |  | Phase 2
Q | Projected Profit | Calculated | Override Rev (J if plugged, else F) − Override Cost (N if plugged, else M) | No |  |  |  | Needs Verification
R | Prior Projected Profit | Stored Value | MUST come from stored March WIP baseline — NOT recalculated. Annual starting projection. | No |  | ISSUE: Shows $0 for 51.1151, should be $596,848. Formula uses 10% calc instead of stored March WIP plug. Most persistent bug — since 2015. Ask Nicole: is it always the March baseline? |  | Needs Fix
S | Change In Projected Profit | Calculated | Q (Projected Profit) − R (Prior Projected Profit) | No |  |  |  | Needs Verification
T | Completion Date | Override | User-entered expected completion date. Maps to JCCM.ProjCloseDate or UD table. | Yes | Stored to LCGWIPDetail | JCCM.ProjCloseDate exists — check if PNP/SMS already use this. UD tables may exist. |  | Phase 2
U | Spacer (COLSP1) | UI/System | Visual section divider between 'Job at Completion' and 'Job to Date' groups | No | Not a data column |  |  | System/UI
V | JTD % Complete | Calculated | JTD Cost (X) / Override Projected Cost (N if plugged, else M). Null-safe (avoids /0). | No |  | Projected Cost should pull from bJCOR if override exists. |  | Needs Verification
W | JTD Earned Revenue | Calculated | If %Complete (V) < 10%: EarnedRev = JTD Cost. Else: Override Rev × %Complete. GAAP 10% threshold. | No |  | ISSUE: Shows $695,927 for 51.1151, should be $656,956 (=cost) — job is <10% complete. Fixing this cascades to fix AD, AE, AF, AH, AI, AJ, AL, AQ, AR. |  | Needs Fix
X | JTD Cost | Vista | SUM(bJCCD.ActualCost). PR/EM records → use ActualDate; AP and others → use PostedDate. Filter by batch month. | No |  | Use batch month as the primary date driver. Dig into Batch Date vs Actual Date vs Posted Date cascading logic. |  | Verified
Y | JTD Profit | Calculated | JTD Earned Revenue (W) − JTD Cost (X) | No |  |  |  | Needs Verification
Z | JTD Prior Profit | Stored Value | Prior month's JTD Profit — stored in WipDb history table | No | From WipDb history; Phase 2 replaces with Vista UD table |  |  | Phase 2
AA | JTD Change In Profit | Calculated | JTD Profit (Y) − JTD Prior Profit (Z) | No |  |  |  | Needs Verification
AB | Spacer (COLSP2) | UI/System | Visual section divider between 'Job to Date' and 'All Prior Years' groups | No | Not a data column |  |  | System/UI
AC | Previous Yr % Complete | Calculated | PYCost / Prior Year GAAP Proj Cost. PYCost = JTD Cost (X) − Current Yr Cost (AI). | No |  |  |  | Needs Verification
AD | Previous Yr Revenue | Calculated | Prior Year GAAP Projected Rev × (PYCost / Prior Year GAAP Projected Cost) | No |  | ISSUE: Shows $198,246 for 51.1151, should be $187,144. Cascades from Col W earned rev fix. |  | Needs Fix
AE | Previous Yr Cost | Calculated | JTD Cost (X) − Current Year Cost (AI). Prior years' portion of total cost. | No |  |  |  | Needs Verification
AF | Previous Yr Calculated Profit | Calculated | Previous Yr Revenue (AD) − Previous Yr Cost (AE) | No |  | ISSUE: Shows $11,102 for 51.1151, should be $0. Cascades from Col W. |  | Needs Fix
AG | Spacer (COLSP3) | UI/System | Visual section divider between 'All Prior Years' and 'Current Year' groups | No | Not a data column |  |  | System/UI
AH | Current Yr Revenue | Calculated | Earned Rev formula applied to current-year cost only (CY cost / Proj Cost × Proj Rev). | No |  | ISSUE: Shows $497,682 for 51.1151, should be $469,812. Cascades from Col W. |  | Needs Fix
AI | Current Yr Cost | Vista | SUM(bJCCD.ActualCost WHERE ActualDate or PostedDate >= fiscal year start) | No |  | COLCYCost — current calendar year cost from bJCCD |  | Needs Verification
AJ | Current Yr Calculated Profit | Calculated | Current Yr Revenue (AH) − Current Yr Cost (AI) | No |  | ISSUE: Shows ($11,102) for 51.1151, should be $0. Cascades from Col W. |  | Needs Fix
AK | Spacer (COLSP4) | UI/System | Visual section divider between 'Current Year' and 'Backlog' groups | No | Not a data column |  |  | System/UI
AL | Remaining Revenue (Backlog) | Calculated | Override Rev − JTD Earned Revenue (W). Future revenue still to be earned. | No |  | ISSUE: Shows $9,962,273 for 51.1151, should be $10,001,244. Cascades from Col W. |  | Needs Fix
AM | Remaining Cost | Calculated | Override Projected Cost − JTD Cost (X). Future cost still to be incurred. | No |  |  |  | Needs Verification
AN | GAAP Remaining Profit | Calculated | Remaining Revenue (AL) − Remaining Cost (AM) | No |  |  |  | Needs Verification
AO | Spacer (COLSP5) | UI/System | Visual section divider between 'Backlog' and 'Billings' groups | No | Not a data column |  |  | System/UI
AP | JTD Billings | Vista | Posted billings through batch month — from JB (Job Billing) tables in Vista | No |  |  |  | Verified
AQ | Revenue in Excess of Billing | Calculated | MAX(JTD Earned Rev − JTD Billings, 0). Asset on balance sheet. | No |  | ISSUE: Must use BONUS overridden revenue per business rule, not just calculated earned rev. |  | Needs Fix
AR | Billings in Excess of Revenue | Calculated | MAX(JTD Billings − JTD Earned Rev, 0). Liability on balance sheet. | No |  | ISSUE: Shows $85,821 for 51.1151, should be $124,792. Cascades from Col W. |  | Needs Fix
AS-AW | Hidden System Columns | System | COLZudChg, COLZOPsRev, COLZOPsCost, COLZGAAPRev, COLZGAAPCost — change-tracking flags and stored override values for auditing | No | Not visible to users — used by VBA for change detection and history |  |  | Hidden/System

## Ops Columns
Col Letter | Column Header Name | Data Source | Formula or Logic | Editable? | If Edited, What Happens? | Known Issue? | Nicole's Notes | Status
NOTE: Ops columns mirror GAAP structure but use 30% completion threshold (vs GAAP 10%) and add Bonus Profit columns (Z, AJ, AO). GAAP has one extra approval column (I=GAAP Done) that shifts columns I onward by 1 vs Ops. Fill in during walkthrough meeting.
A | Job Number | Vista | bJCJM.Contract (RTRIM) | No |  |  |  | Verified
B | Job Description | Vista | bJCCM.Description | No |  |  |  | Verified
C | Project Manager | Vista | bJCMP.Name via bJCJM.ProjectMgr | No |  |  |  | Verified
D | Exclude All (UI Toggle) | UI/System | COLExAll — narrow column, collapses/expands all division grouping rows | No | Do not use for data — UI control only |  |  | System/UI
E | Current Contract Amount | Calculated | bJCCM.OrigContractAmt + SUM(bJCID.ContractAmt WHERE JCTransType='CO', status=Interfaced) | No |  | Approved COs only (not PCOs). |  | Verified
F | PM Projected Revenue | Vista | bJCCM.ContractAmt (if no JCOR override), else bJCOR projected value | No | This is the PNP baseline before any overrides. |  |  | Verified
G | Close Flag | Approval | COLClose — 'C' when user marks WIP entry closed for this cycle | Yes | Phase 2: closes the WIP row for this cycle |  |  | Phase 2
H | Op's Done | Approval | COLDone — 'Y' when Ops / Division Manager approves | Yes | Phase 2: Ops approval flag (NOTE: Ops sheet has only one Done flag vs GAAP's two) |  |  | Phase 2
I | Ops Override Revenue Projection | Override (WipDb) | PM/DM/President tiered override of projected revenue — Ops version | Yes | Bold = Plugged ('Y'). Stored to LCGWIPDetail (Ops). Delta vs PNP shown. | Tiered override: PM → DM → President. |  | Phase 2
J | Ops Override Revenue Notes (hidden) | Override (WipDb) | Full notes text — hidden system column | No | System column, not visible to user |  |  | Hidden/System
K | Ops Override Revenue Notes Display | Override (WipDb) | COLOvrRevProjNotes2 — shortened display version of override notes | Yes | Stored to LCGWIPDetail |  |  | Phase 2
L | PM Projected Cost | Vista | SUM(bJCCD.ProjCost) WHERE JCTransType=PF AND CostType=99 | No |  |  |  | Verified
M | Ops Override Cost Projection | Override (WipDb) | PM/DM/President override of projected cost — Ops version | Yes | Bold = Plugged ('Y'). Stored to LCGWIPDetail. |  |  | Phase 2
N | Ops Override Cost Notes (hidden) | Override (WipDb) | Full notes text — hidden system column | No | System column, not visible to user |  |  | Hidden/System
O | Ops Override Cost Notes Display | Override (WipDb) | COLOvrCostProjNotes2 — shortened display version | Yes | Stored to LCGWIPDetail |  |  | Phase 2
P | Projected Profit | Calculated | Override Rev (I if plugged, else F) − Override Cost (M if plugged, else L) | No |  |  |  | Needs Verification
Q | Prior Projected Profit | Stored Value | Prior month's projected profit stored from WipDb history | No | From WipDb history; same staleness issue as GAAP Col R |  |  | Phase 2
R | Change In Projected Profit | Calculated | Projected Profit (P) − Prior Projected Profit (Q) | No |  |  |  | Needs Verification
S | Completion Date | Override | User-entered expected completion date | Yes | Stored to LCGWIPDetail | JCCM.ProjCloseDate exists — check if PNP/SMS use this. UD tables may exist. |  | Phase 2
T | Spacer (COLSP1) | UI/System | Visual section divider between 'Job at Completion' and 'Job to Date' groups | No | Not a data column |  |  | System/UI
U | JTD % Complete | Calculated | JTD Cost (X) / Override Projected Cost (M if plugged, else L). Null-safe. | No |  |  |  | Needs Verification
V | JTD Calculated Earned Revenue | Calculated | OPS-ONLY: if Override Cost > 0 AND (Cost/Override Cost) > 30%: (Cost/Override Cost) × Override Rev; else 0. Uses 30% threshold. | No |  | Ops uses 30% completion threshold (vs GAAP's 10%). This column uses the COST-based %complete against override values. |  | Needs Verification
W | JTD Earned Revenue | Calculated | If %Complete (U) < 30%: EarnedRev = 0 (Ops does not recognize below 30%). Else: Override Rev × %Complete. | No |  | Ops uses 30% threshold. Below 30%, NO profit recognized and earned rev = 0 (different from GAAP which uses cost as floor). |  | Needs Verification
X | JTD Cost | Vista | SUM(bJCCD.ActualCost) with same date logic as GAAP | No |  |  |  | Verified
Y | JTD Profit | Calculated | JTD Earned Revenue (W) − JTD Cost (X) | No |  |  |  | Needs Verification
Z | Bonus JTD Profit | Override (WipDb) | OPS-ONLY: DM/Ops override of anticipated profit for bonus calculation purposes | Yes | Bold = Plugged ('Y'). Yellow highlight. Stored to LCGWIPDetail.BonusProfit. | Should be stored back to Vista UD tables in Phase 2. |  | Phase 2
AA | Bonus Profit Notes | Override (WipDb) | Justification notes for bonus profit override | Yes | Stored to LCGWIPDetail.BonusProfitNotes |  |  | Phase 2
AB | Bonus Notes Display | Override (WipDb) | COLJTDBonusProfitNotesShow — display version of bonus notes | Yes | Stored to LCGWIPDetail |  |  | Phase 2
AC | JTD Prior Profit | Stored Value | Prior month's JTD Profit — stored in WipDb history | No | From WipDb history; Phase 2 replaces with Vista UD table |  |  | Phase 2
AD | JTD Change In Profit | Calculated | JTD Profit (Y) − JTD Prior Profit (AC) | No |  |  |  | Needs Verification
AE | Spacer (COLSP2) | UI/System | Visual section divider between 'Job to Date' and 'All Prior Years' groups | No | Not a data column |  |  | System/UI
AF | Previous Yr % Complete | Calculated | PYCost / Prior Year Ops Projected Cost | No |  |  |  | Needs Verification
AG | Previous Yr Revenue | Calculated | PYCost + Prior Year Bonus Profit (AJ). Ops uses cost+bonus method, not % × Rev. | No |  | NOTE: Ops prior-year revenue formula differs from GAAP — uses COLAPYRev = PYCost + PriorYrBonusProfit |  | Needs Verification
AH | Previous Yr Cost | Calculated | JTD Cost (X) − Current Year Cost (AM) | No |  |  |  | Needs Verification
AI | Previous Yr Calculated Profit | Calculated | Previous Yr Revenue (AG) − Previous Yr Cost (AH) | No |  |  |  | Needs Verification
AJ | Previous Year Bonus Profit | Stored Value | Prior year bonus profit stored at year-end snapshot | No | Stored from WipDb year-end; Phase 2 → Vista UD table |  |  | Phase 2
AK | Spacer (COLSP3) | UI/System | Visual section divider | No | Not a data column |  |  | System/UI
AL | Current Yr Revenue | Calculated | Current-year earned rev (using same 30% threshold but CY cost portion) | No |  |  |  | Needs Verification
AM | Current Yr Cost | Vista | SUM(bJCCD.ActualCost WHERE date >= fiscal year start) | No |  |  |  | Needs Verification
AN | Current Yr Calculated Profit | Calculated | Current Yr Revenue (AL) − Current Yr Cost (AM) | No |  |  |  | Needs Verification
AO | Current Year Bonus Profit | Calculated | OPS-ONLY: Current year portion of bonus profit | No |  |  |  | Needs Verification
AP | Spacer (COLSP4) | UI/System | Visual section divider between 'Current Year' and 'Backlog' groups | No | Not a data column |  |  | System/UI
AQ | Remaining Revenue (Backlog) | Calculated | Override Rev − JTD Earned Revenue (W) | No |  |  |  | Needs Verification
AR | Remaining Cost | Calculated | Override Projected Cost − JTD Cost (X) | No |  |  |  | Needs Verification
AS | Bonus Remaining Profit | Calculated | OPS-ONLY: Remaining Revenue (AQ) − Remaining Cost (AR). Uses bonus profit logic. | No |  |  |  | Needs Verification
AT | Spacer (COLSP5) | UI/System | Visual section divider between 'Backlog' and 'Billings' groups | No | Not a data column |  |  | System/UI
AU | JTD Billings | Vista | Posted billings through batch month — from JB tables in Vista | No |  |  |  | Verified
AV | Revenue in Excess of Billing | Calculated | MAX(JTD Earned Rev − JTD Billings, 0). Asset on balance sheet. | No |  |  |  | Needs Verification
AW | Billings in Excess of Revenue | Calculated | MAX(JTD Billings − JTD Earned Rev, 0). Liability on balance sheet. | No |  |  |  | Needs Verification
AX-BF | Hidden System Columns | System | COLZOPsRChg, COLZOPsCChg, COLZudChg, COLZOPsRev, COLZOPsCost — change-tracking flags and stored override values | No | Not visible to users |  |  | Hidden/System

## Job Inclusion Rules
Rule | Description | Known Issue | Nicole's Notes | Status
Open jobs at month end | All jobs with ContractStatus=1 (Open) in Vista at the WIP month |  |  | Verified
Soft closed jobs | Jobs soft-closed between report start and end dates |  |  | Verified
Hard closed jobs | Jobs hard-closed in reporting period |  |  | Verified
Cross-year reversals | Jobs with prior year cost reversed in current year MUST appear even if JTD=$0. Needed so MTD changes are accurate. | ISSUE: Jobs 56.1022 and 56.1057 missing — had cost reversed and closed with $0 but need to show for MTD accuracy. |  | Needs Fix
Re-opened jobs | Jobs closed then re-opened must reflect CURRENT Vista status, not cached status | ISSUE: Job 54.9033 shows closed but was re-opened in Vista. WipDb cached stale status. |  | Needs Fix
GAAP quarterly filter | GAAP data only populated in Mar/Jun/Sep/Dec. Non-quarterly months should have NO GAAP values. |  |  | Verified
No future-month jobs | Jobs with no cost until a future month should not appear on earlier months |  |  | Needs Verification
Reversed-and-closed cutoff | Jobs reversed-and-closed should stop appearing AFTER the reversal month |  |  | Needs Verification
JV jobs | Joint venture jobs appear on separate JV tabs (Sheet15/16). Different accounting treatment — currently manual. | JV accounting rules are in flux per Kevin. Manual entry for now. |  | Phase 2

## Discrepancies - June 2025
Item # | Category | Column | Description | Job Example | WIP Shows | Should Be | Root Cause (our analysis) | Fix Status
1 | Bonus Jobs | Status | Job 54.9033 listed as closed on Auto WIP but has ContractStatus=1 (Open) in Vista. Was briefly closed in 2024 then re-opened. | 54.9033 | Closed | Open | WipDb caches job status, never refreshes from Vista. Phase 1 pulls directly from Vista — may already be fixed. | To Verify
2 | Bonus Jobs | Job List | Jobs 56.1022 and 56.1057 missing from Bonus tab. Both had cost in prior months then reversed and closed with $0. Still need to appear so MTD changes are accurate. | 56.1022 56.1057 | Missing | Should appear | Job inclusion logic filters out JTD=$0 jobs. Need to include jobs with MTD activity (reversals) even if JTD nets to zero. | To Fix
3 | GAAP | Col R Prior Proj Profit | Shows $0 but should have data from March WIP. Formula refers to 10% completion when it should be a plug from March WIP schedule. | 51.1151 | $0 | $596,848 | Formula uses 10% calc instead of stored March WIP baseline. Most persistent bug — same issue documented since 2015. Need stored historical value, not recalculated. | To Fix
4 | GAAP | Col W JTD Earned Rev | Not calculating correctly. Job is <10% complete so earned revenue should equal cost (no profit recognition under GAAP 10% rule). | 51.1151 | $695,927 | $656,956 (= cost) | 10% completion threshold not applied correctly. When %complete < 10%, earned rev must = cost. Nicole says fixing this cascades to fix items #5-10. | To Fix
5 | GAAP | Col AD Prev Yr Rev | Previous year revenue showing incorrect amounts. | 51.1151 | $198,246 | $187,144 | Cascades from Col W (item #4). Once earned rev is correct, prev yr rev recalculates correctly. | Cascades from #4
6 | GAAP | Col AF Prev Yr Calc Profit | Previous year calculated profit showing incorrect amounts. | 51.1151 | $11,102 | $0 | Cascades from Col W (item #4). | Cascades from #4
7 | GAAP | Col AH Curr Yr Rev | Current year revenue showing incorrect amounts. | 51.1151 | $497,682 | $469,812 | Cascades from Col W (item #4). | Cascades from #4
8 | GAAP | Col AJ Curr Yr Calc Profit | Current year calculated profit showing incorrect amounts. | 51.1151 | ($11,102) | $0 | Cascades from Col W (item #4). | Cascades from #4
9 | GAAP | Col AL Remaining Rev | Remaining revenue showing incorrect amounts. | 51.1151 | $9,962,273 | $10,001,244 | Cascades from Col W (item #4). | Cascades from #4
10 | GAAP | Col AQ/AR Rev/Bill Excess | Revenue in Excess / Billings in Excess showing incorrect amounts. | 51.1151 | $85,821 (Col AR) | $124,792 (Col AR) | Cascades from Col W (item #4). Also: must use BONUS overridden revenue, not calculated revenue. | Cascades from #4