## Open Jobs
W.M. Lyles Co.
JOB SUMMARIES BY AREA
FISCAL YEAR ENDING 12/31/25
For the 12 Months Period Ended 12/31/25
[12 empty] | Month: | 2025-12-31
[12 empty] | Anticipated | Contractual | Change in | Previous
Job | Description and | Project | Project | Contract | % | Revenue | Cost | Profit | Prior Year | Current | Revenue | Total | Completion | Anticipated | Anticipated
No. | Customer | Sup | Est | Amount | Comp | to Date | to Date | to Date | Profit | Profit | Remaining | Profit | Date | Profit | Profits | Notes
Area: | Rocklin
51.1108 | JV w/AECOM - Stockton - RWCF Phase 2A/2B | DC | Joe, VG, RB, PVT | 94196098 | 99.93% | 94126376.71 | 93268107.71 | 858269 | 858269 | 0 | 69721.29 | 858269 | 2026-03-28 | 0 | 858269 | Through Amendment 23. Includes anticipated profits from the 3% OH generated from the issued JV's SC's & PA's less credit back for management 50hr vs 40hr. Completion date listed for building completion - minus 10% management OH credit back to JV. Adjusted contract value to match anticipated reported on JV financials
51.1109 | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) | DC | N/A |  | 98.09% | 0 | -3462489.91 | 3462489.91 | 3470130.75 | -7640.84 | 0 | 3530000 | 2026-03-28 | 0 | 3530000 | Revenue generated by billing to 51.1108.
51.1129 | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications | RB/AH | RB/MV | 126483580.84 | 75.77% | 96373952.3761 | 87315159.22 | 9058793.1561 | 7950623.3602 | 1108169.7959 | 30109628.4639 | 11250000 | 2027-06-25 | 0 | 11250000 | Through change order 111 minus 2, 29, 58, 78, 84 & 99. Increase in profits to date are realized buyout items and VE ideas gains. Problem with material delivery delayed the project. Profit projection includes the project realized gains (buyout/VE/profits) and projected losses due to delay.
51.1137 | CA Water Service Co. - Bear Gulch Pump Station 18 | AH | KS | 1312151.46 | 86.96% | 1141050.9871 | 1042229.29 | 98821.6971 | 27243.5887 | 71578.1085 | 171100.4729 | 113640 | 2026-01-31 | 0 | 113640
51.1144 | Silicon Valley Clean Water - FEP Improvements Project | EL | VG | 14969566 | 60.74% | 9093138.9678 | 8406760.8 | 686378.1678 | 90331.4512 | 596046.7166 | 5876427.0322 | 1129949 | 2026-12-20 | 0 | 1129949 | Stage 1 Design is to be completed by 9/30/24 by PDB Agreement but is behind -20 days due to Owner Delay. Stage 2 construction anticipated to begin 3/25 and complete by 12/20/26 and is seasonal
51.1146 | National Carbon Technologies, LLC - Aymium Williams Production Facility | MS | MV | 60980234 | 92.94% | 56675078.5373 | 42734066.47 | 13941012.0673 | 510849.94 | 13430162.1273 | 4305155.4627 | 15000000 | 2026-02-28 | 1400000 | 13600000 | We demobilized in early November. All in, the Project has the potential to be $20m ($18.2 51.1146 + $1.8 51.1155). This does not include potential greivence settletmens or setttling up with Amyium. Based on all this, the December projection is $15.0m. We are holding back -$1m for Union grievances and another -$2m for other open issues w/ Amyium regarding their refusal to release retention.
51.1151 | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | MV | SS | 10658200 | 48.85% | 5206183.5756 | 4923435.18 | 282748.3956 | 0 | 282748.3956 | 5452016.4244 | 578848 | 2026-11-25 | 0 | 578848
51.1152 | Mozingo Construction Inc - ElD Sly Park Intertie Project | MV | EG | 19974489.34 | 72.33% | 14448073.7521 | 13474808.54 | 973265.2121 | 0 | 973265.2121 | 5526415.5879 | 1345541 | 2026-06-30 | 0 | 1345541
51.1153 | Linda County Water Dist. - Aeration Blower Replacement | JL | JL | 562824.68 | 73.61% | 414268.175 | 334550.81 | 79717.365 | 12859.3892 | 66857.9758 | 148556.505 | 108304 | 2026-01-31 | 0 | 108304 | Checking for final invoices, Should move to closed jobs next month
51.1154 | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | LP | KS | 13363835 | 95.06% | 12704149.552 | 11872342.6 | 831806.952 | 0 | 831806.952 | 659685.448 | 875000 | 2026-02-15 | 0 | 875000
51.1155 | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out |  |  |  | 100% | 0 | -1783379.97 | 1783379.97 | 571197.48 | 1212182.49 | 0 | 1783379.97 | 2026-02-28 | -16620.03 | 1800000
51.1158 | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric |  |  | 104446 | 54.54% | 56960.69 | 56960.69 | 0 | 0 | 0 | 47485.31 | 0 | 2026-05-31 | 0 | 0 | Hold at $0 profit, need to verify final numbers once project path is determined (go/no-go). Do not close WIP.
51.1159 | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | EG | MV | 1199000 | 73.2% | 877720.7043 | 790051.12 | 87669.5843 | 0 | 87669.5843 | 321279.2957 | 119760 | 2026-03-15 | 0 | 119760
51.116 | City of Galt Public Works - Industrial WWTP Expansion | JL | MV | 1757000 | 14.82% | 250518.05 | 250518.05 | 0 | 0 | 0 | 1506481.95 | 67000 | 2026-09-20 | 0 | 67000
51.1161 | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | JA | MV | 10848599.45 | 5.865% | 601852.17 | 601852.17 | 0 | 0 | 0 | 10246747.28 | 587347 | 2026-12-10 | 0 | 587347
51.1162 | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project | CT | MV | 6029750 | 1.47% | 85941.38 | 85941.38 | 0 | 0 | 0 | 5943808.62 | 184487 | 2027-10-21 | 0 | 184487
51.1164 | CA Water Service Co. - Stockton Roofing | JL | JS | 387260 | 1.138% | 4363.25 | 4363.25 | 0 |  | 0 | 382896.75 | 3873 | 2026-03-31 | 3873
51.1165 | City of Yuba City - WTP Aquifer Storage and Recovery Well No. 3 | EG | MV | 5304500 | 0.4775% | 23330.33 | 23330.33 | 0 |  | 0 | 5281169.67 | 418057 | 2027-09-30 | 418057
| Rocklin Totals this Month |  |  | 368131534.77 |  | 292082959.2072 | 259938607.73 | 32144351.4772 | 13491504.9592 | 18652846.518 | 76048575.5628 | 37953454.97 |  | 1805309.97 | 36148145
| Rocklin Closed Job Total |  |  | 18225884.89 |  | 18225884.89 | 18509364.3 | -283479.41 | 1459158.2509 | -1742637.6609 | 0 | -283479.41 |  | -525178.96 | 241699.55
| Rocklin Total |  |  | 386357419.66 |  | 310308844.0972 | 278447972.03 | 31860872.0672 | 14950663.2101 | 16910208.8571 | 76048575.5628 | 37669975.56 |  | 1280131.01 | 36389844.55
JV | Stockton - RWCF Phase 2A/2B | DC | Joe, VG, RB, PVT | 112542778.5 | 99.9% | 112438999.5 | 106020819 | 6418180.5 | 7118423.5 | -700243 | 103779 | 6418180.5 | 2026-03-28 | -31801 | 6449981.5 | Includes December JV Financials | Profit fade is a result of exceleration of the buildings to complete by Jan '25. Paying for subcontractors to work extended hours and weekends -$250k plus an additional -200k in reimbursable change order work in negotiations with Owner (tracking $400k allowing for 50% recovery). Added another -$100k for future sub accel to complete buildings on time. Overall project impacts on buildings alone due to design/misc. issues - $1.6m. See project narrative for more details.
| Rocklin Totals this Month w/ JVs & Closed Jobs | [8 empty] | 16209965.8571 | [7 empty] | Curr Month | 278447972.03
| Rocklin Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | 14439549.3237 | [7 empty] | Company Activity | -7220844.25
| Rocklin Current Month Changes w/ JV's & Closed Jobs | [8 empty] | 1770416.5334 | [8 empty] | 271227127.78
[18 empty] | Prior Month | 271227127.78
Area: | Fresno | [16 empty] | Variance | 0
52.8563 | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | RM | JL | 1174182.73 | 98.15% | 1152462.29 | 1152462.29 | 0 | 0 | 0 | 21720.44 | 0 | 2026-02-06 | 0 | 0
52.8564 | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out | RM | JL |  | 100% | 0 | -293385.24 | 293385.24 | 264189.76 | 29195.48 | 0 | 293392.63 | 2026-02-06 | 0 | 293392.63 | Through JV Amendment 4
52.8566 | City of Visalia - Water Reclamation Facility RPGS SCR System | RM | RM | 1259398 | 99.46% | 1252574.9834 | 1023821.05 | 228753.9334 | 223974.5063 | 4779.4271 | 6823.0166 | 230000 | 2026-02-28 | 0 | 230000 | Waiting on Cummins (owner furnished equipment), to complete their commissioning.
52.8586 | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | RM | RM | 12611349 | 99.1% | 12497922.4241 | 10565460.74 | 1932461.6841 | 1757780.0079 | 174681.6762 | 113426.5759 | 1950000 | 2026-01-31 | 0 | 1950000
52.8634 | City of Huron - Water Treatment Plant Imp. Phase 2 | DG | KSH | 13892722.74 | 88.75% | 12330098.7698 | 11707058.24 | 623040.5298 | 277972.0115 | 345068.5183 | 1562623.9702 | 702000 | 2026-05-06 | 0 | 702000
52.8636 | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | PR | KSH | 3642197 | 100% | 3642035.1389 | 3367047.36 | 274987.7789 | 204319.7111 | 70668.0678 | 161.8611 | 275000 | 2026-02-28 | -35000 | 310000 | Reduced profits. Performing additional work on Odor Control System. Anaergia will be issuing an RFP which will increase the contract and put back the profits at a later date.
52.8637 | Root Creek Water Dist. - Groundwater Blending & Arsenic | LP | KSH | 26264577.65 | 99.02% | 26008192.3257 | 24374299.03 | 1633893.2957 | 1208391.7577 | 425501.538 | 256385.3243 | 1650000 | 2026-02-28 | 0 | 1650000
52.864 | City of Dos Palos - WTP Replacement Project | TC | KSH | 38646363.16 | 87.45% | 33797041.051 | 32158781.48 | 1638259.571 | 703966.8389 | 934292.7322 | 4849322.109 | 1873323 | 2026-04-17 | 0 | 1873323
52.8668 | California Water Service Co. - Cal Water - Salinas Station 57 | EB | SF | 411851 | 94.88% | 390782.6533 | 357710.67 | 33071.9833 | 0 | 33071.9833 | 21068.3467 | 34855 | 2025-12-31 | -1145 | 36000 | All work has been completed. Waiting on final change order to be processed.
52.8678 | City of Chowchilla - Well 15 & Generator Improvement Projects | EB | RH | 1240321 | 79.67% | 988148.9819 | 926007.31 | 62141.6719 | 0 | 62141.6719 | 252172.0181 | 78000 | 2026-01-31 | 0 | 78000
52.8687 | California Water Service Co. - Salinas Station 205 | EB | JS | 877954 | 93.66% | 822283.7912 | 740629.43 | 81654.3612 | 0 | 81654.3612 | 55670.2088 | 87182.52 | 2025-12-31 | 5760.52 | 81422 | All work has been completed. Waiting on final change order to be processed.
52.8692 | New England Sheet Metal and Mechanical Co. - Clovis South T&M | DG | DG | 55135.37 | 100% | 55135.37 | 49682.49 | 5452.88 | 0 | 5452.88 | 0 | 5452.88 | 2026-01-31 | 0 | 5452.88 | January costs, will be billed in January
52.8697 | City of Tulare - Industrial WWTP Dewatering Improvements | JL | RM | 1388000 | 58.26% | 808608.9206 | 772187.73 | 36421.1906 | 0 | 36421.1906 | 579391.0794 | 62518 | 2026-07-22 | 0 | 62518
52.8698 | California Water Service Co. - Tesoro Viejo RWSP Liner Repair |  |  | 22713 | 94.64% | 21496.2321 | 15264 | 6232.2321 |  | 6232.2321 | 1216.7679 | 6585 | 2026-01-31 | 6585
52.8704 | City of Visalia - Solids Handling Improvements Project | LP | SF | 13744000 | 6.085% | 820988.3 | 820988.3 | 0 | 0 | 0 | 12923011.7 | 252873 | 2027-01-31 | 0 | 252873
52.8705 | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | MDA | JS | 775000 | 39.68% | 307545.1617 | 285425.72 | 22119.4417 | 0 | 22119.4417 | 467454.8383 | 55740 | 2026-02-28 | 0 | 55740
52.8707 | County of Fresno - Westside Water Tank and Pump Station | AC | RM | 3693200 | 29.24% | 1079776.4803 | 1012057.14 | 67719.3403 | 0 | 67719.3403 | 2613423.5197 | 231623 | 2026-07-12 | 0 | 231623
52.8708 | County of Fresno - CSA 44A Wastewater Improvements | AKC | JS | 363833 | 2.302% | 7682.19 | 7682.19 | 0 |  | 0 | 356150.81 | 30076 | 2026-02-28 | 0 | 30076
52.8711 | California Water Service Co. - Tesoro Viejo ARV Replacement | AKC | AKC | 6860 | 72.35% | 4963.1095 | 4568.81 | 394.2995 |  | 394.2995 | 1896.8905 | 545 | 2026-01-31 | 545
52.8713 | City of Visalia - Remove & Replace Chain and Flight Mechanic | EB | EB | 218842 | 0.487% | 927.5 | 927.5 | 0 |  | 0 | 217914.5 | 28403 | 2026-03-31 | 28403
52.8714 | New England Sheet Metal and Mechanical Co. - VCH Digging Water Line T&M | DG | DG | 5084.94 | 100% | 5084.94 | 4465.61 | 619.33 |  | 619.33 | 0 | 619.33 | 2026-01-31 | 619.33
| Fresno Totals this Month |  |  | 120293584.59 |  | 95993750.6135 | 89053141.85 | 6940608.7635 | 4640594.5933 | 2300014.1702 | 24299833.9765 | 7848188.36 |  | 5767.85 | 7842420.51
| Fresno Closed Job Total |  |  | 24381266.32 |  | 24381266.32 | 23380699.1 | 1000567.22 | 947524.5165 | 53042.7035 | 0 | 1000567.22 | 0 | -98924.13 | 1099491.35
| Fresno Total |  |  | 144674850.91 |  | 120375016.9335 | 112433840.95 | 7941175.9835 | 5588119.1098 | 2353056.8737 | 24299833.9765 | 8848755.58 |  | -93156.28 | 8941911.86
JV | City of Santa Cruz - Graham Hill WTP Facility Improvements | RM | JL | 5521233.5 | 99.44% | 5490375 | 5473212.5 | 17162.5 | 171855.18 | -154692.68 | 30858.5 | 17258.5 | 2026-02-06 | 0 | 17258.5 | Includes December JV Financials | Used March 2024 JV - WML Adjusted Finanicals, Note Schedule showing project now -79 float behind as a result of push on 90% Design Review and resulting 100% Design efforts, likely City will reduce some of their review or negotiation period to reduce this
| Fresno Totals this Month w/ JVs & Closed Jobs | [8 empty] | 2198364.1937 | [7 empty] | Curr Month | 112433840.95
| Fresno Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | 1916999.697 | [7 empty] | Company Activity | -7110923.38
| Fresno Current Month Changes w/ JV's & Closed Jobs | [8 empty] | 281364.4967 | [8 empty] | 105322917.57
[18 empty] | Prior Month | 105322917.57
Area: | East Bay | [16 empty] | Variance | 0
53.2007 | Union Sanitary Dist. - Phase 1B Secondary Clarifiers |  |  | 324530134 | 0.1389% | 404852.16 | 404852.16 | 0 | 0 | 0 | 324125281.84 | 33000000 | 1931-01-29 | 0 | 33000000
| East Bay Totals this Month |  |  | 324530134 |  | 404852.16 | 404852.16 | 0 | 0 | 0 | 324125281.84 | 33000000 |  | 0 | 33000000 |  |  | Curr Month | 1969911.49
| East Bay Closed Job Total |  |  | 1173753.47 | 0 | 1173753.47 | 1565059.33 | -391305.86 | 0 | -391305.86 | 0 | -391305.86 | 0 | -27859.93 | -363445.93 |  |  | Company Activity | -245768.3
| East Bay Total |  |  | 325703887.47 |  | 1578605.63 | 1969911.49 | -391305.86 | 0 | -391305.86 | 324125281.84 | 32608694.14 |  | -27859.93 | 32636554.07 |  |  |  | 1724143.19
| East Bay Totals this Month w/ JVs & Closed Jobs | [8 empty] | -391305.86 | [7 empty] | Prior Month | 1724143.19
| East Bay Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | -369273.7769 | [7 empty] | Variance | 0
| East Bay Current Month Changes w/ JV's & Closed Jobs | [8 empty] | -22032.0831
Area: | Bakersfield
54.9033 | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | REA | REA | 118278.58 | 100% | 118278.58 | 104550.27 | 13728.31 | 10966.87 | 2761.44 | 0 | 13728.31 | 2026-12-01 | 2761.31 | 10967 | Please do not close at year-end REA applying consulting time
54.9135 | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | AH | REA | 9470658.62 | 100% | 9470658.62 | 9050951.86 | 419706.76 | 551994.3651 | -132287.6051 | 0 | 419706.76 | 2026-01-01 | -214351.24 | 634058 | Antcipating dispute on unpaid T&M Change Order work.
54.9257 | City of Guadalupe - Highway 1 Lift Station | PR | PR | 1471328 | 53.44% | 786258.4621 | 762211.05 | 24047.4121 | 0 | 24047.4121 | 685069.5379 | 45000 | 2026-03-15 | 0 | 45000
54.9268 | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | DS | RA | 949567.99 | 95.49% | 909648.28 | 844648.28 | 65000 | 71013.0668 | -6013.0668 | 39919.71 | 65000 | 2026-02-01 | 0 | 65000 | Pump accepted will close when invoice clears ---- Per Dave S., no December billing
54.9269 | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | KSH | REA | 625819.17 | 92.94% | 584066.79 | 549817.74 | 34249.05 | 34249.05 | 0 | 41752.38 | 34249.05 | 2026-07-01 | 0.05 | 34249 | Profit accounts for Phase 1 work. Phase 2 may be subject to a loss
54.9285 | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | DS | DS | 462022 | 80.86% | 373583.5648 | 312939.77 | 60643.7948 | 35686.2378 | 24957.557 | 88438.4352 | 75000 | 2026-02-01 | 0 | 75000 | CCO coming for control changes
54.9313 | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | PR | KSH | 7886885.04 | 93.78% | 7396392.3889 | 6449205.22 | 947187.1689 | 197714.5111 | 749472.6578 | 490492.6511 | 1010000 | 2026-02-01 | 130000 | 880000 | Owner reduction in scope, increased profit projection.
54.933 | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | DS | JS | 324900 | 99.54% | 323400.7694 | 306221.41 | 17179.3594 | 10642.1273 | 6537.2322 | 1499.2306 | 17259 | 2025-12-31 | 1259 | 16000 | Waiting on final Change Order to be executed to finalize contract value
54.9336 | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | CB | MC | 25191176.64 | 53.03% | 13359053.4129 | 12340864.27 | 1018189.1429 | 0 | 1018189.1429 | 11832123.2271 | 1920000 | 2026-09-09 | 20000 | 1900000
54.9337 | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | DS | JS | 4104848 | 38.25% | 1570273.3156 | 1509066.73 | 61206.5856 | 0 | 61206.5856 | 2534574.6844 | 160000 | 2026-10-26 | 0 | 160000 | 5 CCOs expected with +-10 Mo Time extension
54.9343 | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | RH | RH | 6881300 | 57.1% | 3929247.3572 | 3415344.08 | 513903.2772 | 0 | 513903.2772 | 2952052.6428 | 900000 | 2026-05-26 | 50000 | 850000
54.9356 | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | TM | JS | 1298330 | 84.94% | 1102799.0115 | 775780.75 | 327018.2615 | 0 | 327018.2615 | 195530.9885 | 385000 | 2026-04-30 | 0 | 385000 | Completetion date pushed back due to vessel design discrepancy
54.9366 | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | PR | PR | 1230131 | 85.47% | 1051430.0181 | 923220.5 | 128209.5181 | 0 | 128209.5181 | 178700.9819 | 150000 | 2026-05-01 | 60000 | 90000
54.9369 | California Water Service Co. - PFAS Treatment Program Project | PR | JS | 28550624.7 | 10.65% | 2787466.66 | 2787466.66 | 0 | 0 | 0 | 25763158.04 | 2370843 | 2027-04-01 | 0 | 2370843
54.9373 | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | PR | PR | 1524766 | 3.61% | 50303.97 | 50303.97 | 0 | 0 | 0 | 1474462.03 | 131440 | 2026-05-30 | 0 | 131440
54.9389 | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | PR | RH | 299780 | 99.08% | 296891.85 | 311891.85 | -15000 | 0 | -15000 | 2888.15 | -15000 | 2026-02-28 | 0 | -15000
54.9391 | Arvin Edison Water Storage Dist. - HQ Concrete R&R | RF | RF | 532604.57 | 100% | 532604.57 | 512057.34 | 20547.23 | 0 | 20547.23 | 0 | 20547.23 | 2026-01-31 | 547.23 | 20000 | Project being performed for AEWSD at reduced mark-up to keep crews busy
54.9395 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | DS | DS | 1795652.66 | 79.69% | 1430881.5112 | 1349601.92 | 81279.5912 | 0 | 81279.5912 | 364771.1488 | 102000 | 2026-02-26 | 72000 | 30000
54.9396 | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | JM | MC | 157746.09 | 100% | 157746.09 | 157746.09 | 0 | 0 | 0 | 0 | 0 | 2026-04-26 | -9546 | 9546
54.9397 | Cawelo Water Dist. - Friant-Kern Canal Pump Station | RF | JS | 3690645 | 30.53% | 1126646.6941 | 1035065.41 | 91581.2841 | 0 | 91581.2841 | 2563998.3059 | 300000 | 2026-04-01 | 0 | 300000
54.9403 | Lost Hills Utility Dist. - WTP Improvements | TM | RH | 381600 | 38.16% | 145602.2491 | 129004.89 | 16597.3591 | 0 | 16597.3591 | 235997.7509 | 43499 | 2026-02-26 | 0 | 43499
54.9404 | Cawelo Water Dist. - Reuse of Produced Water | RF | SF | 3720000 | 54.08% | 2011822.3122 | 1939024.63 | 72797.6822 | 0 | 72797.6822 | 1708177.6878 | 134608 | 2026-02-27 | 0 | 134608
54.9405 | Semitropic Water Storage Dist. - Pump Platform Replacement Project | DS | DS | 942000 | 71.16% | 670300.4713 | 577796.16 | 92504.3113 | 0 | 92504.3113 | 271699.5287 | 130000 | 2026-03-26 | 10000 | 120000
54.9406 | California Water Service Co. - Emergency PACL leak repair | DS | DS | 1120.65 | 100% | 1120.65 | 1120.65 | 0 | 0 | 0 | 0 | 0 | 2026-01-01 | 0
54.9408 | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line | PR | SF | 3777777 | 1.178% | 41652.43 | 41652.43 | 0 | 0 | 0 | 3736124.57 | 240592 | 2026-07-31 | 0 | 240592
54.9411 | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation | AH | AH | 103300 | 91.15% | 94158.4777 | 71370.85 | 22787.6277 | 0 | 22787.6277 | 9141.5223 | 25000 | 2026-01-01 | 0 | 25000 | WML will need to relocate ARV due to survey error. Pursuing CO for remob.
54.9412 | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork | RF | RF | 116752.04 | 100% | 116752.04 | 115708.88 | 1043.16 | 0 | 1043.16 | 0 | 1043.16 | 2026-01-01 | -4956.84 | 6000 | Leave job open WIP
54.9413 | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork | RF | RF | 149366.83 | 100% | 149366.83 | 132138.74 | 17228.09 | 0 | 17228.09 | 0 | 17228.09 | 2026-01-01 | 7228.09 | 10000 | Leave job open WIP
54.9414 | Cawelo Water Dist. - Cawelo Diversion Structure Rehab | AH | AH | 358674.83 | 99.65% | 357415.4563 | 337485.68 | 19929.7763 | 0 | 19929.7763 | 1259.3737 | 20000 | 2026-01-01 | -5000 | 25000
54.9416 | California Water Service Co. - BK 147 Station Improvements | TM | JS | 1260000 | 0.6409% | 7257.82 | 7257.82 | 0 | 0 | 0 | 1252742.18 | 127602 | 2026-07-01 | 0 | 127602
54.9417 | County of Santa Barbara-Public Works - Laguna WWTP WAS Pipe Modifications | PR | PR | 48439 | 5.361% | 2299.41 | 2299.41 | 0 | 0 | 0 | 46139.59 | 5546 | 2026-03-31 | 5546
54.9418 | GenerateUpcycle - Organics Waste Processing Facility | JM | JL | 15739 | 100% | 15739 | 15739 | 0 | 0 | 0 | 0 | 0 | 2026-02-01 | -10000 | 10000
54.9421 | Nipomo Community Service Dist. - Tefft Emergency Pipe Repair | PR | PR | 3703.18 | 100% | 3703.18 | 3703.18 | 0 | 0 | 0 | 0 | 0 | 2026-02-28 | 0
| Bakersfield Totals this Month |  |  | 107445536.59 |  | 50974822.2426 | 46923257.49 | 4051564.7526 | 912266.2281 | 3139298.5245 | 56470714.3474 | 8849891.6 |  | 115487.6 | 8734404 |  |  | Curr Month | 131355636.81
| Bakersfield Closed Job Total |  |  | 97414231.62 | 0 | 97414231.62 | 84432379.32 | 12981852.3 | 13874672.8184 | -892820.5184 | 0 | 12981852.3 | 0 | -77720.64 | 13059572.94 |  |  | Company Activity | -8588450.47
| Bakersfield Total |  |  | 204859768.21 |  | 148389053.8626 | 131355636.81 | 17033417.0526 | 14786939.0465 | 2246478.0061 | 56470714.3474 | 21831743.9 |  | 37766.96 | 21793976.94 |  |  |  | 122767186.34
| Bakersfield Totals this Month w/ JVs & Closed Jobs | [8 empty] | 2246478.0061 | [7 empty] | Prior Month | 122767186.34
| Bakersfield Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | 1424332.7554 | [7 empty] | Variance | 0
| Bakersfield Current Month Changes w/ JV's & Closed Jobs | [8 empty] | 822145.2507
Northern Totals
| Northern Totals this Month |  |  | 920400789.95 | 0 | 439456384.2233 | 396319859.23 | 43136524.9933 | 19044365.7806 | 24092159.2127 | 480944405.7267 | 87651534.93 | 0 | 1926565.42 | 85724969.51
| Northern Closed Job Total |  |  | 141195136.3 | 0 | 141195136.3 | 127887502.05 | 13307634.25 | 16281355.5857 | -2973721.3357 | 0 | 13307634.25 | 0 | -729683.66 | 14037317.91
| Northern Total |  |  | 1061595926.25 | 0 | 580651520.5233 | 524207361.28 | 56444159.2433 | 35325721.3663 | 21118437.8769 | 480944405.7267 | 100959169.18 | 0 | 1196881.76 | 99762287.42
| Northern Totals this Month w/ JVs & Closed Jobs | [8 empty] | 20263502.1969
| Northern Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | 17411607.9992
| Northern Current Month Changes w/ JV's & Closed Jobs | [8 empty] | 2851894.1978
Area: | Murrieta
55.109 | JV w/Webcor & Obayashi - Silverlake - LADWP | AB | MC | 5400000 | 98.31% | 5308704.0692 | 3834064.05 | 1474640.0192 | 1463888.1686 | 10751.8507 | 91295.9308 | 1500000 | 2029-12-01 | 3027.8 | 1496972.2
55.1191 | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility | JA | ALL | 341443133.71 | 88.58% | 302890122.84 | 299179624.84 | 3710498 | 7900000 | -4189502 | 38553010.87 | 3710498 | 2027-06-30 | -1500000 | 5210498 | Overhead To June 2027
55.1192 | Inland Empire Utilities - IEUA RP-1 Flare Improvements | TV | ALL | 6651803.53 | 99.88% | 6643992.69 | 6393992.69 | 250000 | 350000 | -100000 | 7810.84 | 250000 | 2026-01-31 | 0 | 250000
55.12 | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 | MM | ALL | 198075877 | 99.84% | 197751131.77 | 197751131.77 | 0 | 0 | 0 | 324745.23 | 0 | 2027-07-31 | 0 | 0
55.1201 | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out | MM | ALL |  | 96.05% | 0 | -7779994.28 | 7779994.28 | 5995115.13 | 1784879.15 | 0 | 8100000 | 2027-07-31 | 0 | 8100000 | OH for 55.1200
55.1202 | LA County Sanitation District - Oxygen Generation Project | AB | MC | 16396051.58 | 63.01% | 10330718.4749 | 9590124.35 | 740594.1249 | 647450.7063 | 93143.4186 | 6065333.1051 | 1175409 | 2026-08-01 | 0 | 1175409
55.1204 | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 | KS | ALL | 57722227 | 99.75% | 57575368.22 | 57575368.22 | 0 | 0 | 0 | 146858.78 | 0 | 2027-08-31 | 0 | 0
55.1205 | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out | KS | ALL |  | 94.48% | 0 | -2362039.01 | 2362039.01 | 1917801.19 | 444237.82 | 0 | 2500000 | 2027-08-31 | 0 | 2500000 | OH for 55.1204
55.1227 | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | SM | RA | 41504206.39 | 99.46% | 41279468.4824 | 36953022.96 | 4326445.5224 | 3399354.1719 | 927091.3505 | 224737.9076 | 4350000 | 2026-02-28 | 0 | 4350000
55.1233 | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project | SM | MC | 9838187 | 1.282% | 134506.16 | 126077.16 | 8429 | 8428.84 | 0.16 | 9703680.84 | 0 | 2028-02-28 | 2344.53 | -2344.53 | Moved profits to JV Below
55.1248 | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | JA | MC | 5759301.81 | 73.4% | 4227318.998 | 3621770.22 | 605548.778 | 0 | 605548.778 | 1531982.812 | 825000 | 2026-03-01 | 100000 | 725000
55.1249 | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | SM | RA | 147525113 | 10.77% | 15046313.77 | 15046313.77 | 0 | 0 | 0 | 132478799.23 | 7821208 | 2029-02-01 | 0 | 7821208
55.1254 | JV w/AECOM - City of Banning - Wastewater Treatment Plant Recycled Water | VG | RA | 471896.25 | 33.18% | 156561.66 | 156561.66 | 0 | 0 | 0 | 315334.59 | 0 | 2026-05-25 | 0 | 0 | Moved profits to JV Below
55.1255 | City of Riverside - RWQCP Emergency Repair | KG | JA | 14160.81 | 100% | 14160.81 | 14160.81 | 0 | 0 | 0 | 0 | 0 | 2026-01-31 | 0 | 0 | T&M Repair - Leave open WIP
55.1256 | Anaergia Technologies LLC - City of Riverside - OPS | JA | MC | 2888100 | 3.501% | 94989.88 | 94989.88 | 0 | 0 | 0 | 2793110.12 | 175000 | 2026-03-01 | 0 | 175000
| Murrieta Totals this Month |  |  | 833690058.08 |  | 641453357.8246 | 620195169.09 | 21258188.7346 | 21682038.2067 | -423849.4721 | 192236700.2554 | 30407115 |  | -1394627.67 | 31801742.67
| Murrieta Closed Job Total |  |  | 6861630.35 | 0 | 6861630.35 | 7786658.8 | -925028.45 | 1217319.0687 | -2142347.5187 | 0 | -925028.45 | 0 | -175237.12 | -749791.33
| Murrieta Totals |  |  | 840551688.43 |  | 648314988.1746 | 627981827.89 | 20333160.2846 | 22899357.2754 | -2566196.9908 | 192236700.2554 | 29482086.55 | 0 | -1569864.79 | 31051951.34
JV | East County Advanced Water Purification Project - Package 1 | MR | ALL | 239937310 | 87.83% | 211769168.5 | 203222516.5 | 8546652 | 15750000 | -7203348 | 28168141.5 | 8546652 | 2027-04-02 | -3618554 | 12165206 | Includes December JV Financials
JV | East County Advanced Water Purification Project - Package 3 | MR | ALL | 45865869.5 | 83.25% | 36465046 | 46728002 | -10262956 | -5900000 | -4362956 | 9400823.5 | -10262956 | 2027-02-27 | -2090767 | -8172189 | Includes December JV Financials
JV | LADWP Silverlake Storage Replacement Project | AB | ALL | 91586461.5 | 98.47% | 90175346.75 | 83932670 | 6242676.75 | 6094760 | 147916.75 | 1411114.75 | 6346256.75 | 2029-12-01 | -356.75 | 6346613.5 | Includes December JV Financials
JV | JV w/AECOM - City of Banning - Wastewater Treatment Plant Recycled Water | VG | RA | 1999314 | 28.59% | 571506 | 571506 | 0 | 0 | 0 | 1427808 | 0 | 2026-05-25 | -147696.5 | 147696.5 | Includes December JV Financials
| Murrieta Totals this Month w/ JVs & Closed Jobs | [8 empty] | -13984584.2408 | [7 empty] | Curr Month | 627981827.89
| Murrieta Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | -6955456.9963 | [7 empty] | Company Activity | -11754545.83
| Murrieta Current Month Changes w/ JV's & Closed Jobs | [8 empty] | -7029127.2445 | [8 empty] | 616227282.06
[18 empty] | Prior Month | 616227282.06
Area: | San Diego | [16 empty] | Variance | 0
57.0003 | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | JR | MC | 38165419.5 | 17.67% | 6440831.3025 | 6316909.13 | 123922.1725 | 96385.4118 | 27536.7607 | 31724588.1975 | 2407086 | 2027-04-01 | 0 | 2407086
57.0004 | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | JR | MC | 40106224.63 | 1.98% | 750298.86 | 750298.86 | 0 | 0 | 0 | 39355925.77 | 2209857 | 2026-03-25 | 0 | 2209857 | Project has not started yet
57.0007 | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | MR | RA | 162630 | 100% | 162630 | 196248.4 | -33618.4 | 0 | -33618.4 | 0 | -33618.4 | 2026-01-31 | -1383.3 | -32235.1 | WIP - Do not close
57.0008 | Imperial Irrigation Dist. - El Centro Generating Station WWTP | MR |  | 2876047 | 9.562% | 262382.86 | 262382.86 | 0 | 0 | 0 | 2613664.14 | 132065 | 2026-11-01 | 0 | 132065 | Phase 1 Design GMP to 100% - does not include Phase 2 Construction
| San Diego Totals this Month |  |  | 81310321.13 |  | 7616143.0225 | 7525839.25 | 90303.7725 | 96385.4118 | -6081.6393 | 73694178.1075 | 4715389.6 |  | -1383.3 | 4716772.9
| San Diego Closed Job Total |  |  | 0 | 0 | 0 | 106618.02 | -106618.02 | 0 | -106618.02 | 0 | -106618.02 | 0 | -16243.04 | -90374.98
| San Diego Total |  |  | 81310321.13 |  | 7616143.0225 | 7632457.27 | -16314.2475 | 96385.4118 | -112699.6593 | 73694178.1075 | 4608771.58 |  | -17626.34 | 4626397.92
| San Diego Totals this Month w/ JVs & Closed Jobs | [8 empty] | -112699.6593 | [7 empty] | Curr Month | 7632457.27
| San Diego Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | -122609.8224 | [7 empty] | Company Activity | -1720763.84
| San Diego Current Month Changes w/ JV's & Closed Jobs | [8 empty] | 9910.1631 | [8 empty] | 5911693.43
[18 empty] | Prior Month | 5911693.43
Area: | Los Angeles | [16 empty] | Variance | 0
58.0003 | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | DF | RA | 22525189.2 | 52.01% | 11715063.7148 | 11034781.79 | 680281.9248 | 0 | 680281.9248 | 10810125.4852 | 1308015 | 2026-08-01 | 0 | 1308015
| Los Angeles Totals this Month |  |  | 22525189.2 |  | 11715063.7148 | 11034781.79 | 680281.9248 | 0 | 680281.9248 | 10810125.4852 | 1308015 |  | 0 | 1308015
| Los Angeles Closed Job Total |  |  | 0 | 0 | 0 | 282319.21 | -282319.21 | 0 | -282319.21 | 0 | -282319.21 | 0 | -65732.76 | -216586.45
| Los Angeles Total |  |  | 22525189.2 |  | 11715063.7148 | 11317101 | 397962.7148 | 0 | 397962.7148 | 10810125.4852 | 1025695.79 |  | -65732.76 | 1091428.55
| Los Angeles Totals this Month w/ JVs & Closed Jobs | [8 empty] | 397962.7148 | [7 empty] | Curr Month | 11317101
| Los Angeles Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | 307817.8883 | [7 empty] | Company Activity | -2770322.88
| Los Angeles Current Month Changes w/ JV's & Closed Jobs | [8 empty] | 90144.8264 | [8 empty] | 8546778.12
[18 empty] | Prior Month | 8546778.12
Southern Totals | [17 empty] | Variance | 0
| Southern Totals this Month |  |  | 937525568.41 | 0 | 660784564.5619 | 638755790.13 | 22028774.4319 | 21778423.6185 | 250350.8133 | 276741003.8481 | 36430519.6 | 0 | -1396010.97 | 37826530.57
| Southern Closed Job Total |  |  | 6861630.35 | 0 | 6861630.35 | 8175596.03 | -1313965.68 | 1217319.0687 | -2531284.7487 | 0 | -1313965.68 | 0 | -257212.92 | -1056752.76
| Southern Total |  |  | 944387198.76 | 0 | 667646194.9119 | 646931386.16 | 20714808.7519 | 22995742.6873 | -2280933.9354 | 276741003.8481 | 35116553.92 | 0 | -1653223.89 | 36769777.81
| Southern Totals this Month w/ JVs & Closed Jobs | [8 empty] | -13699321.1854
| Southern Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | -6770248.9304
| Southern Current Month Changes w/ JV's & Closed Jobs | [8 empty] | -6929072.2549
Northern & Southern Construction Totals
| Northern & Southern Totals this Month |  |  | 1857926358.36 | 0 | 1100240948.7851 | 1035075649.36 | 65165299.4251 | 40822789.3991 | 24342510.026 | 757685409.5749 | 124082054.53 | 0 | 530554.45 | 123551500.08
| Northern & Southern Closed Job Total |  |  | 148056766.65 | 0 | 148056766.65 | 136063098.08 | 11993668.57 | 17498674.6545 | -5505006.0845 | 0 | 11993668.57 | 0 | -986896.58 | 12980565.15
| Northern & Southern Total |  |  | 2005983125.01 | 0 | 1248297715.4351 | 1171138747.44 | 77158967.9951 | 58321464.0536 | 18837503.9416 | 757685409.5749 | 136075723.1 | 0 | -456342.13 | 136532065.23
| Northern & Southern Totals this Month w/ JVs & Closed Jobs | [8 empty] | 6564181.0116
| Northern & Southern Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | 10641359.0687
| Northern & Southern Current Month Changes w/ JV's & Closed Jobs | [8 empty] | -4077178.0572
System Integration Totals
| System Integration Totals this Month |  |  | 14022847.25 |  | 7566720.7016 | 6459348.91 | 1107371.7916 | 247627.6836 | 859744.108 | 6456126.5484 | 2055056.86 |  | -30581.31 | 2085638.17
| System Integration Closed Job Total |  |  | 4511779.65 | 0 | 4511779.65 | 7995768.94 | -3483989.29 | 335306.4276 | -3819295.7176 | 0 | -3483989.29 | 0 | 79234.05 | -3563223.34
| System Integration Total |  |  | 18534626.9 |  | 12078500.3516 | 14455117.85 | -2376617.4984 | 582934.1113 | -2959551.6097 | 6456126.5484 | -1428932.43 |  | 48652.74 | -1477585.17
| System Integration Totals this Month w/ JVs & Closed Jobs | [8 empty] | -2959551.6097
| System Integration Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | -3153564.4264
| System Integration Current Month Changes w/ JV's & Closed Jobs | [8 empty] | 194012.8167
Infrastructure and System Integration Grand Totals
| Infrastructure & System Integration Totals this Month |  |  | 1871949205.61 | 0 | 1107807669.4867 | 1041534998.27 | 66272671.2167 | 41070417.0828 | 25202254.134 | 764141536.1233 | 126137111.39 | 0 | 499973.14 | 125637138.25
| Infrastructure & System Integration Closed Job Total |  |  | 152568546.3 | 0 | 152568546.3 | 144058867.02 | 8509679.28 | 17833981.0821 | -9324301.8021 | 0 | 8509679.28 | 0 | -907662.53 | 9417341.81
| Infrastructure & System Integration Total |  |  | 2024517751.91 | 0 | 1260376215.7867 | 1185593865.29 | 74782350.4967 | 58904398.1649 | 15877952.3319 | 764141536.1233 | 134646790.67 | 0 | -407689.39 | 135054480.06
| Infrastructure & System Integration Totals this Month w/ JVs & Closed Jobs | [8 empty] | 3604629.4019
| Infrastructure & System Integration Prior Month Totals w/ JV's & Closed Jobs | [8 empty] | 7487794.6423
| Infrastructure & System Integration Current Month Changes w/ JV's & Closed Jobs | [8 empty] | -3883165.2405
[6 empty] | Curr Month | 1171138747.44
[6 empty] | Company Activity | -39411618.95
1131727128.49
[6 empty] | Prior Month | 1131727128.49
[6 empty] | Variance | 0
Note on E37: Tony Mueller: From JCR Cell G39
Note on H37: Tony Mueller: From JCR Cell H34
Note on M37: Tony Mueller: From JCR Cell K44 Took JCR total plus $617,760 in interest generated from escrow account plus

## Closed Jobs
[12 empty] | Month: | 2025-12-31
[12 empty] | Anticipated |  | Change in | Previous
Job | Customer and | Project |  | Contract | % | Revenue | Cost | Profit | Prior Year | Current | Revenue | Total | Completion | Anticipated | Anticipated
No. | Description | Sup | Est | Amount | Comp | to Date | to Date | to Date | Profit | Profit | Remaining | Profit | Date | Profit | Profits
Northern Closed Jobs
Area: | Rocklin
51.1133 | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | AH | KS | 372738 | 100% | 372738 | 331855.28 | 40882.72 | 17359.5806 | 23523.1394 | 0 | 40882.72 | 2025-03-31 | 0 | 40882.72
51.1136 | Union Sanitary Dist - USD Plant Misc. Improvements | SS | MV | 5483550 | 100% | 5483550 | 4531817.86 | 951732.14 | 758905.7861 | 192826.3539 | 0 | 951732.14 | 2026-01-31 | -281873.86 | 1233606
51.1138 | CA Water Service Co. - Bear Gulch Pump Station 21 | AH | KS | 1120182.07 | 100% | 1120182.07 | 1167704.15 | -47522.08 | 77778.0991 | -125300.1791 | 0 | -47522.08 | 2025-05-25 | 0 | -47522.08
51.1139 | CA Water Service Co. - Bear Gulch Pump Station 14/29 | AH | KS | 61902 | 100% | 61902 | 56994.44 | 4907.56 | 4426.359 | 481.201 | 0 | 4907.56 | 2026-01-31 | -5300.17 | 10207.73
51.1141 | City of Colfax - WWTP Algae Reduction Project | EG | MV | 3967189.79 | 100% | 3967189.79 | 3835094.73 | 132095.06 | 79920.2987 | 52174.7613 | 0 | 132095.06 | 2025-04-30 | 0 | 132095.06
51.1143 | Olivehurst Plumas Lake Manganese Filter Expansion | JL | MV | 1991231.37 | 100% | 1991231.37 | 1758132.57 | 233098.8 | 226011.7629 | 7087.0371 | 0 | 233098.8 | 2025-06-25 | 0 | 233098.8
51.1147 | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | JL | MV | 2742860.08 | 100% | 2742860.08 | 2548724.92 | 194135.16 | 128284.5352 | 65850.6248 | 0 | 194135.16 | 2026-01-31 | -111.5 | 194246.66
51.115 | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | MV | TBD | 2486231.58 | 100% | 2486231.58 | 2239435.14 | 246796.44 | 166471.8295 | 80324.6105 | 0 | 246796.44 | 2025-03-31 | 0 | 246796.44
51.1156 | Rocklin Overhead 2025 | DC | DC |  | 100% | 0 | 1426058.69 | -1426058.69 | 0 | -1426058.69 | 0 | -1426058.69 | 2025-12-31 | -176737.46 | -1249321.23
51.1157 | Rocklin Estimating 2025 | DC | DC |  | 100% | 0 | 613546.52 | -613546.52 | 0 | -613546.52 | 0 | -613546.52 | 2025-12-31 | -61155.97 | -552390.55
| Rocklin Totals this Month |  |  | 18225884.89 |  | 18225884.89 | 18509364.3 | -283479.41 | 1459158.2509 | -1742637.6609 | 0 | -283479.41 |  | -525178.96 | 241699.55
Area: | Fresno
52.8567 | City of Modesto - Grayson Well 69 | DG | KA | 3059858.99 | 100% | 3059858.99 | 3128023.93 | -68164.94 | -83000 | 14835.06 | 0 | -68164.94 | 2025-05-30 | 0 | -68164.94
52.8604 | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | TC | GK | 5095690.97 | 100% | 5095690.97 | 4572503.23 | 523187.74 | 329989.1327 | 193198.6073 | 0 | 523187.74 | 2025-06-30 | 0 | 523187.74
52.8628 | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | AKC | SF | 5213345.5 | 100% | 5213345.5 | 4745798.53 | 467546.97 | 197224.7538 | 270322.2162 | 0 | 467546.97 | 2025-12-31 | 42546.97 | 425000
52.8631 | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | DG | KA | 2560650.14 | 100% | 2560650.14 | 2448658.26 | 111991.88 | 73003.7005 | 38988.1795 | 0 | 111991.88 | 2025-12-31 | -5008.12 | 117000
52.8652 | California Water Service Co. - Salinas 77 Booster Station | PR | KA | 1290184 | 100% | 1290184 | 1039376.08 | 250807.92 | 170698.8374 | 80109.0826 | 0 | 250807.92 | 2025-09-11 | 0 | 250807.92
52.8658 | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | MDA | SF | 1870914.99 | 100% | 1870914.99 | 1633530.21 | 237384.78 | 148751 | 88633.78 | 0 | 237384.78 | 2025-07-30 | 0 | 237384.78
52.8663 | Root Creek Water Dist. - Ag Well 277 Conversion Project | LP | RM | 1641800 | 100% | 1641800 | 1379688.28 | 262111.72 | 42676.9508 | 219434.7692 | 0 | 262111.72 | 2026-02-28 | 2111.72 | 260000
52.8667 | California Water Service Co. - Cal Water Salinas Station 33 | EB | KA | 314085.77 | 100% | 314085.77 | 290726.11 | 23359.66 | 26868.8653 | -3509.2053 | 0 | 23359.66 | 2025-05-31 | 0 | 23359.66
52.867 | California Water Service Co. - Cal Water - King City Station 10 | EB | SF | 274166.01 | 100% | 274166.01 | 267282.05 | 6883.96 | 10404.4356 | -3520.4756 | 0 | 6883.96 | 2025-06-30 | 0 | 6883.96
52.8674 | City of Hanford - WWTP Standby Influent Pump Install | DG | SF | 279244 | 100% | 279244 | 251088.2 | 28155.8 | 15534.5836 | 12621.2164 | 0 | 28155.8 | 2025-01-31 | 0 | 28155.8
52.8677 | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | DG | SF | 796055.3 | 100% | 796055.3 | 689831.96 | 106223.34 | 0 | 106223.34 | 0 | 106223.34 | 2025-12-31 | 18223.34 | 88000
52.868 | City of Orange Cove - Orange Cove West Clarifier T&M | DG | DG | 29838.25 | 100% | 29838.25 | 26088.33 | 3749.92 | 0 | 3749.92 | 0 | 3749.92 | 2025-06-30 | 0 | 3749.92
52.8682 | Fresno Overhead 2025 | RM | RM |  | 100% | 0 | 1121157.1 | -1121157.1 | 0 | -1121157.1 | 0 | -1121157.1 | 2025-12-31 | -156002.73 | -965154.37
52.8683 | Fresno Estimating 2025 | RM | RM |  | 100% | 0 | 415452.52 | -415452.52 | 0 | -415452.52 | 0 | -415452.52 | 2025-12-31 | -64541.14 | -350911.38
52.8684 | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | JL | JL | 50568.05 | 100% | 50568.05 | 45291.39 | 5276.66 | 0 | 5276.66 | 0 | 5276.66 | 2025-10-09 | 830.03 | 4446.63
52.8685 | Malaga County Water Dist. - Malaga County Water District | DG | JS | 451254 | 100% | 451254 | 382067.32 | 69186.68 | 0 | 69186.68 | 0 | 69186.68 | 2025-12-31 | 34186.68 | 35000
52.8686 | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | LP | LP | 23957 | 100% | 23957 | 7505.26 | 16451.74 | 15372.2567 | 1079.4833 | 0 | 16451.74 | 2025-12-31 | 0 | 16451.74
52.8688 | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | DG | DG | 132492.2 | 100% | 132492.2 | 116972.75 | 15519.45 | 0 | 15519.45 | 0 | 15519.45 | 2025-08-31 | 0 | 15519.45
52.8689 | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | DG | DG | 16665.83 | 100% | 16665.83 | 16095.58 | 570.25 |  | 570.25 | 0 | 570.25 | 2025-05-31 | 0 | 570.25
52.869 | City of Dinuba - WWTP Rake Replacement | DG | DG | 14151.97 | 100% | 14151.97 | 13155.83 | 996.14 |  | 996.14 | 0 | 996.14 | 2025-05-02 | 0 | 996.14
52.8691 | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | TC | TC | 11302.84 | 100% | 11302.84 | 8287.82 | 3015.02 | 0 | 3015.02 | 0 | 3015.02 | 2025-06-30 | 0 | 3015.02
52.8693 | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | AC | RH | 1120704.2 | 100% | 1120704.2 | 663140.99 | 457563.21 | 0 | 457563.21 | 0 | 457563.21 | 2025-12-31 | 27563.21 | 430000
52.8694 | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | JL | JL | 43047.45 | 100% | 43047.45 | 38541.99 | 4505.46 | 0 | 4505.46 | 0 | 4505.46 | 2025-04-30 | 0 | 4505.46
52.8695 | Lyles Services Co. - LSC GO Trash Enclosure | LP | LP | 13769 | 100% | 13769 | 13024.37 | 744.63 | 0 | 744.63 | 0 | 744.63 | 2025-06-30 | 0 | 744.63
52.8696 | American Paving Co. - Hot Tap for APC- Tule River Parkway | DG | DG | 1059.22 | 100% | 1059.22 | 887.65 | 171.57 |  | 171.57 | 0 | 171.57 | 2025-05-31 | 0 | 171.57
52.8699 | City of Hanford - WWTP Repair T&M | DG | DG | 3001.12 | 100% | 3001.12 | 2948.91 | 52.21 | 0 | 52.21 | 0 | 52.21 | 2025-06-30 | 0 | 52.21
52.87 | Lyles Services Co. - LSC GO Misc. Work | LP | LP | 5297 | 100% | 5297 | 4446.13 | 850.87 | 0 | 850.87 | 0 | 850.87 | 2025-12-31 | 500.87 | 350
52.8701 | County of Fresno - 47 Water | AC | AC | 13433.85 | 100% | 13433.85 | 12421.08 | 1012.77 | 0 | 1012.77 | 0 | 1012.77 | 2025-08-31 | -234.89 | 1247.66
52.8702 | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M | DG | DG | 5626.78 | 100% | 5626.78 | 4725.28 | 901.5 | 0 | 901.5 | 0 | 901.5 | 2025-07-31 | 0 | 901.5
52.8703 | County of Fresno - CSA 47 Egret Point Water Line Repair | AC | AC | 14402.18 | 100% | 14402.18 | 12571.54 | 1830.64 | 0 | 1830.64 | 0 | 1830.64 | 2025-08-11 | -341.28 | 2171.92
52.8706 | City of Hanford - WWTP Weld Repair T&M 2 | DG | DG | 2868.6 | 100% | 2868.6 | 2435.78 | 432.82 | 0 | 432.82 | 0 | 432.82 | 2025-09-30 | 0 | 432.82
52.8709 | County of Fresno - 47.1 Water | AC | AC | 17765.14 | 100% | 17765.14 | 14874.36 | 2890.78 |  | 2890.78 | 0 | 2890.78 | 2025-11-30 | -174.78 | 3065.56
52.871 | City of Dinuba - WWTP Bar Screen Motor Bracket Repair | DG | DG | 4064.54 | 100% | 4064.54 | 3514.84 | 549.7 |  | 549.7 | 0 | 549.7 | 2025-11-30 | 0 | 549.7
52.8715 | New England Sheet Metal and Mechanical Co. - Vitro Glass Plant Concrete Pad T&M | DG | DG | 10001.43 | 100% | 10001.43 | 8585.44 | 1415.99 |  | 1415.99 | 0 | 1415.99 | 2026-01-31 | 1415.99
| Fresno Totals this Month |  |  | 24381266.32 |  | 24381266.32 | 23380699.1 | 1000567.22 | 947524.5165 | 53042.7035 | 0 | 1000567.22 |  | -98924.13 | 1099491.35
Area: | East Bay
53.2004 | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | RB | MV | 1173753.47 | 100% | 1173753.47 | 980791.05 | 192962.42 | 0 | 192962.42 | 0 | 192962.42 | 2026-01-31 | 9072.42 | 183890
53.2005 | East Bay Overhead 2025 | RB | RB |  | 100% | 0 | 279281.96 | -279281.96 | 0 | -279281.96 | 0 | -279281.96 | 2025-12-31 | -36895.25 | -242386.71
53.2006 | East Bay Estimating 2026 | RB | RB |  | 100% | 0 | 304986.32 | -304986.32 | 0 | -304986.32 | 0 | -304986.32 | 2025-12-31 | -37.1 | -304949.22
| East Bay Totals this Month |  |  | 1173753.47 |  | 1173753.47 | 1565059.33 | -391305.86 | 0 | -391305.86 | 0 | -391305.86 |  | -27859.93 | -363445.93
Area: | Bakersfield
54.9099 | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | PR | KSH | 55712110 | 100% | 55712110 | 45328892.68 | 10383217.32 | 10372751.5815 | 10465.7385 | 0 | 10383217.32 | 2025-12-31 | 8217.32 | 10375000
54.9172 | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | AH | RA | 24160002.44 | 100% | 24160002.44 | 21018432.22 | 3141570.22 | 3076351.4492 | 65218.7708 | 0 | 3141570.22 | 2025-03-01 | 0 | 3141570.22
54.9216 | CA Dept. of Corr. - Water Treatment Improvements | DS | DS | 2472164.05 | 100% | 2472164.05 | 2286264.43 | 185899.62 | 140849.7535 | 45049.8665 | 0 | 185899.62 | 2025-09-25 | -196.73 | 186096.35
54.9246 | Kern County Water Agency - Well 38 & 39 Well Equipping Project | DS | SF | 1777852 | 100% | 1777852 | 1708475.32 | 69376.68 | 69196.4543 | 180.2257 | 0 | 69376.68 | 2025-12-31 | 9376.68 | 60000
54.9265 | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | DS | DS | 223896.47 | 100% | 223896.47 | 220754.51 | 3141.96 | 0 | 3141.96 | 0 | 3141.96 | 2025-05-30 | 0 | 3141.96
54.9279 | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | RF | KA | 3216240.01 | 100% | 3216240.01 | 3153237.4 | 63002.61 | -15000 | 78002.61 | 0 | 63002.61 | 2025-08-01 | 0 | 63002.61
54.9289 | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | KSH | KSH | 44560 | 100% | 44560 | 25097.25 | 19462.75 | 669.81 | 18792.94 | 0 | 19462.75 | 2026-12-01 | 0 | 19462.75
54.9292 | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | KSH | KSH | 4300 | 100% | 4300 | 1313.45 | 2986.55 | 2986.55 | 0 | 0 | 2986.55 | 2025-12-31 | 0 | 2986.55
54.9309 | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | AH | SF | 3968668.9 | 100% | 3968668.9 | 3790858.34 | 177810.56 | 62853.4158 | 114957.1442 | 0 | 177810.56 | 2025-12-25 | 12810.56 | 165000
54.9323 | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | DS | DS | 110661.47 | 100% | 110661.47 | 94483.21 | 16178.26 | 0 | 16178.26 | 0 | 16178.26 | 2025-03-31 | 0 | 16178.26
54.9329 | Kern Water Bank Authority - Valve Replacement Parts | DS | DS | 18201.12 | 100% | 18201.12 | 16466.72 | 1734.4 |  | 1734.4 | 0 | 1734.4 | 2025-10-01 | 0 | 1734.4
54.9333 | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | DS | DS | 427464.77 | 100% | 427464.77 | 371915.26 | 55549.51 | 14888.68 | 40660.83 | 0 | 55549.51 | 2025-03-01 | -3099.97 | 58649.48
54.9338 | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | PR | PR | 175884.64 | 100% | 175884.64 | 119186.11 | 56698.53 | 54179.7977 | 2518.7323 | 0 | 56698.53 | 2025-01-31 | 0 | 56698.53
54.9341 | Nipomo Community Service Dist. - Water Project Interconnection Improvements | PR | PR | 1251279 | 100% | 1251279 | 1063532.4 | 187746.6 | 0 | 187746.6 | 0 | 187746.6 | 2025-12-31 | 415.6 | 187331
54.9342 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | DS | DS | 199161.5 | 100% | 199161.5 | 124146.3 | 75015.2 | 41394.1127 | 33621.0873 | 0 | 75015.2 | 2025-01-31 | 0 | 75015.2
54.9347 | City of Guadalupe - Effluent Pump Station Flow Meter Installation | JG | PR | 7100 | 100% | 7100 | 3227.7 | 3872.3 |  | 3872.3 | 0 | 3872.3 | 2025-02-28 | 0 | 3872.3
54.9349 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | DS | DS | 290129 | 100% | 290129 | 197889.31 | 92239.69 | 4519.6837 | 87720.0063 | 0 | 92239.69 | 2025-02-28 | 0 | 92239.69
54.935 | Kern Water Bank Authority - Construct New Well 18P01 | DS | DS | 129965.06 | 100% | 129965.06 | 120318.68 | 9646.38 | 0 | 9646.38 | 0 | 9646.38 | 2025-03-31 | 0 | 9646.38
54.9351 | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | RF | RF | 153298.79 | 100% | 153298.79 | 136808.3 | 16490.49 | 11095.2671 | 5395.2229 | 0 | 16490.49 | 2025-01-31 | 0 | 16490.49
54.9353 | Kern Water Bank Authority - Cut In Valve at Well 18R01 | DS | DS | 2008.42 | 100% | 2008.42 | 1117.5 | 890.92 | 0 | 890.92 | 0 | 890.92 | 2025-03-31 | 0 | 890.92
54.9354 | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | DS | DS | 9571.2 | 100% | 9571.2 | 8230.83 | 1340.37 | 1923.43 | -583.06 | 0 | 1340.37 | 2025-01-31 | 0 | 1340.37
54.9355 | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | DS | DS | 2806.42 | 100% | 2806.42 | 1815.23 | 991.19 | 0 | 991.19 | 0 | 991.19 | 2025-03-31 | 0 | 991.19
54.9357 | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | DS | DS | 1760.42 | 100% | 1760.42 | 889.66 | 870.76 | 0 | 870.76 | 0 | 870.76 | 2025-03-31 | 0 | 870.76
54.9358 | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | AH | SF | 1147640 | 100% | 1147640 | 1125399.83 | 22240.17 | 15917.5507 | 6322.6193 | 0 | 22240.17 | 2025-09-25 | 0 | 22240.17
54.936 | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | DS | DS | 1855.92 | 100% | 1855.92 | 1144.88 | 711.04 | 0 | 711.04 | 0 | 711.04 | 2025-03-31 | 0 | 711.04
54.9361 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | DS | DS | 108668.35 | 100% | 108668.35 | 107074.87 | 1593.48 |  | 1593.48 | 0 | 1593.48 | 2025-03-30 | 0 | 1593.48
54.9362 | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | AH | AH | 425035.04 | 100% | 425035.04 | 375601.24 | 49433.8 | 18050.9922 | 31382.8078 | 0 | 49433.8 | 2025-01-25 | 0 | 49433.8
54.9363 | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | DS | DS | 1855.92 | 100% | 1855.92 | 777.55 | 1078.37 | 0 | 1078.37 | 0 | 1078.37 | 2025-03-31 | 0 | 1078.37
54.9365 | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | DS | DS | 2216.42 | 100% | 2216.42 | 1263.33 | 953.09 | 0 | 953.09 | 0 | 953.09 | 2025-03-31 | 0 | 953.09
54.9367 | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | DS | DS | 2540.42 | 100% | 2540.42 | 1602.33 | 938.09 | 0 | 938.09 | 0 | 938.09 | 2025-03-31 | 0 | 938.09
54.9368 | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | DS | DS | 15697.91 | 100% | 15697.91 | 13653.62 | 2044.29 | 2044.29 | 0 | 0 | 2044.29 | 2025-01-31 | 0 | 2044.29
54.937 | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | DS | DS | 1760.42 | 100% | 1760.42 | 889.64 | 870.78 | 0 | 870.78 | 0 | 870.78 | 2025-03-31 | 0 | 870.78
54.9371 | Bakersfield Overhead 2025 | JJM | JJM |  | 100% | 0 | 1267652.77 | -1267652.77 | 0 | -1267652.77 | 0 | -1267652.77 | 2025-12-31 | -70266.13 | -1197386.64
54.9372 | Bakersfield Estimating 2025 | JJM | JJM |  | 100% | 0 | 588792.6 | -588792.6 | 0 | -588792.6 | 0 | -588792.6 | 2025-12-31 | -39388.72 | -549403.88
54.9374 | City of Santa Maria - WWTP Trickling Filter Repairs | PR | PR | 32962 | 100% | 32962 | 19986.45 | 12975.55 |  | 12975.55 | 0 | 12975.55 | 2025-03-31 | 0 | 12975.55
54.9375 | City of Santa Maria - WWTP Clarifier Repairs | PR | PR | 8232.73 | 100% | 8232.73 | 4545.48 | 3687.25 |  | 3687.25 | 0 | 3687.25 | 2025-03-13 | 0 | 3687.25
54.9379 | Semitropic Water Storage Dist. - Delta System Pipe Repair | DS | DS | 41679.77 | 100% | 41679.77 | 36111.95 | 5567.82 |  | 5567.82 | 0 | 5567.82 | 2025-02-28 | 0 | 5567.82
54.938 | Cawelo Water Dist. - CWD Pump Station Pipe Repair | RF | AH | 22446.19 | 100% | 22446.19 | 18064.72 | 4381.47 |  | 4381.47 | 0 | 4381.47 | 2025-03-25 | 0 | 4381.47
54.9381 | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | DS | DS | 58900 | 100% | 58900 | 28875.38 | 30024.62 |  | 30024.62 | 0 | 30024.62 | 2025-03-30 | 0 | 30024.62
54.9382 | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | PR | PR | 143799 | 100% | 143799 | 108690.45 | 35108.55 | 0 | 35108.55 | 0 | 35108.55 | 2026-01-31 | 2108.55 | 33000
54.9383 | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | DS | DS | 17542.44 | 100% | 17542.44 | 15759.76 | 1782.68 |  | 1782.68 | 0 | 1782.68 | 2025-12-30 | 0 | 1782.68
54.9384 | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | DS | DS | 79531.98 | 100% | 79531.98 | 70340.57 | 9191.41 |  | 9191.41 | 0 | 9191.41 | 2025-04-30 | 0 | 9191.41
54.9385 | Westside Water Authority - Pump Station A - Electrical Controls and Civil | DS | DS | 102913.84 | 100% | 102913.84 | 98598.77 | 4315.07 | 0 | 4315.07 | 0 | 4315.07 | 2025-05-25 | 0 | 4315.07
54.9386 | Kern Valley State Prison - Arsenic Pipe Leak Repair | DS | DS | 96086 | 100% | 96086 | 75784.74 | 20301.26 |  | 20301.26 | 0 | 20301.26 | 2025-06-30 | 0 | 20301.26
54.9387 | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | PR | PR | 22619.54 | 100% | 22619.54 | 19011.65 | 3607.89 |  | 3607.89 | 0 | 3607.89 | 2025-08-01 | 0 | 3607.89
54.9388 | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | AH | AH | 7454.07 | 100% | 7454.07 | 6535.41 | 918.66 |  | 918.66 | 0 | 918.66 | 2025-07-01 | 0 | 918.66
54.939 | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | RF | RF | 101491.67 | 100% | 101491.67 | 96329.49 | 5162.18 |  | 5162.18 | 0 | 5162.18 | 2025-06-01 | 0 | 5162.18
54.9392 | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | RF | RF | 217648.89 | 100% | 217648.89 | 208346.69 | 9302.2 | 0 | 9302.2 | 0 | 9302.2 | 2025-12-31 | 2302.2 | 7000
54.9393 | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | DS | DS | 31523.02 | 100% | 31523.02 | 27539.82 | 3983.2 |  | 3983.2 | 0 | 3983.2 | 2025-06-30 | 0 | 3983.2
54.9394 | City of Arvin - Haven Drive Lateral Repair | DS | DS | 15966.99 | 100% | 15966.99 | 14039.55 | 1927.44 |  | 1927.44 | 0 | 1927.44 | 2025-06-30 | 0 | 1927.44
54.9398 | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | JG | PR | 14300 | 100% | 14300 | 8192.79 | 6107.21 | 0 | 6107.21 | 0 | 6107.21 | 2025-07-25 | 0 | 6107.21
54.9399 | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | PR | PR | 24775 | 100% | 24775 | 11291.59 | 13483.41 |  | 13483.41 | 0 | 13483.41 | 2025-06-01 | 0 | 13483.41
54.94 | Arvin Edison Water Storage Dist. - FFPP Core Drilling | RF | RF | 800.69 | 100% | 800.69 | 771.32 | 29.37 |  | 29.37 | 0 | 29.37 | 2025-08-01 | 0 | 29.37
54.9401 | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R | RF | RF | 247539.61 | 100% | 247539.61 | 236312.57 | 11227.04 | 0 | 11227.04 | 0 | 11227.04 | 2025-11-25 | 0 | 11227.04
54.9407 | Semitropic Water Storage Dist. - North Plant Emergency Repair | DS | DS | 31296.85 | 100% | 31296.85 | 25667.34 | 5629.51 | 0 | 5629.51 | 0 | 5629.51 | 2025-10-01 | 0 | 5629.51
54.9409 | Nipomo CSD Osage Emergency Waterline Repair | PR | PR | 20123.71 | 100% | 20123.71 | 17411.71 | 2712 | 0 | 2712 | 0 | 2712 | 2025-12-01 | 0 | 2712
54.941 | SWID - Burbank St. Repair | DS | DS | 8241.55 | 100% | 8241.55 | 6965.65 | 1275.9 | 0 | 1275.9 | 0 | 1275.9 | 2025-10-01 | 0 | 1275.9
| Bakersfield Totals this Month |  |  | 97414231.62 |  | 97414231.62 | 84432379.32 | 12981852.3 | 13874672.8184 | -892820.5184 | 0 | 12981852.3 |  | -77720.64 | 13059572.94
Northern Closed Jobs Totals
| Northern Totals this Month |  |  | 141195136.3 |  | 141195136.3 | 127887502.05 | 13307634.25 | 16281355.5857 | -2973721.3357 | 0 | 13307634.25 |  | -729683.66 | 14037317.91
Southern Closed Jobs
Area: | Murrieta
55.123 | Anaergia Technologies - VVWRA - DAF 3 Replacement | SM | RA | 2273682.69 | 100% | 2273682.69 | 1665145.3 | 608537.39 | 480252.0335 | 128285.3565 | 0 | 608537.39 | 2025-03-31 | 0 | 608537.39
55.1231 | City of Corona - WRF 1 Aeration System Improvements | IA | MC | 4046200 | 100% | 4046200 | 3321856.36 | 724343.64 | 627907.3954 | 96436.2446 | 0 | 724343.64 | 2025-03-31 | 0 | 724343.64
55.1238 | Anaergia Technologies LLC - East County Package 5 | VG | MC | 34207.53 | 100% | 34207.53 | 32500.86 | 1706.67 | 8107.48 | -6400.81 | 0 | 1706.67 | 2026-12-31 | -499.55 | 2206.22
55.125 | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | SM | MC | 184557.17 | 100% | 184557.17 | 48293.94 | 136263.23 | 101052.1598 | 35211.0702 | 0 | 136263.23 | 2025-03-31 | 0 | 136263.23
55.1251 | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | IA | RA | 322982.96 | 100% | 322982.96 | 284221.86 | 38761.1 |  | 38761.1 | 0 | 38761.1 | 2025-04-25 | 0 | 38761.1
55.1252 | Murrieta Overhead 2025 | JA | JA |  | 100% | 0 | 1958826.45 | -1958826.45 | 0 | -1958826.45 | 0 | -1958826.45 | 2025-12-31 | -154979.89 | -1803846.56
55.1253 | Murrieta Estimating 2025 | JA | JA |  | 100% | 0 | 475814.03 | -475814.03 | 0 | -475814.03 | 0 | -475814.03 | 2025-12-31 | -19757.68 | -456056.35
| Murrieta Totals this Month |  |  | 6861630.35 |  | 6861630.35 | 7786658.8 | -925028.45 | 1217319.0687 | -2142347.5187 | 0 | -925028.45 |  | -175237.12 | -749791.33
Area: | San Diego
57.0005 | San Diego Overhead 2025 | MR | MM |  | 100% | 0 | 92874.26 | -92874.26 | 0 | -92874.26 | 0 | -92874.26 | 2025-12-31 | -12910.6 | -79963.66
57.0006 | San Diego Estimating 2025 | MR | MM |  | 100% | 0 | 13743.76 | -13743.76 | 0 | -13743.76 | 0 | -13743.76 | 2025-12-31 | -3332.44 | -10411.32
| San Diego Totals this Month |  |  | 0 |  | 0 | 106618.02 | -106618.02 | 0 | -106618.02 | 0 | -106618.02 |  | -16243.04 | -90374.98
Area: | Los Angeles
58.0004 | Los Angeles Overhead 2025 | JA | JA |  | 100% | 0 | 147282.12 | -147282.12 | 0 | -147282.12 | 0 | -147282.12 | 2025-12-31 | -7983.11 | -139299.01
58.0005 | Los Angeles Estimating 2025 | JA | JA |  | 100% | 0 | 135037.09 | -135037.09 | 0 | -135037.09 | 0 | -135037.09 | 2025-12-31 | -57749.65 | -77287.44
| Los Angeles Totals this Month |  |  | 0 |  | 0 | 282319.21 | -282319.21 | 0 | -282319.21 | 0 | -282319.21 |  | -65732.76 | -216586.45
Southern Closed Jobs Totals
| Southern Totals this Month |  |  | 6861630.35 | 0 | 6861630.35 | 8175596.03 | -1313965.68 | 1217319.0687 | -2531284.7487 | 0 | -1313965.68 | 0 | -257212.92 | -1056752.76
Northern & Southern Construction Closed Jobs Totals
| Northern & Southern Totals this Month |  |  | 148056766.65 | 0 | 148056766.65 | 136063098.08 | 11993668.57 | 17498674.6545 | -5505006.0845 | 0 | 11993668.57 | 0 | -986896.58 | 12980565.15