## Revenue
Month | Contract | Description | GAAP Overide Revenue Projection | Ops Overide Revenue Projection | Bonus Profit | Anticipated Completion Date
2025-12-01 | 51.1108. | JV w/AECOM - Stockton - RWCF Phase 2A/2B | 94045647.86 | 94196098 | 858269 | 2026-03-28
2025-12-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) | 0 | 0 | 3462489.91 | 2026-03-28
2025-12-01 | 51.1129. | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications | 126483580.84 | 126483580.84 | 9058793.1561 | 2027-06-25
2025-12-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 | 1312151.46 | 1312151.46 | 98821.6971 | 2026-01-31
2025-12-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project | 14969566 | 14969566 | 686378.1678 | 2026-12-20
2025-12-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility | 60980234 | 60980234 | 13941012.0673 | 2026-02-28
2025-12-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 10658200 | 10658200 | 282748.3956 | 2026-11-25
2025-12-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project | 19974489.34 | 19974489.34 | 973265.2121 | 2026-06-30
2025-12-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement | 562824.68 | 562824.68 | 79717.365 | 2026-01-31
2025-12-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 13363835 | 13363835 | 831806.952 | 2026-02-15
2025-12-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out | 0 | 0 | 1783379.97 | 2026-02-28
2025-12-01 | 51.1158. | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 104446 | 104446 | 0 | 2026-05-31
2025-12-01 | 51.1159. | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 1199000 | 1199000 | 87669.5843 | 2026-03-15
2025-12-01 | 51.1160. | City of Galt Public Works - Industrial WWTP Expansion | 1757000 | 1757000 | 0 | 2026-09-20
2025-12-01 | 51.1161. | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | 10848599.45 | 10848599.45 | 0 | 2026-12-10
2025-12-01 | 51.1162. | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project | 6029750 | 6029750 | 0 | 2027-10-21
2025-12-01 | 51.1164. | CA Water Service Co. - Stockton Roofing | 387260 | 387260 | 0 | 2026-03-31
2025-12-01 | 51.1165. | City of Yuba City - WTP Aquifer Storage and Recovery Well No. 3 | 5304500 | 5304500 | 0 | 2027-09-30
2025-12-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 372738 | 372738 | 40882.72 | 2025-09-30
2025-12-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements | 5483550 | 5483550 | 951732.14 | 2025-12-31
2025-12-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 | 1120182.07 | 1120182.07 | -47522.08 | 2025-11-30
2025-12-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 61902 | 61902 | 4907.56 | 2025-12-31
2025-12-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project | 3967189.79 | 3967189.79 | 132095.06 | 2025-09-30
2025-12-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion | 1991231.37 | 1991231.37 | 233098.8 | 2025-06-25
2025-12-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2742860.08 | 2742860.08 | 194135.16 | 2025-10-31
2025-12-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2486231.58 | 2486231.58 | 246796.44 | 2025-09-30
2025-12-01 | 51.1156. | Rocklin Overhead 2025 | 0 | 0 | -1426058.69 | 2025-12-31
2025-12-01 | 51.1157. | Rocklin Estimating 2025 | 0 | 0 | -613546.52 | 2025-12-31
2025-12-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 1134038.13 | 1174182.73 | 0 | 2026-02-06
2025-12-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out | 0 | 0 | 293385.24 | 2026-02-06
2025-12-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System | 1259398 | 1259398 | 228753.9334 | 2026-02-28
2025-12-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 12611349 | 12611349 | 1932461.6841 | 2026-01-31
2025-12-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 | 13892722.74 | 13892722.74 | 623040.5298 | 2026-05-06
2025-12-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 3656112 | 3642197 | 274987.7789 | 2026-02-28
2025-12-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic | 26264577.65 | 26264577.65 | 1633893.2957 | 2026-02-28
2025-12-01 | 52.8640. | City of Dos Palos - WTP Replacement Project | 38646363.16 | 38646363.16 | 1638259.571 | 2026-04-17
2025-12-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 | 411851 | 411851 | 33071.9833 | 2025-12-31
2025-12-01 | 52.8678. | City of Chowcilla - Well 15 & Generator Improvement Projects | 1240321 | 1240321 | 62141.6719 | 2026-01-31
2025-12-01 | 52.8687. | California Water Service Co. - Salinas Station 205 | 877954 | 877954 | 81654.3612 | 2025-12-31
2025-12-01 | 52.8692. | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 55135.37 | 55135.37 | 5452.88 | 2026-01-31
2025-12-01 | 52.8697. | City of Tulare - Industrial WWTP Dewatering Improvements Pro | 1388000 | 1388000 | 36421.1906 | 2026-07-22
2025-12-01 | 52.8698. | California Water Service Co. - Tesoro Viejo RWSP Liner Repair | 22713 | 22713 | 6232.2321 | 2026-01-31
2025-12-01 | 52.8704. | City of Visalia - Solids Handling Improvements Project | 13744000 | 13744000 | 0 | 2027-01-31
2025-12-01 | 52.8705. | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | 775000 | 775000 | 22119.4417 | 2026-02-28
2025-12-01 | 52.8707. | County of Fresno - Westside Water Tank and Pump Station | 3693200 | 3693200 | 67719.3403 | 2026-07-12
2025-12-01 | 52.8708. | County of Fresno - CSA 44A Wastewater Improvements | 363833 | 363833 | 0 | 2026-02-28
2025-12-01 | 52.8711. | California Water Service Co. - Tesoro Viejo ARV Replacement | 6860 | 6860 | 394.2995 | 2026-01-31
2025-12-01 | 52.8713. | City of Visalia - Remove & Replace Chain and Flight Mechanic | 218842 | 218842 | 0 | 2026-03-31
2025-12-01 | 52.8714. | New England Sheet Metal and Mechanical Co. - VCH Digging Water Line T&M | 5084.94 | 5084.94 | 619.33 | 2026-01-31
2025-12-01 | 52.8567. | City of Modesto - Grayson Well 69 | 3059858.99 | 3059858.99 | -68164.94 | 2025-08-31
2025-12-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 5095690.97 | 5095690.97 | 523187.74 | 2025-08-31
2025-12-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 5213345.5 | 5213345.5 | 467546.97 | 2025-12-31
2025-12-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 2560650.14 | 2560650.14 | 111991.88 | 2025-12-31
2025-12-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station | 1290184 | 1290184 | 250807.92 | 2025-09-11
2025-12-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1870914.99 | 1870914.99 | 237384.78 | 2025-11-30
2025-12-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1641800 | 1641800 | 262111.72 | 2025-12-31
2025-12-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 | 314085.77 | 314085.77 | 23359.66 | 2025-07-31
2025-12-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 | 274166.01 | 274166.01 | 6883.96 | 2025-06-30
2025-12-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install | 279244 | 279244 | 28155.8 | 2025-03-31
2025-12-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 796055.3 | 796055.3 | 106223.34 | 2025-12-31
2025-12-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M | 29838.25 | 29838.25 | 3749.92 | 2025-06-30
2025-12-01 | 52.8682. | Fresno Overhead 2025 | 0 | 0 | -1121157.1 | 2025-12-31
2025-12-01 | 52.8683. | Fresno Estimating 2025 | 0 | 0 | -415452.52 | 2025-12-31
2025-12-01 | 52.8684. | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 50568.05 | 50568.05 | 5276.66 | 2025-11-30
2025-12-01 | 52.8685. | Malaga County Water Dist. - Malaga County Water District | 451254 | 451254 | 69186.68 | 2025-12-31
2025-12-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 23957 | 23957 | 16451.74 | 2025-03-31
2025-12-01 | 52.8688. | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 132492.2 | 132492.2 | 15519.45 | 2025-10-31
2025-12-01 | 52.8689. | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 16665.83 | 16665.83 | 570.25 | 2025-04-30
2025-12-01 | 52.8690. | City of Dinuba - WWTP Rake Replacement | 14151.97 | 14151.97 | 996.14 | 2025-05-02
2025-12-01 | 52.8691. | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 11302.84 | 11302.84 | 3015.02 | 2025-06-30
2025-12-01 | 52.8693. | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 1120704.2 | 1120704.2 | 457563.21 | 2025-12-31
2025-12-01 | 52.8694. | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 43047.45 | 43047.45 | 4505.46 | 2025-06-30
2025-12-01 | 52.8695. | Lyles Services Co. - LSC GO Trash Enclosure | 13769 | 13769 | 744.63 | 2025-06-30
2025-12-01 | 52.8696. | American Paving Co. - Hot Tap for APC- Tule River Parkway | 1059.22 | 1059.22 | 171.57 | 2025-05-31
2025-12-01 | 52.8699. | City of Hanford - WWTP Repair T&M | 3001.12 | 3001.12 | 52.21 | 2025-08-31
2025-12-01 | 52.8700. | Lyles Services Co. - LSC GO Misc. Work | 5297 | 5297 | 850.87 | 2025-12-31
2025-12-01 | 52.8701. | County of Fresno - 47 Water | 13433.85 | 13433.85 | 1012.77 | 2025-07-31
2025-12-01 | 52.8702. | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M | 5626.78 | 5626.78 | 901.5 | 2025-08-31
2025-12-01 | 52.8703. | County of Fresno - CSA 47 Egret Point Water Line Repair | 14402.18 | 14402.18 | 1830.64 | 2025-09-30
2025-12-01 | 52.8706. | City of Hanford - WWTP Weld Repair T&M 2 | 2868.6 | 2868.6 | 432.82 | 2025-09-30
2025-12-01 | 52.8709. | County of Fresno - 47.1 Water | 17765.14 | 17765.14 | 2890.78 | 2025-11-30
2025-12-01 | 52.8710. | City of Dinuba - WWTP Bar Screen Motor Bracket Repair | 4064.54 | 4064.54 | 549.7 | 2025-11-30
2025-12-01 | 52.8715. | New England Sheet Metal and Mechanical Co. - Vitro Glass Plant Concrete Pad T&M | 10001.43 | 10001.43 | 1415.99 | 2025-12-31
2025-12-01 | 53.2007. | Union Sanitary Dist. - Phase 1B Secondary Clarifiers | 324530134 | 324530134 | 0 | 2031-01-31
2025-12-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 1173753.47 | 1173753.47 | 192962.42 | 2025-12-31
2025-12-01 | 53.2005. | East Bay Overhead 2025 | 0 | 0 | -279281.96 | 2025-12-31
2025-12-01 | 53.2006. | East Bay Estimating 2026 | 0 | 0 | -304986.32 | 2025-12-31
2025-12-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 118278.58 | 118278.58 | 13728.31 | 2026-12-01
2025-12-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 9470658.62 | 9470658.62 | 419706.76 | 2026-01-01
2025-12-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station | 1471328 | 1471328 | 24047.4121 | 2026-03-15
2025-12-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 949567.99 | 949567.99 | 65000 | 2026-02-01
2025-12-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 625819.17 | 625819.17 | 34249.05 | 2026-07-01
2025-12-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 462022 | 462022 | 60643.7948 | 2026-02-01
2025-12-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 7886885.04 | 7886885.04 | 947187.1689 | 2026-02-01
2025-12-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 324900 | 324900 | 17179.3594 | 2025-12-31
2025-12-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 25191176.64 | 25191176.64 | 1018189.1429 | 2026-09-09
2025-12-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 4104848 | 4104848 | 61206.5856 | 2026-10-26
2025-12-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 6881300 | 6881300 | 513903.2772 | 2026-05-26
2025-12-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 1298330 | 1298330 | 327018.2615 | 2026-04-30
2025-12-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1230131 | 1230131 | 128209.5181 | 2026-05-26
2025-12-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project | 28550624.7 | 28550624.7 | 0 | 2027-04-01
2025-12-01 | 54.9373. | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 1524766 | 1524766 | 0 | 2026-05-30
2025-12-01 | 54.9389. | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 299780 | 299780 | -15000 | 2026-02-28
2025-12-01 | 54.9391. | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 532604.57 | 532604.57 | 20547.23 | 2026-01-31
2025-12-01 | 54.9395. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 1795652.66 | 1795652.66 | 81279.5912 | 2026-02-26
2025-12-01 | 54.9396. | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | 157746.09 | 157746.09 | 0 | 2026-04-26
2025-12-01 | 54.9397. | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 3690645 | 3690645 | 91581.2841 | 2026-04-01
2025-12-01 | 54.9403. | Lost Hills Utility Dist. - WTP Improvements | 381600 | 381600 | 16597.3591 | 2026-02-26
2025-12-01 | 54.9404. | Cawelo Water Dist. - Reuse of Produced Water | 3720000 | 3720000 | 72797.6822 | 2026-02-27
2025-12-01 | 54.9405. | Semitropic Water Storage Dist. - Pump Platform Replacement Project | 942000 | 942000 | 92504.3113 | 2026-03-26
2025-12-01 | 54.9406. | California Water Service Co. - Emergency PACL leak repair | 1120.65 | 1120.65 | 0 | 2026-01-01
2025-12-01 | 54.9408. | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line | 3777777 | 3777777 | 0 | 2026-07-31
2025-12-01 | 54.9411. | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation | 103300 | 103300 | 22787.6277 | 2026-01-01
2025-12-01 | 54.9412. | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork | 116752.04 | 116752.04 | 1043.16 | 2026-01-01
2025-12-01 | 54.9413. | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork | 149366.83 | 149366.83 | 17228.09 | 2026-01-01
2025-12-01 | 54.9414. | Cawelo Water Dist. - Cawelo Diversion Structure Rehab | 337485.68 | 358674.83 | 19929.7763 | 2026-01-01
2025-12-01 | 54.9416. | California Water Service Co. - BK 147 Station Improvements | 1260000 | 1260000 | 0 | 2026-07-01
2025-12-01 | 54.9417. | County of Santa Barbara-Public Works - Laguna WWTP WAS Pipe Modifications | 48439 | 48439 | 0 | 2026-03-31
2025-12-01 | 54.9418. | GenerateUpcycle - Organics Waste Processing Facility | 15739 | 15739 | 0 | 2026-02-01
2025-12-01 | 54.9421. | Nipomo Community Service Dist. - Tefft Emergency Pipe Repair | 3703.18 | 3703.18 | 0 | 2026-02-28
2025-12-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 55712110 | 55712110 | 10383217.32 | 2025-12-31
2025-12-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 24160002.44 | 24160002.44 | 3141570.22 | 2025-03-01
2025-12-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements | 2472164.05 | 2472164.05 | 185899.62 | 2025-09-25
2025-12-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 1777852 | 1777852 | 69376.68 | 2025-12-31
2025-12-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 223896.47 | 223896.47 | 3141.96 | 2025-07-31
2025-12-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3216240.01 | 3216240.01 | 63002.61 | 2025-08-01
2025-12-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 44560 | 44560 | 19462.75 | 2025-08-01
2025-12-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 4300 | 4300 | 2986.55 | 2025-03-31
2025-12-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3968668.9 | 3968668.9 | 177810.56 | 2025-12-25
2025-12-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 110661.47 | 110661.47 | 16178.26 | 2025-06-30
2025-12-01 | 54.9329. | Kern Water Bank Authority - Valve Replacement Parts | 18201.12 | 18201.12 | 1734.4 | 2025-10-31
2025-12-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 427464.77 | 427464.77 | 55549.51 | 2025-06-30
2025-12-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 175884.64 | 175884.64 | 56698.53 | 2025-03-31
2025-12-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1251279 | 1251279 | 187746.6 | 2025-12-31
2025-12-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 199161.5 | 199161.5 | 75015.2 | 2025-03-31
2025-12-01 | 54.9347. | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 7100 | 7100 | 3872.3 | 2025-04-30
2025-12-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 290129 | 290129 | 92239.69 | 2025-04-30
2025-12-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 | 129965.06 | 129965.06 | 9646.38 | 2025-06-30
2025-12-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 153298.79 | 153298.79 | 16490.49 | 2025-04-30
2025-12-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 2008.42 | 2008.42 | 890.92 | 2025-03-31
2025-12-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 9571.2 | 9571.2 | 1340.37 | 2025-03-31
2025-12-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 2806.42 | 2806.42 | 991.19 | 2025-03-31
2025-12-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 1760.42 | 1760.42 | 870.76 | 2025-03-31
2025-12-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1147640 | 1147640 | 22240.17 | 2025-10-31
2025-12-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1855.92 | 1855.92 | 711.04 | 2025-03-31
2025-12-01 | 54.9361. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 108668.35 | 108668.35 | 1593.48 | 2025-05-31
2025-12-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 425035.04 | 425035.04 | 49433.8 | 2025-03-31
2025-12-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 1855.92 | 1855.92 | 1078.37 | 2025-03-31
2025-12-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 2216.42 | 2216.42 | 953.09 | 2025-03-31
2025-12-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 2540.42 | 2540.42 | 938.09 | 2025-03-31
2025-12-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 15697.91 | 15697.91 | 2044.29 | 2025-03-31
2025-12-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 1760.42 | 1760.42 | 870.78 | 2025-03-31
2025-12-01 | 54.9371. | Bakersfield Overhead 2025 | 0 | 0 | -1267652.77 | 2025-12-31
2025-12-01 | 54.9372. | Bakersfield Estimating 2025 | 0 | 0 | -588792.6 | 2025-12-31
2025-12-01 | 54.9374. | City of Santa Maria - WWTP Trickling Filter Repairs | 32962 | 32962 | 12975.55 | 2025-06-30
2025-12-01 | 54.9375. | City of Santa Maria - WWTP Clarifier Repairs | 8232.73 | 8232.73 | 3687.25 | 2025-03-31
2025-12-01 | 54.9379. | Semitropic Water Storage Dist. - Delta System Pipe Repair | 41679.77 | 41679.77 | 5567.82 | 2025-03-31
2025-12-01 | 54.9380. | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 22446.19 | 22446.19 | 4381.47 | 2025-03-31
2025-12-01 | 54.9381. | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 58900 | 58900 | 30024.62 | 2025-04-30
2025-12-01 | 54.9382. | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 143799 | 143799 | 35108.55 | 2025-12-31
2025-12-01 | 54.9383. | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 17542.44 | 17542.44 | 1782.68 | 2025-05-31
2025-12-01 | 54.9384. | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 79531.98 | 79531.98 | 9191.41 | 2025-07-31
2025-12-01 | 54.9385. | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 102913.84 | 102913.84 | 4315.07 | 2025-11-30
2025-12-01 | 54.9386. | Kern Valley State Prison - Arsenic Pipe Leak Repair | 96086 | 96086 | 20301.26 | 2025-07-31
2025-12-01 | 54.9387. | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 22619.54 | 22619.54 | 3607.89 | 2025-08-31
2025-12-01 | 54.9388. | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 7454.07 | 7454.07 | 918.66 | 2025-06-30
2025-12-01 | 54.9390. | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 101491.67 | 101491.67 | 5162.18 | 2025-08-31
2025-12-01 | 54.9392. | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 217648.89 | 217648.89 | 9302.2 | 2025-12-31
2025-12-01 | 54.9393. | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 31523.02 | 31523.02 | 3983.2 | 2025-06-30
2025-12-01 | 54.9394. | City of Arvin - Haven Drive Lateral Repair | 15966.99 | 15966.99 | 1927.44 | 2025-08-31
2025-12-01 | 54.9398. | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 14300 | 14300 | 6107.21 | 2025-09-30
2025-12-01 | 54.9399. | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 24775 | 24775 | 13483.41 | 2025-08-31
2025-12-01 | 54.9400. | Arvin Edison Water Storage Dist. - FFPP Core Drilling | 800.69 | 800.69 | 29.37 | 2025-07-31
2025-12-01 | 54.9401. | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R | 247539.61 | 247539.61 | 11227.04 | 2025-10-31
2025-12-01 | 54.9407. | Semitropic Water Storage Dist. - North Plant Emergency Repair | 31296.85 | 31296.85 | 5629.51 | 2025-10-31
2025-12-01 | 54.9409. | Nipomo CSD Osage Emergency Waterline Repair | 20123.71 | 20123.71 | 2712 | 2025-10-31
2025-12-01 | 54.9410. | SWID - Burbank St. Repair | 8241.55 | 8241.55 | 1275.9 | 2025-10-31
2025-12-01 | 55.1090. | JV w/Webcor & Obayashi - Silverlake - LADWP | 5235272.36 | 5400000 | 1474640.0192 | 2029-12-01
2025-12-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility | 341443133.71 | 341443133.71 | 3710498 | 2027-06-30
2025-12-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6651803.53 | 6651803.53 | 250000 | 2026-01-31
2025-12-01 | 55.1200. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 | 197175877 | 198075877 | 0 | 2027-07-31
2025-12-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out | 0 | 0 | 7779994.28 | 2027-07-31
2025-12-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project | 16396051.58 | 16396051.58 | 740594.1249 | 2026-08-01
2025-12-01 | 55.1204. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 | 57142227 | 57722227 | 0 | 2027-08-31
2025-12-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out | 0 | 0 | 2362039.01 | 2027-08-31
2025-12-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 41504206.39 | 41504206.39 | 4326445.5224 | 2026-02-28
2025-12-01 | 55.1233. | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 126077.16 | 9838187 | 8429 | 2028-02-28
2025-12-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 5759301.81 | 5759301.81 | 605548.778 | 2026-03-01
2025-12-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 147525113 | 147525113 | 0 | 2029-02-01
2025-12-01 | 55.1254. | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 158952.89 | 471896.25 | 0 | 2026-05-25
2025-12-01 | 55.1255. | City of Riverside - RWQCP Emergency Repair | 14160.81 | 14160.81 | 0 | 2026-01-31
2025-12-01 | 55.1256. | Anaergia Technologies LLC - City of Riverside - OPS | 2888100 | 2888100 | 0 | 2026-03-01
2025-12-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement | 2273682.69 | 2273682.69 | 608537.39 | 2025-05-31
2025-12-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements | 4046200 | 4046200 | 724343.64 | 2025-03-31
2025-12-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 | 34207.53 | 34207.53 | 1706.67 | 2025-09-30
2025-12-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 184557.17 | 184557.17 | 136263.23 | 2025-03-31
2025-12-01 | 55.1251. | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 322982.96 | 322982.96 | 38761.1 | 2025-05-31
2025-12-01 | 55.1252. | Murrieta Overhead 2025 | 0 | 0 | -1958826.45 | 2025-12-31
2025-12-01 | 55.1253. | Murrieta Estimating 2025 | 0 | 0 | -475814.03 | 2025-12-31
2025-12-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 38165419.5 | 38165419.5 | 123922.1725 | 2027-04-01
2025-12-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 40106224.63 | 40106224.63 | 0 | 2026-03-25
2025-12-01 | 57.0007. | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | 196248.4 | 162630 | -33618.4 | 2026-01-31
2025-12-01 | 57.0008. | Imperial Irrigation Dist. - El Centro Generating Station WWTP | 2876047 | 2876047 | 0 | 2026-11-01
2025-12-01 | 57.0005. | San Diego Overhead 2025 | 0 | 0 | -92874.26 | 2025-12-31
2025-12-01 | 57.0006. | San Diego Estimating 2025 | 0 | 0 | -13743.76 | 2025-12-31
2025-12-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 22525189 | 22525189 | 680281.9248 | 2026-08-01
2025-12-01 | 58.0004. | Los Angeles Overhead 2025 | 0 | 0 | -147282.12 | 2025-12-31
2025-12-01 | 58.0005. | Los Angeles Estimating 2025 | 0 | 0 | -135037.09 | 2025-12-31
2025-12-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 373425 | 373425 | 90738.1145 | 2026-03-31
2025-12-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 135000 | 135000 | 50249.6318 | 2026-03-31
2025-12-01 | 56.1010. | Placer County Water Agency -PCWA Time & Material Contract | 49250 | 49250 | 12788.06 | 2026-12-31
2025-12-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 160000 | 230000 | 18522.3319 | 2026-06-30
2025-12-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 102868 | 102868 | -12027 | 2026-03-31
2025-12-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 153913 | 153913 | 48979.1346 | 2026-03-31
2025-12-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 85000 | 85000 | 854.767 | 2026-03-31
2025-12-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 276000 | 276000 | 34301.8572 | 2026-06-30
2025-12-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 36491 | 36491 | 14816.8 | 2026-12-31
2025-12-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 95000 | 95000 | -22376 | 2026-03-31
2025-12-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 375000 | 375000 | 41657.3982 | 2026-03-31
2025-12-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services | 277565 | 277565 | 46892.8489 | 2026-03-31
2025-12-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 336610 | 336610 | 17412.0037 | 2026-03-31
2025-12-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 77120 | 77120 | -2836 | 2026-03-31
2025-12-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 2394758 | 2394758 | 278228.8307 | 2026-12-31
2025-12-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 200000 | 200000 | 38108.093 | 2026-03-31
2025-12-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 308725 | 308725 | 51567.0603 | 2026-03-31
2025-12-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 3792559 | 3792559 | 117462.9679 | 2026-12-31
2025-12-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 120891 | 120891 | 23780.8675 | 2026-03-31
2025-12-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 399389 | 399389 | 50278.8329 | 2026-06-30
2025-12-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 404663 | 404663 | 37090.1278 | 2026-09-30
2025-12-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 108000 | 108000 | 7620.973 | 2026-06-30
2025-12-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 595000 | 595000 | 56882.856 | 2026-03-31
2025-12-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 478000 | 478000 | 15647.3849 | 2026-09-30
2025-12-01 | 56.1073. | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 122210 | 122210 | 7791.4367 | 2026-06-30
2025-12-01 | 56.1075. | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 27665.92 | 950000 | 0 | 2026-06-30
2025-12-01 | 56.1078. | City of Napa - On-Call Control Systems Integrator Services | 25356.25 | 25356.25 | 0 | 2026-09-30
2025-12-01 | 56.1081. | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 179690 | 179690 | 19526.2176 | 2026-03-31
2025-12-01 | 56.1083. | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 717010 | 717010 | 32151.6842 | 2026-06-30
2025-12-01 | 56.1085. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 80000 | 80000 | 0 | 2026-06-30
2025-12-01 | 56.1086. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 376000 | 376000 | 0 | 2026-09-30
2025-12-01 | 56.1087. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 49369 | 49369 | 5767.3948 | 2026-06-30
2025-12-01 | 56.1088. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 117985 | 117985 | 25493.1166 | 2026-03-31
2025-12-01 | 56.1002. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 185000 | 185000 | 70514.18 | 2025-04-30
2025-12-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 332901 | 332901 | 109505.26 | 2025-12-31
2025-12-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 16814 | 16814 | -2548.98 | 2025-12-31
2025-12-01 | 56.1008. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 55000 | 55000 | 24448.08 | 2025-03-31
2025-12-01 | 56.1010.01 | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 9569 | 9569 | 2471.9 | 2025-03-31
2025-12-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 150064.25 | 150064.25 | 39980.63 | 2025-09-09
2025-12-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 193845 | 193845 | 50080.42 | 2025-12-31
2025-12-01 | 56.1021. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 244760 | 244760 | 128007.48 | 2025-06-30
2025-12-01 | 56.1022. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 0 | 0 | 0 | 2025-03-31
2025-12-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 220390 | 220390 | 69885.27 | 2025-09-30
2025-12-01 | 56.1030. | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 689578.64 | 689578.64 | 0 | 2025-09-30
2025-12-01 | 56.1041. | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 20016.78 | 20016.78 | 0 | 2025-07-31
2025-12-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 136875 | 136875 | 38156.82 | 2025-12-31
2025-12-01 | 56.1052. | San Jose Water - Williams Back ATS Replacement | 8887 | 8887 | 2486.06 | 2025-04-30
2025-12-01 | 56.1053. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 35000 | 35000 | 15035.22 | 2025-03-31
2025-12-01 | 56.1054. | AIC - Riverside Public Works - Digester 5 Rehab | 37648.03 | 37648.03 | 0 | 2025-09-30
2025-12-01 | 56.1056. | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan | 98280.63 | 98280.63 | 0 | 2025-07-31
2025-12-01 | 56.1057. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 0 | 0 | 0 | 2025-04-30
2025-12-01 | 56.1061. | San Jose Water - PLC System Assessment | 11269 | 11269 | 5686.34 | 2025-03-31
2025-12-01 | 56.1062. | AIC - SCADA System Upgrade - City of Brentwood | 409988.07 | 409988.07 | 0 | 2025-07-31
2025-12-01 | 56.1064. | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 435153 | 435153 | 232886.6 | 2025-05-31
2025-12-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 226400.8 | 226400.8 | 34376.99 | 2025-12-31
2025-12-01 | 56.1069. | City of Brentwood - Brentwood, City of - On-Call Agreement | 2525 | 2525 | -1296.46 | 2025-06-30
2025-12-01 | 56.1071. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 34000 | 34000 | 30403.44 | 2025-06-30
2025-12-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 65960 | 65960 | 24421.16 | 2025-12-31
2025-12-01 | 56.1074. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 12650 | 12650 | 2008.14 | 2025-03-31
2025-12-01 | 56.1076. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 19200 | 19200 | 7622.23 | 2025-03-31
2025-12-01 | 56.1077. | System Integration Overhead 2025 | 0 | 0 | -4370841.4 | 2025-12-25
2025-12-01 | 56.1079. | AIC - San Jose Water Co - Montevina PLC Upgrade | 29235.63 | 29235.63 | 0 | 2025-07-31
2025-12-01 | 56.1080. | AIC - San Jose Water Co - PLC System Assessment | 359469 | 359469 | 0 | 2025-07-31
2025-12-01 | 56.1082. | City of Clovis - Pump Station E New Pump 5 VFD Startup | 19800 | 19800 | -783.04 | 2025-09-09
2025-12-01 | 56.1084. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 8000 | 8000 | 3771.87 | 2025-09-09
2025-12-01 | 56.1102. | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 19815.94 | 19815.94 | 0 | 2025-07-31
2025-12-01 | 56.1103. | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 55855.24 | 55855.24 | 0 | 2025-07-31
2025-12-01 | 56.1104. | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 9500.31 | 9500.31 | 0 | 2025-07-31
2025-12-01 | 56.1105. | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 30502.53 | 30502.53 | 0 | 2025-07-31
2025-12-01 | 56.1106. | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 54742.18 | 54742.18 | 0 | 2025-07-31
2025-12-01 | 56.1107. | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 3429.06 | 3429.06 | 0 | 2025-07-31
2025-12-01 | 56.1108. | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 20729.84 | 20729.84 | 0 | 2025-07-31
2025-12-01 | 56.1109. | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 14772.26 | 14772.26 | 0 | 2025-07-31
2025-12-01 | 56.1110. | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 4596.42 | 4596.42 | 0 | 2025-07-31
2025-12-01 | 56.1111. | AIC - California American Water - Luzern Well Treatment Design | 17210.01 | 17210.01 | 0 | 2025-07-31
2025-12-01 | 56.1112. | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 27241.58 | 27241.58 | 0 | 2025-07-31
2025-12-01 | 56.1113. | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 49233.44 | 49233.44 | 0 | 2025-07-31
2025-12-01 | 56.1115. | AIC - UC Davis - WWTP Annual Instrument Calibrations | 5895.77 | 5895.77 | 0 | 2025-04-30
2025-12-01 | 56.1119. | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 22184.06 | 22184.06 | 0 | 2025-07-31
2025-12-01 | 56.1120. | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 1045.63 | 1045.63 | 0 | 2025-07-31
2025-12-01 | 56.1121. | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 22824.38 | 22824.38 | 0 | 2025-07-31
2025-12-01 | 56.1122. | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 6289.38 | 6289.38 | 0 | 2025-07-31
2025-12-01 | 56.1123. | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 3772.82 | 3772.82 | 0 | 2025-07-31
2025-12-01 | 56.1124. | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 28950 | 28950 | 0 | 2025-07-31
2025-12-01 | 56.1125. | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 14229.38 | 14229.38 | 0 | 2025-07-31
2025-12-01 | 56.1126. | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 9526.88 | 9526.88 | 0 | 2025-07-31
2025-12-01 | 56.1127. | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 6519.07 | 6519.07 | 0 | 2025-07-31
2025-12-01 | 56.1128. | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 4793.13 | 4793.13 | 0 | 2025-07-31
2025-12-01 | 56.1129. | AIC - RMCSD - VEEAM SFTWR | 133.75 | 133.75 | 0 | 2025-07-31
2025-12-01 | 56.1130. | System Integration Division Estimating 2025 | 0 | 0 | -267.5 | 2025-07-31
2025-12-01 | 56.1131. | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 2388.75 | 2388.75 | 0 | 2025-07-31
2025-12-01 | 56.1132. | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 585 | 585 | 0 | 2025-07-31
2025-12-01 | 56.1133. | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 2827.5 | 2827.5 | 0 | 2025-07-31
2025-12-01 | 56.1134. | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 965.51 | 965.51 | 0 | 2025-07-31
2025-12-01 | 56.1135. | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 112.5 | 112.5 | 0 | 2025-07-31
2025-12-01 | 56.1141. | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 2827.5 | 2827.5 | 0 | 2025-07-31
2025-12-01 | 50.0541. | W.M. Lyles Co. - General Overhead | 0 | 0 | -3642039.89 | 2025-12-31
2025-12-01 | 50.0542. | W.M. Lyles Co. - General Estimating | 0 | 0 | -100487.45 | 2025-12-31
2025-12-01 | 50.0543. | American Paving | 7051.01 | 7051.01 | 0 | 2025-12-31
2025-12-01 | 50.0544. | Lyles Services Co. | 13555.8 | 13555.8 | 0 | 2025-12-31
2025-12-01 | 50.0545. | New England Sheet Metal and Mechanical Co. | 2226.16 | 2226.16 | 0 | 2025-12-31
2025-12-01 | 50.0546. | Lyles Utility Construction, LLC | 11256.72 | 11256.72 | 788.66 | 2025-12-31
2025-12-01 | 50.0551. | Advanced Integration & Controls | 5457.42 | 5457.42 | 0 | 2025-12-31

## Cost
Month | Job | Job Desc | GAAP Overide Cost Projection | Ops Overide Cost Projection
2025-12-01 | 51.1108. | JV w/AECOM - Stockton - RWCF Phase 2A/2B | 93268107.71 | 93337829
2025-12-01 | 51.1109. | JV w/AECOM - Stockton - RWCF Phase 2A/2B Overhead (JV) | -3462489.91 | -3530000
2025-12-01 | 51.1129. | Union Sanitary Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin Modifications | 115233580.84 | 115233580.84
2025-12-01 | 51.1137. | CA Water Service Co. - Bear Gulch Pump Station 18 | 1198511.46 | 1198511.46
2025-12-01 | 51.1144. | Silicon Valley Clean Water - FEP Improvements Project | 13839617 | 13839617
2025-12-01 | 51.1146. | National Carbon Technologies, LLC - Aymium Williams Production Facility | 45980234 | 45980234
2025-12-01 | 51.1151. | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 10079352 | 10079352
2025-12-01 | 51.1152. | Mozingo Construction Inc - ElD Sly Park Intertie Project | 18628948.34 | 18628948.34
2025-12-01 | 51.1153. | Linda County Water Dist. - Aeration Blower Replacement | 454520.68 | 454520.68
2025-12-01 | 51.1154. | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 12488835 | 12488835
2025-12-01 | 51.1155. | National Carbon Technologies, LLC - Aymium Williams Production Facility - Mgmt Chg Out | -1783379.97 | -1783379.97
2025-12-01 | 51.1158. | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 104446 | 104446
2025-12-01 | 51.1159. | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 1079240 | 1079240
2025-12-01 | 51.1160. | City of Galt Public Works - Industrial WWTP Expansion | 1690000 | 1690000
2025-12-01 | 51.1161. | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | 10261252.45 | 10261252.45
2025-12-01 | 51.1162. | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project | 5845263 | 5845263
2025-12-01 | 51.1164. | CA Water Service Co. - Stockton Roofing | 383387 | 383387
2025-12-01 | 51.1165. | City of Yuba City - WTP Aquifer Storage and Recovery Well No. 3 | 4886443 | 4886443
2025-12-01 | 51.1133. | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 331855.28 | 331855.28
2025-12-01 | 51.1136. | Union Sanitary Dist - USD Plant Misc. Improvements | 4531817.86 | 4531817.86
2025-12-01 | 51.1138. | CA Water Service Co. - Bear Gulch Pump Station 21 | 1167704.15 | 1167704.15
2025-12-01 | 51.1139. | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 56994.44 | 56994.44
2025-12-01 | 51.1141. | City of Colfax - WWTP Algae Reduction Project | 3835094.73 | 3835094.73
2025-12-01 | 51.1143. | Olivehurst Plumas Lake Manganese Filter Expansion | 1758132.57 | 1758132.57
2025-12-01 | 51.1147. | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2548724.92 | 2548724.92
2025-12-01 | 51.1150. | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2239435.14 | 2239435.14
2025-12-01 | 51.1156. | Rocklin Overhead 2025 | 1426058.69 | 1426058.69
2025-12-01 | 51.1157. | Rocklin Estimating 2025 | 613546.52 | 613546.52
2025-12-01 | 52.8563. | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 1152462.29 | 1174182.73
2025-12-01 | 52.8564. | City of Santa Cruz - Graham Hill WTP Facility Improvements -Mgmt Chg Out | -293385.24 | -293392.63
2025-12-01 | 52.8566. | City of Visalia - Water Reclamation Facility RPGS SCR System | 1029398 | 1029398
2025-12-01 | 52.8586. | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 10661349 | 10661349
2025-12-01 | 52.8634. | City of Huron - Water Treatment Plant Imp. Phase 2 | 13190722.74 | 13190722.74
2025-12-01 | 52.8636. | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 3381112 | 3367197
2025-12-01 | 52.8637. | Root Creek Water Dist. - Groundwater Blending & Arsenic | 24614577.65 | 24614577.65
2025-12-01 | 52.8640. | City of Dos Palos - WTP Replacement Project | 36773040.16 | 36773040.16
2025-12-01 | 52.8668. | California Water Service Co. - Cal Water - Salinas Station 57 | 376996 | 376996
2025-12-01 | 52.8678. | City of Chowcilla - Well 15 & Generator Improvement Projects | 1162321 | 1162321
2025-12-01 | 52.8687. | California Water Service Co. - Salinas Station 205 | 790771.48 | 790771.48
2025-12-01 | 52.8692. | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 49682.49 | 49682.49
2025-12-01 | 52.8697. | City of Tulare - Industrial WWTP Dewatering Improvements Pro | 1325482 | 1325482
2025-12-01 | 52.8698. | California Water Service Co. - Tesoro Viejo RWSP Liner Repair | 16128 | 16128
2025-12-01 | 52.8704. | City of Visalia - Solids Handling Improvements Project | 13491127 | 13491127
2025-12-01 | 52.8705. | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | 719260 | 719260
2025-12-01 | 52.8707. | County of Fresno - Westside Water Tank and Pump Station | 3461577 | 3461577
2025-12-01 | 52.8708. | County of Fresno - CSA 44A Wastewater Improvements | 333757 | 333757
2025-12-01 | 52.8711. | California Water Service Co. - Tesoro Viejo ARV Replacement | 6315 | 6315
2025-12-01 | 52.8713. | City of Visalia - Remove & Replace Chain and Flight Mechanic | 190439 | 190439
2025-12-01 | 52.8714. | New England Sheet Metal and Mechanical Co. - VCH Digging Water Line T&M | 4465.61 | 4465.61
2025-12-01 | 52.8567. | City of Modesto - Grayson Well 69 | 3128023.93 | 3128023.93
2025-12-01 | 52.8604. | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 4572503.23 | 4572503.23
2025-12-01 | 52.8628. | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 4745798.53 | 4745798.53
2025-12-01 | 52.8631. | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 2448658.26 | 2448658.26
2025-12-01 | 52.8652. | California Water Service Co. - Salinas 77 Booster Station | 1039376.08 | 1039376.08
2025-12-01 | 52.8658. | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1633530.21 | 1633530.21
2025-12-01 | 52.8663. | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1379688.28 | 1379688.28
2025-12-01 | 52.8667. | California Water Service Co. - Cal Water Salinas Station 33 | 290726.11 | 290726.11
2025-12-01 | 52.8670. | California Water Service Co. - Cal Water - King City Station 10 | 267282.05 | 267282.05
2025-12-01 | 52.8674. | City of Hanford - WWTP Standby Influent Pump Install | 251088.2 | 251088.2
2025-12-01 | 52.8677. | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 689831.96 | 689831.96
2025-12-01 | 52.8680. | City of Orange Cove - Orange Cove West Clarifier T&M | 26088.33 | 26088.33
2025-12-01 | 52.8682. | Fresno Overhead 2025 | 1121157.1 | 1121157.1
2025-12-01 | 52.8683. | Fresno Estimating 2025 | 415452.52 | 415452.52
2025-12-01 | 52.8684. | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 45291.39 | 45291.39
2025-12-01 | 52.8685. | Malaga County Water Dist. - Malaga County Water District | 382067.32 | 382067.32
2025-12-01 | 52.8686. | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 7505.26 | 7505.26
2025-12-01 | 52.8688. | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 116972.75 | 116972.75
2025-12-01 | 52.8689. | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 16095.58 | 16095.58
2025-12-01 | 52.8690. | City of Dinuba - WWTP Rake Replacement | 13155.83 | 13155.83
2025-12-01 | 52.8691. | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 8287.82 | 8287.82
2025-12-01 | 52.8693. | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 663140.99 | 663140.99
2025-12-01 | 52.8694. | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 38541.99 | 38541.99
2025-12-01 | 52.8695. | Lyles Services Co. - LSC GO Trash Enclosure | 13024.37 | 13024.37
2025-12-01 | 52.8696. | American Paving Co. - Hot Tap for APC- Tule River Parkway | 887.65 | 887.65
2025-12-01 | 52.8699. | City of Hanford - WWTP Repair T&M | 2948.91 | 2948.91
2025-12-01 | 52.8700. | Lyles Services Co. - LSC GO Misc. Work | 4446.13 | 4446.13
2025-12-01 | 52.8701. | County of Fresno - 47 Water | 12421.08 | 12421.08
2025-12-01 | 52.8702. | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M | 4725.28 | 4725.28
2025-12-01 | 52.8703. | County of Fresno - CSA 47 Egret Point Water Line Repair | 12571.54 | 12571.54
2025-12-01 | 52.8706. | City of Hanford - WWTP Weld Repair T&M 2 | 2435.78 | 2435.78
2025-12-01 | 52.8709. | County of Fresno - 47.1 Water | 14874.36 | 14874.36
2025-12-01 | 52.8710. | City of Dinuba - WWTP Bar Screen Motor Bracket Repair | 3514.84 | 3514.84
2025-12-01 | 52.8715. | New England Sheet Metal and Mechanical Co. - Vitro Glass Plant Concrete Pad T&M | 8585.44 | 8585.44
2025-12-01 | 53.2007. | Union Sanitary Dist. - Phase 1B Secondary Clarifiers | 291530134 | 291530134
2025-12-01 | 53.2004. | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 980791.05 | 980791.05
2025-12-01 | 53.2005. | East Bay Overhead 2025 | 279281.96 | 279281.96
2025-12-01 | 53.2006. | East Bay Estimating 2026 | 304986.32 | 304986.32
2025-12-01 | 54.9033. | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 104550.27 | 104550.27
2025-12-01 | 54.9135. | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 9050951.86 | 9050951.86
2025-12-01 | 54.9257. | City of Guadalupe - Highway 1 Lift Station | 1426328 | 1426328
2025-12-01 | 54.9268. | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 884567.99 | 884567.99
2025-12-01 | 54.9269. | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 549817.74 | 591570.12
2025-12-01 | 54.9285. | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 387022 | 387022
2025-12-01 | 54.9313. | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 6876885.04 | 6876885.04
2025-12-01 | 54.9330. | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 307641 | 307641
2025-12-01 | 54.9336. | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 23271176.64 | 23271176.64
2025-12-01 | 54.9337. | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 3944848 | 3944848
2025-12-01 | 54.9343. | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 5981300 | 5981300
2025-12-01 | 54.9356. | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 913330 | 913330
2025-12-01 | 54.9366. | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1080131 | 1080131
2025-12-01 | 54.9369. | California Water Service Co. - PFAS Treatment Program Project | 26179781.7 | 26179781.7
2025-12-01 | 54.9373. | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 1393326 | 1393326
2025-12-01 | 54.9389. | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 314780 | 314780
2025-12-01 | 54.9391. | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 512057.34 | 512057.34
2025-12-01 | 54.9395. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 1693652.66 | 1693652.66
2025-12-01 | 54.9396. | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | 157746.09 | 157746.09
2025-12-01 | 54.9397. | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 3390645 | 3390645
2025-12-01 | 54.9403. | Lost Hills Utility Dist. - WTP Improvements | 338101 | 338101
2025-12-01 | 54.9404. | Cawelo Water Dist. - Reuse of Produced Water | 3585392 | 3585392
2025-12-01 | 54.9405. | Semitropic Water Storage Dist. - Pump Platform Replacement Project | 812000 | 812000
2025-12-01 | 54.9406. | California Water Service Co. - Emergency PACL leak repair | 1120.65 | 1120.65
2025-12-01 | 54.9408. | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line | 3537185 | 3537185
2025-12-01 | 54.9411. | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation | 78300 | 78300
2025-12-01 | 54.9412. | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork | 115708.88 | 115708.88
2025-12-01 | 54.9413. | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork | 132138.74 | 132138.74
2025-12-01 | 54.9414. | Cawelo Water Dist. - Cawelo Diversion Structure Rehab | 337485.68 | 338674.83
2025-12-01 | 54.9416. | California Water Service Co. - BK 147 Station Improvements | 1132398 | 1132398
2025-12-01 | 54.9417. | County of Santa Barbara-Public Works - Laguna WWTP WAS Pipe Modifications | 42893 | 42893
2025-12-01 | 54.9418. | GenerateUpcycle - Organics Waste Processing Facility | 15739 | 15739
2025-12-01 | 54.9421. | Nipomo Community Service Dist. - Tefft Emergency Pipe Repair | 3703.18 | 3703.18
2025-12-01 | 54.9099. | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 45328892.68 | 45328892.68
2025-12-01 | 54.9172. | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 21018432.22 | 21018432.22
2025-12-01 | 54.9216. | CA Dept. of Corr. - Water Treatment Improvements | 2286264.43 | 2286264.43
2025-12-01 | 54.9246. | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 1708475.32 | 1708475.32
2025-12-01 | 54.9265. | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 220754.51 | 220754.51
2025-12-01 | 54.9279. | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3153237.4 | 3153237.4
2025-12-01 | 54.9289. | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 25097.25 | 25097.25
2025-12-01 | 54.9292. | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 1313.45 | 1313.45
2025-12-01 | 54.9309. | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3790858.34 | 3790858.34
2025-12-01 | 54.9323. | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 94483.21 | 94483.21
2025-12-01 | 54.9329. | Kern Water Bank Authority - Valve Replacement Parts | 16466.72 | 16466.72
2025-12-01 | 54.9333. | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 371915.26 | 371915.26
2025-12-01 | 54.9338. | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 119186.11 | 119186.11
2025-12-01 | 54.9341. | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1063532.4 | 1063532.4
2025-12-01 | 54.9342. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 124146.3 | 124146.3
2025-12-01 | 54.9347. | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 3227.7 | 3227.7
2025-12-01 | 54.9349. | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 197889.31 | 197889.31
2025-12-01 | 54.9350. | Kern Water Bank Authority - Construct New Well 18P01 | 120318.68 | 120318.68
2025-12-01 | 54.9351. | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 136808.3 | 136808.3
2025-12-01 | 54.9353. | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 1117.5 | 1117.5
2025-12-01 | 54.9354. | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 8230.83 | 8230.83
2025-12-01 | 54.9355. | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 1815.23 | 1815.23
2025-12-01 | 54.9357. | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 889.66 | 889.66
2025-12-01 | 54.9358. | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1125399.83 | 1125399.83
2025-12-01 | 54.9360. | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1144.88 | 1144.88
2025-12-01 | 54.9361. | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 107074.87 | 107074.87
2025-12-01 | 54.9362. | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 375601.24 | 375601.24
2025-12-01 | 54.9363. | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 777.55 | 777.55
2025-12-01 | 54.9365. | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 1263.33 | 1263.33
2025-12-01 | 54.9367. | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 1602.33 | 1602.33
2025-12-01 | 54.9368. | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 13653.62 | 13653.62
2025-12-01 | 54.9370. | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 889.64 | 889.64
2025-12-01 | 54.9371. | Bakersfield Overhead 2025 | 1267652.77 | 1267652.77
2025-12-01 | 54.9372. | Bakersfield Estimating 2025 | 588792.6 | 588792.6
2025-12-01 | 54.9374. | City of Santa Maria - WWTP Trickling Filter Repairs | 19986.45 | 19986.45
2025-12-01 | 54.9375. | City of Santa Maria - WWTP Clarifier Repairs | 4545.48 | 4545.48
2025-12-01 | 54.9379. | Semitropic Water Storage Dist. - Delta System Pipe Repair | 36111.95 | 36111.95
2025-12-01 | 54.9380. | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 18064.72 | 18064.72
2025-12-01 | 54.9381. | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 28875.38 | 28875.38
2025-12-01 | 54.9382. | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 108690.45 | 108690.45
2025-12-01 | 54.9383. | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 15759.76 | 15759.76
2025-12-01 | 54.9384. | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 70340.57 | 70340.57
2025-12-01 | 54.9385. | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 98598.77 | 98598.77
2025-12-01 | 54.9386. | Kern Valley State Prison - Arsenic Pipe Leak Repair | 75784.74 | 75784.74
2025-12-01 | 54.9387. | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 19011.65 | 19011.65
2025-12-01 | 54.9388. | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 6535.41 | 6535.41
2025-12-01 | 54.9390. | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 96329.49 | 96329.49
2025-12-01 | 54.9392. | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 208346.69 | 208346.69
2025-12-01 | 54.9393. | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 27539.82 | 27539.82
2025-12-01 | 54.9394. | City of Arvin - Haven Drive Lateral Repair | 14039.55 | 14039.55
2025-12-01 | 54.9398. | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 8192.79 | 8192.79
2025-12-01 | 54.9399. | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 11291.59 | 11291.59
2025-12-01 | 54.9400. | Arvin Edison Water Storage Dist. - FFPP Core Drilling | 771.32 | 771.32
2025-12-01 | 54.9401. | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R | 236312.57 | 236312.57
2025-12-01 | 54.9407. | Semitropic Water Storage Dist. - North Plant Emergency Repair | 25667.34 | 25667.34
2025-12-01 | 54.9409. | Nipomo CSD Osage Emergency Waterline Repair | 17411.71 | 17411.71
2025-12-01 | 54.9410. | SWID - Burbank St. Repair | 6965.65 | 6965.65
2025-12-01 | 55.1090. | JV w/Webcor & Obayashi - Silverlake - LADWP | 3834064.05 | 3900000
2025-12-01 | 55.1191. | Inland Empire Utilities - IEUA RP-5 Liquids Expans. & Solids Treat. Facility | 337732635.71 | 337732635.71
2025-12-01 | 55.1192. | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6401803.53 | 6401803.53
2025-12-01 | 55.1200. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 1 | 197751131.77 | 198075877
2025-12-01 | 55.1201. | JV w/AECOM - East County AWP Package 1 - Mgmt. Charge Out | -7779994.28 | -8100000
2025-12-01 | 55.1202. | LA County Sanitation District - Oxygen Generation Project | 15220642.58 | 15220642.58
2025-12-01 | 55.1204. | JV w/AECOM - East County Adv. Water Purification Proj. - Package 3 | 57575368.22 | 57722227
2025-12-01 | 55.1205. | JV w/AECOM - East County AWP - Package 3 - Mgmt. Charge Out | -2362039.01 | -2500000
2025-12-01 | 55.1227. | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 37154206.39 | 37154206.39
2025-12-01 | 55.1233. | JV w/AECOM - Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 126077.16 | 9838187
2025-12-01 | 55.1248. | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 4934301.81 | 4934301.81
2025-12-01 | 55.1249. | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 139703905 | 139703905
2025-12-01 | 55.1254. | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 156561.66 | 471896.25
2025-12-01 | 55.1255. | City of Riverside - RWQCP Emergency Repair | 14160.81 | 14160.81
2025-12-01 | 55.1256. | Anaergia Technologies LLC - City of Riverside - OPS | 2713100 | 2713100
2025-12-01 | 55.1230. | Anaergia Technologies - VVWRA - DAF 3 Replacement | 1665145.3 | 1665145.3
2025-12-01 | 55.1231. | City of Corona - WRF 1 Aeration System Improvements | 3321856.36 | 3321856.36
2025-12-01 | 55.1238. | Anaergia Technologies LLC - East County Package 5 | 32500.86 | 32500.86
2025-12-01 | 55.1250. | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 48293.94 | 48293.94
2025-12-01 | 55.1251. | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 284221.86 | 284221.86
2025-12-01 | 55.1252. | Murrieta Overhead 2025 | 1958826.45 | 1958826.45
2025-12-01 | 55.1253. | Murrieta Estimating 2025 | 475814.03 | 475814.03
2025-12-01 | 57.0003. | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 35758333.5 | 35758333.5
2025-12-01 | 57.0004. | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 37896367.63 | 37896367.63
2025-12-01 | 57.0007. | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | 196248.4 | 196248.4
2025-12-01 | 57.0008. | Imperial Irrigation Dist. - El Centro Generating Station WWTP | 2743982 | 2743982
2025-12-01 | 57.0005. | San Diego Overhead 2025 | 92874.26 | 92874.26
2025-12-01 | 57.0006. | San Diego Estimating 2025 | 13743.76 | 13743.76
2025-12-01 | 58.0003. | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 21217174 | 21217174
2025-12-01 | 58.0004. | Los Angeles Overhead 2025 | 147282.12 | 147282.12
2025-12-01 | 58.0005. | Los Angeles Estimating 2025 | 135037.09 | 135037.09
2025-12-01 | 56.1004. | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 269840 | 269840
2025-12-01 | 56.1005. | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 68025 | 68025
2025-12-01 | 56.1010. | Placer County Water Agency -PCWA Time & Material Contract | 36461.94 | 36461.94
2025-12-01 | 56.1015. | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 142358.95 | 203520
2025-12-01 | 56.1017. | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 114895 | 114895
2025-12-01 | 56.1018. | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 71045 | 71045
2025-12-01 | 56.1032. | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 82975 | 82975
2025-12-01 | 56.1036. | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 209024 | 209024
2025-12-01 | 56.1037. | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 21674.2 | 21674.2
2025-12-01 | 56.1038. | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 117376 | 117376
2025-12-01 | 56.1039. | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 332284 | 332284
2025-12-01 | 56.1042. | Trabuco Canyon Water Dist. - SCADA Integration Services | 218288 | 218288
2025-12-01 | 56.1043. | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 311391 | 311391
2025-12-01 | 56.1046. | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 79956 | 79956
2025-12-01 | 56.1047. | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 2040555 | 2040555
2025-12-01 | 56.1048. | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 161119 | 161119
2025-12-01 | 56.1049. | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 248873 | 248873
2025-12-01 | 56.1050. | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 3365567 | 3365567
2025-12-01 | 56.1055. | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 92848 | 92848
2025-12-01 | 56.1059. | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 329206 | 329206
2025-12-01 | 56.1060. | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 322491 | 322491
2025-12-01 | 56.1063. | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 97921 | 97921
2025-12-01 | 56.1066. | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 531490 | 531490
2025-12-01 | 56.1067. | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 415878 | 415878
2025-12-01 | 56.1073. | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 114047 | 114047
2025-12-01 | 56.1075. | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 27665.92 | 779048
2025-12-01 | 56.1078. | City of Napa - On-Call Control Systems Integrator Services | 25356.25 | 25356.25
2025-12-01 | 56.1081. | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 159785 | 159785
2025-12-01 | 56.1083. | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 656363 | 656363
2025-12-01 | 56.1085. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 66955 | 66955
2025-12-01 | 56.1086. | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 295102 | 295102
2025-12-01 | 56.1087. | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 43026 | 43026
2025-12-01 | 56.1088. | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 85405 | 85405
2025-12-01 | 56.1002. | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 114485.82 | 114485.82
2025-12-01 | 56.1003. | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 223395.74 | 223395.74
2025-12-01 | 56.1007. | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 19362.98 | 19362.98
2025-12-01 | 56.1008. | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 30551.92 | 30551.92
2025-12-01 | 56.1010.01 | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 7097.1 | 7097.1
2025-12-01 | 56.1016. | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 110083.62 | 110083.62
2025-12-01 | 56.1019. | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 143764.58 | 143764.58
2025-12-01 | 56.1021. | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 116752.52 | 116752.52
2025-12-01 | 56.1022. | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 0 | 0
2025-12-01 | 56.1023. | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 150504.73 | 150504.73
2025-12-01 | 56.1030. | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 689578.64 | 689578.64
2025-12-01 | 56.1041. | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 20016.78 | 20016.78
2025-12-01 | 56.1051. | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 98718.18 | 98718.18
2025-12-01 | 56.1052. | San Jose Water - Williams Back ATS Replacement | 6400.94 | 6400.94
2025-12-01 | 56.1053. | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 19964.78 | 19964.78
2025-12-01 | 56.1054. | AIC - Riverside Public Works - Digester 5 Rehab | 37648.03 | 37648.03
2025-12-01 | 56.1056. | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan | 98280.63 | 98280.63
2025-12-01 | 56.1057. | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 0 | 0
2025-12-01 | 56.1061. | San Jose Water - PLC System Assessment | 5582.66 | 5582.66
2025-12-01 | 56.1062. | AIC - SCADA System Upgrade - City of Brentwood | 409988.07 | 409988.07
2025-12-01 | 56.1064. | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 202266.4 | 202266.4
2025-12-01 | 56.1065. | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 192023.81 | 192023.81
2025-12-01 | 56.1069. | City of Brentwood - Brentwood, City of - On-Call Agreement | 3821.46 | 3821.46
2025-12-01 | 56.1071. | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 3596.56 | 3596.56
2025-12-01 | 56.1072. | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 41538.84 | 41538.84
2025-12-01 | 56.1074. | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 10641.86 | 10641.86
2025-12-01 | 56.1076. | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 11577.77 | 11577.77
2025-12-01 | 56.1077. | System Integration Overhead 2025 | 4370841.4 | 4370841.4
2025-12-01 | 56.1079. | AIC - San Jose Water Co - Montevina PLC Upgrade | 29235.63 | 29235.63
2025-12-01 | 56.1080. | AIC - San Jose Water Co - PLC System Assessment | 359469 | 359469
2025-12-01 | 56.1082. | City of Clovis - Pump Station E New Pump 5 VFD Startup | 20583.04 | 20583.04
2025-12-01 | 56.1084. | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 4228.13 | 4228.13
2025-12-01 | 56.1102. | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 19815.94 | 19815.94
2025-12-01 | 56.1103. | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 55855.24 | 55855.24
2025-12-01 | 56.1104. | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 9500.31 | 9500.31
2025-12-01 | 56.1105. | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 30502.53 | 30502.53
2025-12-01 | 56.1106. | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 54742.18 | 54742.18
2025-12-01 | 56.1107. | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 3429.06 | 3429.06
2025-12-01 | 56.1108. | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 20729.84 | 20729.84
2025-12-01 | 56.1109. | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 14772.26 | 14772.26
2025-12-01 | 56.1110. | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 4596.42 | 4596.42
2025-12-01 | 56.1111. | AIC - California American Water - Luzern Well Treatment Design | 17210.01 | 17210.01
2025-12-01 | 56.1112. | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 27241.58 | 27241.58
2025-12-01 | 56.1113. | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 49233.44 | 49233.44
2025-12-01 | 56.1115. | AIC - UC Davis - WWTP Annual Instrument Calibrations | 5895.77 | 5895.77
2025-12-01 | 56.1119. | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 22184.06 | 22184.06
2025-12-01 | 56.1120. | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 1045.63 | 1045.63
2025-12-01 | 56.1121. | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 22824.38 | 22824.38
2025-12-01 | 56.1122. | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 6289.38 | 6289.38
2025-12-01 | 56.1123. | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 3772.82 | 3772.82
2025-12-01 | 56.1124. | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 28950 | 28950
2025-12-01 | 56.1125. | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 14229.38 | 14229.38
2025-12-01 | 56.1126. | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 9526.88 | 9526.88
2025-12-01 | 56.1127. | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 6519.07 | 6519.07
2025-12-01 | 56.1128. | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 4793.13 | 4793.13
2025-12-01 | 56.1129. | AIC - RMCSD - VEEAM SFTWR | 133.75 | 133.75
2025-12-01 | 56.1130. | System Integration Division Estimating 2025 | 267.5 | 267.5
2025-12-01 | 56.1131. | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 2388.75 | 2388.75
2025-12-01 | 56.1132. | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 585 | 585
2025-12-01 | 56.1133. | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 2827.5 | 2827.5
2025-12-01 | 56.1134. | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 965.51 | 965.51
2025-12-01 | 56.1135. | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 112.5 | 112.5
2025-12-01 | 56.1141. | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 2827.5 | 2827.5
2025-12-01 | 50.0541. | W.M. Lyles Co. - General Overhead | 3642039.89 | 3642039.89
2025-12-01 | 50.0542. | W.M. Lyles Co. - General Estimating | 100487.45 | 100487.45
2025-12-01 | 50.0543. | American Paving | 7051.01 | 7051.01
2025-12-01 | 50.0544. | Lyles Services Co. | 13555.8 | 13555.8
2025-12-01 | 50.0545. | New England Sheet Metal and Mechanical Co. | 2226.16 | 2226.16
2025-12-01 | 50.0546. | Lyles Utility Construction, LLC | 10468.06 | 10468.06
2025-12-01 | 50.0551. | Advanced Integration & Controls | 5457.42 | 5457.42