## JV GAAP WIP
W.M. Lyles Co.
JV WORK IN PROCESS-GAAP BASIS
For the 12 Months Period Ended 12/31/25
|  | AMOUNT | REMAINING | TOTAL | COSTS | ESTIMATED | TOTAL | TOTAL | % OF |  | OVER
|  | BILLED | TO BE | ESTIMATED | INCURED | COSTS TO | ESTIMATED | ESTIMATED | COMPLETION | PROFIT / | (UNDER)
AREA | DESCRIPTION | TO DATE | BILLED | CONTRACT | TO DATE | COMPLETE | COSTS | PROFIT | COST/COST | LOSS | BILLIING
Northern | Stockton Phase 1 | 5508112 | 0 | 5508112 | 4939022 | 0 | 4939022 | 569090 | 100% | 569090 | 0
Northern | Stockton Phase 2 | 225085557 | 644014.63 | 225729571.63 | 212615001.63 | 0 | 212615001.63 | 13114570 | 100% | 13114570 | -644014.63
Northern | City of Santa Cruz - Graham Hill WTP | 11042467.79 | 55906.69 | 11098374.48 | 10929117.72 | 0 | 10929117.72 | 169256.76 | 100% | 169256.76 | -55906.69
Southern | Silverlake | 364279554 | 2066292 | 366345846 | 335294794.56 | 5666024.44 | 340960819 | 25385027 | 98.34% | 25406592.44 | 3578167
Southern | East County Advanced Package 1 | 416844515.34 | 63585780.69 | 480430296.03 | 404115748.69 | 48017632.47 | 452133381.16 | 28296914.87 | 89.38% | 30680782.89 | -17952016.24
Southern | East County Advanced Package 3 | 73088486 | 21497344.49 | 94585830.49 | 92385153.68 | 0 | 92385153.68 | 2200676.81 | 100% | 2200676.81 | -21497344.49
Southern | City of Banning | 1255755.76 | 2742872.24 | 3998628 | 1142481.3 | 2492634.7 | 3635116 | 363512 | 31.43% | 113274.33 | 0.13
|  | 1097104447.89 | 90592210.74 | 1187696658.63 | 1061421319.58 | 56176291.61 | 1117597611.19 | 70099047.44 |  | 72254243.23 | -36571114.92

## JV GAAP
W.M. Lyles Co.
JV WORK IN PROCESS
FISCAL YEAR ENDING 12/31/25
For the 12 Months Period Ended 12/31/25
Full JV
|  |  | CONTRACT | EST. TOTAL | EXPECTED | JOB TO DATE | COST / | JOB TO DATE | JOB TO DATE |  |  | EST. COST TO | CONTRACT | PRIOR YR | CURRENT
AREA | DESCRIPTION |  | AMOUNT | COSTS | PROFIT | JOB COSTS | COST | PROFIT/LOSS | EARNED REV. | JTD BILLED | CURRENT WIP | COMPLETE | BALANCE | JTD PROFIT | YTD PROFIT
JV Projects
Northern | Stockton Phase 1 |  | 5508112 | 4939022 | 569090 | 4939022 | 100% | 569090 | 5508112 | 5508112 | 0 | 0 | 0 | 569090 | 0
Northern | Stockton Phase 2 |  | 225729571.63 | 212615001.63 | 13114570 | 212615001.63 | 100% | 13114570 | 225729571.63 | 225085557 | -644014.63 | 0 | 644014.63 | 19477450.52 | -6362880.52
Northern | City of Santa Cruz - Graham Hill WTP |  | 11098374.48 | 10929117.72 | 169256.76 | 10929117.72 | 100% | 169256.76 | 11098374.48 | 11042467.79 | -55906.69 | 0 | 55906.69 | -62367.34 | 231624.1
Southern | Silverlake |  | 366345846 | 340960819 | 25385027 | 335294794.56 | 98.34% | 25406592.44 | 360701387 | 364279554 | 3578167 | 5666024.44 | 2066292 | 24716046.44 | 690546
Southern | East County Advanced Package 1 |  | 480430296.03 | 452133381.16 | 28296914.87 | 404115748.69 | 89.38% | 30680782.89 | 434796531.58 | 416844515.34 | -17952016.24 | 48017632.47 | 63585780.69 | 26187672.92 | 4493109.97
Southern | East County Advanced Package 3 |  | 94585830.49 | 92385153.68 | 2200676.81 | 92385153.68 | 100% | 2200676.81 | 94585830.49 | 73088486 | -21497344.49 | 0 | 21497344.49 | 3468742.28 | -1268065.47
Southern | City of Banning |  | 3998628 | 3635116 | 363512 | 1142481.3 | 31.43% | 113274.33 | 1255755.63 | 1255755.76 | 0.13 | 2492634.7 | 2742872.24 | 0 | 113274.33
Grand Totals |  |  | 1187696658.63 | 1117597611.19 | 70099047.44 | 1061421319.58 |  | 72254243.23 | 1133675562.81 | 1097104447.89 | -36571114.92 | 56176291.61 | 90592210.74 | 74356634.82 | -2102391.59
WML Portion
AREA | DESCRIPTION | % of JV | CONTRACT AMOUNT | EST. TOTALS COSTS | EXPECTED PROFIT | JOB TO DATE JOB COSTS | COST/COST | JOB TO DATE PROFIT/LOSS | JOB TO DATE EARNED REV. | JTD BILLED | CURRENT WIP | EST. COST TO COMPLETE | CONTRACT BALANCE | PRIOR YR JTD PROFIT | CURRENT YTD PROFIT
JV Projects
Northern | Stockton Phase 1 | 50% | 2754056 | 2469511 | 284545 | 2469511 | 100% | 284545 | 2754056 | 2754056 | 0 | 0 | 0 | 284545 | 0
Northern | Stockton Phase 2 | 50% | 112864785.815 | 106307500.815 | 6557285 | 106307500.815 | 100% | 6557285 | 112864785.815 | 112542778.5 | -322007.315 | 0 | 322007.315 | 9738725.26 | -3181440.26
Northern | City of Santa Cruz - Graham Hill WTP | 50% | 5549187.24 | 5464558.86 | 84628.38 | 5464558.86 | 100% | 84628.38 | 5549187.24 | 5521233.895 | -27953.345 | 0 | 27953.345 | -31183.67 | 115812.05
Southern | Silverlake | 25% | 91586461.5 | 85240204.75 | 6346256.75 | 83823698.64 | 98.34% | 6351648.11 | 90175346.75 | 91069888.5 | 894541.75 | 1416506.11 | 516573 | 6179011.61 | 172636.5
Southern | East County Advanced Package 1 | 50% | 240215148.015 | 226066690.58 | 14148457.435 | 202057874.345 | 89.38% | 15340391.445 | 217398265.79 | 208422257.67 | -8976008.12 | 24008816.235 | 31792890.345 | 13093836.46 | 2246554.985
Southern | East County Advanced Package 3 | 50% | 47292915.245 | 46192576.84 | 1100338.405 | 46192576.84 | 100% | 1100338.405 | 47292915.245 | 36544243 | -10748672.245 | 0 | 10748672.245 | 1734371.14 | -634032.735
Southern | City of Banning | 50% | 1999314 | 1817558 | 181756 | 571240.65 | 31.43% | 56637.165 | 627877.815 | 627877.88 | 0.065 | 1246317.35 | 1371436.12 | 0 | 56637.165
Totals |  |  | 502261867.815 | 473558600.845 | 28703266.97 | 446886961.15 |  | 29775473.505 | 476662434.655 | 457482335.445 | -19180099.21 | 26671639.695 | 44779532.37 | 30999305.8 | -1223832.295
JTD Profit Comparison
|  |  | GAAP | BONUS
AREA | Description |  | PROFIT | PROFIT | Variance
JV Projects
Northern | Stockton Phase 1 |  | 284545 | 284545 | 0
Northern | Stockton Phase 2 |  | 6557285 | 6418180.5 | 139104.5
Northern | City of Santa Cruz - Graham Hill WTP |  | 84628.38 | 17162.5 | 67465.88
Southern | Silverlake |  | 6351648.11 | 6242676.75 | 108971.36
Southern | East County Advanced Package 1 |  | 15340391.445 | 8546652 | 6793739.445
Southern | East County Advanced Package 3 |  | 1100338.405 | -10262956 | 11363294.405
Southern | City of Banning |  | 56637.165 | 0 | 56637.165
WML % JV Job Totals |  |  | 29775473.505 | 11246260.75 | 18529212.755

## Bonus vs GAAP
W. M. Lyles Co.
Bonus vs. GAAP Comparison
For the Month Period Ended 12/31/2025
|  |  |  | Job to Date | [9 empty] | Year to Date | [9 empty] | 2024 Job to Date
|  | Bonus | GAAP | Bonus |  |  |  | GAAP |  |  | Bonus vs GAAP |  |  | Bonus |  |  |  | GAAP |  |  | Bonus vs GAAP
Job | Description | % Complete | % Complete | Revenue | Cost | Profit |  | Revenue | Cost | Profit | Revenue | Cost | Profit | Revenue | Cost | Profit |  | Revenue | Cost | Profit | Revenue | Cost | Profit | Bonus vs GAAP
Rocklin Open Jobs | [23 empty] | 0
51.1108 | City of Stockton - RWCF Phase 2A/2B | 100% | 100% | 94126376.71 | 89805617.8 | 4320758.91 |  | 94045647.86 | 89805617.8 | 4240030.06 | 80728.85 | 0 | 80728.85 | 1278781.99 | 1286422.83 | -7640.84 |  | 1490690.32 | 1286422.83 | 204267.49 | -211908.33 | 0 | -211908.33 | 292637.18
51.1129 | Union Sanit. Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin | 75.77% | 75.77% | 96373952.3761 | 87315159.22 | 9058793.1561 |  | 95839545.3761 | 87315159.22 | 8524386.1561 | 534407 | 0 | 534407 | 24666258.3459 | 23558088.55 | 1108169.7959 |  | 25124997.3459 | 23558088.55 | 1566908.7959 | -458739 | 0 | -458739 | 993146
51.1137 | CA Water Service Co. - Bear Gulch Pump Station 18 | 86.96% | 86.96% | 1141050.9871 | 1042229.29 | 98821.6971 |  | 1141050.9871 | 1042229.29 | 98821.6971 | 0 | 0 | 0 | 842122.9785 | 770544.87 | 71578.1085 |  | 842122.9785 | 770544.87 | 71578.1085 | 0 | 0 | 0 | 0
51.1144 | Silicon Valley Clean Water - FEP Improvements Project | 60.74% | 60.74% | 9093138.9678 | 8406760.8 | 686378.1678 |  | 9093138.9678 | 8406760.8 | 686378.1678 | 0 | 0 | 0 | 7649428.0966 | 7053381.38 | 596046.7166 |  | 7649428.0966 | 7053381.38 | 596046.7166 | 0 | 0 | 0 | 0
51.1146 | National Carbon Technologies, LLC - Aymium Williams Production Facility | 92.66% | 92.66% | 56675078.5373 | 40950686.5 | 15724392.0373 |  | 56501361.919 | 40950686.5 | 15550675.419 | 173716.6183 | 0 | 173716.6183 | 51031949.9073 | 36389605.29 | 14642344.6173 |  | 51940280.709 | 36389605.29 | 15550675.419 | -908330.8017 | 0 | -908330.8017 | 1082047.42
51.1151 | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 48.85% | 48.85% | 5206183.5756 | 4923435.18 | 282748.3956 |  | 5206183.5756 | 4923435.18 | 282748.3956 | 0 | 0 | 0 | 5019039.4956 | 4736291.1 | 282748.3956 |  | 5019039.4956 | 4736291.1 | 282748.3956 | 0 | 0 | 0 | 0
51.1152 | Mozingo Construction Inc - ElD Sly Park Intertie Project | 72.33% | 72.33% | 14448073.7521 | 13474808.54 | 973265.2121 |  | 14448073.7521 | 13474808.54 | 973265.2121 | 0 | 0 | 0 | 13001302.8521 | 12028037.64 | 973265.2121 |  | 13001302.8521 | 12028037.64 | 973265.2121 | 0 | 0 | 0 | 0
51.1153 | Linda County Water Dist. - Aeration Blower Replacement | 73.61% | 73.61% | 414268.175 | 334550.81 | 79717.365 |  | 414268.175 | 334550.81 | 79717.365 | 0 | 0 | 0 | 302445.4258 | 235587.45 | 66857.9758 |  | 302445.4258 | 235587.45 | 66857.9758 | 0 | 0 | 0 | 0
51.1154 | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 95.06% | 95.06% | 12704149.552 | 11872342.6 | 831806.952 |  | 12704149.552 | 11872342.6 | 831806.952 | 0 | 0 | 0 | 10325590.392 | 9493783.44 | 831806.952 |  | 10231269.9694 | 9493783.44 | 737486.5294 | 94320.4226 | 0 | 94320.4226 | -94320.4226
51.1158 | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 54.54% | 54.54% | 56960.69 | 56960.69 | 0 |  | 56960.69 | 56960.69 | 0 | 0 | 0 | 0 | 56960.69 | 56960.69 | 0 |  | 56960.69 | 56960.69 | 0 | 0 | 0 | 0 | 0
51.1159 | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 73.2% | 73.2% | 877720.7043 | 790051.12 | 87669.5843 |  | 877720.7043 | 790051.12 | 87669.5843 | 0 | 0 | 0 | 877720.7043 | 790051.12 | 87669.5843 |  | 877720.7043 | 790051.12 | 87669.5843 | 0 | 0 | 0 | 0
51.116 | City of Galt Public Works - Industrial WWTP Expansion | 14.82% | 14.82% | 250518.05 | 250518.05 | 0 |  | 260449.8307 | 250518.05 | 9931.7807 | -9931.7807 | 0 | -9931.7807 | 250518.05 | 250518.05 | 0 |  | 260449.8307 | 250518.05 | 9931.7807 | -9931.7807 | 0 | -9931.7807 | 0
51.1161 | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | 5.865% | 5.865% | 601852.17 | 601852.17 | 0 |  | 601852.17 | 601852.17 | 0 | 0 | 0 | 0 | 601852.17 | 601852.17 | 0 |  | 601852.17 | 601852.17 | 0 | 0 | 0 | 0 | 0
51.1162 | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project | 1.47% | 1.47% | 85941.38 | 85941.38 | 0 |  | 85941.38 | 85941.38 | 0 | 0 | 0 | 0 | 85941.38 | 85941.38 | 0 |  | 85941.38 | 85941.38 | 0 | 0 | 0 | 0 | 0
51.1164 | CA Water Service Co. - Stockton Roofing | 1.138% | 1.138% | 4363.25 | 4363.25 | 0 |  | 4363.25 | 4363.25 | 0 | 0 | 0 | 0 | 4363.25 | 4363.25 | 0 |  | 4363.25 | 4363.25 | 0 | 0 | 0 | 0 | 0
51.1165 | City of Yuba City - WTP Aquifer Storage and Recovery Well No. 3 | 0.4775% | 0.4775% | 23330.33 | 23330.33 | 0 |  | 23330.33 | 23330.33 | 0 | 0 | 0 | 0 | 23330.33 | 23330.33 | 0 |  | 23330.33 | 23330.33 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 |  | 0 | [7 empty] | 0
Rocklin Open Jobs Total |  |  |  | 292082959.2072 | 259938607.73 | 32144351.4772 |  | 291304038.5196 | 259938607.73 | 31365430.7896 | 778920.6876 | 0 | 778920.6876 | 116017606.058 | 97364759.54 | 18652846.518 |  | 117512195.5478 | 97364759.54 | 20147436.0078 | -1494589.4898 | 0 | -1494589.4898 | 2273510.1774
0
Rocklin Closed Jobs | [23 empty] | 0
51.1133 | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 100% | 100% | 372738 | 331855.28 | 40882.72 |  | 372738 | 331855.28 | 40882.72 | 0 | 0 | 0 | 52253.0094 | 28729.87 | 23523.1394 |  | 52253.0094 | 28729.87 | 23523.1394 | 0 | 0 | 0 | 0
51.1136 | Union Sanitary Dist - USD Plant Misc. Improvements | 100% | 100% | 5483550 | 4531817.86 | 951732.14 |  | 5483550 | 4531817.86 | 951732.14 | 0 | 0 | 0 | 495311.3739 | 302485.02 | 192826.3539 |  | 495311.3739 | 302485.02 | 192826.3539 | 0 | 0 | 0 | 0
51.1138 | CA Water Service Co. - Bear Gulch Pump Station 21 | 100% | 100% | 1120182.07 | 1167704.15 | -47522.08 |  | 1120182.07 | 1167704.15 | -47522.08 | 0 | 0 | 0 | 255501.9209 | 380802.1 | -125300.1791 |  | 255501.9209 | 380802.1 | -125300.1791 | 0 | 0 | 0 | 0
51.1139 | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 100% | 100% | 61902 | 56994.44 | 4907.56 |  | 61902 | 56994.44 | 4907.56 | 0 | 0 | 0 | 481.201 | 0 | 481.201 |  | 481.201 | 0 | 481.201 | 0 | 0 | 0 | 0
51.1141 | City of Colfax - WWTP Algae Reduction Project | 100% | 100% | 3967189.79 | 3835094.73 | 132095.06 |  | 3967189.79 | 3835094.73 | 132095.06 | 0 | 0 | 0 | 777363.7313 | 725188.97 | 52174.7613 |  | 777363.7313 | 725188.97 | 52174.7613 | 0 | 0 | 0 | 0
51.1143 | Olivehurst Plumas Lake Manganese Filter Expansion | 100% | 100% | 1991231.37 | 1758132.57 | 233098.8 |  | 1991231.37 | 1758132.57 | 233098.8 | 0 | 0 | 0 | 34528.6371 | 27441.6 | 7087.0371 |  | 34528.6371 | 27441.6 | 7087.0371 | 0 | 0 | 0 | 0
51.1147 | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 100% | 100% | 2742860.08 | 2548724.92 | 194135.16 |  | 2742860.08 | 2548724.92 | 194135.16 | 0 | 0 | 0 | 864663.2248 | 798812.6 | 65850.6248 |  | 864663.2248 | 798812.6 | 65850.6248 | 0 | 0 | 0 | 0
51.115 | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 100% | 100% | 2486231.58 | 2239435.14 | 246796.44 |  | 2486231.58 | 2239435.14 | 246796.44 | 0 | 0 | 0 | 248682.9505 | 168358.34 | 80324.6105 |  | 248682.9505 | 168358.34 | 80324.6105 | 0 | 0 | 0 | 0
51.1156 | Rocklin Overhead 2025 | 100% | 100% | 0 | 1426058.69 | -1426058.69 |  | 0 | 1426058.69 | -1426058.69 | 0 | 0 | 0 | 0 | 1426058.69 | -1426058.69 |  | 0 | 1426058.69 | -1426058.69 | 0 | 0 | 0 | 0
51.1157 | Rocklin Estimating 2025 | 100% | 100% | 0 | 613546.52 | -613546.52 |  | 0 | 613546.52 | -613546.52 | 0 | 0 | 0 | 0 | 613546.52 | -613546.52 |  | 0 | 613546.52 | -613546.52 | 0 | 0 | 0 | 0
0
Rocklin Closed Jobs Total |  |  |  | 18225884.89 | 18509364.3 | -283479.41 |  | 18225884.89 | 18509364.3 | -283479.41 | 0 | 0 | 0 | 2728786.0491 | 4471423.71 | -1742637.6609 |  | 2728786.0491 | 4471423.71 | -1742637.6609 | 0 | 0 | 0 | 0
0
Rocklin Total |  |  |  | 310308844.0972 | 278447972.03 | 31860872.0672 |  | 309529923.4096 | 278447972.03 | 31081951.3796 | 778920.6876 | 0 | 778920.6876 | 118746392.1071 | 101836183.25 | 16910208.8571 |  | 120240981.5969 | 101836183.25 | 18404798.3469 | -1494589.4898 | 0 | -1494589.4898 | 2273510.1774
Fresno Open Jobs
52.8563 | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 97.53% | 100% | 1152462.29 | 859077.05 | 293385.24 |  | 1134038.13 | 859077.05 | 274961.08 | 18424.16 | 0 | 18424.16 | 167405.78 | 138210.3 | 29195.48 |  | 218705.64 | 138210.3 | 80495.34 | -51299.86 | 0 | -51299.86 | 69724.02
52.8566 | City of Visalia - Water Reclamation Facility RPGS SCR System | 99.46% | 99.46% | 1252574.9834 | 1023821.05 | 228753.9334 |  | 1252574.9834 | 1023821.05 | 228753.9334 | 0 | 0 | 0 | 33809.9171 | 29030.49 | 4779.4271 |  | 33809.9171 | 29030.49 | 4779.4271 | 0 | 0 | 0 | 0
52.8586 | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 99.1% | 99.1% | 12497922.4241 | 10565460.74 | 1932461.6841 |  | 12497922.4241 | 10565460.74 | 1932461.6841 | 0 | 0 | 0 | 506849.7062 | 332168.03 | 174681.6762 |  | 506849.7062 | 332168.03 | 174681.6762 | 0 | 0 | 0 | 0
52.8634 | City of Huron - Water Treatment Plant Imp. Phase 2 | 88.75% | 88.75% | 12330098.7698 | 11707058.24 | 623040.5298 |  | 12330098.7698 | 11707058.24 | 623040.5298 | 0 | 0 | 0 | 6838700.1383 | 6493631.62 | 345068.5183 |  | 6838700.1383 | 6493631.62 | 345068.5183 | 0 | 0 | 0 | 0
52.8636 | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 100% | 99.58% | 3642035.1389 | 3367047.36 | 274987.7789 |  | 3640903.4239 | 3367047.36 | 273856.0639 | 1131.7149 | 0 | 1131.7149 | 1980915.8878 | 1910247.82 | 70668.0678 |  | 1979784.1728 | 1910247.82 | 69536.3528 | 1131.7149 | 0 | 1131.7149 | -1.7462e-10
52.8637 | Root Creek Water Dist. - Groundwater Blending & Arsenic | 99.02% | 99.02% | 26008192.3257 | 24374299.03 | 1633893.2957 |  | 26008192.3257 | 24374299.03 | 1633893.2957 | 0 | 0 | 0 | 5357985.578 | 4932484.04 | 425501.538 |  | 5357985.578 | 4932484.04 | 425501.538 | 0 | 0 | 0 | 0
52.864 | City of Dos Palos - WTP Replacement Project | 87.45% | 87.45% | 33797041.051 | 32158781.48 | 1638259.571 |  | 33797041.051 | 32158781.48 | 1638259.571 | 0 | 0 | 0 | 20058621.4722 | 19124328.74 | 934292.7322 |  | 20058621.4722 | 19124328.74 | 934292.7322 | 0 | 0 | 0 | 0
52.8668 | California Water Service Co. - Cal Water - Salinas Station 57 | 94.88% | 94.88% | 390782.6533 | 357710.67 | 33071.9833 |  | 390782.6533 | 357710.67 | 33071.9833 | 0 | 0 | 0 | 341717.6533 | 308645.67 | 33071.9833 |  | 336444.6068 | 308645.67 | 27798.9368 | 5273.0464 | 0 | 5273.0464 | -5273.0464
52.8678 | City of Chowcilla - Well 15 & Generator Improvement Projects | 79.67% | 79.67% | 988148.9819 | 926007.31 | 62141.6719 |  | 988148.9819 | 926007.31 | 62141.6719 | 0 | 0 | 0 | 982585.3519 | 920443.68 | 62141.6719 |  | 982585.3519 | 920443.68 | 62141.6719 | 0 | 0 | 0 | 0
52.8687 | California Water Service Co. - Salinas Station 205 | 93.66% | 93.66% | 822283.7912 | 740629.43 | 81654.3612 |  | 822283.7912 | 740629.43 | 81654.3612 | 0 | 0 | 0 | 822283.7912 | 740629.43 | 81654.3612 |  | 822283.7912 | 740629.43 | 81654.3612 | 0 | 0 | 0 | 0
52.8692 | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 100% | 100% | 55135.37 | 49682.49 | 5452.88 |  | 55135.37 | 49682.49 | 5452.88 | 0 | 0 | 0 | 55135.37 | 49682.49 | 5452.88 |  | 55135.37 | 49682.49 | 5452.88 | 0 | 0 | 0 | 0
52.8697 | City of Tulare - Industrial WWTP Dewatering Improvements Pro | 58.26% | 58.26% | 808608.9206 | 772187.73 | 36421.1906 |  | 808608.9206 | 772187.73 | 36421.1906 | 0 | 0 | 0 | 808608.9206 | 772187.73 | 36421.1906 |  | 808608.9206 | 772187.73 | 36421.1906 | 0 | 0 | 0 | 0
52.8698 | California Water Service Co. - Tesoro Viejo RWSP Liner Repair | 94.64% | 94.64% | 21496.2321 | 15264 | 6232.2321 |  | 21496.2321 | 15264 | 6232.2321 | 0 | 0 | 0 | 21496.2321 | 15264 | 6232.2321 |  | 21496.2321 | 15264 | 6232.2321 | 0 | 0 | 0 | 0
52.8704 | City of Visalia - Solids Handling Improvements Project | 6.085% | 6.085% | 820988.3 | 820988.3 | 0 |  | 820988.3 | 820988.3 | 0 | 0 | 0 | 0 | 820988.3 | 820988.3 | 0 |  | 820988.3 | 820988.3 | 0 | 0 | 0 | 0 | 0
52.8705 | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | 39.68% | 39.68% | 307545.1617 | 285425.72 | 22119.4417 |  | 307545.1617 | 285425.72 | 22119.4417 | 0 | 0 | 0 | 307545.1617 | 285425.72 | 22119.4417 |  | 307545.1617 | 285425.72 | 22119.4417 | 0 | 0 | 0 | 0
52.8707 | County of Fresno - Westside Water Tank and Pump Station | 29.24% | 29.24% | 1079776.4803 | 1012057.14 | 67719.3403 |  | 1079776.4803 | 1012057.14 | 67719.3403 | 0 | 0 | 0 | 1079776.4803 | 1012057.14 | 67719.3403 |  | 1079776.4803 | 1012057.14 | 67719.3403 | 0 | 0 | 0 | 0
52.8708 | County of Fresno - CSA 44A Wastewater Improvements | 2.302% | 2.302% | 7682.19 | 7682.19 | 0 |  | 7682.19 | 7682.19 | 0 | 0 | 0 | 0 | 7682.19 | 7682.19 | 0 |  | 7682.19 | 7682.19 | 0 | 0 | 0 | 0 | 0
52.8711 | California Water Service Co. - Tesoro Viejo ARV Replacement | 72.35% | 72.35% | 4963.1095 | 4568.81 | 394.2995 |  | 4963.1095 | 4568.81 | 394.2995 | 0 | 0 | 0 | 4963.1095 | 4568.81 | 394.2995 |  | 4963.1095 | 4568.81 | 394.2995 | 0 | 0 | 0 | 0
52.8713 | City of Visalia - Remove & Replace Chain and Flight Mechanic | 0.487% | 0.487% | 927.5 | 927.5 | 0 |  | 927.5 | 927.5 | 0 | 0 | 0 | 0 | 927.5 | 927.5 | 0 |  | 927.5 | 927.5 | 0 | 0 | 0 | 0 | 0
52.8714 | New England Sheet Metal and Mechanical Co. - VCH Digging Water Line T&M | 100% | 100% | 5084.94 | 4465.61 | 619.33 |  | 5084.94 | 4465.61 | 619.33 | 0 | 0 | 0 | 5084.94 | 4465.61 | 619.33 |  | 5084.94 | 4465.61 | 619.33 | 0 | 0 | 0 | 0
[15 empty] | 0 | [8 empty] | 0
Fresno Open Jobs Total |  |  |  | 95993750.6135 | 89053141.85 | 6940608.7635 |  | 95974194.7386 | 89053141.85 | 6921052.8886 | 19555.8749 | 0 | 19555.8749 | 40203083.4802 | 37903069.31 | 2300014.1702 |  | 40247978.5788 | 37903069.31 | 2344909.2688 | -44895.0986 | 0 | -44895.0986 | 64450.9736
0
Fresno Closed Jobs | [23 empty] | 0
52.8567 | City of Modesto - Grayson Well 69 | 100% | 100% | 3059858.99 | 3128023.93 | -68164.94 |  | 3059858.99 | 3128023.93 | -68164.94 | 0 | 0 | 0 | 49233.73 | 34398.67 | 14835.06 |  | 49233.73 | 34398.67 | 14835.06 | 0 | 0 | 0 | 0
52.8604 | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 100% | 100% | 5095690.97 | 4572503.23 | 523187.74 |  | 5095690.97 | 4572503.23 | 523187.74 | 0 | 0 | 0 | 1102038.3473 | 908839.74 | 193198.6073 |  | 1102038.3473 | 908839.74 | 193198.6073 | 0 | 0 | 0 | 0
52.8628 | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 100% | 100% | 5213345.5 | 4745798.53 | 467546.97 |  | 5213345.5 | 4745798.53 | 467546.97 | 0 | 0 | 0 | 1174192.7562 | 903870.54 | 270322.2162 |  | 1174192.7562 | 903870.54 | 270322.2162 | 0 | 0 | 0 | 0
52.8631 | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 100% | 100% | 2560650.14 | 2448658.26 | 111991.88 |  | 2560650.14 | 2448658.26 | 111991.88 | 0 | 0 | 0 | 237953.2995 | 198965.12 | 38988.1795 |  | 237953.2995 | 198965.12 | 38988.1795 | 0 | 0 | 0 | 0
52.8652 | California Water Service Co. - Salinas 77 Booster Station | 100% | 100% | 1290184 | 1039376.08 | 250807.92 |  | 1290184 | 1039376.08 | 250807.92 | 0 | 0 | 0 | 133540.6726 | 53431.59 | 80109.0826 |  | 133540.6726 | 53431.59 | 80109.0826 | 0 | 0 | 0 | 0
52.8658 | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 100% | 100% | 1870914.99 | 1633530.21 | 237384.78 |  | 1870914.99 | 1633530.21 | 237384.78 | 0 | 0 | 0 | 200545.22 | 111911.44 | 88633.78 |  | 203409.6146 | 111911.44 | 91498.1746 | -2864.3946 | 0 | -2864.3946 | 2864.3946
52.8663 | Root Creek Water Dist. - Ag Well 277 Conversion Project | 100% | 100% | 1641800 | 1379688.28 | 262111.72 |  | 1641800 | 1379688.28 | 262111.72 | 0 | 0 | 0 | 1192257.6592 | 972822.89 | 219434.7692 |  | 1192257.6592 | 972822.89 | 219434.7692 | 0 | 0 | 0 | 0
52.8667 | California Water Service Co. - Cal Water Salinas Station 33 | 100% | 100% | 314085.77 | 290726.11 | 23359.66 |  | 314085.77 | 290726.11 | 23359.66 | 0 | 0 | 0 | 1869.5547 | 5378.76 | -3509.2053 |  | 1869.5547 | 5378.76 | -3509.2053 | 0 | 0 | 0 | 0
52.867 | California Water Service Co. - Cal Water - King City Station 10 | 100% | 100% | 274166.01 | 267282.05 | 6883.96 |  | 274166.01 | 267282.05 | 6883.96 | 0 | 0 | 0 | 142646.0644 | 146166.54 | -3520.4756 |  | 142646.0644 | 146166.54 | -3520.4756 | 0 | 0 | 0 | 0
52.8674 | City of Hanford - WWTP Standby Influent Pump Install | 100% | 100% | 279244 | 251088.2 | 28155.8 |  | 279244 | 251088.2 | 28155.8 | 0 | 0 | 0 | 78969.7964 | 66348.58 | 12621.2164 |  | 78969.7964 | 66348.58 | 12621.2164 | 0 | 0 | 0 | 0
52.8677 | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 100% | 100% | 796055.3 | 689831.96 | 106223.34 |  | 796055.3 | 689831.96 | 106223.34 | 0 | 0 | 0 | 762769.27 | 656545.93 | 106223.34 |  | 762769.27 | 656545.93 | 106223.34 | 0 | 0 | 0 | 0
52.868 | City of Orange Cove - Orange Cove West Clarifier T&M | 100% | 100% | 29838.25 | 26088.33 | 3749.92 |  | 29838.25 | 26088.33 | 3749.92 | 0 | 0 | 0 | 23324.04 | 19574.12 | 3749.92 |  | 23324.04 | 19574.12 | 3749.92 | 0 | 0 | 0 | 0
52.8682 | Fresno Overhead 2025 | 100% | 100% | 0 | 1121157.1 | -1121157.1 |  | 0 | 1121157.1 | -1121157.1 | 0 | 0 | 0 | 0 | 1121157.1 | -1121157.1 |  | 0 | 1121157.1 | -1121157.1 | 0 | 0 | 0 | 0
52.8683 | Fresno Estimating 2025 | 100% | 100% | 0 | 415452.52 | -415452.52 |  | 0 | 415452.52 | -415452.52 | 0 | 0 | 0 | 0 | 415452.52 | -415452.52 |  | 0 | 415452.52 | -415452.52 | 0 | 0 | 0 | 0
52.8684 | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 100% | 100% | 50568.05 | 45291.39 | 5276.66 |  | 50568.05 | 45291.39 | 5276.66 | 0 | 0 | 0 | 50568.05 | 45291.39 | 5276.66 |  | 50568.05 | 45291.39 | 5276.66 | 0 | 0 | 0 | 0
52.8685 | Malaga County Water Dist. - Malaga County Water District | 100% | 100% | 451254 | 382067.32 | 69186.68 |  | 451254 | 382067.32 | 69186.68 | 0 | 0 | 0 | 451254 | 382067.32 | 69186.68 |  | 451254 | 382067.32 | 69186.68 | 0 | 0 | 0 | 0
52.8686 | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 100% | 100% | 23957 | 7505.26 | 16451.74 |  | 23957 | 7505.26 | 16451.74 | 0 | 0 | 0 | 2293.8733 | 1214.39 | 1079.4833 |  | 2293.8733 | 1214.39 | 1079.4833 | 0 | 0 | 0 | 0
52.8688 | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 100% | 100% | 132492.2 | 116972.75 | 15519.45 |  | 132492.2 | 116972.75 | 15519.45 | 0 | 0 | 0 | 132492.2 | 116972.75 | 15519.45 |  | 132492.2 | 116972.75 | 15519.45 | 0 | 0 | 0 | 0
52.8689 | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 100% | 100% | 16665.83 | 16095.58 | 570.25 |  | 16665.83 | 16095.58 | 570.25 | 0 | 0 | 0 | 16665.83 | 16095.58 | 570.25 |  | 16665.83 | 16095.58 | 570.25 | 0 | 0 | 0 | 0
52.869 | City of Dinuba - WWTP Rake Replacement | 100% | 100% | 14151.97 | 13155.83 | 996.14 |  | 14151.97 | 13155.83 | 996.14 | 0 | 0 | 0 | 14151.97 | 13155.83 | 996.14 |  | 14151.97 | 13155.83 | 996.14 | 0 | 0 | 0 | 0
52.8691 | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 100% | 100% | 11302.84 | 8287.82 | 3015.02 |  | 11302.84 | 8287.82 | 3015.02 | 0 | 0 | 0 | 11302.84 | 8287.82 | 3015.02 |  | 11302.84 | 8287.82 | 3015.02 | 0 | 0 | 0 | 0
52.8693 | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 100% | 100% | 1120704.2 | 663140.99 | 457563.21 |  | 1120704.2 | 663140.99 | 457563.21 | 0 | 0 | 0 | 1120704.2 | 663140.99 | 457563.21 |  | 1120704.2 | 663140.99 | 457563.21 | 0 | 0 | 0 | 0
52.8694 | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 100% | 100% | 43047.45 | 38541.99 | 4505.46 |  | 43047.45 | 38541.99 | 4505.46 | 0 | 0 | 0 | 43047.45 | 38541.99 | 4505.46 |  | 43047.45 | 38541.99 | 4505.46 | 0 | 0 | 0 | 0
52.8695 | Lyles Services Co. - LSC GO Trash Enclosure | 100% | 100% | 13769 | 13024.37 | 744.63 |  | 13769 | 13024.37 | 744.63 | 0 | 0 | 0 | 13769 | 13024.37 | 744.63 |  | 13769 | 13024.37 | 744.63 | 0 | 0 | 0 | 0
52.8696 | American Paving Co. - Hot Tap for APC- Tule River Parkway | 100% | 100% | 1059.22 | 887.65 | 171.57 |  | 1059.22 | 887.65 | 171.57 | 0 | 0 | 0 | 1059.22 | 887.65 | 171.57 |  | 1059.22 | 887.65 | 171.57 | 0 | 0 | 0 | 0
52.8699 | City of Hanford - WWTP Repair T&M | 100% | 100% | 3001.12 | 2948.91 | 52.21 |  | 3001.12 | 2948.91 | 52.21 | 0 | 0 | 0 | 3001.12 | 2948.91 | 52.21 |  | 3001.12 | 2948.91 | 52.21 | 0 | 0 | 0 | 0
52.87 | Lyles Services Co. - LSC GO Misc. Work | 100% | 100% | 5297 | 4446.13 | 850.87 |  | 5297 | 4446.13 | 850.87 | 0 | 0 | 0 | 5297 | 4446.13 | 850.87 |  | 5297 | 4446.13 | 850.87 | 0 | 0 | 0 | 0
52.8701 | County of Fresno - 47 Water | 100% | 100% | 13433.85 | 12421.08 | 1012.77 |  | 13433.85 | 12421.08 | 1012.77 | 0 | 0 | 0 | 13433.85 | 12421.08 | 1012.77 |  | 13433.85 | 12421.08 | 1012.77 | 0 | 0 | 0 | 0
52.8702 | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M | 100% | 100% | 5626.78 | 4725.28 | 901.5 |  | 5626.78 | 4725.28 | 901.5 | 0 | 0 | 0 | 5626.78 | 4725.28 | 901.5 |  | 5626.78 | 4725.28 | 901.5 | 0 | 0 | 0 | 0
52.8703 | County of Fresno - CSA 47 Egret Point Water Line Repair | 100% | 100% | 14402.18 | 12571.54 | 1830.64 |  | 14402.18 | 12571.54 | 1830.64 | 0 | 0 | 0 | 14402.18 | 12571.54 | 1830.64 |  | 14402.18 | 12571.54 | 1830.64 | 0 | 0 | 0 | 0
52.8706 | City of Hanford - WWTP Weld Repair T&M 2 | 100% | 100% | 2868.6 | 2435.78 | 432.82 |  | 2868.6 | 2435.78 | 432.82 | 0 | 0 | 0 | 2868.6 | 2435.78 | 432.82 |  | 2868.6 | 2435.78 | 432.82 | 0 | 0 | 0 | 0
52.8709 | County of Fresno - 47.1 Water | 100% | 100% | 17765.14 | 14874.36 | 2890.78 |  | 17765.14 | 14874.36 | 2890.78 | 0 | 0 | 0 | 17765.14 | 14874.36 | 2890.78 |  | 17765.14 | 14874.36 | 2890.78 | 0 | 0 | 0 | 0
52.871 | City of Dinuba - WWTP Bar Screen Motor Bracket Repair | 100% | 100% | 4064.54 | 3514.84 | 549.7 |  | 4064.54 | 3514.84 | 549.7 | 0 | 0 | 0 | 4064.54 | 3514.84 | 549.7 |  | 4064.54 | 3514.84 | 549.7 | 0 | 0 | 0 | 0
52.8715 | New England Sheet Metal and Mechanical Co. - Vitro Glass Plant Concrete Pad T&M | 100% | 100% | 10001.43 | 8585.44 | 1415.99 |  | 10001.43 | 8585.44 | 1415.99 | 0 | 0 | 0 | 10001.43 | 8585.44 | 1415.99 |  | 10001.43 | 8585.44 | 1415.99 | 0 | 0 | 0 | 0
0
Fresno Closed Jobs Total |  |  |  | 24381266.32 | 23380699.1 | 1000567.22 |  | 24381266.32 | 23380699.1 | 1000567.22 | 0 | 0 | 0 | 7033109.6835 | 6980066.98 | 53042.7035 |  | 7035974.0781 | 6980066.98 | 55907.0981 | -2864.3946 | 0 | -2864.3946 | 2864.3946
Fresno Total |  |  |  | 120375016.9335 | 112433840.95 | 7941175.9835 |  | 120355461.0586 | 112433840.95 | 7921620.1086 | 19555.8749 | 0 | 19555.8749 | 47236193.1637 | 44883136.29 | 2353056.8737 |  | 47283952.6569 | 44883136.29 | 2400816.3669 | -47759.4932 | 0 | -47759.4932 | 67315.3682
East Bay Open Jobs
53.2007 | Union Sanitary Dist. - Phase 1B Secondary Clarifiers | 0.1389% | 0.1389% | 404852.16 | 404852.16 | 0 |  | 404852.16 | 404852.16 | 0 | 0 | 0 | 0 | 404852.16 | 404852.16 | 0 |  | 404852.16 | 404852.16 | 0 | 0 | 0 | 0 | 0
0
East Bay Open Jobs Total |  |  |  | 404852.16 | 404852.16 | 0 |  | 404852.16 | 404852.16 | 0 | 0 | 0 | 0 | 404852.16 | 404852.16 | 0 |  | 404852.16 | 404852.16 | 0 | 0 | 0 | 0 | 0
East Bay Closed Jobs
53.2004 | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 100% | 100% | 1173753.47 | 980791.05 | 192962.42 |  | 1173753.47 | 980791.05 | 192962.42 | 0 | 0 | 0 | 1151824.99 | 958862.57 | 192962.42 |  | 1151824.99 | 958862.57 | 192962.42 | 0 | 0 | 0 | 0
53.2005 | East Bay Overhead 2025 | 100% | 100% | 0 | 279281.96 | -279281.96 |  | 0 | 279281.96 | -279281.96 | 0 | 0 | 0 | 0 | 279281.96 | -279281.96 |  | 0 | 279281.96 | -279281.96 | 0 | 0 | 0 | 0
53.2006 | East Bay Estimating 2026 | 100% | 100% | 0 | 304986.32 | -304986.32 |  | 0 | 304986.32 | -304986.32 | 0 | 0 | 0 | 0 | 304986.32 | -304986.32 |  | 0 | 304986.32 | -304986.32 | 0 | 0 | 0 | 0
0
East Bay Closed Jobs Total |  |  |  | 1173753.47 | 1565059.33 | -391305.86 |  | 1173753.47 | 1565059.33 | -391305.86 | 0 | 0 | 0 | 1151824.99 | 1543130.85 | -391305.86 |  | 1151824.99 | 1543130.85 | -391305.86 | 0 | 0 | 0 | 0
East Bay Total |  |  |  | 1578605.63 | 1969911.49 | -391305.86 |  | 1578605.63 | 1969911.49 | -391305.86 | 0 | 0 | 0 | 1556677.15 | 1947983.01 | -391305.86 |  | 1556677.15 | 1947983.01 | -391305.86 | 0 | 0 | 0 | 0
Bakersfield Open Jobs
54.9033 | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 100% | 100% | 118278.58 | 104550.27 | 13728.31 |  | 118278.58 | 104550.27 | 13728.31 | 0 | 0 | 0 | 24368.78 | 21607.34 | 2761.44 |  | 24368.78 | 21607.34 | 2761.44 | 0 | 0 | 0 | 0
54.9135 | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 100% | 100% | 9470658.62 | 9050951.86 | 419706.76 |  | 9470658.62 | 9050951.86 | 419706.76 | 0 | 0 | 0 | 1547627.9249 | 1679915.53 | -132287.6051 |  | 2099622.29 | 1679915.53 | 419706.76 | -551994.3651 | 0 | -551994.3651 | 551994.3651
54.9257 | City of Guadalupe - Highway 1 Lift Station | 53.44% | 53.44% | 786258.4621 | 762211.05 | 24047.4121 |  | 786258.4621 | 762211.05 | 24047.4121 | 0 | 0 | 0 | 772222.6321 | 748175.22 | 24047.4121 |  | 772222.6321 | 748175.22 | 24047.4121 | 0 | 0 | 0 | 0
54.9268 | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 95.49% | 95.49% | 909648.28 | 844648.28 | 65000 |  | 906714.892 | 844648.28 | 62066.612 | 2933.388 | 0 | 2933.388 | 50581.4432 | 56594.51 | -6013.0668 |  | 47648.0552 | 56594.51 | -8946.4548 | 2933.388 | 0 | 2933.388 | -2.9104e-11
54.9269 | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 92.94% | 100% | 584066.79 | 549817.74 | 34249.05 |  | 625819.17 | 549817.74 | 76001.43 | -41752.38 | 0 | -41752.38 | 243796.33 | 243796.33 | 0 |  | 285548.71 | 243796.33 | 41752.38 | -41752.38 | 0 | -41752.38 | 0
54.9285 | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 80.86% | 80.86% | 373583.5648 | 312939.77 | 60643.7948 |  | 373583.5648 | 312939.77 | 60643.7948 | 0 | 0 | 0 | 151844.577 | 126887.02 | 24957.557 |  | 151844.577 | 126887.02 | 24957.557 | 0 | 0 | 0 | 0
54.9313 | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 93.78% | 93.78% | 7396392.3889 | 6449205.22 | 947187.1689 |  | 7396392.3889 | 6449205.22 | 947187.1689 | 0 | 0 | 0 | 5277538.7678 | 4528066.11 | 749472.6578 |  | 5277538.7678 | 4528066.11 | 749472.6578 | 0 | 0 | 0 | 0
54.933 | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 99.54% | 99.54% | 323400.7694 | 306221.41 | 17179.3594 |  | 323400.7694 | 306221.41 | 17179.3594 | 0 | 0 | 0 | 131310.3722 | 124773.14 | 6537.2322 |  | 131310.3722 | 124773.14 | 6537.2322 | 0 | 0 | 0 | 0
54.9336 | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 53.03% | 53.03% | 13359053.4129 | 12340864.27 | 1018189.1429 |  | 13359053.4129 | 12340864.27 | 1018189.1429 | 0 | 0 | 0 | 11238995.8629 | 10220806.72 | 1018189.1429 |  | 11238995.8629 | 10220806.72 | 1018189.1429 | 0 | 0 | 0 | 0
54.9337 | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 38.25% | 38.25% | 1570273.3156 | 1509066.73 | 61206.5856 |  | 1570273.3156 | 1509066.73 | 61206.5856 | 0 | 0 | 0 | 1417261.6056 | 1356055.02 | 61206.5856 |  | 1417261.6056 | 1356055.02 | 61206.5856 | 0 | 0 | 0 | 0
54.9343 | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 57.1% | 57.1% | 3929247.3572 | 3415344.08 | 513903.2772 |  | 3929247.3572 | 3415344.08 | 513903.2772 | 0 | 0 | 0 | 3329055.5672 | 2815152.29 | 513903.2772 |  | 3329055.5672 | 2815152.29 | 513903.2772 | 0 | 0 | 0 | 0
54.9356 | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 84.94% | 84.94% | 1102799.0115 | 775780.75 | 327018.2615 |  | 1102799.0115 | 775780.75 | 327018.2615 | 0 | 0 | 0 | 1039914.2515 | 712895.99 | 327018.2615 |  | 1039914.2515 | 712895.99 | 327018.2615 | 0 | 0 | 0 | 0
54.9366 | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 85.47% | 85.47% | 1051430.0181 | 923220.5 | 128209.5181 |  | 1051430.0181 | 923220.5 | 128209.5181 | 0 | 0 | 0 | 1045916.9581 | 917707.44 | 128209.5181 |  | 1045916.9581 | 917707.44 | 128209.5181 | 0 | 0 | 0 | 0
54.9369 | California Water Service Co. - PFAS Treatment Program Project | 10.65% | 10.65% | 2787466.66 | 2787466.66 | 0 |  | 3039899.8504 | 2787466.66 | 252433.1904 | -252433.1904 | 0 | -252433.1904 | 2786224.21 | 2786224.21 | 0 |  | 3038657.4004 | 2786224.21 | 252433.1904 | -252433.1904 | 0 | -252433.1904 | 0
54.9373 | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 3.61% | 3.61% | 50303.97 | 50303.97 | 0 |  | 50303.97 | 50303.97 | 0 | 0 | 0 | 0 | 50303.97 | 50303.97 | 0 |  | 50303.97 | 50303.97 | 0 | 0 | 0 | 0 | 0
54.9389 | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 99.08% | 99.08% | 296891.85 | 311891.85 | -15000 |  | 296891.85 | 311891.85 | -15000 | 0 | 0 | 0 | 296891.85 | 311891.85 | -15000 |  | 296891.85 | 311891.85 | -15000 | 0 | 0 | 0 | 0
54.9391 | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 100% | 100% | 532604.57 | 512057.34 | 20547.23 |  | 532604.57 | 512057.34 | 20547.23 | 0 | 0 | 0 | 532604.57 | 512057.34 | 20547.23 |  | 532604.57 | 512057.34 | 20547.23 | 0 | 0 | 0 | 0
54.9395 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 79.69% | 79.69% | 1430881.5112 | 1349601.92 | 81279.5912 |  | 1430881.5112 | 1349601.92 | 81279.5912 | 0 | 0 | 0 | 1430881.5112 | 1349601.92 | 81279.5912 |  | 1430881.5112 | 1349601.92 | 81279.5912 | 0 | 0 | 0 | 0
54.9396 | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | 100% | 100% | 157746.09 | 157746.09 | 0 |  | 157746.09 | 157746.09 | 0 | 0 | 0 | 0 | 157746.09 | 157746.09 | 0 |  | 157746.09 | 157746.09 | 0 | 0 | 0 | 0 | 0
54.9397 | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 30.53% | 30.53% | 1126646.6941 | 1035065.41 | 91581.2841 |  | 1126646.6941 | 1035065.41 | 91581.2841 | 0 | 0 | 0 | 1126646.6941 | 1035065.41 | 91581.2841 |  | 1126646.6941 | 1035065.41 | 91581.2841 | 0 | 0 | 0 | 0
54.9403 | Lost Hills Utility Dist. - WTP Improvements | 38.16% | 38.16% | 145602.2491 | 129004.89 | 16597.3591 |  | 145602.2491 | 129004.89 | 16597.3591 | 0 | 0 | 0 | 145602.2491 | 129004.89 | 16597.3591 |  | 145602.2491 | 129004.89 | 16597.3591 | 0 | 0 | 0 | 0
54.9404 | Cawelo Water Dist. - Reuse of Produced Water | 54.08% | 54.08% | 2011822.3122 | 1939024.63 | 72797.6822 |  | 2011822.3122 | 1939024.63 | 72797.6822 | 0 | 0 | 0 | 2011822.3122 | 1939024.63 | 72797.6822 |  | 2011822.3122 | 1939024.63 | 72797.6822 | 0 | 0 | 0 | 0
54.9405 | Semitropic Water Storage Dist. - Pump Platform Replacement Project | 71.16% | 71.16% | 670300.4713 | 577796.16 | 92504.3113 |  | 670300.4713 | 577796.16 | 92504.3113 | 0 | 0 | 0 | 670300.4713 | 577796.16 | 92504.3113 |  | 670300.4713 | 577796.16 | 92504.3113 | 0 | 0 | 0 | 0
54.9406 | California Water Service Co. - Emergency PACL leak repair | 100% | 100% | 1120.65 | 1120.65 | 0 |  | 1120.65 | 1120.65 | 0 | 0 | 0 | 0 | 1120.65 | 1120.65 | 0 |  | 1120.65 | 1120.65 | 0 | 0 | 0 | 0 | 0
54.9408 | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line | 1.178% | 1.178% | 41652.43 | 41652.43 | 0 |  | 41652.43 | 41652.43 | 0 | 0 | 0 | 0 | 41652.43 | 41652.43 | 0 |  | 41652.43 | 41652.43 | 0 | 0 | 0 | 0 | 0
54.9411 | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation | 91.15% | 91.15% | 94158.4777 | 71370.85 | 22787.6277 |  | 94158.4777 | 71370.85 | 22787.6277 | 0 | 0 | 0 | 94158.4777 | 71370.85 | 22787.6277 |  | 94158.4777 | 71370.85 | 22787.6277 | 0 | 0 | 0 | 0
54.9412 | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork | 100% | 100% | 116752.04 | 115708.88 | 1043.16 |  | 116752.04 | 115708.88 | 1043.16 | 0 | 0 | 0 | 116752.04 | 115708.88 | 1043.16 |  | 116752.04 | 115708.88 | 1043.16 | 0 | 0 | 0 | 0
54.9413 | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork | 100% | 100% | 149366.83 | 132138.74 | 17228.09 |  | 149366.83 | 132138.74 | 17228.09 | 0 | 0 | 0 | 149366.83 | 132138.74 | 17228.09 |  | 149366.83 | 132138.74 | 17228.09 | 0 | 0 | 0 | 0
54.9414 | Cawelo Water Dist. - Cawelo Diversion Structure Rehab | 99.65% | 100% | 357415.4563 | 337485.68 | 19929.7763 |  | 337485.68 | 337485.68 | 0 | 19929.7763 | 0 | 19929.7763 | 357415.4563 | 337485.68 | 19929.7763 |  | 337485.68 | 337485.68 | 0 | 19929.7763 | 0 | 19929.7763 | 0
54.9416 | California Water Service Co. - BK 147 Station Improvements | 0.6409% | 0.6409% | 7257.82 | 7257.82 | 0 |  | 7257.82 | 7257.82 | 0 | 0 | 0 | 0 | 7257.82 | 7257.82 | 0 |  | 7257.82 | 7257.82 | 0 | 0 | 0 | 0 | 0
54.9417 | County of Santa Barbara-Public Works - Laguna WWTP WAS Pipe Modifications | 5.361% | 5.361% | 2299.41 | 2299.41 | 0 |  | 2299.41 | 2299.41 | 0 | 0 | 0 | 0 | 2299.41 | 2299.41 | 0 |  | 2299.41 | 2299.41 | 0 | 0 | 0 | 0 | 0
54.9418 | GenerateUpcycle - Organics Waste Processing Facility | 100% | 100% | 15739 | 15739 | 0 |  | 15739 | 15739 | 0 | 0 | 0 | 0 | 15739 | 15739 | 0 |  | 15739 | 15739 | 0 | 0 | 0 | 0 | 0
54.9421 | Nipomo Community Service Dist. - Tefft Emergency Pipe Repair | 100% | 100% | 3703.18 | 3703.18 | 0 |  | 3703.18 | 3703.18 | 0 | 0 | 0 | 0 | 3703.18 | 3703.18 | 0 |  | 3703.18 | 3703.18 | 0 | 0 | 0 | 0 | 0
[23 empty] | 0 | 0
Bakersfield Open Jobs Total |  |  |  | 50974822.2426 | 46923257.49 | 4051564.7526 |  | 51246144.6487 | 46923257.49 | 4322887.1587 | -271322.4061 | 0 | -271322.4061 | 36268924.2945 | 33129625.77 | 3139298.5245 |  | 37092241.0656 | 33129625.77 | 3962615.2956 | -823316.7711 | 0 | -823316.7711 | 551994.3651
Bakersfield Closed Jobs
54.9099 | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 100% | 100% | 55712110 | 45328892.68 | 10383217.32 |  | 55712110 | 45328892.68 | 10383217.32 | 0 | 0 | 0 | 276297.1285 | 265831.39 | 10465.7385 |  | 276297.1285 | 265831.39 | 10465.7385 | 0 | 0 | 0 | 0
54.9172 | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 100% | 100% | 24160002.44 | 21018432.22 | 3141570.22 |  | 24160002.44 | 21018432.22 | 3141570.22 | 0 | 0 | 0 | 37421.7408 | -27797.03 | 65218.7708 |  | 5871.37 | -27797.03 | 33668.4 | 31550.3708 | 0 | 31550.3708 | -31550.3708
54.9216 | CA Dept. of Corr. - Water Treatment Improvements | 100% | 100% | 2472164.05 | 2286264.43 | 185899.62 |  | 2472164.05 | 2286264.43 | 185899.62 | 0 | 0 | 0 | 277016.2465 | 231966.38 | 45049.8665 |  | 277016.2465 | 231966.38 | 45049.8665 | 0 | 0 | 0 | 0
54.9246 | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 100% | 100% | 1777852 | 1708475.32 | 69376.68 |  | 1777852 | 1708475.32 | 69376.68 | 0 | 0 | 0 | 358127.9957 | 357947.77 | 180.2257 |  | 358127.9957 | 357947.77 | 180.2257 | 0 | 0 | 0 | 0
54.9265 | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 100% | 100% | 223896.47 | 220754.51 | 3141.96 |  | 223896.47 | 220754.51 | 3141.96 | 0 | 0 | 0 | 20651.96 | 17510 | 3141.96 |  | 20651.96 | 17510 | 3141.96 | 0 | 0 | 0 | 0
54.9279 | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 100% | 100% | 3216240.01 | 3153237.4 | 63002.61 |  | 3216240.01 | 3153237.4 | 63002.61 | 0 | 0 | 0 | 477072.51 | 399069.9 | 78002.61 |  | 477072.51 | 399069.9 | 78002.61 | 0 | 0 | 0 | 0
54.9289 | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 100% | 100% | 44560 | 25097.25 | 19462.75 |  | 44560 | 25097.25 | 19462.75 | 0 | 0 | 0 | 30384 | 11591.06 | 18792.94 |  | 30384 | 11591.06 | 18792.94 | 0 | 0 | 0 | 0
54.9292 | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 100% | 100% | 4300 | 1313.45 | 2986.55 |  | 4300 | 1313.45 | 2986.55 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
54.9309 | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 100% | 100% | 3968668.9 | 3790858.34 | 177810.56 |  | 3968668.9 | 3790858.34 | 177810.56 | 0 | 0 | 0 | 1964416.3142 | 1849459.17 | 114957.1442 |  | 1964416.3142 | 1849459.17 | 114957.1442 | 0 | 0 | 0 | 0
54.9323 | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 100% | 100% | 110661.47 | 94483.21 | 16178.26 |  | 110661.47 | 94483.21 | 16178.26 | 0 | 0 | 0 | 25596.84 | 9418.58 | 16178.26 |  | 25596.84 | 9418.58 | 16178.26 | 0 | 0 | 0 | 0
54.9329 | Kern Water Bank Authority - Valve Replacement Parts | 100% | 100% | 18201.12 | 16466.72 | 1734.4 |  | 18201.12 | 16466.72 | 1734.4 | 0 | 0 | 0 | 18201.12 | 16466.72 | 1734.4 |  | 18201.12 | 16466.72 | 1734.4 | 0 | 0 | 0 | 0
54.9333 | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 100% | 100% | 427464.77 | 371915.26 | 55549.51 |  | 427464.77 | 371915.26 | 55549.51 | 0 | 0 | 0 | 260484.33 | 219823.5 | 40660.83 |  | 260484.33 | 219823.5 | 40660.83 | 0 | 0 | 0 | 0
54.9338 | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 100% | 100% | 175884.64 | 119186.11 | 56698.53 |  | 175884.64 | 119186.11 | 56698.53 | 0 | 0 | 0 | 15890.7123 | 13371.98 | 2518.7323 |  | 15890.7123 | 13371.98 | 2518.7323 | 0 | 0 | 0 | 0
54.9341 | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 100% | 100% | 1251279 | 1063532.4 | 187746.6 |  | 1251279 | 1063532.4 | 187746.6 | 0 | 0 | 0 | 1053706.26 | 865959.66 | 187746.6 |  | 1044408.8741 | 865959.66 | 178449.2141 | 9297.3859 | 0 | 9297.3859 | -9297.3859
54.9342 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 100% | 100% | 199161.5 | 124146.3 | 75015.2 |  | 199161.5 | 124146.3 | 75015.2 | 0 | 0 | 0 | 38308.5773 | 4687.49 | 33621.0873 |  | 38308.5773 | 4687.49 | 33621.0873 | 0 | 0 | 0 | 0
54.9347 | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 100% | 100% | 7100 | 3227.7 | 3872.3 |  | 7100 | 3227.7 | 3872.3 | 0 | 0 | 0 | 7100 | 3227.7 | 3872.3 |  | 7100 | 3227.7 | 3872.3 | 0 | 0 | 0 | 0
54.9349 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 100% | 100% | 290129 | 197889.31 | 92239.69 |  | 290129 | 197889.31 | 92239.69 | 0 | 0 | 0 | 179170.7663 | 91450.76 | 87720.0063 |  | 179170.7663 | 91450.76 | 87720.0063 | 0 | 0 | 0 | 0
54.935 | Kern Water Bank Authority - Construct New Well 18P01 | 100% | 100% | 129965.06 | 120318.68 | 9646.38 |  | 129965.06 | 120318.68 | 9646.38 | 0 | 0 | 0 | 119854.46 | 110208.08 | 9646.38 |  | 119854.46 | 110208.08 | 9646.38 | 0 | 0 | 0 | 0
54.9351 | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 100% | 100% | 153298.79 | 136808.3 | 16490.49 |  | 153298.79 | 136808.3 | 16490.49 | 0 | 0 | 0 | 5395.2229 | 0 | 5395.2229 |  | 16490.49 | 0 | 16490.49 | -11095.2671 | 0 | -11095.2671 | 11095.2671
54.9353 | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 100% | 100% | 2008.42 | 1117.5 | 890.92 |  | 2008.42 | 1117.5 | 890.92 | 0 | 0 | 0 | 890.92 | 0 | 890.92 |  | 890.92 | 0 | 890.92 | 0 | 0 | 0 | 0
54.9354 | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 100% | 100% | 9571.2 | 8230.83 | 1340.37 |  | 9571.2 | 8230.83 | 1340.37 | 0 | 0 | 0 | -4703.34 | -4120.28 | -583.06 |  | -4703.34 | -4120.28 | -583.06 | 0 | 0 | 0 | 0
54.9355 | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 100% | 100% | 2806.42 | 1815.23 | 991.19 |  | 2806.42 | 1815.23 | 991.19 | 0 | 0 | 0 | 991.19 | 0 | 991.19 |  | 991.19 | 0 | 991.19 | 0 | 0 | 0 | 0
54.9357 | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 100% | 100% | 1760.42 | 889.66 | 870.76 |  | 1760.42 | 889.66 | 870.76 | 0 | 0 | 0 | 870.76 | 0 | 870.76 |  | 870.76 | 0 | 870.76 | 0 | 0 | 0 | 0
54.9358 | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 100% | 100% | 1147640 | 1125399.83 | 22240.17 |  | 1147640 | 1125399.83 | 22240.17 | 0 | 0 | 0 | 811430.2993 | 805107.68 | 6322.6193 |  | 811430.2993 | 805107.68 | 6322.6193 | 0 | 0 | 0 | 0
54.936 | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 100% | 100% | 1855.92 | 1144.88 | 711.04 |  | 1855.92 | 1144.88 | 711.04 | 0 | 0 | 0 | 711.04 | 0 | 711.04 |  | 711.04 | 0 | 711.04 | 0 | 0 | 0 | 0
54.9361 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 100% | 100% | 108668.35 | 107074.87 | 1593.48 |  | 108668.35 | 107074.87 | 1593.48 | 0 | 0 | 0 | 108668.35 | 107074.87 | 1593.48 |  | 108668.35 | 107074.87 | 1593.48 | 0 | 0 | 0 | 0
54.9362 | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 100% | 100% | 425035.04 | 375601.24 | 49433.8 |  | 425035.04 | 375601.24 | 49433.8 | 0 | 0 | 0 | 244525.1178 | 213142.31 | 31382.8078 |  | 262576.11 | 213142.31 | 49433.8 | -18050.9922 | 0 | -18050.9922 | 18050.9922
54.9363 | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 100% | 100% | 1855.92 | 777.55 | 1078.37 |  | 1855.92 | 777.55 | 1078.37 | 0 | 0 | 0 | 1078.37 | 0 | 1078.37 |  | 1078.37 | 0 | 1078.37 | 0 | 0 | 0 | 0
54.9365 | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 100% | 100% | 2216.42 | 1263.33 | 953.09 |  | 2216.42 | 1263.33 | 953.09 | 0 | 0 | 0 | 953.09 | 0 | 953.09 |  | 953.09 | 0 | 953.09 | 0 | 0 | 0 | 0
54.9367 | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 100% | 100% | 2540.42 | 1602.33 | 938.09 |  | 2540.42 | 1602.33 | 938.09 | 0 | 0 | 0 | 938.09 | 0 | 938.09 |  | 938.09 | 0 | 938.09 | 0 | 0 | 0 | 0
54.9368 | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 100% | 100% | 15697.91 | 13653.62 | 2044.29 |  | 15697.91 | 13653.62 | 2044.29 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
54.937 | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 100% | 100% | 1760.42 | 889.64 | 870.78 |  | 1760.42 | 889.64 | 870.78 | 0 | 0 | 0 | 870.78 | 0 | 870.78 |  | 870.78 | 0 | 870.78 | 0 | 0 | 0 | 0
54.9371 | Bakersfield Overhead 2025 | 100% | 100% | 0 | 1267652.77 | -1267652.77 |  | 0 | 1267652.77 | -1267652.77 | 0 | 0 | 0 | 0 | 1267652.77 | -1267652.77 |  | 0 | 1267652.77 | -1267652.77 | 0 | 0 | 0 | 0
54.9372 | Bakersfield Estimating 2025 | 100% | 100% | 0 | 588792.6 | -588792.6 |  | 0 | 588792.6 | -588792.6 | 0 | 0 | 0 | 0 | 588792.6 | -588792.6 |  | 0 | 588792.6 | -588792.6 | 0 | 0 | 0 | 0
54.9374 | City of Santa Maria - WWTP Trickling Filter Repairs | 100% | 100% | 32962 | 19986.45 | 12975.55 |  | 32962 | 19986.45 | 12975.55 | 0 | 0 | 0 | 32962 | 19986.45 | 12975.55 |  | 32962 | 19986.45 | 12975.55 | 0 | 0 | 0 | 0
54.9375 | City of Santa Maria - WWTP Clarifier Repairs | 100% | 100% | 8232.73 | 4545.48 | 3687.25 |  | 8232.73 | 4545.48 | 3687.25 | 0 | 0 | 0 | 8232.73 | 4545.48 | 3687.25 |  | 8232.73 | 4545.48 | 3687.25 | 0 | 0 | 0 | 0
54.9379 | Semitropic Water Storage Dist. - Delta System Pipe Repair | 100% | 100% | 41679.77 | 36111.95 | 5567.82 |  | 41679.77 | 36111.95 | 5567.82 | 0 | 0 | 0 | 41679.77 | 36111.95 | 5567.82 |  | 41679.77 | 36111.95 | 5567.82 | 0 | 0 | 0 | 0
54.938 | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 100% | 100% | 22446.19 | 18064.72 | 4381.47 |  | 22446.19 | 18064.72 | 4381.47 | 0 | 0 | 0 | 22446.19 | 18064.72 | 4381.47 |  | 22446.19 | 18064.72 | 4381.47 | 0 | 0 | 0 | 0
54.9381 | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 100% | 100% | 58900 | 28875.38 | 30024.62 |  | 58900 | 28875.38 | 30024.62 | 0 | 0 | 0 | 58900 | 28875.38 | 30024.62 |  | 58900 | 28875.38 | 30024.62 | 0 | 0 | 0 | 0
54.9382 | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 100% | 100% | 143799 | 108690.45 | 35108.55 |  | 143799 | 108690.45 | 35108.55 | 0 | 0 | 0 | 143799 | 108690.45 | 35108.55 |  | 143799 | 108690.45 | 35108.55 | 0 | 0 | 0 | 0
54.9383 | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 100% | 100% | 17542.44 | 15759.76 | 1782.68 |  | 17542.44 | 15759.76 | 1782.68 | 0 | 0 | 0 | 17542.44 | 15759.76 | 1782.68 |  | 17542.44 | 15759.76 | 1782.68 | 0 | 0 | 0 | 0
54.9384 | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 100% | 100% | 79531.98 | 70340.57 | 9191.41 |  | 79531.98 | 70340.57 | 9191.41 | 0 | 0 | 0 | 79531.98 | 70340.57 | 9191.41 |  | 79531.98 | 70340.57 | 9191.41 | 0 | 0 | 0 | 0
54.9385 | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 100% | 100% | 102913.84 | 98598.77 | 4315.07 |  | 102913.84 | 98598.77 | 4315.07 | 0 | 0 | 0 | 102913.84 | 98598.77 | 4315.07 |  | 102913.84 | 98598.77 | 4315.07 | 0 | 0 | 0 | 0
54.9386 | Kern Valley State Prison - Arsenic Pipe Leak Repair | 100% | 100% | 96086 | 75784.74 | 20301.26 |  | 96086 | 75784.74 | 20301.26 | 0 | 0 | 0 | 96086 | 75784.74 | 20301.26 |  | 96086 | 75784.74 | 20301.26 | 0 | 0 | 0 | 0
54.9387 | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 100% | 100% | 22619.54 | 19011.65 | 3607.89 |  | 22619.54 | 19011.65 | 3607.89 | 0 | 0 | 0 | 22619.54 | 19011.65 | 3607.89 |  | 22619.54 | 19011.65 | 3607.89 | 0 | 0 | 0 | 0
54.9388 | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 100% | 100% | 7454.07 | 6535.41 | 918.66 |  | 7454.07 | 6535.41 | 918.66 | 0 | 0 | 0 | 7454.07 | 6535.41 | 918.66 |  | 7454.07 | 6535.41 | 918.66 | 0 | 0 | 0 | 0
54.939 | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 100% | 100% | 101491.67 | 96329.49 | 5162.18 |  | 101491.67 | 96329.49 | 5162.18 | 0 | 0 | 0 | 101491.67 | 96329.49 | 5162.18 |  | 101491.67 | 96329.49 | 5162.18 | 0 | 0 | 0 | 0
54.9392 | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 100% | 100% | 217648.89 | 208346.69 | 9302.2 |  | 217648.89 | 208346.69 | 9302.2 | 0 | 0 | 0 | 217648.89 | 208346.69 | 9302.2 |  | 217648.89 | 208346.69 | 9302.2 | 0 | 0 | 0 | 0
54.9393 | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 100% | 100% | 31523.02 | 27539.82 | 3983.2 |  | 31523.02 | 27539.82 | 3983.2 | 0 | 0 | 0 | 31523.02 | 27539.82 | 3983.2 |  | 31523.02 | 27539.82 | 3983.2 | 0 | 0 | 0 | 0
54.9394 | City of Arvin - Haven Drive Lateral Repair | 100% | 100% | 15966.99 | 14039.55 | 1927.44 |  | 15966.99 | 14039.55 | 1927.44 | 0 | 0 | 0 | 15966.99 | 14039.55 | 1927.44 |  | 15966.99 | 14039.55 | 1927.44 | 0 | 0 | 0 | 0
54.9398 | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 100% | 100% | 14300 | 8192.79 | 6107.21 |  | 14300 | 8192.79 | 6107.21 | 0 | 0 | 0 | 14300 | 8192.79 | 6107.21 |  | 14300 | 8192.79 | 6107.21 | 0 | 0 | 0 | 0
54.9399 | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 100% | 100% | 24775 | 11291.59 | 13483.41 |  | 24775 | 11291.59 | 13483.41 | 0 | 0 | 0 | 24775 | 11291.59 | 13483.41 |  | 24775 | 11291.59 | 13483.41 | 0 | 0 | 0 | 0
54.94 | Arvin Edison Water Storage Dist. - FFPP Core Drilling | 100% | 100% | 800.69 | 771.32 | 29.37 |  | 800.69 | 771.32 | 29.37 | 0 | 0 | 0 | 800.69 | 771.32 | 29.37 |  | 800.69 | 771.32 | 29.37 | 0 | 0 | 0 | 0
54.9401 | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R | 100% | 100% | 247539.61 | 236312.57 | 11227.04 |  | 247539.61 | 236312.57 | 11227.04 | 0 | 0 | 0 | 247539.61 | 236312.57 | 11227.04 |  | 247539.61 | 236312.57 | 11227.04 | 0 | 0 | 0 | 0
54.9407 | Semitropic Water Storage Dist. - North Plant Emergency Repair | 100% | 100% | 31296.85 | 25667.34 | 5629.51 |  | 31296.85 | 25667.34 | 5629.51 | 0 | 0 | 0 | 31296.85 | 25667.34 | 5629.51 |  | 31296.85 | 25667.34 | 5629.51 | 0 | 0 | 0 | 0
54.9409 | Nipomo CSD Osage Emergency Waterline Repair | 100% | 100% | 20123.71 | 17411.71 | 2712 |  | 20123.71 | 17411.71 | 2712 | 0 | 0 | 0 | 20123.71 | 17411.71 | 2712 |  | 20123.71 | 17411.71 | 2712 | 0 | 0 | 0 | 0
54.941 | SWID - Burbank St. Repair | 100% | 100% | 8241.55 | 6965.65 | 1275.9 |  | 8241.55 | 6965.65 | 1275.9 | 0 | 0 | 0 | 8241.55 | 6965.65 | 1275.9 |  | 8241.55 | 6965.65 | 1275.9 | 0 | 0 | 0 | 0
0
Bakersfield Closed Jobs Total |  |  |  | 97414231.62 | 84432379.32 | 12981852.3 |  | 97414231.62 | 84432379.32 | 12981852.3 | 0 | 0 | 0 | 7680196.3916 | 8573016.91 | -892820.5184 |  | 7668494.8941 | 8573016.91 | -904522.0159 | 11701.4975 | 0 | 11701.4975 | -11701.4975
0
Bakersfield Total |  |  |  | 148389053.8626 | 131355636.81 | 17033417.0526 |  | 148660376.2687 | 131355636.81 | 17304739.4587 | -271322.4061 | 0 | -271322.4061 | 43949120.6861 | 41702642.68 | 2246478.0061 |  | 44760735.9598 | 41702642.68 | 3058093.2798 | -811615.2737 | 0 | -811615.2737 | 540292.8676
0
Northern Open Jobs Total |  |  |  | 439456384.2233 | 396319859.23 | 43136524.9933 |  | 438929230.0668 | 396319859.23 | 42609370.8368 | 527154.1564 | 0 | 527154.1564 | 192894465.9927 | 168802306.78 | 24092159.2127 |  | 195257267.3522 | 168802306.78 | 26454960.5722 | -2362801.3596 | 0 | -2362801.3596 | 2889955.516
Northern Closed Jobs Total |  |  |  | 141195136.3 | 127887502.05 | 13307634.25 |  | 141195136.3 | 127887502.05 | 13307634.25 | 0 | 0 | 0 | 18593917.1143 | 21567638.45 | -2973721.3357 |  | 18585080.0114 | 21567638.45 | -2982558.4386 | 8837.1029 | 0 | 8837.1029 | -8837.1029
Northern Total |  |  |  | 580651520.5233 | 524207361.28 | 56444159.2433 |  | 580124366.3668 | 524207361.28 | 55917005.0868 | 527154.1564 | 0 | 527154.1564 | 211488383.1069 | 190369945.23 | 21118437.8769 |  | 213842347.3636 | 190369945.23 | 23472402.1336 | -2353964.2567 | 0 | -2353964.2567 | 2881118.4131
Murrieta Open Jobs
55.109 | LA Dept of Water and Power - Silverlake | 98.31% | 100% | 5308704.0692 | 3834064.05 | 1474640.0192 |  | 5235272.36 | 3834064.05 | 1401208.31 | 73431.7092 | 0 | 73431.7092 | 227019.4507 | 216267.6 | 10751.8507 |  | 261110.82 | 216267.6 | 44843.22 | -34091.3693 | 0 | -34091.3693 | 107523.0786
55.1191 | Inland Empire Utilities - IEUA RP-5 Liquids Exp. & Solids Treat. Facility | 88.58% | 88.58% | 302890122.84 | 299179624.84 | 3710498 |  | 302466560.369 | 299179624.84 | 3286935.529 | 423562.471 | 0 | 423562.471 | 12322287.82 | 16511789.82 | -4189502 |  | 13096053.8474 | 16511789.82 | -3415735.9726 | -773766.0274 | 0 | -773766.0274 | 1197328.4984
55.1192 | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 99.88% | 99.88% | 6643992.69 | 6393992.69 | 250000 |  | 6643687.665 | 6393992.69 | 249694.975 | 305.025 | 0 | 305.025 | 331298.96 | 431298.96 | -100000 |  | 346030.0954 | 431298.96 | -85268.8646 | -14731.1354 | 0 | -14731.1354 | 15036.1604
55.12 | East County Advanced Water Purification Project - Package 1 | 100% | 100% | 197751131.77 | 189971137.49 | 7779994.28 |  | 197175877 | 189971137.49 | 7204739.51 | 575254.77 | 0 | 575254.77 | 55551078.55 | 53766199.4 | 1784879.15 |  | 56796106 | 53766199.4 | 3029906.6 | -1245027.45 | 0 | -1245027.45 | 1820282.22
55.1202 | LA County Sanitation District - Oxygen Generation Project | 63.01% | 63.01% | 10330718.4749 | 9590124.35 | 740594.1249 |  | 10330718.4749 | 9590124.35 | 740594.1249 | 0 | 0 | 0 | 1453695.6386 | 1360552.22 | 93143.4186 |  | 1453695.6386 | 1360552.22 | 93143.4186 | 0 | 0 | 0 | 0
55.1204 | East County Advanced Water Purification Project - Package 3 | 99.98% | 100% | 57575368.22 | 55213329.21 | 2362039.01 |  | 57142227 | 55213329.21 | 1928897.79 | 433141.22 | 0 | 433141.22 | 17497029.81 | 17052791.99 | 444237.82 |  | 17354647 | 17052791.99 | 301855.01 | 142382.81 | 0 | 142382.81 | 290758.41
55.1227 | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 99.46% | 99.46% | 41279468.4824 | 36953022.96 | 4326445.5224 |  | 41279468.4824 | 36953022.96 | 4326445.5224 | 0 | 0 | 0 | 8547343.0405 | 7620251.69 | 927091.3505 |  | 8537226.8737 | 7620251.69 | 916975.1837 | 10116.1668 | 0 | 10116.1668 | -10116.1668
55.1233 | Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 1.282% | 100% | 134506.16 | 126077.16 | 8429 |  | 126077.16 | 126077.16 | 0 | 8429 | 0 | 8429 | 49747.52 | 49747.36 | 0.16 |  | 41318.52 | 49747.36 | -8428.84 | 8429 | 0 | 8429 | 0
55.1248 | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 73.4% | 73.4% | 4227318.998 | 3621770.22 | 605548.778 |  | 4227318.998 | 3621770.22 | 605548.778 | 0 | 0 | 0 | 3912565.908 | 3307017.13 | 605548.778 |  | 3912565.908 | 3307017.13 | 605548.778 | 0 | 0 | 0 | 0
55.1249 | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 10.77% | 10.77% | 15046313.77 | 15046313.77 | 0 |  | 15888669.2477 | 15046313.77 | 842355.4777 | -842355.4777 | 0 | -842355.4777 | 14105058.15 | 14105058.15 | 0 |  | 14947413.6277 | 14105058.15 | 842355.4777 | -842355.4777 | 0 | -842355.4777 | 0
55.1254 | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 33.18% | 100% | 156561.66 | 156561.66 | 0 |  | 158952.89 | 156561.66 | 2391.23 | -2391.23 | 0 | -2391.23 | 156561.66 | 156561.66 | 0 |  | 158952.89 | 156561.66 | 2391.23 | -2391.23 | 0 | -2391.23 | 0
55.1255 | City of Riverside - RWQCP Emergency Repair | 100% | 100% | 14160.81 | 14160.81 | 0 |  | 14160.81 | 14160.81 | 0 | 0 | 0 | 0 | 14160.81 | 14160.81 | 0 |  | 14160.81 | 14160.81 | 0 | 0 | 0 | 0 | 0
55.1256 | Anaergia Technologies LLC - City of Riverside - OPS | 3.501% | 3.501% | 94989.88 | 94989.88 | 0 |  | 94989.88 | 94989.88 | 0 | 0 | 0 | 0 | 94989.88 | 94989.88 | 0 |  | 94989.88 | 94989.88 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0
Murrieta Open Jobs Total |  |  |  | 641453357.8246 | 620195169.09 | 21258188.7346 |  | 640783980.3371 | 620195169.09 | 20588811.2471 | 669377.4876 | 0 | 669377.4876 | 114262837.1979 | 114686686.67 | -423849.4721 |  | 117014271.9108 | 114686686.67 | 2327585.2408 | -2751434.7129 | 0 | -2751434.7129 | 3420812.2005
Murrieta Closed Jobs
55.123 | Anaergia Technologies - VVWRA - DAF 3 Replacement | 100% | 100% | 2273682.69 | 1665145.3 | 608537.39 |  | 2273682.69 | 1665145.3 | 608537.39 | 0 | 0 | 0 | 128285.3565 | 0 | 128285.3565 |  | 128285.3565 | 0 | 128285.3565 | 0 | 0 | 0 | 0
55.1231 | City of Corona - WRF 1 Aeration System Improvements | 100% | 100% | 4046200 | 3321856.36 | 724343.64 |  | 4046200 | 3321856.36 | 724343.64 | 0 | 0 | 0 | 112084.8546 | 15648.61 | 96436.2446 |  | 112084.8546 | 15648.61 | 96436.2446 | 0 | 0 | 0 | 0
55.1238 | Anaergia Technologies LLC - East County Package 5 | 100% | 100% | 34207.53 | 32500.86 | 1706.67 |  | 34207.53 | 32500.86 | 1706.67 | 0 | 0 | 0 | 0 | 6400.81 | -6400.81 |  | 0 | 6400.81 | -6400.81 | 0 | 0 | 0 | 0
55.125 | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 100% | 100% | 184557.17 | 48293.94 | 136263.23 |  | 184557.17 | 48293.94 | 136263.23 | 0 | 0 | 0 | 36965.3702 | 1754.3 | 35211.0702 |  | 36965.3702 | 1754.3 | 35211.0702 | 0 | 0 | 0 | 0
55.1251 | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 100% | 100% | 322982.96 | 284221.86 | 38761.1 |  | 322982.96 | 284221.86 | 38761.1 | 0 | 0 | 0 | 322982.96 | 284221.86 | 38761.1 |  | 322982.96 | 284221.86 | 38761.1 | 0 | 0 | 0 | 0
55.1252 | Murrieta Overhead 2025 | 100% | 100% | 0 | 1958826.45 | -1958826.45 |  | 0 | 1958826.45 | -1958826.45 | 0 | 0 | 0 | 0 | 1958826.45 | -1958826.45 |  | 0 | 1958826.45 | -1958826.45 | 0 | 0 | 0 | 0
55.1253 | Murrieta Estimating 2025 | 100% | 100% | 0 | 475814.03 | -475814.03 |  | 0 | 475814.03 | -475814.03 | 0 | 0 | 0 | 0 | 475814.03 | -475814.03 |  | 0 | 475814.03 | -475814.03 | 0 | 0 | 0 | 0
0
Murrieta Closed Jobs Total |  |  |  | 6861630.35 | 7786658.8 | -925028.45 |  | 6861630.35 | 7786658.8 | -925028.45 | 0 | 0 | 0 | 600318.5413 | 2742666.06 | -2142347.5187 |  | 600318.5413 | 2742666.06 | -2142347.5187 | 0 | 0 | 0 | 0
0
Murrieta Total |  |  |  | 648314988.1746 | 627981827.89 | 20333160.2846 |  | 647645610.6871 | 627981827.89 | 19663782.7971 | 669377.4876 | 0 | 669377.4876 | 114863155.7392 | 117429352.73 | -2566196.9908 |  | 117614590.4521 | 117429352.73 | 185237.7221 | -2751434.7129 | 0 | -2751434.7129 | 3420812.2005
San Diego Open Jobs
57.0003 | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 17.67% | 17.67% | 6440831.3025 | 6316909.13 | 123922.1725 |  | 6742134.3025 | 6316909.13 | 425225.1725 | -301303 | 0 | -301303 | 5442603.9807 | 5415067.22 | 27536.7607 |  | 5743906.9807 | 5415067.22 | 328839.7607 | -301303 | 0 | -301303 | 0
57.0004 | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 1.98% | 1.98% | 750298.86 | 750298.86 | 0 |  | 750298.86 | 750298.86 | 0 | 0 | 0 | 0 | 63391.12 | 63391.12 | 0 |  | 63391.12 | 63391.12 | 0 | 0 | 0 | 0 | 0
57.0007 | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | 100% | 100% | 162630 | 196248.4 | -33618.4 |  | 196248.4 | 196248.4 | 0 | -33618.4 | 0 | -33618.4 | 162630 | 196248.4 | -33618.4 |  | 196248.4 | 196248.4 | 0 | -33618.4 | 0 | -33618.4 | 0
57.0008 | Imperial Irrigation Dist. - El Centro Generating Station WWTP | 9.562% | 9.562% | 262382.86 | 262382.86 | 0 |  | 262382.86 | 262382.86 | 0 | 0 | 0 | 0 | 262382.86 | 262382.86 | 0 |  | 262382.86 | 262382.86 | 0 | 0 | 0 | 0 | 0
0
San Diego Open Jobs Total |  |  |  | 7616143.0225 | 7525839.25 | 90303.7725 |  | 7951064.4225 | 7525839.25 | 425225.1725 | -334921.4 | 0 | -334921.4 | 5931007.9607 | 5937089.6 | -6081.6393 |  | 6265929.3607 | 5937089.6 | 328839.7607 | -334921.4 | 0 | -334921.4 | 0
San Diego Closed Jobs
57.0005 | San Diego Overhead 2025 | 100% | 100% | 0 | 92874.26 | -92874.26 |  | 0 | 92874.26 | -92874.26 | 0 | 0 | 0 | 0 | 92874.26 | -92874.26 |  | 0 | 92874.26 | -92874.26 | 0 | 0 | 0 | 0
57.0006 | San Diego Estimating 2025 | 100% | 100% | 0 | 13743.76 | -13743.76 |  | 0 | 13743.76 | -13743.76 | 0 | 0 | 0 | 0 | 13743.76 | -13743.76 |  | 0 | 13743.76 | -13743.76 | 0 | 0 | 0 | 0
0
San Diego Closed Jobs Total |  |  |  | 0 | 106618.02 | -106618.02 |  | 0 | 106618.02 | -106618.02 | 0 | 0 | 0 | 0 | 106618.02 | -106618.02 |  | 0 | 106618.02 | -106618.02 | 0 | 0 | 0 | 0
San Diego Total |  |  |  | 7616143.0225 | 7632457.27 | -16314.2475 |  | 7951064.4225 | 7632457.27 | 318607.1525 | -334921.4 | 0 | -334921.4 | 5931007.9607 | 6043707.62 | -112699.6593 |  | 6265929.3607 | 6043707.62 | 222221.7407 | -334921.4 | 0 | -334921.4 | 0
Los Angeles Open Jobs
58.0003 | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 52.01% | 52.01% | 11715063.7212 | 11034781.79 | 680281.9312 |  | 11715063.7212 | 11034781.79 | 680281.9312 | 0 | 0 | 0 | 9333607.2412 | 8653325.31 | 680281.9312 |  | 9182098.4276 | 8653325.31 | 528773.1176 | 151508.8135 | 0 | 151508.8135 | -151508.8135
0
Los Angeles Open Jobs Total |  |  |  | 11715063.7212 | 11034781.79 | 680281.9312 |  | 11715063.7212 | 11034781.79 | 680281.9312 | 0 | 0 | 0 | 9333607.2412 | 8653325.31 | 680281.9312 |  | 9182098.4276 | 8653325.31 | 528773.1176 | 151508.8135 | 0 | 151508.8135 | -151508.8135
Los Angeles Closed Jobs
58.0004 | Los Angeles Overhead 2025 | 100% | 100% | 0 | 147282.12 | -147282.12 |  | 0 | 147282.12 | -147282.12 | 0 | 0 | 0 | 0 | 147282.12 | -147282.12 |  | 0 | 147282.12 | -147282.12 | 0 | 0 | 0 | 0
58.0005 | Los Angeles Estimating 2025 | 100% | 100% | 0 | 135037.09 | -135037.09 |  | 0 | 135037.09 | -135037.09 | 0 | 0 | 0 | 0 | 135037.09 | -135037.09 |  | 0 | 135037.09 | -135037.09 | 0 | 0 | 0 | 0
0
Los Angeles Closed Jobs Total |  |  |  | 0 | 282319.21 | -282319.21 |  | 0 | 282319.21 | -282319.21 | 0 | 0 | 0 | 0 | 282319.21 | -282319.21 |  | 0 | 282319.21 | -282319.21 | 0 | 0 | 0 | 0
Los Angeles Total |  |  |  | 11715063.7212 | 11317101 | 397962.7212 |  | 11715063.7212 | 11317101 | 397962.7212 | 0 | 0 | 0 | 9333607.2412 | 8935644.52 | 397962.7212 |  | 9182098.4276 | 8935644.52 | 246453.9076 | 151508.8135 | 0 | 151508.8135 | -151508.8135
Southern Open Jobs Total |  |  |  | 660784564.5683 | 638755790.13 | 22028774.4383 |  | 660450108.4807 | 638755790.13 | 21694318.3507 | 334456.0876 | 0 | 334456.0876 | 129527452.3997 | 129277101.58 | 250350.8197 |  | 132462299.6991 | 129277101.58 | 3185198.1191 | -2934847.2994 | 0 | -2934847.2994 | 3269303.387
Southern Closed Jobs Total |  |  |  | 6861630.35 | 8175596.03 | -1313965.68 |  | 6861630.35 | 8175596.03 | -1313965.68 | 0 | 0 | 0 | 600318.5413 | 3131603.29 | -2531284.7487 |  | 600318.5413 | 3131603.29 | -2531284.7487 | 0 | 0 | 0 | 0
Southern Total |  |  |  | 667646194.9183 | 646931386.16 | 20714808.7583 |  | 667311738.8307 | 646931386.16 | 20380352.6707 | 334456.0876 | 0 | 334456.0876 | 130127770.941 | 132408704.87 | -2280933.929 |  | 133062618.2404 | 132408704.87 | 653913.3704 | -2934847.2994 | 0 | -2934847.2994 | 3269303.387
System Integration Open Jobs
56.1004 | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 87.6% | 87.6% | 327111.8445 | 236373.73 | 90738.1145 |  | 327111.8445 | 236373.73 | 90738.1145 | 0 | 0 | 0 | 122870.3418 | 83492.19 | 39378.1518 |  | 122870.3418 | 83492.19 | 39378.1518 | 0 | 0 | 0 | 0
56.1005 | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 75.03% | 75.03% | 101287.0518 | 51037.42 | 50249.6318 |  | 101287.0518 | 51037.42 | 50249.6318 | 0 | 0 | 0 | 85373.7218 | 35124.09 | 50249.6318 |  | 70848.3946 | 35124.09 | 35724.3046 | 14525.3272 | 0 | 14525.3272 | -14525.3272
56.101 | Placer County Water Agency -PCWA Time & Material Contract | 100% | 100% | 49250 | 36461.94 | 12788.06 |  | 49250 | 36461.94 | 12788.06 | 0 | 0 | 0 | 49250 | 36461.94 | 12788.06 |  | 49250 | 36461.94 | 12788.06 | 0 | 0 | 0 | 0
56.1015 | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 69.95% | 100% | 160881.2819 | 142358.95 | 18522.3319 |  | 160000 | 142358.95 | 17641.05 | 881.2819 | 0 | 881.2819 | 31372.1716 | 42245.17 | -10872.9984 |  | 30490.8897 | 42245.17 | -11754.2803 | 881.2819 | 0 | 881.2819 | 7.276e-12
56.1017 | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 83.08% | 83.08% | 83423.46 | 95450.46 | -12027 |  | 83423.46 | 95450.46 | -12027 | 0 | 0 | 0 | 21693.9972 | 52737.57 | -31043.5728 |  | 21693.9972 | 52737.57 | -31043.5728 | 0 | 0 | 0 | 0
56.1018 | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 59.11% | 59.11% | 90970.2846 | 41991.15 | 48979.1346 |  | 90970.2846 | 41991.15 | 48979.1346 | 0 | 0 | 0 | 40855.43 | 23859.25 | 16996.18 |  | 40855.43 | 23859.25 | 16996.18 | 0 | 0 | 0 | 0
56.1032 | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 42.21% | 42.21% | 35879.107 | 35024.34 | 854.767 |  | 35879.107 | 35024.34 | 854.767 | 0 | 0 | 0 | 26940.547 | 26085.78 | 854.767 |  | 25895.9571 | 26085.78 | -189.8229 | 1044.5898 | 0 | 1044.5898 | -1044.5898
56.1036 | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 51.22% | 51.22% | 141353.8072 | 107051.95 | 34301.8572 |  | 141353.8072 | 107051.95 | 34301.8572 | 0 | 0 | 0 | 88716.5572 | 54414.7 | 34301.8572 |  | 70900.9079 | 54414.7 | 16486.2079 | 17815.6493 | 0 | 17815.6493 | -17815.6493
56.1037 | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 100% | 100% | 36491 | 21674.2 | 14816.8 |  | 36491 | 21674.2 | 14816.8 | 0 | 0 | 0 | 34128.5 | 19649.82 | 14478.68 |  | 34128.5 | 19649.82 | 14478.68 | 0 | 0 | 0 | 0
56.1038 | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 85.24% | 85.24% | 77673.89 | 100049.89 | -22376 |  | 77673.89 | 100049.89 | -22376 | 0 | 0 | 0 | 16550.2658 | 45229.72 | -28679.4542 |  | 16550.2658 | 45229.72 | -28679.4542 | 0 | 0 | 0 | 0
56.1039 | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 97.52% | 97.52% | 365706.6282 | 324049.23 | 41657.3982 |  | 365706.6282 | 324049.23 | 41657.3982 | 0 | 0 | 0 | 321087.4982 | 279430.1 | 41657.3982 |  | 316565.607 | 279430.1 | 37135.507 | 4521.8913 | 0 | 4521.8913 | -4521.8913
56.1042 | Trabuco Canyon Water Dist. - SCADA Integration Services | 79.11% | 79.11% | 219576.1189 | 172683.27 | 46892.8489 |  | 219576.1189 | 172683.27 | 46892.8489 | 0 | 0 | 0 | 96610.7607 | 84540.13 | 12070.6307 |  | 96610.7607 | 84540.13 | 12070.6307 | 0 | 0 | 0 | 0
56.1043 | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 69.04% | 69.04% | 232406.3037 | 214994.3 | 17412.0037 |  | 232406.3037 | 214994.3 | 17412.0037 | 0 | 0 | 0 | 194947.4237 | 177535.42 | 17412.0037 |  | 190497.7689 | 177535.42 | 12962.3489 | 4449.6548 | 0 | 4449.6548 | -4449.6548
56.1046 | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 97.26% | 97.26% | 74929.8 | 77765.8 | -2836 |  | 74929.8 | 77765.8 | -2836 | 0 | 0 | 0 | 65463.4 | 68299.4 | -2836 |  | 63859.7527 | 68299.4 | -4439.6473 | 1603.6473 | 0 | 1603.6473 | -1603.6473
56.1047 | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 78.55% | 78.55% | 1881098.4607 | 1602869.63 | 278228.8307 |  | 1881098.4607 | 1602869.63 | 278228.8307 | 0 | 0 | 0 | 1820562.3007 | 1542333.47 | 278228.8307 |  | 1820562.3007 | 1542333.47 | 278228.8307 | 0 | 0 | 0 | 0
56.1048 | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 98.01% | 98.01% | 196024.243 | 157916.15 | 38108.093 |  | 196024.243 | 157916.15 | 38108.093 | 0 | 0 | 0 | 175234.893 | 137126.8 | 38108.093 |  | 140591.15 | 137126.8 | 3464.35 | 34643.7429 | 0 | 34643.7429 | -34643.7429
56.1049 | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 86.16% | 86.16% | 265990.1203 | 214423.06 | 51567.0603 |  | 265990.1203 | 214423.06 | 51567.0603 | 0 | 0 | 0 | 64100.2693 | 86942.28 | -22842.0107 |  | 64100.2693 | 86942.28 | -22842.0107 | 0 | 0 | 0 | 0
56.105 | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 27.51% | 27.51% | 1043310.4979 | 925847.53 | 117462.9679 |  | 1043310.4979 | 925847.53 | 117462.9679 | 0 | 0 | 0 | 988845.8779 | 871382.91 | 117462.9679 |  | 988845.8779 | 871382.91 | 117462.9679 | 0 | 0 | 0 | 0
56.1055 | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 84.8% | 84.8% | 102517.3075 | 78736.44 | 23780.8675 |  | 102517.3075 | 78736.44 | 23780.8675 | 0 | 0 | 0 | 88246.2975 | 64465.43 | 23780.8675 |  | 85731.308 | 64465.43 | 21265.878 | 2514.9896 | 0 | 2514.9896 | -2514.9896
56.1059 | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 71.64% | 71.64% | 286120.7529 | 235841.92 | 50278.8329 |  | 286120.7529 | 235841.92 | 50278.8329 | 0 | 0 | 0 | 259417.3729 | 209138.54 | 50278.8329 |  | 259417.3729 | 209138.54 | 50278.8329 | 0 | 0 | 0 | 0
56.106 | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 45.14% | 45.14% | 182653.4878 | 145563.36 | 37090.1278 |  | 182653.4878 | 145563.36 | 37090.1278 | 0 | 0 | 0 | 146206.9278 | 109116.8 | 37090.1278 |  | 135265.3659 | 109116.8 | 26148.5659 | 10941.5619 | 0 | 10941.5619 | -10941.5619
56.1063 | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 75.61% | 75.61% | 81661.383 | 74040.41 | 7620.973 |  | 81661.383 | 74040.41 | 7620.973 | 0 | 0 | 0 | 64053.573 | 56432.6 | 7620.973 |  | 61085.5021 | 56432.6 | 4652.9021 | 2968.0708 | 0 | 2968.0708 | -2968.0708
56.1066 | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 89.57% | 89.57% | 532912.916 | 476030.06 | 56882.856 |  | 532912.916 | 476030.06 | 56882.856 | 0 | 0 | 0 | 520441.786 | 463558.93 | 56882.856 |  | 520441.786 | 463558.93 | 56882.856 | 0 | 0 | 0 | 0
56.1067 | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 25.19% | 25.19% | 120399.3749 | 104751.99 | 15647.3849 |  | 120399.3749 | 104751.99 | 15647.3849 | 0 | 0 | 0 | 116332.9949 | 100685.61 | 15647.3849 |  | 116332.9949 | 100685.61 | 15647.3849 | 0 | 0 | 0 | 0
56.1073 | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 95.45% | 95.45% | 116647.2467 | 108855.81 | 7791.4367 |  | 116647.2467 | 108855.81 | 7791.4367 | 0 | 0 | 0 | 116647.2467 | 108855.81 | 7791.4367 |  | 116647.2467 | 108855.81 | 7791.4367 | 0 | 0 | 0 | 0
56.1075 | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 3.551% | 100% | 27665.92 | 27665.92 | 0 |  | 27665.92 | 27665.92 | 0 | 0 | 0 | 0 | 27665.92 | 27665.92 | 0 |  | 27665.92 | 27665.92 | 0 | 0 | 0 | 0 | 0
56.1078 | City of Napa - On-Call Control Systems Integrator Services | 100% | 100% | 25356.25 | 25356.25 | 0 |  | 25356.25 | 25356.25 | 0 | 0 | 0 | 0 | 25356.25 | 25356.25 | 0 |  | 25356.25 | 25356.25 | 0 | 0 | 0 | 0 | 0
56.1081 | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 98.1% | 98.1% | 176270.5876 | 156744.37 | 19526.2176 |  | 176270.5876 | 156744.37 | 19526.2176 | 0 | 0 | 0 | 176270.5876 | 156744.37 | 19526.2176 |  | 176270.5876 | 156744.37 | 19526.2176 | 0 | 0 | 0 | 0
56.1083 | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 53.01% | 53.01% | 380119.0342 | 347967.35 | 32151.6842 |  | 380119.0342 | 347967.35 | 32151.6842 | 0 | 0 | 0 | 380119.0342 | 347967.35 | 32151.6842 |  | 380119.0342 | 347967.35 | 32151.6842 | 0 | 0 | 0 | 0
56.1085 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 1.628% | 1.628% | 1090.31 | 1090.31 | 0 |  | 1090.31 | 1090.31 | 0 | 0 | 0 | 0 | 1090.31 | 1090.31 | 0 |  | 1090.31 | 1090.31 | 0 | 0 | 0 | 0 | 0
56.1086 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 4.315% | 4.315% | 12732.69 | 12732.69 | 0 |  | 12732.69 | 12732.69 | 0 | 0 | 0 | 0 | 12732.69 | 12732.69 | 0 |  | 12732.69 | 12732.69 | 0 | 0 | 0 | 0 | 0
56.1087 | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 90.93% | 90.93% | 44888.9348 | 39121.54 | 5767.3948 |  | 44888.9348 | 39121.54 | 5767.3948 | 0 | 0 | 0 | 44888.9348 | 39121.54 | 5767.3948 |  | 44888.9348 | 39121.54 | 5767.3948 | 0 | 0 | 0 | 0
56.1088 | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 78.25% | 78.25% | 92320.6066 | 66827.49 | 25493.1166 |  | 92320.6066 | 66827.49 | 25493.1166 | 0 | 0 | 0 | 92320.6066 | 66827.49 | 25493.1166 |  | 92320.6066 | 66827.49 | 25493.1166 | 0 | 0 | 0 | 0
0
System Integration Open Jobs Totals |  |  |  | 7566720.7016 | 6459348.91 | 1107371.7916 |  | 7565839.4196 | 6459348.91 | 1106490.5096 | 881.2819 | 0 | 881.2819 | 6316394.488 | 5456650.38 | 859744.108 |  | 6220484.0811 | 5456650.38 | 763833.7011 | 95910.4068 | 0 | 95910.4068 | -95029.1249
System Integration Closed Jobs
56.1002 | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 100% | 100% | 185000 | 114485.82 | 70514.18 |  | 185000 | 114485.82 | 70514.18 | 0 | 0 | 0 | 20413.1505 | 644.21 | 19768.9405 |  | 20413.1505 | 644.21 | 19768.9405 | 0 | 0 | 0 | 0
56.1003 | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 100% | 100% | 332901 | 223395.74 | 109505.26 |  | 332901 | 223395.74 | 109505.26 | 0 | 0 | 0 | 113346.7237 | 68302.45 | 45044.2737 |  | 113346.7237 | 68302.45 | 45044.2737 | 0 | 0 | 0 | 0
56.1007 | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 100% | 100% | 16814 | 19362.98 | -2548.98 |  | 16814 | 19362.98 | -2548.98 | 0 | 0 | 0 | -680.041 | 5046.38 | -5726.421 |  | -680.041 | 5046.38 | -5726.421 | 0 | 0 | 0 | 0
56.1008 | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 100% | 100% | 55000 | 30551.92 | 24448.08 |  | 55000 | 30551.92 | 24448.08 | 0 | 0 | 0 | 1480.7976 | 126.74 | 1354.0576 |  | 1480.7976 | 126.74 | 1354.0576 | 0 | 0 | 0 | 0
56.1010.01 | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 100% | 100% | 9569 | 7097.1 | 2471.9 |  | 9569 | 7097.1 | 2471.9 | 0 | 0 | 0 | 6483.9829 | 4631.73 | 1852.2529 |  | 6483.9829 | 4631.73 | 1852.2529 | 0 | 0 | 0 | 0
56.1016 | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 100% | 100% | 150064.25 | 110083.62 | 39980.63 |  | 150064.25 | 110083.62 | 39980.63 | 0 | 0 | 0 | 78249.75 | 53012.48 | 25237.27 |  | 78249.75 | 53012.48 | 25237.27 | 0 | 0 | 0 | 0
56.1019 | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 100% | 100% | 193845 | 143764.58 | 50080.42 |  | 193845 | 143764.58 | 50080.42 | 0 | 0 | 0 | 173402.48 | 123322.06 | 50080.42 |  | 168807.6857 | 123322.06 | 45485.6257 | 4594.7943 | 0 | 4594.7943 | -4594.7943
56.1021 | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 100% | 100% | 244760 | 116752.52 | 128007.48 |  | 244760 | 116752.52 | 128007.48 | 0 | 0 | 0 | 92166.0507 | 3037.11 | 89128.9407 |  | 92166.0507 | 3037.11 | 89128.9407 | 0 | 0 | 0 | 0
56.1022 | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 0% | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -88093.56 | -88093.56 | 0 |  | -88093.56 | -88093.56 | 0 | 0 | 0 | 0 | 0
56.1023 | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 100% | 100% | 220390 | 150504.73 | 69885.27 |  | 220390 | 150504.73 | 69885.27 | 0 | 0 | 0 | 68197.3875 | 38407.43 | 29789.9575 |  | 68197.3875 | 38407.43 | 29789.9575 | 0 | 0 | 0 | 0
56.103 | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 100% | 100% | 689578.64 | 689578.64 | 0 |  | 689578.64 | 689578.64 | 0 | 0 | 0 | 0 | 567471.07 | 567471.07 | 0 |  | 549437.051 | 567471.07 | -18034.019 | 18034.019 | 0 | 18034.019 | -18034.019
56.1041 | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 100% | 100% | 20016.78 | 20016.78 | 0 |  | 20016.78 | 20016.78 | 0 | 0 | 0 | 0 | 3887.412 | 10889.65 | -7002.238 |  | 3887.412 | 10889.65 | -7002.238 | 0 | 0 | 0 | 0
56.1051 | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 100% | 100% | 136875 | 98718.18 | 38156.82 |  | 136875 | 98718.18 | 38156.82 | 0 | 0 | 0 | 81400.1502 | 59463.87 | 21936.2802 |  | 81400.1502 | 59463.87 | 21936.2802 | 0 | 0 | 0 | 0
56.1052 | San Jose Water - Williams Back ATS Replacement | 100% | 100% | 8887 | 6400.94 | 2486.06 |  | 8887 | 6400.94 | 2486.06 | 0 | 0 | 0 | 2603.2164 | 486.25 | 2116.9664 |  | 2603.2164 | 486.25 | 2116.9664 | 0 | 0 | 0 | 0
56.1053 | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 100% | 100% | 35000 | 19964.78 | 15035.22 |  | 35000 | 19964.78 | 15035.22 | 0 | 0 | 0 | 29289.5 | 14254.28 | 15035.22 |  | 25102.1394 | 14254.28 | 10847.8594 | 4187.3606 | 0 | 4187.3606 | -4187.3606
56.1054 | AIC - Riverside Public Works - Digester 5 Rehab | 100% | 100% | 37648.03 | 37648.03 | 0 |  | 37648.03 | 37648.03 | 0 | 0 | 0 | 0 | 26897.97 | 26897.97 | 0 |  | 26897.97 | 26897.97 | 0 | 0 | 0 | 0 | 0
56.1056 | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan | 100% | 100% | 98280.63 | 98280.63 | 0 |  | 98280.63 | 98280.63 | 0 | 0 | 0 | 0 | 66850.82 | 66850.82 | 0 |  | 46299.2443 | 66850.82 | -20551.5757 | 20551.5757 | 0 | 20551.5757 | -20551.5757
56.1057 | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 0% | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -16238.75 | -16238.75 | 0 |  | -16238.75 | -16238.75 | 0 | 0 | 0 | 0 | 0
56.1061 | San Jose Water - PLC System Assessment | 100% | 100% | 11269 | 5582.66 | 5686.34 |  | 11269 | 5582.66 | 5686.34 | 0 | 0 | 0 | 1024.0696 | 501.56 | 522.5096 |  | 1024.0696 | 501.56 | 522.5096 | 0 | 0 | 0 | 0
56.1062 | AIC - SCADA System Upgrade - City of Brentwood | 100% | 100% | 409988.07 | 409988.07 | 0 |  | 409988.07 | 409988.07 | 0 | 0 | 0 | 0 | 383762.17 | 383762.17 | 0 |  | 383762.17 | 383762.17 | 0 | 0 | 0 | 0 | 0
56.1064 | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 100% | 100% | 435153 | 202266.4 | 232886.6 |  | 435153 | 202266.4 | 232886.6 | 0 | 0 | 0 | 241255.3004 | 77865.19 | 163390.1104 |  | 241255.3004 | 77865.19 | 163390.1104 | 0 | 0 | 0 | 0
56.1065 | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 100% | 100% | 226400.8 | 192023.81 | 34376.99 |  | 226400.8 | 192023.81 | 34376.99 | 0 | 0 | 0 | 210538.17 | 176161.18 | 34376.99 |  | 210538.17 | 176161.18 | 34376.99 | 0 | 0 | 0 | 0
56.1069 | AIC - City of Brentwood - Brentwood, City of - On-Call Agreement | 100% | 100% | 2525 | 3821.46 | -1296.46 |  | 2525 | 3821.46 | -1296.46 | 0 | 0 | 0 | 2525 | 3821.46 | -1296.46 |  | 2525 | 3821.46 | -1296.46 | 0 | 0 | 0 | 0
56.1071 | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 100% | 100% | 34000 | 3596.56 | 30403.44 |  | 34000 | 3596.56 | 30403.44 | 0 | 0 | 0 | 33683.5 | 3280.06 | 30403.44 |  | 33683.5 | 3280.06 | 30403.44 | 0 | 0 | 0 | 0
56.1072 | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 100% | 100% | 65960 | 41538.84 | 24421.16 |  | 65960 | 41538.84 | 24421.16 | 0 | 0 | 0 | 64717.9 | 40296.74 | 24421.16 |  | 64717.9 | 40296.74 | 24421.16 | 0 | 0 | 0 | 0
56.1074 | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 100% | 100% | 12650 | 10641.86 | 2008.14 |  | 12650 | 10641.86 | 2008.14 | 0 | 0 | 0 | 4653.0319 | 3884.58 | 768.4519 |  | 4653.0319 | 3884.58 | 768.4519 | 0 | 0 | 0 | 0
56.1076 | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 100% | 100% | 19200 | 11577.77 | 7622.23 |  | 19200 | 11577.77 | 7622.23 | 0 | 0 | 0 | 18595.19 | 10972.96 | 7622.23 |  | 18595.19 | 10972.96 | 7622.23 | 0 | 0 | 0 | 0
56.1077 | System Integration Overhead 2025 | 100% | 100% | 0 | 4370841.4 | -4370841.4 |  | 0 | 4370841.4 | -4370841.4 | 0 | 0 | 0 | 0 | 4370841.4 | -4370841.4 |  | 0 | 4370841.4 | -4370841.4 | 0 | 0 | 0 | 0
56.1079 | AIC - San Jose Water Co - Montevina PLC Upgrade | 100% | 100% | 29235.63 | 29235.63 | 0 |  | 29235.63 | 29235.63 | 0 | 0 | 0 | 0 | 29235.63 | 29235.63 | 0 |  | 29235.63 | 29235.63 | 0 | 0 | 0 | 0 | 0
56.108 | AIC - San Jose Water Co - PLC System Assessment | 100% | 100% | 359469 | 359469 | 0 |  | 359469 | 359469 | 0 | 0 | 0 | 0 | 359469 | 359469 | 0 |  | 359469 | 359469 | 0 | 0 | 0 | 0 | 0
56.1082 | City of Clovis - Pump Station E New Pump 5 VFD Startup | 100% | 100% | 19800 | 20583.04 | -783.04 |  | 19800 | 20583.04 | -783.04 | 0 | 0 | 0 | 19800 | 20583.04 | -783.04 |  | 19800 | 20583.04 | -783.04 | 0 | 0 | 0 | 0
56.1084 | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 100% | 100% | 8000 | 4228.13 | 3771.87 |  | 8000 | 4228.13 | 3771.87 | 0 | 0 | 0 | 8000 | 4228.13 | 3771.87 |  | 8000 | 4228.13 | 3771.87 | 0 | 0 | 0 | 0
56.1102 | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 100% | 100% | 19815.94 | 19815.94 | 0 |  | 19815.94 | 19815.94 | 0 | 0 | 0 | 0 | 19815.94 | 19815.94 | 0 |  | 19815.94 | 19815.94 | 0 | 0 | 0 | 0 | 0
56.1103 | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 100% | 100% | 55855.24 | 55855.24 | 0 |  | 55855.24 | 55855.24 | 0 | 0 | 0 | 0 | 55855.24 | 55855.24 | 0 |  | 55855.24 | 55855.24 | 0 | 0 | 0 | 0 | 0
56.1104 | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 100% | 100% | 9500.31 | 9500.31 | 0 |  | 9500.31 | 9500.31 | 0 | 0 | 0 | 0 | 9500.31 | 9500.31 | 0 |  | 9500.31 | 9500.31 | 0 | 0 | 0 | 0 | 0
56.1105 | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 100% | 100% | 30502.53 | 30502.53 | 0 |  | 30502.53 | 30502.53 | 0 | 0 | 0 | 0 | 30502.53 | 30502.53 | 0 |  | 30502.53 | 30502.53 | 0 | 0 | 0 | 0 | 0
56.1106 | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 100% | 100% | 54742.18 | 54742.18 | 0 |  | 54742.18 | 54742.18 | 0 | 0 | 0 | 0 | 54742.18 | 54742.18 | 0 |  | 54742.18 | 54742.18 | 0 | 0 | 0 | 0 | 0
56.1107 | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 100% | 100% | 3429.06 | 3429.06 | 0 |  | 3429.06 | 3429.06 | 0 | 0 | 0 | 0 | 3429.06 | 3429.06 | 0 |  | 3429.06 | 3429.06 | 0 | 0 | 0 | 0 | 0
56.1108 | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 100% | 100% | 20729.84 | 20729.84 | 0 |  | 20729.84 | 20729.84 | 0 | 0 | 0 | 0 | 20729.84 | 20729.84 | 0 |  | 20729.84 | 20729.84 | 0 | 0 | 0 | 0 | 0
56.1109 | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 100% | 100% | 14772.26 | 14772.26 | 0 |  | 14772.26 | 14772.26 | 0 | 0 | 0 | 0 | 14772.26 | 14772.26 | 0 |  | 14772.26 | 14772.26 | 0 | 0 | 0 | 0 | 0
56.111 | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 100% | 100% | 4596.42 | 4596.42 | 0 |  | 4596.42 | 4596.42 | 0 | 0 | 0 | 0 | 4596.42 | 4596.42 | 0 |  | 4596.42 | 4596.42 | 0 | 0 | 0 | 0 | 0
56.1111 | AIC - California American Water - Luzern Well Treatment Design | 100% | 100% | 17210.01 | 17210.01 | 0 |  | 17210.01 | 17210.01 | 0 | 0 | 0 | 0 | 17210.01 | 17210.01 | 0 |  | 17210.01 | 17210.01 | 0 | 0 | 0 | 0 | 0
56.1112 | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 100% | 100% | 27241.58 | 27241.58 | 0 |  | 27241.58 | 27241.58 | 0 | 0 | 0 | 0 | 27241.58 | 27241.58 | 0 |  | 27241.58 | 27241.58 | 0 | 0 | 0 | 0 | 0
56.1113 | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 100% | 100% | 49233.44 | 49233.44 | 0 |  | 49233.44 | 49233.44 | 0 | 0 | 0 | 0 | 49233.44 | 49233.44 | 0 |  | 49233.44 | 49233.44 | 0 | 0 | 0 | 0 | 0
56.1115 | AIC - UC Davis - WWTP Annual Instrument Calibrations | 100% | 100% | 5895.77 | 5895.77 | 0 |  | 5895.77 | 5895.77 | 0 | 0 | 0 | 0 | 5895.77 | 5895.77 | 0 |  | 5895.77 | 5895.77 | 0 | 0 | 0 | 0 | 0
56.1119 | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 100% | 100% | 22184.06 | 22184.06 | 0 |  | 22184.06 | 22184.06 | 0 | 0 | 0 | 0 | 22184.06 | 22184.06 | 0 |  | 22184.06 | 22184.06 | 0 | 0 | 0 | 0 | 0
56.112 | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 100% | 100% | 1045.63 | 1045.63 | 0 |  | 1045.63 | 1045.63 | 0 | 0 | 0 | 0 | 1045.63 | 1045.63 | 0 |  | 1045.63 | 1045.63 | 0 | 0 | 0 | 0 | 0
56.1121 | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 100% | 100% | 22824.38 | 22824.38 | 0 |  | 22824.38 | 22824.38 | 0 | 0 | 0 | 0 | 22824.38 | 22824.38 | 0 |  | 22824.38 | 22824.38 | 0 | 0 | 0 | 0 | 0
56.1122 | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 100% | 100% | 6289.38 | 6289.38 | 0 |  | 6289.38 | 6289.38 | 0 | 0 | 0 | 0 | 6289.38 | 6289.38 | 0 |  | 6289.38 | 6289.38 | 0 | 0 | 0 | 0 | 0
56.1123 | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 100% | 100% | 3772.82 | 3772.82 | 0 |  | 3772.82 | 3772.82 | 0 | 0 | 0 | 0 | 3772.82 | 3772.82 | 0 |  | 3772.82 | 3772.82 | 0 | 0 | 0 | 0 | 0
56.1124 | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 100% | 100% | 28950 | 28950 | 0 |  | 28950 | 28950 | 0 | 0 | 0 | 0 | 28950 | 28950 | 0 |  | 28950 | 28950 | 0 | 0 | 0 | 0 | 0
56.1125 | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 100% | 100% | 14229.38 | 14229.38 | 0 |  | 14229.38 | 14229.38 | 0 | 0 | 0 | 0 | 14229.38 | 14229.38 | 0 |  | 14229.38 | 14229.38 | 0 | 0 | 0 | 0 | 0
56.1126 | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 100% | 100% | 9526.88 | 9526.88 | 0 |  | 9526.88 | 9526.88 | 0 | 0 | 0 | 0 | 9526.88 | 9526.88 | 0 |  | 9526.88 | 9526.88 | 0 | 0 | 0 | 0 | 0
56.1127 | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 100% | 100% | 6519.07 | 6519.07 | 0 |  | 6519.07 | 6519.07 | 0 | 0 | 0 | 0 | 6519.07 | 6519.07 | 0 |  | 6519.07 | 6519.07 | 0 | 0 | 0 | 0 | 0
56.1128 | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 100% | 100% | 4793.13 | 4793.13 | 0 |  | 4793.13 | 4793.13 | 0 | 0 | 0 | 0 | 4793.13 | 4793.13 | 0 |  | 4793.13 | 4793.13 | 0 | 0 | 0 | 0 | 0
56.1129 | AIC - RMCSD - VEEAM SFTWR | 100% | 100% | 133.75 | 133.75 | 0 |  | 133.75 | 133.75 | 0 | 0 | 0 | 0 | 133.75 | 133.75 | 0 |  | 133.75 | 133.75 | 0 | 0 | 0 | 0 | 0
56.113 | System Integration Division Estimating 2025 | 100% | 100% | 0 | 267.5 | -267.5 |  | 0 | 267.5 | -267.5 | 0 | 0 | 0 | 0 | 267.5 | -267.5 |  | 0 | 267.5 | -267.5 | 0 | 0 | 0 | 0
56.1131 | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 100% | 100% | 2388.75 | 2388.75 | 0 |  | 2388.75 | 2388.75 | 0 | 0 | 0 | 0 | 2388.75 | 2388.75 | 0 |  | 2388.75 | 2388.75 | 0 | 0 | 0 | 0 | 0
56.1132 | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 100% | 100% | 585 | 585 | 0 |  | 585 | 585 | 0 | 0 | 0 | 0 | 585 | 585 | 0 |  | 585 | 585 | 0 | 0 | 0 | 0 | 0
56.1133 | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 100% | 100% | 2827.5 | 2827.5 | 0 |  | 2827.5 | 2827.5 | 0 | 0 | 0 | 0 | 2827.5 | 2827.5 | 0 |  | 2827.5 | 2827.5 | 0 | 0 | 0 | 0 | 0
56.1134 | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 100% | 100% | 965.51 | 965.51 | 0 |  | 965.51 | 965.51 | 0 | 0 | 0 | 0 | 965.51 | 965.51 | 0 |  | 965.51 | 965.51 | 0 | 0 | 0 | 0 | 0
56.1135 | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 100% | 100% | 112.5 | 112.5 | 0 |  | 112.5 | 112.5 | 0 | 0 | 0 | 0 | 112.5 | 112.5 | 0 |  | 112.5 | 112.5 | 0 | 0 | 0 | 0 | 0
56.1141 | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 100% | 100% | 2827.5 | 2827.5 | 0 |  | 2827.5 | 2827.5 | 0 | 0 | 0 | 0 | 2827.5 | 2827.5 | 0 |  | 2827.5 | 2827.5 | 0 | 0 | 0 | 0 | 0
0
System Integration Closed Jobs Totals |  |  |  | 4511779.65 | 7995768.94 | -3483989.29 |  | 4511779.65 | 7995768.94 | -3483989.29 | 0 | 0 | 0 | 3047886.8924 | 6867182.61 | -3819295.7176 |  | 3000519.1427 | 6867182.61 | -3866663.4673 | 47367.7496 | 0 | 47367.7496 | -47367.7496
System Integration Total |  |  |  | 12078500.3516 | 14455117.85 | -2376617.4984 |  | 12077619.0696 | 14455117.85 | -2377498.7804 | 881.2819 | 0 | 881.2819 | 9364281.3803 | 12323832.99 | -2959551.6097 |  | 9221003.2238 | 12323832.99 | -3102829.7662 | 143278.1565 | 0 | 143278.1565 | -142396.8745
W Jobs
50.0541 | W.M. Lyles Co. - General Overhead | 100% | 100% | 0 | 3642039.89 | -3642039.89 |  | 0 | 3642039.89 | -3642039.89 | 0 | 0 | 0 | 0 | 3642039.89 | -3642039.89 |  | 0 | 3642039.89 | -3642039.89 | 0 | 0 | 0 | 0
50.0542 | W.M. Lyles Co. - General Estimating | 100% | 100% | 0 | 100487.45 | -100487.45 |  | 0 | 100487.45 | -100487.45 | 0 | 0 | 0 | 0 | 100487.45 | -100487.45 |  | 0 | 100487.45 | -100487.45 | 0 | 0 | 0 | 0
50.0543 | American Paving | 100% | 100% | 7051.01 | 7051.01 | 0 |  | 7051.01 | 7051.01 | 0 | 0 | 0 | 0 | 7051.01 | 7051.01 | 0 |  | 7051.01 | 7051.01 | 0 | 0 | 0 | 0 | 0
50.0544 | Lyles Services Co. | 100% | 100% | 13555.8 | 13555.8 | 0 |  | 13555.8 | 13555.8 | 0 | 0 | 0 | 0 | 13555.8 | 13555.8 | 0 |  | 13555.8 | 13555.8 | 0 | 0 | 0 | 0 | 0
50.0545 | New England Sheet Metal and Mechanical Co. | 100% | 100% | 2226.16 | 2226.16 | 0 |  | 2226.16 | 2226.16 | 0 | 0 | 0 | 0 | 2226.16 | 2226.16 | 0 |  | 2226.16 | 2226.16 | 0 | 0 | 0 | 0 | 0
50.0546 | Lyles Utility Construction, LLC | 100% | 100% | 11256.72 | 10468.06 | 788.66 |  | 11256.72 | 10468.06 | 788.66 | 0 | 0 | 0 | 11256.72 | 10468.06 | 788.66 |  | 11256.72 | 10468.06 | 788.66 | 0 | 0 | 0 | 0
50.0551 | Advanced Integration & Controls | 100% | 100% | 5457.42 | 5457.42 | 0 |  | 5457.42 | 5457.42 | 0 | 0 | 0 | 0 | 5457.42 | 5457.42 | 0 |  | 5457.42 | 5457.42 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0
W Job Total |  |  |  | 39547.11 | 3781285.79 | -3741738.68 |  | 39547.11 | 3781285.79 | -3741738.68 | 0 | 0 | 0 | 39547.11 | 3781285.79 | -3741738.68 |  | 39547.11 | 3781285.79 | -3741738.68 | 0 | 0 | 0 | 0
Open Jobs Totals |  |  |  | 1107807669.4931 | 1041534998.27 | 66272671.2231 |  | 1106945177.9672 | 1041534998.27 | 65410179.6972 | 862491.5259 | 0 | 862491.5259 | 328738312.8804 | 303536058.74 | 25202254.1404 |  | 333940051.1325 | 303536058.74 | 30403992.3925 | -5201738.2521 | 0 | -5201738.2521 | 6064229.778
Closed Job Totals |  |  |  | 152608093.41 | 147840152.81 | 4767940.6 | 0 | 152608093.41 | 147840152.81 | 4767940.6 | 0 | 0 | 0 | 22281669.6579 | 35347710.14 | -13066040.4821 | 0 | 22225464.8054 | 35347710.14 | -13122245.3346 | 56204.8525 | 0 | 56204.8525 | -56204.8525
Company Totals - Jobs |  |  |  | 1260415762.9031 | 1189375151.08 | 71040611.8231 |  | 1259553271.3772 | 1189375151.08 | 70178120.2972 | 862491.5259 | 0 | 862491.5259 | 351019982.5383 | 338883768.88 | 12136213.6583 |  | 356165515.9379 | 338883768.88 | 17281747.0579 | -5145533.3996 | 0 | -5145533.3996 | 6008024.9256
Joint Ventures
Rocklin | Stockton Phase 1 & 2 | 99.86% | 100% | 115193055.5 | 108490330 | 6702725.5 |  | 115618841.815 | 108777011.815 | 6841830 | -425786.315 | -286681.815 | -139104.5 | 1939329.5 | 2639572.5 | -700243 |  | 339552.32 | 3520992.32 | -3181440 | 1599777.18 | -881419.82 | 2481197 | -2620301.5
Fresno | City of Santa Cruz - Graham Hill WTP | 98% | 100% | 5490375 | 5473212.5 | 17162.5 |  | 5549187.24 | 5464558.86 | 84628.38 | -58812.24 | 8653.64 | -67465.88 | 979.32 | 155672 | -154692.68 |  | 273389.61 | 157577.56 | 115812.05 | -272410.29 | -1905.56 | -270504.73 | 203038.85
Murrieta | Silverlake | 98.29% | 98.34% | 90175346.75 | 83932670 | 6242676.75 |  | 90175346.75 | 83823698.64 | 6351648.11 | 0 | 108971.36 | -108971.36 | 1588012 | 1440095.25 | 147916.75 |  | 1588012 | 1415375.5 | 172636.5 | 0 | 24719.75 | -24719.75 | -84251.61
Murrieta | East County Advanced Package 1 | 83.35% | 89.38% | 211769168.5 | 203222516.5 | 8546652 |  | 217398265.79 | 202057874.345 | 15340391.445 | -5629097.29 | 1164642.155 | -6793739.445 | 47478147.5 | 54681495.5 | -7203348 |  | 62842339.86 | 60595784.47 | 2246555.39 | -15364192.36 | -5914288.97 | -9449903.39 | 2656163.945
Murrieta | East County Advanced Package 3 | 70.6% | 100% | 36465046 | 46728002 | -10262956 |  | 47292915.245 | 46192576.84 | 1100338.405 | -10827869.245 | 535425.16 | -11363294.405 | 9017291.5 | 13380247.5 | -4362956 |  | 13625288.77 | 14259321.31 | -634032.54 | -4607997.27 | -879073.81 | -3728923.46 | -7634370.945
Murrieta | City of Banning | 25.1% | 31.43% | 571506 | 571506 | 0 |  | 627877.815 | 571240.65 | 56637.165 | -56371.815 | 265.35 | -56637.165 | 571506 | 571506 | 0 |  | 627877.82 | 571240.65 | 56637.17 | -56371.82 | 265.35 | -56637.17 | 0.005
WML % JV Job Totals |  |  |  | 459664497.75 | 448418237 | 11246260.75 |  | 476662434.655 | 446886961.15 | 29775473.505 | -16997936.905 | 1531275.85 | -18529212.755 | 60595265.82 | 72868588.75 | -12273322.93 |  | 79296460.38 | 80520291.81 | -1223831.43 | -18701194.56 | -7651703.06 | -11049491.5 | -7479721.255
WML Jobs and JV's |  |  |  | 1720080260.6531 | 1637793388.08 | 82286872.5731 |  | 1736215706.0322 | 1636262112.23 | 99953593.8022 | -16135445.3791 | 1531275.85 | -17666721.2291 | 411615248.3583 | 411752357.63 | -137109.2717 |  | 435461976.3179 | 419404060.69 | 16057915.6279 | -23846727.9596 | -7651703.06 | -16195024.8996 | -1471696.3294
0
Proof to Bonus/GAAP Op. Stmt. Variance
[21 empty] | Profit Sharing |  | 1618101.49
[21 empty] | Bonus |  | 3423547.75
[21 empty] | Income Tax |  | 308000
[21 empty] | Lease Liability Adj. |  | -12928.5
[21 empty] | SI Adjustment |  | 3288034.49
[21 empty] | Jobs/JV's Variance |  | -16195024.8996
[21 empty] | Total Variance |  | -7570269.6696
[21 empty] | Bonus Net Income |  | 10715183.33 |  | From Op. Statement row 48
[21 empty] | GAAP Net Income |  | 18285453 |  | From GAAP Op. Statement row 56
[21 empty] | Net Income Variance |  | -7570269.67 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0

## Job Status
W. M. Lyles Co. | [15 empty] | A | Opened in PY, Closed in CY
Job Status Analysis | [15 empty] | B | Opened in PY, Still Open:
For the Month Ended December 31, 2025 | [7 empty] | 2025-12-31 | [7 empty] | C | Open in CY, Closed in CY:
[16 empty] | D | Opened in CY, Still Open:
|  | Billed | Remaining | Total | Cost | Estimate |  | Projected |  |  | Prior | Net |  |  |  | O | Overhead Jobs
|  | To | To | Contract | Incurred | Cost To | Total Estimated | Final | Percent | Job to Date | Amount | Change |  |  |  | U | Under $250,000
Job No. | Project Name | Date | Bill | Amount | To Date | Complete | Cost | Profit/(Loss) | Complete | Profit | Claimed |  |  |  |  | W | W Jobs
Jobs with Contract Amounts greater than $250,000 | [15 empty] | Print this worksheet in B&W!
Opened in PY, Closed in CY: | [12 empty] | Opened | Closed | Size | Section
51.1133 | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 372738 | 0 | 372738 | 331855.28 | 0 | 331855.28 | 40882.72 | 100% | 40882.72 | 17359.5806 | 23523.1394 | 2023 | 2025 | .
51.1136 | Union Sanitary Dist - USD Plant Misc. Improvements | 5483550 | 0 | 5483550 | 4531817.86 | 0 | 4531817.86 | 951732.14 | 100% | 951732.14 | 758905.7861 | 192826.3539 | 2023 | 2025 | .
51.1138 | CA Water Service Co. - Bear Gulch Pump Station 21 | 1120182.07 | 0 | 1120182.07 | 1167704.15 | 0 | 1167704.15 | -47522.08 | 100% | -47522.08 | 77778.0991 | -125300.1791 | 2023 | 2025 | .
51.1141 | City of Colfax - WWTP Algae Reduction Project | 3967189.79 | 0 | 3967189.79 | 3835094.73 | 0 | 3835094.73 | 132095.06 | 100% | 132095.06 | 79920.2987 | 52174.7613 | 2023 | 2025 | .
51.1143 | Olivehurst Plumas Lake Manganese Filter Expansion | 1991231.37 | 0 | 1991231.37 | 1758132.57 | 0 | 1758132.57 | 233098.8 | 100% | 233098.8 | 226011.7629 | 7087.0371 | 2023 | 2025 | .
51.1147 | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2742860.08 | 0 | 2742860.08 | 2548724.92 | 0 | 2548724.92 | 194135.16 | 100% | 194135.16 | 128284.5352 | 65850.6248 | 2023 | 2025 | .
51.115 | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2486231.58 | 0 | 2486231.58 | 2239435.14 | 0 | 2239435.14 | 246796.44 | 100% | 246796.44 | 166471.8295 | 80324.6105 | 2024 | 2025 | .
52.8567 | City of Modesto - Grayson Well 69 | 3059858.99 | 0 | 3059858.99 | 3128023.93 | 0 | 3128023.93 | -68164.94 | 100% | -68164.94 | -83000 | 14835.06 | 2021 | 2025 | .
52.8604 | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 5095690.97 | 0 | 5095690.97 | 4572503.23 | 0 | 4572503.23 | 523187.74 | 100% | 523187.74 | 329989.1327 | 193198.6073 | 2022 | 2025 | .
52.8628 | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 5213345.5 | 0 | 5213345.5 | 4745798.53 | 0 | 4745798.53 | 467546.97 | 100% | 467546.97 | 197224.7538 | 270322.2162 | 2023 | 2025 | .
52.8631 | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 2560650.14 | 0 | 2560650.14 | 2448658.26 | 0 | 2448658.26 | 111991.88 | 100% | 111991.88 | 73003.7005 | 38988.1795 | 2023 | 2025 | .
52.8652 | California Water Service Co. - Salinas 77 Booster Station | 1290184 | 0 | 1290184 | 1039376.08 | 0 | 1039376.08 | 250807.92 | 100% | 250807.92 | 170698.8374 | 80109.0826 | 2024 | 2025 | .
52.8658 | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1870914.99 | 0 | 1870914.99 | 1633530.21 | 0 | 1633530.21 | 237384.78 | 100% | 237384.78 | 145886.6054 | 91498.1746 | 2023 | 2025 | .
52.8663 | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1641800 | 0 | 1641800 | 1379688.28 | 0 | 1379688.28 | 262111.72 | 100% | 262111.72 | 42676.9508 | 219434.7692 | 2024 | 2025 | .
52.8667 | California Water Service Co. - Cal Water Salinas Station 33 | 314085.77 | 0 | 314085.77 | 290726.11 | 0 | 290726.11 | 23359.66 | 100% | 23359.66 | 26868.8653 | -3509.2053 | 2024 | 2025 | .
52.867 | California Water Service Co. - Cal Water - King City Station 10 | 274166.01 | 0 | 274166.01 | 267282.05 | 0 | 267282.05 | 6883.96 | 100% | 6883.96 | 10404.4356 | -3520.4756 | 2024 | 2025 | .
52.8674 | City of Hanford - WWTP Standby Influent Pump Install | 279244 | 0 | 279244 | 251088.2 | 0 | 251088.2 | 28155.8 | 100% | 28155.8 | 15534.5836 | 12621.2164 | 2024 | 2025 | .
52.8677 | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 796055.3 | 0 | 796055.3 | 689831.96 | 0 | 689831.96 | 106223.34 | 100% | 106223.34 | 0 | 106223.34 | 2024 | 2025 | .
53.2004 | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 1173753.47 | 0 | 1173753.47 | 980791.05 | 0 | 980791.05 | 192962.42 | 100% | 192962.42 | 0 | 192962.42 | 2024 | 2025 | .
54.9099 | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 55712110 | 0 | 55712110 | 45328892.68 | 0 | 45328892.68 | 10383217.32 | 100% | 10383217.32 | 10372751.5815 | 10465.7385 | 2020 | 2025 | .
54.9172 | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 24160002.44 | 0 | 24160002.44 | 21018432.22 | 0 | 21018432.22 | 3141570.22 | 100% | 3141570.22 | 3107901.82 | 33668.4 | 2021 | 2025 | .
54.9216 | CA Dept. of Corr. - Water Treatment Improvements | 2472164.05 | 0 | 2472164.05 | 2286264.43 | 0 | 2286264.43 | 185899.62 | 100% | 185899.62 | 140849.7535 | 45049.8665 | 2022 | 2025 | .
54.9246 | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 1777852 | 0 | 1777852 | 1708475.32 | 0 | 1708475.32 | 69376.68 | 100% | 69376.68 | 69196.4543 | 180.2257 | 2022 | 2025 | .
54.9279 | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3216240.01 | 0 | 3216240.01 | 3153237.4 | 0 | 3153237.4 | 63002.61 | 100% | 63002.61 | -15000 | 78002.61 | 2023 | 2025 | .
54.9309 | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3968668.9 | 0 | 3968668.9 | 3790858.34 | 0 | 3790858.34 | 177810.56 | 100% | 177810.56 | 62853.4158 | 114957.1442 | 2024 | 2025 | .
54.9333 | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 427464.77 | 0 | 427464.77 | 371915.26 | 0 | 371915.26 | 55549.51 | 100% | 55549.51 | 14888.68 | 40660.83 | 2024 | 2025 | .
54.9341 | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1251279 | 0 | 1251279 | 1063532.4 | 0 | 1063532.4 | 187746.6 | 100% | 187746.6 | 9297.3859 | 178449.2141 | 2024 | 2025 | .
54.9349 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 290129 | 0 | 290129 | 197889.31 | 0 | 197889.31 | 92239.69 | 100% | 92239.69 | 4519.6837 | 87720.0063 | 2024 | 2025 | .
54.9358 | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1147640 | 0 | 1147640 | 1125399.83 | 0 | 1125399.83 | 22240.17 | 100% | 22240.17 | 15917.5507 | 6322.6193 | 2024 | 2025 | .
54.9362 | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 425035.04 | 0 | 425035.04 | 375601.24 | 0 | 375601.24 | 49433.8 | 100% | 49433.8 | 0 | 49433.8 | 2024 | 2025 | .
55.123 | Anaergia Technologies - VVWRA - DAF 3 Replacement | 2273682.69 | 0 | 2273682.69 | 1665145.3 | 0 | 1665145.3 | 608537.39 | 100% | 608537.39 | 480252.0335 | 128285.3565 | 2023 | 2025 | .
55.1231 | City of Corona - WRF 1 Aeration System Improvements | 4046200 | 0 | 4046200 | 3321856.36 | 0 | 3321856.36 | 724343.64 | 100% | 724343.64 | 627907.3954 | 96436.2446 | 2023 | 2025 | .
56.1003 | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 332901 | 0 | 332901 | 223395.74 | 0 | 223395.74 | 109505.26 | 100% | 109505.26 | 64460.9863 | 45044.2737 | 2023 | 2025 | .
56.103 | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 689578.64 | 0 | 689578.64 | 689578.64 | 0 | 689578.64 | 0 | 100% | 0 | 18034.019 | -18034.019 | 2024 | 2025 | .
56.1062 | AIC - SCADA System Upgrade - City of Brentwood | 409988.07 | 0 | 409988.07 | 409988.07 | 0 | 409988.07 | 0 | 100% | 0 | 0 | 0 | 2024 | 2025 | .
56.1064 | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 435153 | 0 | 435153 | 202266.4 | 0 | 202266.4 | 232886.6 | 100% | 232886.6 | 69496.4896 | 163390.1104 | 2024 | 2025 | .
Opened in PY, Still Open:
51.1108 | City of Stockton - RWCF Phase 2A/2B | 94045647.86 | 0 | 94045647.86 | 89805617.8 | 0 | 89805617.8 | 4240030.06 | 100% | 4240030.06 | 4035762.57 | 204267.49 | 2019 | 0 | .
51.1129 | Union Sanit. Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin | 96918206.9 | 29565373.94 | 126483580.84 | 87315159.22 | 27918421.62 | 115233580.84 | 11250000 | 75.77% | 8524386.1561 | 6957477.3602 | 1566908.7959 | 2022 | 0 | .
51.1137 | CA Water Service Co. - Bear Gulch Pump Station 18 | 1121900.01 | 190251.45 | 1312151.46 | 1042229.29 | 156282.17 | 1198511.46 | 113640 | 86.96% | 98821.6971 | 27243.5887 | 71578.1085 | 2023 | 0 | .
51.1144 | Silicon Valley Clean Water - FEP Improvements Project | 9667725.77 | 5301840.23 | 14969566 | 8406760.8 | 5432856.2 | 13839617 | 1129949 | 60.74% | 686378.1678 | 90331.4512 | 596046.7166 | 2023 | 0 | .
51.1146 | National Carbon Technologies, LLC - Aymium Williams Production Facility | 60980234 | 0 | 60980234 | 40950686.5 | 3246167.53 | 44196854.03 | 16783379.97 | 92.66% | 15550675.419 | 0 | 15550675.419 | 2023 | 0 | .
51.1151 | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 5009265.21 | 5648934.79 | 10658200 | 4923435.18 | 5155916.82 | 10079352 | 578848 | 48.85% | 282748.3956 | 0 | 282748.3956 | 2024 | 0 | .
51.1152 | Mozingo Construction Inc - ElD Sly Park Intertie Project | 15610649.01 | 4363840.33 | 19974489.34 | 13474808.54 | 5154139.8 | 18628948.34 | 1345541 | 72.33% | 973265.2121 | 0 | 973265.2121 | 2024 | 0 | .
51.1153 | Linda County Water Dist. - Aeration Blower Replacement | 549548.83 | 13275.85 | 562824.68 | 334550.81 | 119969.87 | 454520.68 | 108304 | 73.61% | 79717.365 | 12859.3892 | 66857.9758 | 2024 | 0 | .
51.1154 | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 13340008 | 23827 | 13363835 | 11872342.6 | 616492.4 | 12488835 | 875000 | 95.06% | 831806.952 | 94320.4226 | 737486.5294 | 2024 | 0 | .
52.8563 | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 1134038.13 | 0 | 1134038.13 | 859077.05 | 0 | 859077.05 | 274961.08 | 100% | 274961.08 | 194465.74 | 80495.34 | 2021 | 0 | .
52.8566 | City of Visalia - Water Reclamation Facility RPGS SCR System | 1242053 | 17345 | 1259398 | 1023821.05 | 5576.95 | 1029398 | 230000 | 99.46% | 228753.9334 | 223974.5063 | 4779.4271 | 2021 | 0 | .
52.8586 | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 12611349 | 0 | 12611349 | 10565460.74 | 95888.26 | 10661349 | 1950000 | 99.1% | 1932461.6841 | 1757780.0079 | 174681.6762 | 2022 | 0 | .
52.8634 | City of Huron - Water Treatment Plant Imp. Phase 2 | 12576768.04 | 1315954.7 | 13892722.74 | 11707058.24 | 1483664.5 | 13190722.74 | 702000 | 88.75% | 623040.5298 | 277972.0115 | 345068.5183 | 2023 | 0 | .
52.8636 | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 3065635.6 | 590476.4 | 3656112 | 3367047.36 | 14064.64 | 3381112 | 275000 | 99.58% | 273856.0639 | 204319.7111 | 69536.3528 | 2023 | 0 | .
52.8637 | Root Creek Water Dist. - Groundwater Blending & Arsenic | 26148625 | 115952.65 | 26264577.65 | 24374299.03 | 240278.62 | 24614577.65 | 1650000 | 99.02% | 1633893.2957 | 1208391.7577 | 425501.538 | 2023 | 0 | .
52.864 | City of Dos Palos - WTP Replacement Project | 34176041.86 | 4470321.3 | 38646363.16 | 32158781.48 | 4614258.68 | 36773040.16 | 1873323 | 87.45% | 1638259.571 | 703966.8389 | 934292.7322 | 2023 | 0 | .
52.8668 | California Water Service Co. - Cal Water - Salinas Station 57 | 349622.76 | 62228.24 | 411851 | 357710.67 | 19285.33 | 376996 | 34855 | 94.88% | 33071.9833 | 5273.0464 | 27798.9368 | 2024 | 0 | .
52.8678 | City of Chowcilla - Well 15 & Generator Improvement Projects | 1142122 | 98199 | 1240321 | 926007.31 | 236313.69 | 1162321 | 78000 | 79.67% | 62141.6719 | 0 | 62141.6719 | 2024 | 0 | .
54.9135 | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 9470658.62 | 0 | 9470658.62 | 9050951.86 | 0 | 9050951.86 | 419706.76 | 100% | 419706.76 | 0 | 419706.76 | 2021 | 0 | .
54.9257 | City of Guadalupe - Highway 1 Lift Station | 890983 | 580345 | 1471328 | 762211.05 | 664116.95 | 1426328 | 45000 | 53.44% | 24047.4121 | 0 | 24047.4121 | 2023 | 0 | .
54.9268 | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 907298 | 42269.99 | 949567.99 | 844648.28 | 39919.71 | 884567.99 | 65000 | 95.49% | 62066.612 | 71013.0668 | -8946.4548 | 2023 | 0 | .
54.9269 | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 625819.17 | 0 | 625819.17 | 549817.74 | 0 | 549817.74 | 76001.43 | 100% | 76001.43 | 34249.05 | 41752.38 | 2023 | 0 | .
54.9285 | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 427226 | 34796 | 462022 | 312939.77 | 74082.23 | 387022 | 75000 | 80.86% | 60643.7948 | 35686.2378 | 24957.557 | 2023 | 0 | .
54.9313 | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 7886885 | 0.04 | 7886885.04 | 6449205.22 | 427679.82 | 6876885.04 | 1010000 | 93.78% | 947187.1689 | 197714.5111 | 749472.6578 | 2024 | 0 | .
54.933 | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 324900 | 0 | 324900 | 306221.41 | 1419.59 | 307641 | 17259 | 99.54% | 17179.3594 | 10642.1273 | 6537.2322 | 2024 | 0 | .
54.9336 | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 14176592.91 | 11014583.73 | 25191176.64 | 12340864.27 | 10930312.37 | 23271176.64 | 1920000 | 53.03% | 1018189.1429 | 0 | 1018189.1429 | 2024 | 0 | .
54.9337 | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 520441.66 | 3584406.34 | 4104848 | 1509066.73 | 2435781.27 | 3944848 | 160000 | 38.25% | 61206.5856 | 0 | 61206.5856 | 2024 | 0 | .
54.9343 | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 3954560 | 2926740 | 6881300 | 3415344.08 | 2565955.92 | 5981300 | 900000 | 57.1% | 513903.2772 | 0 | 513903.2772 | 2024 | 0 | .
54.9356 | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 685017 | 613313 | 1298330 | 775780.75 | 137549.25 | 913330 | 385000 | 84.94% | 327018.2615 | 0 | 327018.2615 | 2024 | 0 | .
54.9366 | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1160831 | 69300 | 1230131 | 923220.5 | 156910.5 | 1080131 | 150000 | 85.47% | 128209.5181 | 0 | 128209.5181 | 2024 | 0 | .
54.9369 | California Water Service Co. - PFAS Treatment Program Project | 2927422.95 | 25623201.75 | 28550624.7 | 2787466.66 | 23392315.04 | 26179781.7 | 2370843 | 10.65% | 252433.1904 | 0 | 252433.1904 | 2024 | 0 | .
55.109 | LA Dept of Water and Power - Silverlake | 5235272.36 | 0 | 5235272.36 | 3834064.05 | 0 | 3834064.05 | 1401208.31 | 100% | 1401208.31 | 1356365.09 | 44843.22 | 2012 | 0 | .
55.1191 | Inland Empire Utilities - IEUA RP-5 Liquids Exp. & Solids Treat. Facility | 296634984.51 | 44808149.2 | 341443133.71 | 299179624.84 | 38553010.87 | 337732635.71 | 3710498 | 88.58% | 3286935.529 | 6702671.5016 | -3415735.9726 | 2020 | 0 | .
55.1192 | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6645760.51 | 6043.02 | 6651803.53 | 6393992.69 | 7810.84 | 6401803.53 | 250000 | 99.88% | 249694.975 | 334963.8396 | -85268.8646 | 2020 | 0 | .
55.12 | East County Advanced Water Purification Project - Package 1 | 197175877 | 0 | 197175877 | 189971137.49 | 0 | 189971137.49 | 7204739.51 | 100% | 7204739.51 | 4174832.91 | 3029906.6 | 2020 | 0 | .
55.1202 | LA County Sanitation District - Oxygen Generation Project | 10912272.58 | 5483779 | 16396051.58 | 9590124.35 | 5630518.23 | 15220642.58 | 1175409 | 63.01% | 740594.1249 | 647450.7063 | 93143.4186 | 2020 | 0 | .
55.1204 | East County Advanced Water Purification Project - Package 3 | 57142227 | 0 | 57142227 | 55213329.21 | 0 | 55213329.21 | 1928897.79 | 100% | 1928897.79 | 1627042.78 | 301855.01 | 2020 | 0 | .
55.1227 | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 41483406.39 | 20800 | 41504206.39 | 36953022.96 | 201183.43 | 37154206.39 | 4350000 | 99.46% | 4326445.5224 | 3409470.3388 | 916975.1837 | 2022 | 0 | .
55.1233 | Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 123617 | 2460.16 | 126077.16 | 126077.16 | 0 | 126077.16 | 0 | 100% | 0 | 8428.84 | -8428.84 | 2024 | 0 | .
55.1248 | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 4861991.81 | 897310 | 5759301.81 | 3621770.22 | 1312531.59 | 4934301.81 | 825000 | 73.4% | 605548.778 | 0 | 605548.778 | 2024 | 0 | .
55.1249 | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 15047042.84 | 132478070.16 | 147525113 | 15046313.77 | 124657591.23 | 139703905 | 7821208 | 10.77% | 842355.4777 | 0 | 842355.4777 | 2024 | 0 | .
57.0003 | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 6863233.25 | 31302186.25 | 38165419.5 | 6316909.13 | 29441424.37 | 35758333.5 | 2407086 | 17.67% | 425225.1725 | 96385.4118 | 328839.7607 | 2024 | 0 | .
57.0004 | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 900072.76 | 39206151.87 | 40106224.63 | 750298.86 | 37146068.77 | 37896367.63 | 2209857 | 1.98% | 0 | 0 | 0 | 2024 | 0 | .
58.0003 | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 11889201.76 | 10635987.24 | 22525189 | 11034781.79 | 10182392.21 | 21217174 | 1308015 | 52.01% | 680281.9312 | 151508.8135 | 528773.1176 | 2024 | 0 | .
56.1004 | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 371550 | 1875 | 373425 | 236373.73 | 33466.27 | 269840 | 103585 | 87.6% | 90738.1145 | 51359.9627 | 39378.1518 | 2024 | 0 | .
56.1036 | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 48000 | 228000 | 276000 | 107051.95 | 101972.05 | 209024 | 66976 | 51.22% | 34301.8572 | 17815.6493 | 16486.2079 | 2024 | 0 | .
56.1039 | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 330000 | 45000 | 375000 | 324049.23 | 8234.77 | 332284 | 42716 | 97.52% | 41657.3982 | 4521.8913 | 37135.507 | 2024 | 0 | .
56.1042 | Trabuco Canyon Water Dist. - SCADA Integration Services | 217715 | 59850 | 277565 | 172683.27 | 45604.73 | 218288 | 59277 | 79.11% | 46892.8489 | 34822.2181 | 12070.6307 | 2024 | 0 | .
56.1043 | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 0 | 336610 | 336610 | 214994.3 | 96396.7 | 311391 | 25219 | 69.04% | 17412.0037 | 4449.6548 | 12962.3489 | 2024 | 0 | .
56.1047 | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 1905218.25 | 489539.75 | 2394758 | 1602869.63 | 437685.37 | 2040555 | 354203 | 78.55% | 278228.8307 | 0 | 278228.8307 | 2024 | 0 | .
56.1049 | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 291725 | 17000 | 308725 | 214423.06 | 34449.94 | 248873 | 59852 | 86.16% | 51567.0603 | 74409.071 | -22842.0107 | 2024 | 0 | .
56.105 | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 675979.5 | 3116579.5 | 3792559 | 925847.53 | 2439719.47 | 3365567 | 426992 | 27.51% | 117462.9679 | 0 | 117462.9679 | 2024 | 0 | .
56.1059 | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 0 | 399389 | 399389 | 235841.92 | 93364.08 | 329206 | 70183 | 71.64% | 50278.8329 | 0 | 50278.8329 | 2024 | 0 | .
56.106 | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 0 | 404663 | 404663 | 145563.36 | 176927.64 | 322491 | 82172 | 45.14% | 37090.1278 | 10941.5619 | 26148.5659 | 2024 | 0 | .
56.1066 | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 570000 | 25000 | 595000 | 476030.06 | 55459.94 | 531490 | 63510 | 89.57% | 56882.856 | 0 | 56882.856 | 2024 | 0 | .
56.1067 | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 217000 | 261000 | 478000 | 104751.99 | 311126.01 | 415878 | 62122 | 25.19% | 15647.3849 | 0 | 15647.3849 | 2024 | 0 | .
Open in CY, Closed in CY:
52.8685 | Malaga County Water Dist. - Malaga County Water District | 451254 | 0 | 451254 | 382067.32 | 0 | 382067.32 | 69186.68 | 100% | 69186.68 | 0 | 69186.68 | 2025 | 2025 | .
52.8693 | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 1120704.2 | 0 | 1120704.2 | 663140.99 | 0 | 663140.99 | 457563.21 | 100% | 457563.21 | 0 | 457563.21 | 2025 | 2025 | .
55.1251 | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 322982.96 | 0 | 322982.96 | 284221.86 | 0 | 284221.86 | 38761.1 | 100% | 38761.1 | 0 | 38761.1 | 2025 | 2025 | .
56.108 | AIC - San Jose Water Co - PLC System Assessment | 359469 | 0 | 359469 | 359469 | 0 | 359469 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | .
Opened in CY, Still Open:
51.1159 | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 732995 | 466005 | 1199000 | 790051.12 | 289188.88 | 1079240 | 119760 | 73.2% | 87669.5843 | 0 | 87669.5843 | 2025 | 0 | .
51.116 | City of Galt Public Works - Industrial WWTP Expansion | 223725 | 1533275 | 1757000 | 250518.05 | 1439481.95 | 1690000 | 67000 | 14.82% | 9931.7807 | 0 | 9931.7807 | 2025 | 0 | .
51.1161 | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | 745707.2 | 10102892.25 | 10848599.45 | 601852.17 | 9659400.28 | 10261252.45 | 587347 | 5.865% | 0 | 0 | 0 | 2025 | 0 | .
51.1162 | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project | 0 | 6029750 | 6029750 | 85941.38 | 5759321.62 | 5845263 | 184487 | 1.47% | 0 | 0 | 0 | 2025 | 0 | .
51.1164 | CA Water Service Co. - Stockton Roofing | 0 | 387260 | 387260 | 4363.25 | 379023.75 | 383387 | 3873 | 1.138% | 0 | 0 | 0 | 2025 | 0 | .
51.1165 | City of Yuba City - WTP Aquifer Storage and Recovery Well No. 3 | 0 | 5304500 | 5304500 | 23330.33 | 4863112.67 | 4886443 | 418057 | 0.4775% | 0 | 0 | 0 | 2025 | 0 | .
52.8687 | California Water Service Co. - Salinas Station 205 | 827811.95 | 50142.05 | 877954 | 740629.43 | 50142.05 | 790771.48 | 87182.52 | 93.66% | 81654.3612 | 0 | 81654.3612 | 2025 | 0 | .
52.8697 | City of Tulare - Industrial WWTP Dewatering Improvements Pro | 1069317 | 318683 | 1388000 | 772187.73 | 553294.27 | 1325482 | 62518 | 58.26% | 36421.1906 | 0 | 36421.1906 | 2025 | 0 | .
52.8704 | City of Visalia - Solids Handling Improvements Project | 1037950 | 12706050 | 13744000 | 820988.3 | 12670138.7 | 13491127 | 252873 | 6.085% | 0 | 0 | 0 | 2025 | 0 | .
52.8705 | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | 261232 | 513768 | 775000 | 285425.72 | 433834.28 | 719260 | 55740 | 39.68% | 22119.4417 | 0 | 22119.4417 | 2025 | 0 | .
52.8707 | County of Fresno - Westside Water Tank and Pump Station | 913135 | 2780065 | 3693200 | 1012057.14 | 2449519.86 | 3461577 | 231623 | 29.24% | 67719.3403 | 0 | 67719.3403 | 2025 | 0 | .
52.8708 | County of Fresno - CSA 44A Wastewater Improvements | 0 | 363833 | 363833 | 7682.19 | 326074.81 | 333757 | 30076 | 2.302% | 0 | 0 | 0 | 2025 | 0 | .
53.2007 | Union Sanitary Dist. - Phase 1B Secondary Clarifiers | 0 | 324530134 | 324530134 | 404852.16 | 291125281.84 | 291530134 | 33000000 | 0.1389% | 0 | 0 | 0 | 2025 | 0 | .
54.9373 | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 0 | 1524766 | 1524766 | 50303.97 | 1343022.03 | 1393326 | 131440 | 3.61% | 0 | 0 | 0 | 2025 | 0 | .
54.9389 | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 291620 | 8160 | 299780 | 311891.85 | 2888.15 | 314780 | -15000 | 99.08% | -15000 | 0 | -15000 | 2025 | 0 | .
54.9391 | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 532604.57 | 0 | 532604.57 | 512057.34 | 0 | 512057.34 | 20547.23 | 100% | 20547.23 | 0 | 20547.23 | 2025 | 0 | .
54.9395 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 1374448.17 | 421204.49 | 1795652.66 | 1349601.92 | 344050.74 | 1693652.66 | 102000 | 79.69% | 81279.5912 | 0 | 81279.5912 | 2025 | 0 | .
54.9397 | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 1033150.21 | 2657494.79 | 3690645 | 1035065.41 | 2355579.59 | 3390645 | 300000 | 30.53% | 91581.2841 | 0 | 91581.2841 | 2025 | 0 | .
54.9403 | Lost Hills Utility Dist. - WTP Improvements | 140100 | 241500 | 381600 | 129004.89 | 209096.11 | 338101 | 43499 | 38.16% | 16597.3591 | 0 | 16597.3591 | 2025 | 0 | .
54.9404 | Cawelo Water Dist. - Reuse of Produced Water | 1746890 | 1973110 | 3720000 | 1939024.63 | 1646367.37 | 3585392 | 134608 | 54.08% | 72797.6822 | 0 | 72797.6822 | 2025 | 0 | .
54.9405 | Semitropic Water Storage Dist. - Pump Platform Replacement Project | 746125 | 195875 | 942000 | 577796.16 | 234203.84 | 812000 | 130000 | 71.16% | 92504.3113 | 0 | 92504.3113 | 2025 | 0 | .
54.9408 | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line | 0 | 3777777 | 3777777 | 41652.43 | 3495532.57 | 3537185 | 240592 | 1.178% | 0 | 0 | 0 | 2025 | 0 | .
54.9414 | Cawelo Water Dist. - Cawelo Diversion Structure Rehab | 0 | 337485.68 | 337485.68 | 337485.68 | 0 | 337485.68 | 0 | 100% | 0 | 0 | 0 | 2025 | 0 | .
54.9416 | California Water Service Co. - BK 147 Station Improvements | 0 | 1260000 | 1260000 | 7257.82 | 1125140.18 | 1132398 | 127602 | 0.6409% | 0 | 0 | 0 | 2025 | 0 | .
55.1254 | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 158952.89 | 0 | 158952.89 | 156561.66 | 0 | 156561.66 | 2391.23 | 100% | 2391.23 | 0 | 2391.23 | 2025 | 0 | .
55.1256 | Anaergia Technologies LLC - City of Riverside - OPS | 101150 | 2786950 | 2888100 | 94989.88 | 2618110.12 | 2713100 | 175000 | 3.501% | 0 | 0 | 0 | 2025 | 0 | .
57.0008 | Imperial Irrigation Dist. - El Centro Generating Station WWTP | 266758 | 2609289 | 2876047 | 262382.86 | 2481599.14 | 2743982 | 132065 | 9.562% | 0 | 0 | 0 | 2025 | 0 | .
56.1075 | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 0 | 27665.92 | 27665.92 | 27665.92 | 0 | 27665.92 | 0 | 100% | 0 | 0 | 0 | 2025 | 0 | .
56.1083 | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 153616.75 | 563393.25 | 717010 | 347967.35 | 308395.65 | 656363 | 60647 | 53.01% | 32151.6842 | 0 | 32151.6842 | 2025 | 0 | .
56.1086 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 0 | 376000 | 376000 | 12732.69 | 282369.31 | 295102 | 80898 | 4.315% | 0 | 0 | 0 | 2025 | 0 | .
Totals |  | 1252571743.35 | 750339248.31 | 2002910991.66 | 1165739530.62 | 692746728 | 1858486258.62 | 144424733.04 |  | 85669055.3753 | 52278230.6416 | 33390824.7337
[7 empty] | Net change for the period 1/1/25-12/31/25 |  |  |  |  | 33390824.7337 | Update date in next row to appropriate quarter end.
[7 empty] | Profit on jobs with contracts under $250,000 |  |  |  |  | 844276.0942 | 34235100.8279 | =Should tie to Job Margin (not including JV)
[7 empty] | Net Income (Loss) from Joint Ventures |  |  |  |  | -1223832
[7 empty] | Over/(Under) application, including bidding jobs |  |  |  |  | -12586668 | Update date in next row to appropriate quarter end.
[7 empty] | Net Income (Loss) from Operations for the period 1/1/25-12/31/25 |  |  |  |  | 20424600.8279 | Has to tie to the dollar
Closed In Prior Year
Contracts Under $250,000
51.1158 | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 32282 | 72164 | 104446 | 56960.69 | 47485.31 | 104446 | 0 | 54.54% | 0 | 0 | 0 | 2025 | 0 | < 250k
51.1139 | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 61902 | 0 | 61902 | 56994.44 | 0 | 56994.44 | 4907.56 | 100% | 4907.56 | 4426.359 | 481.201 | 2023 | 2025 | < 250k
52.8692 | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 55135.37 | 0 | 55135.37 | 49682.49 | 0 | 49682.49 | 5452.88 | 100% | 5452.88 | 0 | 5452.88 | 2025 | 0 | < 250k
52.8698 | California Water Service Co. - Tesoro Viejo RWSP Liner Repair | 0 | 22713 | 22713 | 15264 | 864 | 16128 | 6585 | 94.64% | 6232.2321 | 0 | 6232.2321 | 2025 | 0 | < 250k
52.8711 | California Water Service Co. - Tesoro Viejo ARV Replacement | 0 | 6860 | 6860 | 4568.81 | 1746.19 | 6315 | 545 | 72.35% | 394.2995 | 0 | 394.2995 | 2025 | 0 | < 250k
52.8713 | City of Visalia - Remove & Replace Chain and Flight Mechanic | 0 | 218842 | 218842 | 927.5 | 189511.5 | 190439 | 28403 | 0.487% | 0 | 0 | 0 | 2025 | 0 | < 250k
52.8714 | New England Sheet Metal and Mechanical Co. - VCH Digging Water Line T&M | 5084.94 | 0 | 5084.94 | 4465.61 | 0 | 4465.61 | 619.33 | 100% | 619.33 | 0 | 619.33 | 2025 | 0 | < 250k
52.868 | City of Orange Cove - Orange Cove West Clarifier T&M | 29838.25 | 0 | 29838.25 | 26088.33 | 0 | 26088.33 | 3749.92 | 100% | 3749.92 | 0 | 3749.92 | 2024 | 2025 | < 250k
52.8684 | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 50568.05 | 0 | 50568.05 | 45291.39 | 0 | 45291.39 | 5276.66 | 100% | 5276.66 | 0 | 5276.66 | 2025 | 2025 | < 250k
52.8686 | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 23957 | 0 | 23957 | 7505.26 | 0 | 7505.26 | 16451.74 | 100% | 16451.74 | 15372.2567 | 1079.4833 | 2024 | 2025 | < 250k
52.8688 | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 132492.2 | 0 | 132492.2 | 116972.75 | 0 | 116972.75 | 15519.45 | 100% | 15519.45 | 0 | 15519.45 | 2025 | 2025 | < 250k
52.8689 | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 16665.83 | 0 | 16665.83 | 16095.58 | 0 | 16095.58 | 570.25 | 100% | 570.25 | 0 | 570.25 | 2025 | 2025 | < 250k
52.869 | City of Dinuba - WWTP Rake Replacement | 14151.97 | 0 | 14151.97 | 13155.83 | 0 | 13155.83 | 996.14 | 100% | 996.14 | 0 | 996.14 | 2025 | 2025 | < 250k
52.8691 | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 11302.84 | 0 | 11302.84 | 8287.82 | 0 | 8287.82 | 3015.02 | 100% | 3015.02 | 0 | 3015.02 | 2025 | 2025 | < 250k
52.8694 | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 43047.45 | 0 | 43047.45 | 38541.99 | 0 | 38541.99 | 4505.46 | 100% | 4505.46 | 0 | 4505.46 | 2025 | 2025 | < 250k
52.8695 | Lyles Services Co. - LSC GO Trash Enclosure | 13769 | 0 | 13769 | 13024.37 | 0 | 13024.37 | 744.63 | 100% | 744.63 | 0 | 744.63 | 2025 | 2025 | < 250k
52.8696 | American Paving Co. - Hot Tap for APC- Tule River Parkway | 1059.22 | 0 | 1059.22 | 887.65 | 0 | 887.65 | 171.57 | 100% | 171.57 | 0 | 171.57 | 2025 | 2025 | < 250k
52.8699 | City of Hanford - WWTP Repair T&M | 3001.12 | 0 | 3001.12 | 2948.91 | 0 | 2948.91 | 52.21 | 100% | 52.21 | 0 | 52.21 | 2025 | 2025 | < 250k
52.87 | Lyles Services Co. - LSC GO Misc. Work | 5297 | 0 | 5297 | 4446.13 | 0 | 4446.13 | 850.87 | 100% | 850.87 | 0 | 850.87 | 2025 | 2025 | < 250k
52.8701 | County of Fresno - 47 Water | 13433.85 | 0 | 13433.85 | 12421.08 | 0 | 12421.08 | 1012.77 | 100% | 1012.77 | 0 | 1012.77 | 2025 | 2025 | < 250k
52.8702 | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M | 5626.78 | 0 | 5626.78 | 4725.28 | 0 | 4725.28 | 901.5 | 100% | 901.5 | 0 | 901.5 | 2025 | 2025 | < 250k
52.8703 | County of Fresno - CSA 47 Egret Point Water Line Repair | 14402.18 | 0 | 14402.18 | 12571.54 | 0 | 12571.54 | 1830.64 | 100% | 1830.64 | 0 | 1830.64 | 2025 | 2025 | < 250k
52.8706 | City of Hanford - WWTP Weld Repair T&M 2 | 2868.6 | 0 | 2868.6 | 2435.78 | 0 | 2435.78 | 432.82 | 100% | 432.82 | 0 | 432.82 | 2025 | 2025 | < 250k
52.8709 | County of Fresno - 47.1 Water | 17765.14 | 0 | 17765.14 | 14874.36 | 0 | 14874.36 | 2890.78 | 100% | 2890.78 | 0 | 2890.78 | 2025 | 2025 | < 250k
52.871 | City of Dinuba - WWTP Bar Screen Motor Bracket Repair | 4064.54 | 0 | 4064.54 | 3514.84 | 0 | 3514.84 | 549.7 | 100% | 549.7 | 0 | 549.7 | 2025 | 2025 | < 250k
52.8715 | New England Sheet Metal and Mechanical Co. - Vitro Glass Plant Concrete Pad T&M | 10001.43 | 0 | 10001.43 | 8585.44 | 0 | 8585.44 | 1415.99 | 100% | 1415.99 | 0 | 1415.99 | 2025 | 2025 | < 250k
54.9033 | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 118278.58 | 0 | 118278.58 | 104550.27 | 0 | 104550.27 | 13728.31 | 100% | 13728.31 | 10966.87 | 2761.44 | 2021 | 0 | < 250k
54.9396 | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | 0 | 157746.09 | 157746.09 | 157746.09 | 0 | 157746.09 | 0 | 100% | 0 | 0 | 0 | 2025 | 0 | < 250k
54.9406 | California Water Service Co. - Emergency PACL leak repair | 0 | 1120.65 | 1120.65 | 1120.65 | 0 | 1120.65 | 0 | 100% | 0 | 0 | 0 | 2025 | 0 | < 250k
54.9411 | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation | 103000 | 300 | 103300 | 71370.85 | 6929.15 | 78300 | 25000 | 91.15% | 22787.6277 | 0 | 22787.6277 | 2025 | 0 | < 250k
54.9412 | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork | 116752.04 | 0 | 116752.04 | 115708.88 | 0 | 115708.88 | 1043.16 | 100% | 1043.16 | 0 | 1043.16 | 2025 | 0 | < 250k
54.9413 | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork | 149366.83 | 0 | 149366.83 | 132138.74 | 0 | 132138.74 | 17228.09 | 100% | 17228.09 | 0 | 17228.09 | 2025 | 0 | < 250k
54.9417 | County of Santa Barbara-Public Works - Laguna WWTP WAS Pipe Modifications | 0 | 48439 | 48439 | 2299.41 | 40593.59 | 42893 | 5546 | 5.361% | 0 | 0 | 0 | 2025 | 0 | < 250k
54.9418 | GenerateUpcycle - Organics Waste Processing Facility | 0 | 15739 | 15739 | 15739 | 0 | 15739 | 0 | 100% | 0 | 0 | 0 | 2025 | 0 | < 250k
54.9421 | Nipomo Community Service Dist. - Tefft Emergency Pipe Repair | 0 | 3703.18 | 3703.18 | 3703.18 | 0 | 3703.18 | 0 | 100% | 0 | 0 | 0 | 2025 | 0 | < 250k
54.9265 | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 223896.47 | 0 | 223896.47 | 220754.51 | 0 | 220754.51 | 3141.96 | 100% | 3141.96 | 0 | 3141.96 | 2023 | 2025 | < 250k
54.9289 | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 44560 | 0 | 44560 | 25097.25 | 0 | 25097.25 | 19462.75 | 100% | 19462.75 | 669.81 | 18792.94 | 2023 | 2025 | < 250k
54.9292 | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 4300 | 0 | 4300 | 1313.45 | 0 | 1313.45 | 2986.55 | 100% | 2986.55 | 2986.55 | 0 | 2023 | 2025 | < 250k
54.9323 | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 110661.47 | 0 | 110661.47 | 94483.21 | 0 | 94483.21 | 16178.26 | 100% | 16178.26 | 0 | 16178.26 | 2024 | 2025 | < 250k
54.9329 | Kern Water Bank Authority - Valve Replacement Parts | 18201.12 | 0 | 18201.12 | 16466.72 | 0 | 16466.72 | 1734.4 | 100% | 1734.4 | 0 | 1734.4 | 2025 | 2025 | < 250k
54.9338 | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 175884.64 | 0 | 175884.64 | 119186.11 | 0 | 119186.11 | 56698.53 | 100% | 56698.53 | 54179.7977 | 2518.7323 | 2024 | 2025 | < 250k
54.9342 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 199161.5 | 0 | 199161.5 | 124146.3 | 0 | 124146.3 | 75015.2 | 100% | 75015.2 | 41394.1127 | 33621.0873 | 2024 | 2025 | < 250k
54.9347 | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 7100 | 0 | 7100 | 3227.7 | 0 | 3227.7 | 3872.3 | 100% | 3872.3 | 0 | 3872.3 | 2025 | 2025 | < 250k
54.935 | Kern Water Bank Authority - Construct New Well 18P01 | 129965.06 | 0 | 129965.06 | 120318.68 | 0 | 120318.68 | 9646.38 | 100% | 9646.38 | 0 | 9646.38 | 2024 | 2025 | < 250k
54.9351 | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 153298.79 | 0 | 153298.79 | 136808.3 | 0 | 136808.3 | 16490.49 | 100% | 16490.49 | 0 | 16490.49 | 2024 | 2025 | < 250k
54.9353 | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 2008.42 | 0 | 2008.42 | 1117.5 | 0 | 1117.5 | 890.92 | 100% | 890.92 | 0 | 890.92 | 2024 | 2025 | < 250k
54.9354 | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 9571.2 | 0 | 9571.2 | 8230.83 | 0 | 8230.83 | 1340.37 | 100% | 1340.37 | 1923.43 | -583.06 | 2024 | 2025 | < 250k
54.9355 | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 2806.42 | 0 | 2806.42 | 1815.23 | 0 | 1815.23 | 991.19 | 100% | 991.19 | 0 | 991.19 | 2024 | 2025 | < 250k
54.9357 | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 1760.42 | 0 | 1760.42 | 889.66 | 0 | 889.66 | 870.76 | 100% | 870.76 | 0 | 870.76 | 2024 | 2025 | < 250k
54.936 | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1855.92 | 0 | 1855.92 | 1144.88 | 0 | 1144.88 | 711.04 | 100% | 711.04 | 0 | 711.04 | 2024 | 2025 | < 250k
54.9361 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 108668.35 | 0 | 108668.35 | 107074.87 | 0 | 107074.87 | 1593.48 | 100% | 1593.48 | 0 | 1593.48 | 2025 | 2025 | < 250k
54.9363 | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 1855.92 | 0 | 1855.92 | 777.55 | 0 | 777.55 | 1078.37 | 100% | 1078.37 | 0 | 1078.37 | 2024 | 2025 | < 250k
54.9365 | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 2216.42 | 0 | 2216.42 | 1263.33 | 0 | 1263.33 | 953.09 | 100% | 953.09 | 0 | 953.09 | 2024 | 2025 | < 250k
54.9367 | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 2540.42 | 0 | 2540.42 | 1602.33 | 0 | 1602.33 | 938.09 | 100% | 938.09 | 0 | 938.09 | 2024 | 2025 | < 250k
54.9368 | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 15697.91 | 0 | 15697.91 | 13653.62 | 0 | 13653.62 | 2044.29 | 100% | 2044.29 | 2044.29 | 0 | 2024 | 2025 | < 250k
54.937 | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 1760.42 | 0 | 1760.42 | 889.64 | 0 | 889.64 | 870.78 | 100% | 870.78 | 0 | 870.78 | 2024 | 2025 | < 250k
54.9374 | City of Santa Maria - WWTP Trickling Filter Repairs | 32962 | 0 | 32962 | 19986.45 | 0 | 19986.45 | 12975.55 | 100% | 12975.55 | 0 | 12975.55 | 2025 | 2025 | < 250k
54.9375 | City of Santa Maria - WWTP Clarifier Repairs | 8232.73 | 0 | 8232.73 | 4545.48 | 0 | 4545.48 | 3687.25 | 100% | 3687.25 | 0 | 3687.25 | 2025 | 2025 | < 250k
54.9379 | Semitropic Water Storage Dist. - Delta System Pipe Repair | 41679.77 | 0 | 41679.77 | 36111.95 | 0 | 36111.95 | 5567.82 | 100% | 5567.82 | 0 | 5567.82 | 2025 | 2025 | < 250k
54.938 | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 22446.19 | 0 | 22446.19 | 18064.72 | 0 | 18064.72 | 4381.47 | 100% | 4381.47 | 0 | 4381.47 | 2025 | 2025 | < 250k
54.9381 | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 58900 | 0 | 58900 | 28875.38 | 0 | 28875.38 | 30024.62 | 100% | 30024.62 | 0 | 30024.62 | 2025 | 2025 | < 250k
54.9382 | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 143799 | 0 | 143799 | 108690.45 | 0 | 108690.45 | 35108.55 | 100% | 35108.55 | 0 | 35108.55 | 2025 | 2025 | < 250k
54.9383 | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 17542.44 | 0 | 17542.44 | 15759.76 | 0 | 15759.76 | 1782.68 | 100% | 1782.68 | 0 | 1782.68 | 2025 | 2025 | < 250k
54.9384 | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 79531.98 | 0 | 79531.98 | 70340.57 | 0 | 70340.57 | 9191.41 | 100% | 9191.41 | 0 | 9191.41 | 2025 | 2025 | < 250k
54.9385 | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 102913.84 | 0 | 102913.84 | 98598.77 | 0 | 98598.77 | 4315.07 | 100% | 4315.07 | 0 | 4315.07 | 2025 | 2025 | < 250k
54.9386 | Kern Valley State Prison - Arsenic Pipe Leak Repair | 96086 | 0 | 96086 | 75784.74 | 0 | 75784.74 | 20301.26 | 100% | 20301.26 | 0 | 20301.26 | 2025 | 2025 | < 250k
54.9387 | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 22619.54 | 0 | 22619.54 | 19011.65 | 0 | 19011.65 | 3607.89 | 100% | 3607.89 | 0 | 3607.89 | 2025 | 2025 | < 250k
54.9388 | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 7454.07 | 0 | 7454.07 | 6535.41 | 0 | 6535.41 | 918.66 | 100% | 918.66 | 0 | 918.66 | 2025 | 2025 | < 250k
54.939 | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 101491.67 | 0 | 101491.67 | 96329.49 | 0 | 96329.49 | 5162.18 | 100% | 5162.18 | 0 | 5162.18 | 2025 | 2025 | < 250k
54.9392 | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 217648.89 | 0 | 217648.89 | 208346.69 | 0 | 208346.69 | 9302.2 | 100% | 9302.2 | 0 | 9302.2 | 2025 | 2025 | < 250k
54.9393 | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 31523.02 | 0 | 31523.02 | 27539.82 | 0 | 27539.82 | 3983.2 | 100% | 3983.2 | 0 | 3983.2 | 2025 | 2025 | < 250k
54.9394 | City of Arvin - Haven Drive Lateral Repair | 15966.99 | 0 | 15966.99 | 14039.55 | 0 | 14039.55 | 1927.44 | 100% | 1927.44 | 0 | 1927.44 | 2025 | 2025 | < 250k
54.9398 | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 14300 | 0 | 14300 | 8192.79 | 0 | 8192.79 | 6107.21 | 100% | 6107.21 | 0 | 6107.21 | 2025 | 2025 | < 250k
54.9399 | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 24775 | 0 | 24775 | 11291.59 | 0 | 11291.59 | 13483.41 | 100% | 13483.41 | 0 | 13483.41 | 2025 | 2025 | < 250k
54.94 | Arvin Edison Water Storage Dist. - FFPP Core Drilling | 800.69 | 0 | 800.69 | 771.32 | 0 | 771.32 | 29.37 | 100% | 29.37 | 0 | 29.37 | 2025 | 2025 | < 250k
54.9401 | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R | 247539.61 | 0 | 247539.61 | 236312.57 | 0 | 236312.57 | 11227.04 | 100% | 11227.04 | 0 | 11227.04 | 2025 | 2025 | < 250k
54.9407 | Semitropic Water Storage Dist. - North Plant Emergency Repair | 31296.85 | 0 | 31296.85 | 25667.34 | 0 | 25667.34 | 5629.51 | 100% | 5629.51 | 0 | 5629.51 | 2025 | 2025 | < 250k
54.9409 | Nipomo CSD Osage Emergency Waterline Repair | 20123.71 | 0 | 20123.71 | 17411.71 | 0 | 17411.71 | 2712 | 100% | 2712 | 0 | 2712 | 2025 | 2025 | < 250k
54.941 | SWID - Burbank St. Repair | 8241.55 | 0 | 8241.55 | 6965.65 | 0 | 6965.65 | 1275.9 | 100% | 1275.9 | 0 | 1275.9 | 2025 | 2025 | < 250k
55.1255 | City of Riverside - RWQCP Emergency Repair | 0 | 14160.81 | 14160.81 | 14160.81 | 0 | 14160.81 | 0 | 100% | 0 | 0 | 0 | 2025 | 0 | < 250k
55.1238 | Anaergia Technologies LLC - East County Package 5 | 34207.53 | 0 | 34207.53 | 32500.86 | 0 | 32500.86 | 1706.67 | 100% | 1706.67 | 8107.48 | -6400.81 | 2023 | 2025 | < 250k
55.125 | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 184557.17 | 0 | 184557.17 | 48293.94 | 0 | 48293.94 | 136263.23 | 100% | 136263.23 | 101052.1598 | 35211.0702 | 2024 | 2025 | < 250k
57.0007 | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | 153858.36 | 42390.04 | 196248.4 | 196248.4 | 0 | 196248.4 | 0 | 100% | 0 | 0 | 0 | 2025 | 0 | < 250k
56.1005 | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 135000 | 0 | 135000 | 51037.42 | 16987.58 | 68025 | 66975 | 75.03% | 50249.6318 | 14525.3272 | 35724.3046 | 2024 | 0 | < 250k
56.101 | Placer County Water Agency -PCWA Time & Material Contract | 49250 | 0 | 49250 | 36461.94 | 0 | 36461.94 | 12788.06 | 100% | 12788.06 | 0 | 12788.06 | 2025 | 0 | < 250k
56.1015 | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 160000 | 0 | 160000 | 142358.95 | 0 | 142358.95 | 17641.05 | 100% | 17641.05 | 29395.3303 | -11754.2803 | 2024 | 0 | < 250k
56.1017 | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 99118 | 3750 | 102868 | 95450.46 | 19444.54 | 114895 | -12027 | 83.08% | -12027 | 19016.5728 | -31043.5728 | 2024 | 0 | < 250k
56.1018 | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 50000 | 103913 | 153913 | 41991.15 | 29053.85 | 71045 | 82868 | 59.11% | 48979.1346 | 31982.9546 | 16996.18 | 2024 | 0 | < 250k
56.1032 | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 0 | 85000 | 85000 | 35024.34 | 47950.66 | 82975 | 2025 | 42.21% | 854.767 | 1044.5898 | -189.8229 | 2024 | 0 | < 250k
56.1037 | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 36491 | 0 | 36491 | 21674.2 | 0 | 21674.2 | 14816.8 | 100% | 14816.8 | 338.12 | 14478.68 | 2024 | 0 | < 250k
56.1038 | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 0 | 95000 | 95000 | 100049.89 | 17326.11 | 117376 | -22376 | 85.24% | -22376 | 6303.4542 | -28679.4542 | 2024 | 0 | < 250k
56.1046 | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 75120 | 2000 | 77120 | 77765.8 | 2190.2 | 79956 | -2836 | 97.26% | -2836 | 1603.6473 | -4439.6473 | 2024 | 0 | < 250k
56.1048 | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 187500 | 12500 | 200000 | 157916.15 | 3202.85 | 161119 | 38881 | 98.01% | 38108.093 | 34643.7429 | 3464.35 | 2024 | 0 | < 250k
56.1055 | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 120891 | 0 | 120891 | 78736.44 | 14111.56 | 92848 | 28043 | 84.8% | 23780.8675 | 2514.9896 | 21265.878 | 2024 | 0 | < 250k
56.1063 | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 10000 | 98000 | 108000 | 74040.41 | 23880.59 | 97921 | 10079 | 75.61% | 7620.973 | 2968.0708 | 4652.9021 | 2024 | 0 | < 250k
56.1073 | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 0 | 122210 | 122210 | 108855.81 | 5191.19 | 114047 | 8163 | 95.45% | 7791.4367 | 0 | 7791.4367 | 2025 | 0 | < 250k
56.1078 | City of Napa - On-Call Control Systems Integrator Services | 17050.24 | 8306.01 | 25356.25 | 25356.25 | 0 | 25356.25 | 0 | 100% | 0 | 0 | 0 | 2025 | 0 | < 250k
56.1081 | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 164416.35 | 15273.65 | 179690 | 156744.37 | 3040.63 | 159785 | 19905 | 98.1% | 19526.2176 | 0 | 19526.2176 | 2025 | 0 | < 250k
56.1085 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 0 | 80000 | 80000 | 1090.31 | 65864.69 | 66955 | 13045 | 1.628% | 0 | 0 | 0 | 2025 | 0 | < 250k
56.1087 | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 37977 | 11392 | 49369 | 39121.54 | 3904.46 | 43026 | 6343 | 90.93% | 5767.3948 | 0 | 5767.3948 | 2025 | 0 | < 250k
56.1088 | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 0 | 117985 | 117985 | 66827.49 | 18577.51 | 85405 | 32580 | 78.25% | 25493.1166 | 0 | 25493.1166 | 2025 | 0 | < 250k
56.1002 | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 185000 | 0 | 185000 | 114485.82 | 0 | 114485.82 | 70514.18 | 100% | 70514.18 | 50745.2395 | 19768.9405 | 2024 | 2025 | < 250k
56.1007 | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 16814 | 0 | 16814 | 19362.98 | 0 | 19362.98 | -2548.98 | 100% | -2548.98 | 3177.441 | -5726.421 | 2024 | 2025 | < 250k
56.1008 | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 55000 | 0 | 55000 | 30551.92 | 0 | 30551.92 | 24448.08 | 100% | 24448.08 | 23094.0224 | 1354.0576 | 2024 | 2025 | < 250k
56.1010.01 | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 9569 | 0 | 9569 | 7097.1 | 0 | 7097.1 | 2471.9 | 100% | 2471.9 | 619.6471 | 1852.2529 | 2024 | 2025 | < 250k
56.1016 | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 150064.25 | 0 | 150064.25 | 110083.62 | 0 | 110083.62 | 39980.63 | 100% | 39980.63 | 14743.36 | 25237.27 | 2024 | 2025 | < 250k
56.1019 | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 193845 | 0 | 193845 | 143764.58 | 0 | 143764.58 | 50080.42 | 100% | 50080.42 | 4594.7943 | 45485.6257 | 2024 | 2025 | < 250k
56.1021 | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 244760 | 0 | 244760 | 116752.52 | 0 | 116752.52 | 128007.48 | 100% | 128007.48 | 38878.5393 | 89128.9407 | 2024 | 2025 | < 250k
56.1022 | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 2024 | 2025 | < 250k
56.1023 | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 220390 | 0 | 220390 | 150504.73 | 0 | 150504.73 | 69885.27 | 100% | 69885.27 | 40095.3125 | 29789.9575 | 2024 | 2025 | < 250k
56.1041 | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 20016.78 | 0 | 20016.78 | 20016.78 | 0 | 20016.78 | 0 | 100% | 0 | 7002.238 | -7002.238 | 2024 | 2025 | < 250k
56.1051 | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 136875 | 0 | 136875 | 98718.18 | 0 | 98718.18 | 38156.82 | 100% | 38156.82 | 16220.5398 | 21936.2802 | 2024 | 2025 | < 250k
56.1052 | San Jose Water - Williams Back ATS Replacement | 8887 | 0 | 8887 | 6400.94 | 0 | 6400.94 | 2486.06 | 100% | 2486.06 | 369.0936 | 2116.9664 | 2024 | 2025 | < 250k
56.1053 | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 35000 | 0 | 35000 | 19964.78 | 0 | 19964.78 | 15035.22 | 100% | 15035.22 | 4187.3606 | 10847.8594 | 2024 | 2025 | < 250k
56.1054 | AIC - Riverside Public Works - Digester 5 Rehab | 37648.03 | 0 | 37648.03 | 37648.03 | 0 | 37648.03 | 0 | 100% | 0 | 0 | 0 | 2024 | 2025 | < 250k
56.1056 | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan | 98280.63 | 0 | 98280.63 | 98280.63 | 0 | 98280.63 | 0 | 100% | 0 | 20551.5757 | -20551.5757 | 2024 | 2025 | < 250k
56.1057 | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 2024 | 2025 | < 250k
56.1061 | San Jose Water - PLC System Assessment | 11269 | 0 | 11269 | 5582.66 | 0 | 5582.66 | 5686.34 | 100% | 5686.34 | 5163.8304 | 522.5096 | 2024 | 2025 | < 250k
56.1065 | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 226400.8 | 0 | 226400.8 | 192023.81 | 0 | 192023.81 | 34376.99 | 100% | 34376.99 | 0 | 34376.99 | 2024 | 2025 | < 250k
56.1069 | AIC - City of Brentwood - Brentwood, City of - On-Call Agreement | 2525 | 0 | 2525 | 3821.46 | 0 | 3821.46 | -1296.46 | 100% | -1296.46 | 0 | -1296.46 | 2025 | 2025 | < 250k
56.1071 | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 34000 | 0 | 34000 | 3596.56 | 0 | 3596.56 | 30403.44 | 100% | 30403.44 | 0 | 30403.44 | 2024 | 2025 | < 250k
56.1072 | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 65960 | 0 | 65960 | 41538.84 | 0 | 41538.84 | 24421.16 | 100% | 24421.16 | 0 | 24421.16 | 2024 | 2025 | < 250k
56.1074 | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 12650 | 0 | 12650 | 10641.86 | 0 | 10641.86 | 2008.14 | 100% | 2008.14 | 1239.6881 | 768.4519 | 2024 | 2025 | < 250k
56.1076 | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 19200 | 0 | 19200 | 11577.77 | 0 | 11577.77 | 7622.23 | 100% | 7622.23 | 0 | 7622.23 | 2024 | 2025 | < 250k
56.1079 | AIC - San Jose Water Co - Montevina PLC Upgrade | 29235.63 | 0 | 29235.63 | 29235.63 | 0 | 29235.63 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1082 | City of Clovis - Pump Station E New Pump 5 VFD Startup | 19800 | 0 | 19800 | 20583.04 | 0 | 20583.04 | -783.04 | 100% | -783.04 | 0 | -783.04 | 2025 | 2025 | < 250k
56.1084 | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 8000 | 0 | 8000 | 4228.13 | 0 | 4228.13 | 3771.87 | 100% | 3771.87 | 0 | 3771.87 | 2025 | 2025 | < 250k
56.1102 | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 19815.94 | 0 | 19815.94 | 19815.94 | 0 | 19815.94 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1103 | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 55855.24 | 0 | 55855.24 | 55855.24 | 0 | 55855.24 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1104 | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 9500.31 | 0 | 9500.31 | 9500.31 | 0 | 9500.31 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1105 | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 30502.53 | 0 | 30502.53 | 30502.53 | 0 | 30502.53 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1106 | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 54742.18 | 0 | 54742.18 | 54742.18 | 0 | 54742.18 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1107 | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 3429.06 | 0 | 3429.06 | 3429.06 | 0 | 3429.06 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1108 | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 20729.84 | 0 | 20729.84 | 20729.84 | 0 | 20729.84 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1109 | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 14772.26 | 0 | 14772.26 | 14772.26 | 0 | 14772.26 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.111 | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 4596.42 | 0 | 4596.42 | 4596.42 | 0 | 4596.42 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1111 | AIC - California American Water - Luzern Well Treatment Design | 17210.01 | 0 | 17210.01 | 17210.01 | 0 | 17210.01 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1112 | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 27241.58 | 0 | 27241.58 | 27241.58 | 0 | 27241.58 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1113 | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 49233.44 | 0 | 49233.44 | 49233.44 | 0 | 49233.44 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1115 | AIC - UC Davis - WWTP Annual Instrument Calibrations | 5895.77 | 0 | 5895.77 | 5895.77 | 0 | 5895.77 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1119 | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 22184.06 | 0 | 22184.06 | 22184.06 | 0 | 22184.06 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.112 | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 1045.63 | 0 | 1045.63 | 1045.63 | 0 | 1045.63 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1121 | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 22824.38 | 0 | 22824.38 | 22824.38 | 0 | 22824.38 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1122 | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 6289.38 | 0 | 6289.38 | 6289.38 | 0 | 6289.38 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1123 | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 3772.82 | 0 | 3772.82 | 3772.82 | 0 | 3772.82 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1124 | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 28950 | 0 | 28950 | 28950 | 0 | 28950 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1125 | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 14229.38 | 0 | 14229.38 | 14229.38 | 0 | 14229.38 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1126 | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 9526.88 | 0 | 9526.88 | 9526.88 | 0 | 9526.88 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1127 | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 6519.07 | 0 | 6519.07 | 6519.07 | 0 | 6519.07 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1128 | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 4793.13 | 0 | 4793.13 | 4793.13 | 0 | 4793.13 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1129 | AIC - RMCSD - VEEAM SFTWR | 133.75 | 0 | 133.75 | 133.75 | 0 | 133.75 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1131 | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 2388.75 | 0 | 2388.75 | 2388.75 | 0 | 2388.75 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1132 | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 585 | 0 | 585 | 585 | 0 | 585 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1133 | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 2827.5 | 0 | 2827.5 | 2827.5 | 0 | 2827.5 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1134 | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 965.51 | 0 | 965.51 | 965.51 | 0 | 965.51 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1135 | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 112.5 | 0 | 112.5 | 112.5 | 0 | 112.5 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
56.1141 | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 2827.5 | 0 | 2827.5 | 2827.5 | 0 | 2827.5 | 0 | 100% | 0 | 0 | 0 | 2025 | 2025 | < 250k
Totals |  | 7420887.21 | 1359507.43 | 8780394.64 | 6642719.58 | 557856.16 | 7200575.74 | 1579818.9 |  | 1462418.6919 | 618142.5977 | 844276.0942
Overhead jobs (Bidding Jobs)
51.1156 | Rocklin Overhead 2025 | 0 | 0 | 0 | 1426058.69 | 0 | 1426058.69 | -1426058.69 | 100% | -1426058.69 | 0 | -1426058.69 | 2025 | 2025 | OH
51.1157 | Rocklin Estimating 2025 | 0 | 0 | 0 | 613546.52 | 0 | 613546.52 | -613546.52 | 100% | -613546.52 | 0 | -613546.52 | 2025 | 2025 | OH
52.8682 | Fresno Overhead 2025 | 0 | 0 | 0 | 1121157.1 | 0 | 1121157.1 | -1121157.1 | 100% | -1121157.1 | 0 | -1121157.1 | 2025 | 2025 | OH
52.8683 | Fresno Estimating 2025 | 0 | 0 | 0 | 415452.52 | 0 | 415452.52 | -415452.52 | 100% | -415452.52 | 0 | -415452.52 | 2025 | 2025 | OH
53.2005 | East Bay Overhead 2025 | 0 | 0 | 0 | 279281.96 | 0 | 279281.96 | -279281.96 | 100% | -279281.96 | 0 | -279281.96 | 2025 | 2025 | OH
53.2006 | East Bay Estimating 2026 | 0 | 0 | 0 | 304986.32 | 0 | 304986.32 | -304986.32 | 100% | -304986.32 | 0 | -304986.32 | 2025 | 2025 | OH
54.9371 | Bakersfield Overhead 2025 | 0 | 0 | 0 | 1267652.77 | 0 | 1267652.77 | -1267652.77 | 100% | -1267652.77 | 0 | -1267652.77 | 2025 | 2025 | OH
54.9372 | Bakersfield Estimating 2025 | 0 | 0 | 0 | 588792.6 | 0 | 588792.6 | -588792.6 | 100% | -588792.6 | 0 | -588792.6 | 2025 | 2025 | OH
55.1252 | Murrieta Overhead 2025 | 0 | 0 | 0 | 1958826.45 | 0 | 1958826.45 | -1958826.45 | 100% | -1958826.45 | 0 | -1958826.45 | 2025 | 2025 | OH
55.1253 | Murrieta Estimating 2025 | 0 | 0 | 0 | 475814.03 | 0 | 475814.03 | -475814.03 | 100% | -475814.03 | 0 | -475814.03 | 2025 | 2025 | OH
56.1077 | System Integration Overhead 2025 | 0 | 0 | 0 | 4370841.4 | 0 | 4370841.4 | -4370841.4 | 100% | -4370841.4 | 0 | -4370841.4 | 2025 | 2025 | OH
56.113 | System Integration Division Estimating 2025 | 0 | 0 | 0 | 267.5 | 0 | 267.5 | -267.5 | 100% | -267.5 | 0 | -267.5 | 2025 | 2025 | OH
57.0005 | San Diego Overhead 2025 | 0 | 0 | 0 | 92874.26 | 0 | 92874.26 | -92874.26 | 100% | -92874.26 | 0 | -92874.26 | 2025 | 2025 | OH
57.0006 | San Diego Estimating 2025 | 0 | 0 | 0 | 13743.76 | 0 | 13743.76 | -13743.76 | 100% | -13743.76 | 0 | -13743.76 | 2025 | 2025 | OH
58.0004 | Los Angeles Overhead 2025 | 0 | 0 | 0 | 147282.12 | 0 | 147282.12 | -147282.12 | 100% | -147282.12 | 0 | -147282.12 | 2025 | 2025 | OH
58.0005 | Los Angeles Estimating 2025 | 0 | 0 | 0 | 135037.09 | 0 | 135037.09 | -135037.09 | 100% | -135037.09 | 0 | -135037.09 | 2025 | 2025 | OH
50-Jobs
50.0541 | W.M. Lyles Co. - General Overhead | 0 | 0 | 0 | 3642039.89 | 0 | 3642039.89 | -3642039.89 | 100% | -3642039.89 | 0 | -3642039.89 | 50 | 50 | 0
50.0542 | W.M. Lyles Co. - General Estimating | 0 | 0 | 0 | 100487.45 | 0 | 100487.45 | -100487.45 | 100% | -100487.45 | 0 | -100487.45 | 50 | 50 | 0
50.0543 | American Paving | 7051.01 | 0 | 7051.01 | 7051.01 | 0 | 7051.01 | 0 | 100% | 0 | 0 | 0 | 50 | 50 | 0
50.0544 | Lyles Services Co. | 13555.8 | 0 | 13555.8 | 13555.8 | 0 | 13555.8 | 0 | 100% | 0 | 0 | 0 | 50 | 50 | 0
50.0545 | New England Sheet Metal and Mechanical Co. | 2226.16 | 0 | 2226.16 | 2226.16 | 0 | 2226.16 | 0 | 100% | 0 | 0 | 0 | 50 | 50 | 0
50.0546 | Lyles Utility Construction, LLC | 11256.72 | 0 | 11256.72 | 10468.06 | 0 | 10468.06 | 788.66 | 100% | 788.66 | 0 | 788.66 | 50 | 50 | 0
50.0551 | Advanced Integration & Controls | 5457.42 | 0 | 5457.42 | 5457.42 | 0 | 5457.42 | 0 | 100% | 0 | 0 | 0 | 50 | 50 | 0
Totals |  | 39547.11 | 0 | 39547.11 | 16992900.88 | 0 | 16992900.88 | -16953353.77 |  | -16953353.77 | 0 | -16953353.77 |  |  |  | This is total of Overhead Jobs (Bidding Jobs) and W-Jobs
Grand Totals |  | 1260032177.67 | 751698755.74 | 2011730933.41 | 1189375151.08 | 693304584.16 | 1882679735.24 | 129051198.17 |  | 70178120.2972 | 52896373.2393 | 17281747.0579
GAAP Totals |  | 1260032177.67 | 751698755.74 | 2011730933.41 | 1189375151.08 | 693304584.16 | 1882679735.24 | 129051198.17 |  | 70178120.2972 | 52896373.2393 | 17281747.0579
Variance Check |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
[11 empty] | OH Jobs | -13211615.09

## GAAP WIP
W.M. Lyles Co.
WORK IN PROCESS-GAAP BASIS
For the Month Period Ended 12/31/2025
|  | AMOUNT | REMAINING | TOTAL | COSTS | ESTIMATED | TOTAL | TOTAL | % OF |  | OVER
|  | BILLED | TO BE | ESTIMATED | INCURED | COSTS TO | ESTIMATED | ESTIMATED | COMPLETION | PROFIT / | (UNDER)
JOB |  | TO DATE | BILLED | CONTRACT | TO DATE | COMPLETE | COSTS | PROFIT | COST/COST | LOSS | BILLIING
51.1108 | City of Stockton - RWCF Phase 2A/2B | 94045647.86 | 0 | 94045647.86 | 89805617.8 | 0 | 89805617.8 | 4240030.06 | 100% | 4240030.06 | 0 |  |  |  | -80728.85 | 80728.85
51.1129 | Union Sanit. Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin | 96918206.9 | 29565373.94 | 126483580.84 | 87315159.22 | 27918421.62 | 115233580.84 | 11250000 | 75.77% | 8524386.1561 | 1078661.5239 |  |  |  | -534407 | 534407
51.1137 | CA Water Service Co. - Bear Gulch Pump Station 18 | 1121900.01 | 190251.45 | 1312151.46 | 1042229.29 | 156282.17 | 1198511.46 | 113640 | 86.96% | 98821.6971 | -19150.9771 |  |  |  | 0 | 0
51.1144 | Silicon Valley Clean Water - FEP Improvements Project | 9667725.77 | 5301840.23 | 14969566 | 8406760.8 | 5432856.2 | 13839617 | 1129949 | 60.74% | 686378.1678 | 574586.8022 |  |  |  | 0 | 0
51.1146 | National Carbon Technologies, LLC - Aymium Williams Production Facility | 60980234 | 0 | 60980234 | 40950686.5 | 3246167.53 | 44196854.03 | 16783379.97 | 92.66% | 15550675.419 | 4478872.081 |  |  |  | -173716.6183 | 173716.6183
51.1151 | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 5009265.21 | 5648934.79 | 10658200 | 4923435.18 | 5155916.82 | 10079352 | 578848 | 48.85% | 282748.3956 | -196918.3656 |  |  |  | 0 | 0
51.1152 | Mozingo Construction Inc - ElD Sly Park Intertie Project | 15610649.01 | 4363840.33 | 19974489.34 | 13474808.54 | 5154139.8 | 18628948.34 | 1345541 | 72.33% | 973265.2121 | 1162575.2579 |  |  |  | 0 | 0
51.1153 | Linda County Water Dist. - Aeration Blower Replacement | 549548.83 | 13275.85 | 562824.68 | 334550.81 | 119969.87 | 454520.68 | 108304 | 73.61% | 79717.365 | 135280.655 |  |  |  | 0 | 0
51.1154 | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 13340008 | 23827 | 13363835 | 11872342.6 | 616492.4 | 12488835 | 875000 | 95.06% | 831806.952 | 635858.448 |  |  |  | 0 | 0
51.1158 | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 32282 | 72164 | 104446 | 56960.69 | 47485.31 | 104446 | 0 | 54.54% | 0 | -24678.69 |  |  |  | 0 | 0
51.1159 | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 732995 | 466005 | 1199000 | 790051.12 | 289188.88 | 1079240 | 119760 | 73.2% | 87669.5843 | -144725.7043 |  |  |  | 0 | 0
51.116 | City of Galt Public Works - Industrial WWTP Expansion | 223725 | 1533275 | 1757000 | 250518.05 | 1439481.95 | 1690000 | 67000 | 14.82% | 9931.7807 | -36724.8307 |  |  |  | 9931.7807 | -9931.7807
51.1161 | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | 745707.2 | 10102892.25 | 10848599.45 | 601852.17 | 9659400.28 | 10261252.45 | 587347 | 5.865% | 0 | 143855.03 |  |  |  | 0 | 0
51.1162 | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project | 0 | 6029750 | 6029750 | 85941.38 | 5759321.62 | 5845263 | 184487 | 1.47% | 0 | -85941.38 |  |  |  | 0 | 0
51.1164 | CA Water Service Co. - Stockton Roofing | 0 | 387260 | 387260 | 4363.25 | 379023.75 | 383387 | 3873 | 1.138% | 0 | -4363.25 |  |  |  | 0 | 0
51.1165 | City of Yuba City - WTP Aquifer Storage and Recovery Well No. 3 | 0 | 5304500 | 5304500 | 23330.33 | 4863112.67 | 4886443 | 418057 | 0.4775% | 0 | -23330.33 |  |  |  | #REF! | #REF!
[15 empty] | 0 | 0
52.8563 | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 1134038.13 | 0 | 1134038.13 | 859077.05 | 0 | 859077.05 | 274961.08 | 100% | 274961.08 | 0 |  |  |  | -18424.16 | 18424.16
52.8566 | City of Visalia - Water Reclamation Facility RPGS SCR System | 1242053 | 17345 | 1259398 | 1023821.05 | 5576.95 | 1029398 | 230000 | 99.46% | 228753.9334 | -10521.9834 |  |  |  | 0 | 0
52.8586 | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 12611349 | 0 | 12611349 | 10565460.74 | 95888.26 | 10661349 | 1950000 | 99.1% | 1932461.6841 | 113426.5759 |  |  |  | 0 | 0
52.8634 | City of Huron - Water Treatment Plant Imp. Phase 2 | 12576768.04 | 1315954.7 | 13892722.74 | 11707058.24 | 1483664.5 | 13190722.74 | 702000 | 88.75% | 623040.5298 | 246669.2702 |  |  |  | 0 | 0
52.8636 | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 3065635.6 | 590476.4 | 3656112 | 3367047.36 | 14064.64 | 3381112 | 275000 | 99.58% | 273856.0639 | -575267.8239 |  |  |  | -1131.7149 | 1131.7149
52.8637 | Root Creek Water Dist. - Groundwater Blending & Arsenic | 26148625 | 115952.65 | 26264577.65 | 24374299.03 | 240278.62 | 24614577.65 | 1650000 | 99.02% | 1633893.2957 | 140432.6743 |  |  |  | 0 | 0
52.864 | City of Dos Palos - WTP Replacement Project | 34176041.86 | 4470321.3 | 38646363.16 | 32158781.48 | 4614258.68 | 36773040.16 | 1873323 | 87.45% | 1638259.571 | 379000.809 |  |  |  | 0 | 0
52.8668 | California Water Service Co. - Cal Water - Salinas Station 57 | 349622.76 | 62228.24 | 411851 | 357710.67 | 19285.33 | 376996 | 34855 | 94.88% | 33071.9833 | -41159.8933 |  |  |  | 0 | 0
52.8678 | City of Chowcilla - Well 15 & Generator Improvement Projects | 1142122 | 98199 | 1240321 | 926007.31 | 236313.69 | 1162321 | 78000 | 79.67% | 62141.6719 | 153973.0181 |  |  |  | 0 | 0
52.8687 | California Water Service Co. - Salinas Station 205 | 827811.95 | 50142.05 | 877954 | 740629.43 | 50142.05 | 790771.48 | 87182.52 | 93.66% | 81654.3612 | 5528.1588 |  |  |  | 0 | 0
52.8692 | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 55135.37 | 0 | 55135.37 | 49682.49 | 0 | 49682.49 | 5452.88 | 100% | 5452.88 | 0 |  |  |  | 0 | 0
52.8697 | City of Tulare - Industrial WWTP Dewatering Improvements Pro | 1069317 | 318683 | 1388000 | 772187.73 | 553294.27 | 1325482 | 62518 | 58.26% | 36421.1906 | 260708.0794 |  |  | 2025 book to tax diff | 0 | 0
52.8698 | California Water Service Co. - Tesoro Viejo RWSP Liner Repair | 0 | 22713 | 22713 | 15264 | 864 | 16128 | 6585 | 94.64% | 6232.2321 | -21496.2321 | sum of | (1) | 5553.6984 | 0 | 0
52.8704 | City of Visalia - Solids Handling Improvements Project | 1037950 | 12706050 | 13744000 | 820988.3 | 12670138.7 | 13491127 | 252873 | 6.085% | 0 | 216961.7 |  |  |  | #REF! | #REF!
52.8705 | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | 261232 | 513768 | 775000 | 285425.72 | 433834.28 | 719260 | 55740 | 39.68% | 22119.4417 | -46313.1617 |  |  |  | 22119.4417 | -263274.8617
52.8707 | County of Fresno - Westside Water Tank and Pump Station | 913135 | 2780065 | 3693200 | 1012057.14 | 2449519.86 | 3461577 | 231623 | 29.24% | 67719.3403 | -166641.4803 |  |  |  | 45599.8986 | -120328.3186
52.8708 | County of Fresno - CSA 44A Wastewater Improvements | 0 | 363833 | 363833 | 7682.19 | 326074.81 | 333757 | 30076 | 2.302% | 0 | -7682.19 |  |  |  | -67719.3403 | 158959.2903
52.8711 | California Water Service Co. - Tesoro Viejo ARV Replacement | 0 | 6860 | 6860 | 4568.81 | 1746.19 | 6315 | 545 | 72.35% | 394.2995 | -4963.1095 |  |  |  | 394.2995 | 2719.0805
52.8713 | City of Visalia - Remove & Replace Chain and Flight Mechanic | 0 | 218842 | 218842 | 927.5 | 189511.5 | 190439 | 28403 | 0.487% | 0 | -927.5 | 100% of loss is recognized for books, not for tax. |  |  | -394.2995 | 4035.6095
52.8714 | New England Sheet Metal and Mechanical Co. - VCH Digging Water Line T&M | 5084.94 | 0 | 5084.94 | 4465.61 | 0 | 4465.61 | 619.33 | 100% | 619.33 | 0 | For tax, need to make an adjustment by taking |  |  | 619.33 | 927.5
[12 empty] | actual %age complete and tax difference as income. |  |  | 0 | 0
53.2007 | Union Sanitary Dist. - Phase 1B Secondary Clarifiers | 0 | 324530134 | 324530134 | 404852.16 | 291125281.84 | 291530134 | 33000000 | 0.1389% | 0 | -404852.16 |  |  |  | #REF! | #REF!
54.9033 | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 118278.58 | 0 | 118278.58 | 104550.27 | 0 | 104550.27 | 13728.31 | 100% | 13728.31 | 0 |  |  |  | 0 | 0
54.9135 | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 9470658.62 | 0 | 9470658.62 | 9050951.86 | 0 | 9050951.86 | 419706.76 | 100% | 419706.76 | 0 |  |  |  | 0 | 0
54.9257 | City of Guadalupe - Highway 1 Lift Station | 890983 | 580345 | 1471328 | 762211.05 | 664116.95 | 1426328 | 45000 | 53.44% | 24047.4121 | 104724.5379 |  |  |  | 0 | 0
54.9268 | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 907298 | 42269.99 | 949567.99 | 844648.28 | 39919.71 | 884567.99 | 65000 | 95.49% | 62066.612 | 583.108 |  |  |  | -2933.388 | 2933.388
54.9269 | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 625819.17 | 0 | 625819.17 | 549817.74 | 0 | 549817.74 | 76001.43 | 100% | 76001.43 | 0 |  |  |  | 41752.38 | -41752.38
54.9285 | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 427226 | 34796 | 462022 | 312939.77 | 74082.23 | 387022 | 75000 | 80.86% | 60643.7948 | 53642.4352 |  |  |  | 0 | 0
54.9313 | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 7886885 | 0.04 | 7886885.04 | 6449205.22 | 427679.82 | 6876885.04 | 1010000 | 93.78% | 947187.1689 | 490492.6111 |  |  |  | 0 | 0
54.933 | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 324900 | 0 | 324900 | 306221.41 | 1419.59 | 307641 | 17259 | 99.54% | 17179.3594 | 1499.2306 |  |  |  | 0 | 0
54.9336 | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 14176592.91 | 11014583.73 | 25191176.64 | 12340864.27 | 10930312.37 | 23271176.64 | 1920000 | 53.03% | 1018189.1429 | 817539.4971 |  |  |  | 0 | 0
54.9337 | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 520441.66 | 3584406.34 | 4104848 | 1509066.73 | 2435781.27 | 3944848 | 160000 | 38.25% | 61206.5856 | -1049831.6556 |  |  |  | 0 | 0
54.9343 | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 3954560 | 2926740 | 6881300 | 3415344.08 | 2565955.92 | 5981300 | 900000 | 57.1% | 513903.2772 | 25312.6428 |  |  |  | 0 | 0
54.9356 | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 685017 | 613313 | 1298330 | 775780.75 | 137549.25 | 913330 | 385000 | 84.94% | 327018.2615 | -417782.0115 |  |  |  | 0 | 0
54.9366 | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1160831 | 69300 | 1230131 | 923220.5 | 156910.5 | 1080131 | 150000 | 85.47% | 128209.5181 | 109400.9819 |  |  |  | 0 | 0
54.9369 | California Water Service Co. - PFAS Treatment Program Project | 2927422.95 | 25623201.75 | 28550624.7 | 2787466.66 | 23392315.04 | 26179781.7 | 2370843 | 10.65% | 252433.1904 | -112476.9004 |  |  |  | 252433.1904 | -252433.1904
54.9373 | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 0 | 1524766 | 1524766 | 50303.97 | 1343022.03 | 1393326 | 131440 | 3.61% | 0 | -50303.97 |  |  |  | 0 | 0
54.9389 | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 291620 | 8160 | 299780 | 311891.85 | 2888.15 | 314780 | -15000 | 99.08% | -15000 | -5271.85 | -14862.3729 | 137.6271 | (1) | 0 | 0
54.9391 | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 532604.57 | 0 | 532604.57 | 512057.34 | 0 | 512057.34 | 20547.23 | 100% | 20547.23 | 0 |  |  |  | 0 | 0
54.9395 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 1374448.17 | 421204.49 | 1795652.66 | 1349601.92 | 344050.74 | 1693652.66 | 102000 | 79.69% | 81279.5912 | -56433.3412 |  |  |  | 0 | 0
54.9396 | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | 0 | 157746.09 | 157746.09 | 157746.09 | 0 | 157746.09 | 0 | 100% | 0 | -157746.09 |  |  |  | 0 | 0
54.9397 | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 1033150.21 | 2657494.79 | 3690645 | 1035065.41 | 2355579.59 | 3390645 | 300000 | 30.53% | 91581.2841 | -93496.4841 |  |  |  | 0 | 0
54.9403 | Lost Hills Utility Dist. - WTP Improvements | 140100 | 241500 | 381600 | 129004.89 | 209096.11 | 338101 | 43499 | 38.16% | 16597.3591 | -5502.2491 |  |  |  | 0 | 0
54.9404 | Cawelo Water Dist. - Reuse of Produced Water | 1746890 | 1973110 | 3720000 | 1939024.63 | 1646367.37 | 3585392 | 134608 | 54.08% | 72797.6822 | -264932.3122 |  |  |  | 0 | 0
54.9405 | Semitropic Water Storage Dist. - Pump Platform Replacement Project | 746125 | 195875 | 942000 | 577796.16 | 234203.84 | 812000 | 130000 | 71.16% | 92504.3113 | 75824.5287 |  |  |  | 0 | 0
54.9406 | California Water Service Co. - Emergency PACL leak repair | 0 | 1120.65 | 1120.65 | 1120.65 | 0 | 1120.65 | 0 | 100% | 0 | -1120.65 |  |  |  | 0 | 0
54.9408 | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line | 0 | 3777777 | 3777777 | 41652.43 | 3495532.57 | 3537185 | 240592 | 1.178% | 0 | -41652.43 |  |  |  | 0 | 0
54.9411 | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation | 103000 | 300 | 103300 | 71370.85 | 6929.15 | 78300 | 25000 | 91.15% | 22787.6277 | 8841.5223 |  |  |  | 0 | 0
54.9412 | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork | 116752.04 | 0 | 116752.04 | 115708.88 | 0 | 115708.88 | 1043.16 | 100% | 1043.16 | 0 |  |  |  | 0 | 0
54.9413 | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork | 149366.83 | 0 | 149366.83 | 132138.74 | 0 | 132138.74 | 17228.09 | 100% | 17228.09 | 0 |  |  |  | 0 | 0
54.9414 | Cawelo Water Dist. - Cawelo Diversion Structure Rehab | 0 | 337485.68 | 337485.68 | 337485.68 | 0 | 337485.68 | 0 | 100% | 0 | -337485.68 |  |  |  | -19929.7763 | 19929.7763
54.9416 | California Water Service Co. - BK 147 Station Improvements | 0 | 1260000 | 1260000 | 7257.82 | 1125140.18 | 1132398 | 127602 | 0.6409% | 0 | -7257.82 |  |  |  | 0 | 0
54.9417 | County of Santa Barbara-Public Works - Laguna WWTP WAS Pipe Modifications | 0 | 48439 | 48439 | 2299.41 | 40593.59 | 42893 | 5546 | 5.361% | 0 | -2299.41 |  |  |  | 0 | 0
54.9418 | GenerateUpcycle - Organics Waste Processing Facility | 0 | 15739 | 15739 | 15739 | 0 | 15739 | 0 | 100% | 0 | -15739 |  |  |  | 0 | 0
54.9421 | Nipomo Community Service Dist. - Tefft Emergency Pipe Repair | 0 | 3703.18 | 3703.18 | 3703.18 | 0 | 3703.18 | 0 | 100% | 0 | -3703.18 |  |  |  | 0 | 0
[15 empty] | 0 | 0
55.109 | LA Dept of Water and Power - Silverlake | 5235272.36 | 0 | 5235272.36 | 3834064.05 | 0 | 3834064.05 | 1401208.31 | 100% | 1401208.31 | 0 |  |  |  | -73431.7092 | 73431.7092
55.1191 | Inland Empire Utilities - IEUA RP-5 Liquids Exp. & Solids Treat. Facility | 296634984.51 | 44808149.2 | 341443133.71 | 299179624.84 | 38553010.87 | 337732635.71 | 3710498 | 88.58% | 3286935.529 | -5831575.859 |  |  |  | -423562.471 | 423562.471
55.1192 | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6645760.51 | 6043.02 | 6651803.53 | 6393992.69 | 7810.84 | 6401803.53 | 250000 | 99.88% | 249694.975 | 2072.845 |  |  |  | -305.025 | 305.025
55.12 | East County Advanced Water Purification Project - Package 1 | 197175877 | 0 | 197175877 | 189971137.49 | 0 | 189971137.49 | 7204739.51 | 100% | 7204739.51 | 0 |  |  |  | -575254.77 | 575254.77
55.1202 | LA County Sanitation District - Oxygen Generation Project | 10912272.58 | 5483779 | 16396051.58 | 9590124.35 | 5630518.23 | 15220642.58 | 1175409 | 63.01% | 740594.1249 | 581554.1051 |  |  |  | 0 | 0
55.1204 | East County Advanced Water Purification Project - Package 3 | 57142227 | 0 | 57142227 | 55213329.21 | 0 | 55213329.21 | 1928897.79 | 100% | 1928897.79 | 0 |  |  |  | -433141.22 | 433141.22
55.1227 | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 41483406.39 | 20800 | 41504206.39 | 36953022.96 | 201183.43 | 37154206.39 | 4350000 | 99.46% | 4326445.5224 | 203937.9076 |  |  |  | 0 | 0
55.1233 | Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 123617 | 2460.16 | 126077.16 | 126077.16 | 0 | 126077.16 | 0 | 100% | 0 | -2460.16 |  |  |  | -8429 | 8429
55.1248 | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 4861991.81 | 897310 | 5759301.81 | 3621770.22 | 1312531.59 | 4934301.81 | 825000 | 73.4% | 605548.778 | 634672.812 |  |  |  | 0 | 0
55.1249 | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 15047042.84 | 132478070.16 | 147525113 | 15046313.77 | 124657591.23 | 139703905 | 7821208 | 10.77% | 842355.4777 | -841626.4077 |  |  |  | 842355.4777 | -842355.4777
55.1254 | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 158952.89 | 0 | 158952.89 | 156561.66 | 0 | 156561.66 | 2391.23 | 100% | 2391.23 | 0
55.1255 | City of Riverside - RWQCP Emergency Repair | 0 | 14160.81 | 14160.81 | 14160.81 | 0 | 14160.81 | 0 | 100% | 0 | -14160.81
55.1256 | Anaergia Technologies LLC - City of Riverside - OPS | 101150 | 2786950 | 2888100 | 94989.88 | 2618110.12 | 2713100 | 175000 | 3.501% | 0 | 6160.12 |  |  |  | #REF! | #REF!
[15 empty] | 0 | 0
57.0003 | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 6863233.25 | 31302186.25 | 38165419.5 | 6316909.13 | 29441424.37 | 35758333.5 | 2407086 | 17.67% | 425225.1725 | 121098.9475 |  |  |  | 301303 | -301303
57.0004 | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 900072.76 | 39206151.87 | 40106224.63 | 750298.86 | 37146068.77 | 37896367.63 | 2209857 | 1.98% | 0 | 149773.9 |  |  |  | 0 | 0
57.0007 | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | 153858.36 | 42390.04 | 196248.4 | 196248.4 | 0 | 196248.4 | 0 | 100% | 0 | -42390.04
57.0008 | Imperial Irrigation Dist. - El Centro Generating Station WWTP | 266758 | 2609289 | 2876047 | 262382.86 | 2481599.14 | 2743982 | 132065 | 9.562% | 0 | 4375.14
[15 empty] | 0 | 0
58.0003 | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 11889201.76 | 10635987.24 | 22525189 | 11034781.79 | 10182392.21 | 21217174 | 1308015 | 52.01% | 680281.9312 | 174138.0388 |  |  |  | 0 | 0
[15 empty] | 0 | 0
56.1004 | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 371550 | 1875 | 373425 | 236373.73 | 33466.27 | 269840 | 103585 | 87.6% | 90738.1145 | 44438.1555 |  |  |  | 0 | 0
56.1005 | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 135000 | 0 | 135000 | 51037.42 | 16987.58 | 68025 | 66975 | 75.03% | 50249.6318 | 33712.9482 |  |  |  | 0 | 0
56.101 | Placer County Water Agency -PCWA Time & Material Contract | 49250 | 0 | 49250 | 36461.94 | 0 | 36461.94 | 12788.06 | 100% | 12788.06 | 0 |  |  |  | 0 | 0
56.1015 | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 160000 | 0 | 160000 | 142358.95 | 0 | 142358.95 | 17641.05 | 100% | 17641.05 | 0 |  |  |  | -881.2819 | 881.2819
56.1017 | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 99118 | 3750 | 102868 | 95450.46 | 19444.54 | 114895 | -12027 | 83.08% | -12027 | 15694.54 | -9991.5809 | 2035.4191 | (1) | 0 | 0
56.1018 | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 50000 | 103913 | 153913 | 41991.15 | 29053.85 | 71045 | 82868 | 59.11% | 48979.1346 | -40970.2846 |  |  |  | 0 | 0
56.1032 | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 0 | 85000 | 85000 | 35024.34 | 47950.66 | 82975 | 2025 | 42.21% | 854.767 | -35879.107 |  |  |  | 0 | 0
56.1036 | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 48000 | 228000 | 276000 | 107051.95 | 101972.05 | 209024 | 66976 | 51.22% | 34301.8572 | -93353.8072 |  |  |  | 0 | 0
56.1037 | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 36491 | 0 | 36491 | 21674.2 | 0 | 21674.2 | 14816.8 | 100% | 14816.8 | 0 |  |  |  | 0 | 0
56.1038 | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 0 | 95000 | 95000 | 100049.89 | 17326.11 | 117376 | -22376 | 85.24% | -22376 | -77673.89 | -19073.0331 | 3302.9669 | (1) | 0 | 0
56.1039 | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 330000 | 45000 | 375000 | 324049.23 | 8234.77 | 332284 | 42716 | 97.52% | 41657.3982 | -35706.6282 |  |  |  | 0 | 0
56.1042 | Trabuco Canyon Water Dist. - SCADA Integration Services | 217715 | 59850 | 277565 | 172683.27 | 45604.73 | 218288 | 59277 | 79.11% | 46892.8489 | -1861.1189 |  |  |  | 0 | 0
56.1043 | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 0 | 336610 | 336610 | 214994.3 | 96396.7 | 311391 | 25219 | 69.04% | 17412.0037 | -232406.3037 |  |  |  | 0 | 0
56.1046 | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 75120 | 2000 | 77120 | 77765.8 | 2190.2 | 79956 | -2836 | 97.26% | -2836 | 190.2 | -2758.3147 | 77.6853 | (1) | 0 | 0
56.1047 | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 1905218.25 | 489539.75 | 2394758 | 1602869.63 | 437685.37 | 2040555 | 354203 | 78.55% | 278228.8307 | 24119.7893 |  |  |  | 0 | 0
56.1048 | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 187500 | 12500 | 200000 | 157916.15 | 3202.85 | 161119 | 38881 | 98.01% | 38108.093 | -8524.243 |  |  |  | 0 | 0
56.1049 | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 291725 | 17000 | 308725 | 214423.06 | 34449.94 | 248873 | 59852 | 86.16% | 51567.0603 | 25734.8797 |  |  |  | 0 | 0
56.105 | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 675979.5 | 3116579.5 | 3792559 | 925847.53 | 2439719.47 | 3365567 | 426992 | 27.51% | 117462.9679 | -367330.9979 |  |  |  | 0 | 0
56.1055 | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 120891 | 0 | 120891 | 78736.44 | 14111.56 | 92848 | 28043 | 84.8% | 23780.8675 | 18373.6925 |  |  |  | 0 | 0
56.1059 | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 0 | 399389 | 399389 | 235841.92 | 93364.08 | 329206 | 70183 | 71.64% | 50278.8329 | -286120.7529 |  |  |  | 0 | 0
56.106 | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 0 | 404663 | 404663 | 145563.36 | 176927.64 | 322491 | 82172 | 45.14% | 37090.1278 | -182653.4878 |  |  |  | 0 | 0
56.1063 | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 10000 | 98000 | 108000 | 74040.41 | 23880.59 | 97921 | 10079 | 75.61% | 7620.973 | -71661.383 |  |  |  | 0 | 0
56.1066 | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 570000 | 25000 | 595000 | 476030.06 | 55459.94 | 531490 | 63510 | 89.57% | 56882.856 | 37087.084 |  |  |  | 0 | 0
56.1067 | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 217000 | 261000 | 478000 | 104751.99 | 311126.01 | 415878 | 62122 | 25.19% | 15647.3849 | 96600.6251 |  |  |  | 0 | 0
56.1073 | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 0 | 122210 | 122210 | 108855.81 | 5191.19 | 114047 | 8163 | 95.45% | 7791.4367 | -116647.2467 |  |  |  | 0 | 0
56.1075 | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 0 | 27665.92 | 27665.92 | 27665.92 | 0 | 27665.92 | 0 | 100% | 0 | -27665.92 |  |  |  | 0 | 0
56.1078 | City of Napa - On-Call Control Systems Integrator Services | 17050.24 | 8306.01 | 25356.25 | 25356.25 | 0 | 25356.25 | 0 | 100% | 0 | -8306.01 |  |  |  | 0 | 0
56.1081 | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 164416.35 | 15273.65 | 179690 | 156744.37 | 3040.63 | 159785 | 19905 | 98.1% | 19526.2176 | -11854.2376 |  |  |  | 0 | 0
56.1083 | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 153616.75 | 563393.25 | 717010 | 347967.35 | 308395.65 | 656363 | 60647 | 53.01% | 32151.6842 | -226502.2842 |  |  |  | 0 | 0
56.1085 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 0 | 80000 | 80000 | 1090.31 | 65864.69 | 66955 | 13045 | 1.628% | 0 | -1090.31 |  |  |  | 0 | 0
56.1086 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 0 | 376000 | 376000 | 12732.69 | 282369.31 | 295102 | 80898 | 4.315% | 0 | -12732.69 |  |  |  | 0 | 0
56.1087 | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 37977 | 11392 | 49369 | 39121.54 | 3904.46 | 43026 | 6343 | 90.93% | 5767.3948 | -6911.9348 |  |  |  | 0 | 0
56.1088 | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 0 | 117985 | 117985 | 66827.49 | 18577.51 | 85405 | 32580 | 78.25% | 25493.1166 | -92320.6066 |  |  |  | 0 | 0
[15 empty] | #REF! | #REF!
|  | 1107424084.26 | 751698755.74 | 1859122840 | 1041534998.27 | 693304584.16 | 1734839582.43 | 124283257.57 |  | 65410179.6972 | 478906.2928 |  |  |  | -862491.5259 | 862491.5259
Proof of GAAP Basis WIP:
[6 empty] | YTD Costs |  | 338883768.88 |  | F/S Footnote:
[6 empty] | Prior Year Adjustment |  |  |  | Cost to Date | 1041534998.27
[6 empty] | YTD Profit |  | 17281747.0579 |  | P/L to Date | 65410179.6972
[6 empty] | YTD Amount Billed |  | -355018357.06 |  |  | 1106945177.9672
[6 empty] | WIP |  | 1147158.8779 |  | Billed to Date | -1107424084.26
[10 empty] | YTD WIP | -478906.2928
[6 empty] | Prior WIP |  | 1626065.1707
[6 empty] | Current WIP |  | -478906.2928
[6 empty] | WIP |  | 1147158.8779
4.6566e-08
[7 empty] | DR 1220 | 1147158.8779
[7 empty] | CR 4010.50 | -1147158.8779
|  | -2.1048e-07 |  |  | 2.5332e-07 |  |  |  |  | 0

## GAAP
W.M. Lyles Co.
PROFIT AND LOSS BY JOB (GAAP Basis)
FISCAL YEAR ENDING 12/31/25 | [18 empty] | Prior year info hidden in Columns N, O & P
For the Month Period Ended 12/31/2025 | [18 empty] | Note: Any job over 95% complete, review Cost to Complete and the cost incurred after 9/30, if costs are substantially more then CTC, profits may need to be reviewed/changed (unless there is CCO work)
|  | CONTRACT | EST. TOTAL | EXPECTED | JOB TO DATE | COST / | JOB TO DATE | JOB TO DATE |  |  | EST. COST TO | CONTRACT | PY JTD COSTS | PY JTD BILLINGS | PY JTD PROFIT |  |  |  | Fiscal Y/E | Fiscal Y/E
JOB | DESCRIPTION | AMOUNT | COSTS | PROFIT | JOB COSTS | COST | PROFIT/LOSS | EARNED REV. | JTD BILLED | CURRENT WIP | COMPLETE | BALANCE | 2024-12-31 | 2024-12-31 | 2024-12-31 | YTD COSTS | YTD BILLINGS | YTD PROFIT | Job Opens | Job Closes
Rocklin Area - Open Jobs
51.1108 | City of Stockton - RWCF Phase 2A/2B | 94045647.86 | 89805617.8 | 4240030.06 | 89805617.8 | 100% | 4240030.06 | 94045647.86 | 94045647.86 | 0 | 0 | 0 | 88519194.97 | 92554957.54 | 4035762.57 | 1286422.83 | 1490690.32 | 204267.49 | 2019 | 0 | .
51.1129 | Union Sanit. Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin | 126483580.84 | 115233580.84 | 11250000 | 87315159.22 | 75.77% | 8524386.1561 | 95839545.3761 | 96918206.9 | 1078661.5239 | 27918421.62 | 29565373.94 | 63757070.67 | 66921921.33 | 6957477.3602 | 23558088.55 | 29996285.57 | 1566908.7959 | 2022 | 0 | .
51.1137 | CA Water Service Co. - Bear Gulch Pump Station 18 | 1312151.46 | 1198511.46 | 113640 | 1042229.29 | 86.96% | 98821.6971 | 1141050.9871 | 1121900.01 | -19150.9771 | 156282.17 | 190251.45 | 271684.42 | 78558 | 27243.5887 | 770544.87 | 1043342.01 | 71578.1085 | 2023 | 0 | .
51.1144 | Silicon Valley Clean Water - FEP Improvements Project | 14969566 | 13839617 | 1129949 | 8406760.8 | 60.74% | 686378.1678 | 9093138.9678 | 9667725.77 | 574586.8022 | 5432856.2 | 5301840.23 | 1353379.42 | 1514359.61 | 90331.4512 | 7053381.38 | 8153366.16 | 596046.7166 | 2023 | 0 | .
51.1146 | National Carbon Technologies, LLC - Aymium Williams Production Facility | 60980234 | 44196854.03 | 16783379.97 | 40950686.5 | 92.66% | 15550675.419 | 56501361.919 | 60980234 | 4478872.081 | 3246167.53 | 0 | 4561081.21 | 9363858.45 | 0 | 36389605.29 | 51616375.55 | 15550675.419 | 2023 | 0 | .
51.1151 | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 10658200 | 10079352 | 578848 | 4923435.18 | 48.85% | 282748.3956 | 5206183.5756 | 5009265.21 | -196918.3656 | 5155916.82 | 5648934.79 | 187144.08 | 0 | 0 | 4736291.1 | 5009265.21 | 282748.3956 | 2024 | 0 | .
51.1152 | Mozingo Construction Inc - ElD Sly Park Intertie Project | 19974489.34 | 18628948.34 | 1345541 | 13474808.54 | 72.33% | 973265.2121 | 14448073.7521 | 15610649.01 | 1162575.2579 | 5154139.8 | 4363840.33 | 1446770.9 | 2807450 | 0 | 12028037.64 | 12803199.01 | 973265.2121 | 2024 | 0 | .
51.1153 | Linda County Water Dist. - Aeration Blower Replacement | 562824.68 | 454520.68 | 108304 | 334550.81 | 73.61% | 79717.365 | 414268.175 | 549548.83 | 135280.655 | 119969.87 | 13275.85 | 98963.36 | 116846.83 | 12859.3892 | 235587.45 | 432702 | 66857.9758 | 2024 | 0 | .
51.1154 | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 13363835 | 12488835 | 875000 | 11872342.6 | 95.06% | 831806.952 | 12704149.552 | 13340008 | 635858.448 | 616492.4 | 23827 | 2378559.16 | 3186935 | 94320.4226 | 9493783.44 | 10153073 | 737486.5294 | 2024 | 0 | .
51.1158 | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 104446 | 104446 | 0 | 56960.69 | 54.54% | 0 | 56960.69 | 32282 | -24678.69 | 47485.31 | 72164 | 0 | 0 | 0 | 56960.69 | 32282 | 0 | 2025 | 0 | < 250k
51.1159 | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 1199000 | 1079240 | 119760 | 790051.12 | 73.2% | 87669.5843 | 877720.7043 | 732995 | -144725.7043 | 289188.88 | 466005 | 0 | 0 | 0 | 790051.12 | 732995 | 87669.5843 | 2025 | 0 | .
51.116 | City of Galt Public Works - Industrial WWTP Expansion | 1757000 | 1690000 | 67000 | 250518.05 | 14.82% | 9931.7807 | 260449.8307 | 223725 | -36724.8307 | 1439481.95 | 1533275 | 0 | 0 | 0 | 250518.05 | 223725 | 9931.7807 | 2025 | 0 | .
51.1161 | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | 10848599.45 | 10261252.45 | 587347 | 601852.17 | 5.865% | 0 | 601852.17 | 745707.2 | 143855.03 | 9659400.28 | 10102892.25 | 0 | 0 | 0 | 601852.17 | 745707.2 | 0 | 2025 | 0 | .
51.1162 | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project | 6029750 | 5845263 | 184487 | 85941.38 | 1.47% | 0 | 85941.38 | 0 | -85941.38 | 5759321.62 | 6029750 | 0 | 0 | 0 | 85941.38 | 0 | 0 | 2025 | 0 | .
51.1164 | CA Water Service Co. - Stockton Roofing | 387260 | 383387 | 3873 | 4363.25 | 1.138% | 0 | 4363.25 | 0 | -4363.25 | 379023.75 | 387260 | 0 | 0 | 0 | 4363.25 | 0 | 0 | 2025 | 0 | .
51.1165 | City of Yuba City - WTP Aquifer Storage and Recovery Well No. 3 | 5304500 | 4886443 | 418057 | 23330.33 | 0.4775% | 0 | 23330.33 | 0 | -23330.33 | 4863112.67 | 5304500 | 0 | 0 | 0 | 23330.33 | 0 | 0 | 2025 | 0 | .
Rocklin Area - Open Job Totals |  | 367981084.63 | 330175868.6 | 37805216.03 | 259938607.73 |  | 31365430.7896 | 291304038.5196 | 298977894.79 | 7673856.2704 | 70237260.87 | 69003189.84 | 162573848.19 | 176544886.76 | 11217994.7818 | 97364759.54 | 122433008.03 | 20147436.0078
Rocklin Area - Closed Jobs
51.1133 | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 372738 | 331855.28 | 40882.72 | 331855.28 | 100% | 40882.72 | 372738 | 372738 | 0 | 0 | 0 | 303125.41 | 326664 | 17359.5806 | 28729.87 | 46074 | 23523.1394 | 2023 | 2025 | .
51.1136 | Union Sanitary Dist - USD Plant Misc. Improvements | 5483550 | 4531817.86 | 951732.14 | 4531817.86 | 100% | 951732.14 | 5483550 | 5483550 | 0 | 0 | 0 | 4229332.84 | 5133927.2 | 758905.7861 | 302485.02 | 349622.8 | 192826.3539 | 2023 | 2025 | .
51.1138 | CA Water Service Co. - Bear Gulch Pump Station 21 | 1120182.07 | 1167704.15 | -47522.08 | 1167704.15 | 100% | -47522.08 | 1120182.07 | 1120182.07 | 0 | 0 | 0 | 786902.05 | 831943.71 | 77778.0991 | 380802.1 | 288238.36 | -125300.1791 | 2023 | 2025 | .
51.1139 | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 61902 | 56994.44 | 4907.56 | 56994.44 | 100% | 4907.56 | 61902 | 61902 | 0 | 0 | 0 | 56994.44 | 61902 | 4426.359 | 0 | 0 | 481.201 | 2023 | 2025 | < 250k
51.1141 | City of Colfax - WWTP Algae Reduction Project | 3967189.79 | 3835094.73 | 132095.06 | 3835094.73 | 100% | 132095.06 | 3967189.79 | 3967189.79 | 0 | 0 | 0 | 3109905.76 | 3392862.8 | 79920.2987 | 725188.97 | 574326.99 | 52174.7613 | 2023 | 2025 | .
51.1143 | Olivehurst Plumas Lake Manganese Filter Expansion | 1991231.37 | 1758132.57 | 233098.8 | 1758132.57 | 100% | 233098.8 | 1991231.37 | 1991231.37 | 0 | 0 | 0 | 1730690.97 | 1955683.37 | 226011.7629 | 27441.6 | 35548 | 7087.0371 | 2023 | 2025 | .
51.1147 | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2742860.08 | 2548724.92 | 194135.16 | 2548724.92 | 100% | 194135.16 | 2742860.08 | 2742860.08 | 0 | 0 | 0 | 1749912.32 | 1894059.69 | 128284.5352 | 798812.6 | 848800.39 | 65850.6248 | 2023 | 2025 | .
51.115 | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2486231.58 | 2239435.14 | 246796.44 | 2239435.14 | 100% | 246796.44 | 2486231.58 | 2486231.58 | 0 | 0 | 0 | 2071076.8 | 2378955.76 | 166471.8295 | 168358.34 | 107275.82 | 80324.6105 | 2024 | 2025 | .
51.1156 | Rocklin Overhead 2025 | 0 | 1426058.69 | -1426058.69 | 1426058.69 | 100% | -1426058.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1426058.69 | 0 | -1426058.69 | 2025 | 2025 | OH
51.1157 | Rocklin Estimating 2025 | 0 | 613546.52 | -613546.52 | 613546.52 | 100% | -613546.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613546.52 | 0 | -613546.52 | 2025 | 2025 | OH
Rocklin Area - Closed Totals |  | 18225884.89 | 18509364.3 | -283479.41 | 18509364.3 |  | -283479.41 | 18225884.89 | 18225884.89 | 0 | 0 | 0 | 14037940.59 | 15975998.53 | 1459158.2509 | 4471423.71 | 2249886.36 | -1742637.6609
Rocklin Area - Grand Totals |  | 386206969.52 | 348685232.9 | 37521736.62 | 278447972.03 |  | 31081951.3796 | 309529923.4096 | 317203779.68 | 7673856.2704 | 70237260.87 | 69003189.84 | 176611788.78 | 192520885.29 | 12677153.0327 | 101836183.25 | 124682894.39 | 18404798.3469
Fresno Area - Open Jobs
52.8563 | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 1134038.13 | 859077.05 | 274961.08 | 859077.05 | 100% | 274961.08 | 1134038.13 | 1134038.13 | 0 | 0 | 0 | 720866.75 | 915332.49 | 194465.74 | 138210.3 | 218705.64 | 80495.34 | 2021 | 0 | .
52.8566 | City of Visalia - Water Reclamation Facility RPGS SCR System | 1259398 | 1029398 | 230000 | 1023821.05 | 99.46% | 228753.9334 | 1252574.9834 | 1242053 | -10521.9834 | 5576.95 | 17345 | 994790.56 | 1242053 | 223974.5063 | 29030.49 | 0 | 4779.4271 | 2021 | 0 | .
52.8586 | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 12611349 | 10661349 | 1950000 | 10565460.74 | 99.1% | 1932461.6841 | 12497922.4241 | 12611349 | 113426.5759 | 95888.26 | 0 | 10233292.71 | 12384954 | 1757780.0079 | 332168.03 | 226395 | 174681.6762 | 2022 | 0 | .
52.8634 | City of Huron - Water Treatment Plant Imp. Phase 2 | 13892722.74 | 13190722.74 | 702000 | 11707058.24 | 88.75% | 623040.5298 | 12330098.7698 | 12576768.04 | 246669.2702 | 1483664.5 | 1315954.7 | 5213426.62 | 5564075.37 | 277972.0115 | 6493631.62 | 7012692.67 | 345068.5183 | 2023 | 0 | .
52.8636 | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 3656112 | 3381112 | 275000 | 3367047.36 | 99.58% | 273856.0639 | 3640903.4239 | 3065635.6 | -575267.8239 | 14064.64 | 590476.4 | 1456799.54 | 1731771.2 | 204319.7111 | 1910247.82 | 1333864.4 | 69536.3528 | 2023 | 0 | .
52.8637 | Root Creek Water Dist. - Groundwater Blending & Arsenic | 26264577.65 | 24614577.65 | 1650000 | 24374299.03 | 99.02% | 1633893.2957 | 26008192.3257 | 26148625 | 140432.6743 | 240278.62 | 115952.65 | 19441814.99 | 20860138 | 1208391.7577 | 4932484.04 | 5288487 | 425501.538 | 2023 | 0 | .
52.864 | City of Dos Palos - WTP Replacement Project | 38646363.16 | 36773040.16 | 1873323 | 32158781.48 | 87.45% | 1638259.571 | 33797041.051 | 34176041.86 | 379000.809 | 4614258.68 | 4470321.3 | 13034452.74 | 13664733.79 | 703966.8389 | 19124328.74 | 20511308.07 | 934292.7322 | 2023 | 0 | .
52.8668 | California Water Service Co. - Cal Water - Salinas Station 57 | 411851 | 376996 | 34855 | 357710.67 | 94.88% | 33071.9833 | 390782.6533 | 349622.76 | -41159.8933 | 19285.33 | 62228.24 | 49065 | 0 | 5273.0464 | 308645.67 | 349622.76 | 27798.9368 | 2024 | 0 | .
52.8678 | City of Chowcilla - Well 15 & Generator Improvement Projects | 1240321 | 1162321 | 78000 | 926007.31 | 79.67% | 62141.6719 | 988148.9819 | 1142122 | 153973.0181 | 236313.69 | 98199 | 5563.63 | 0 | 0 | 920443.68 | 1142122 | 62141.6719 | 2024 | 0 | .
52.8687 | California Water Service Co. - Salinas Station 205 | 877954 | 790771.48 | 87182.52 | 740629.43 | 93.66% | 81654.3612 | 822283.7912 | 827811.95 | 5528.1588 | 50142.05 | 50142.05 | 0 | 0 | 0 | 740629.43 | 827811.95 | 81654.3612 | 2025 | 0 | .
52.8692 | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 55135.37 | 49682.49 | 5452.88 | 49682.49 | 100% | 5452.88 | 55135.37 | 55135.37 | 0 | 0 | 0 | 0 | 0 | 0 | 49682.49 | 55135.37 | 5452.88 | 2025 | 0 | < 250k
52.8697 | City of Tulare - Industrial WWTP Dewatering Improvements Pro | 1388000 | 1325482 | 62518 | 772187.73 | 58.26% | 36421.1906 | 808608.9206 | 1069317 | 260708.0794 | 553294.27 | 318683 | 0 | 0 | 0 | 772187.73 | 1069317 | 36421.1906 | 2025 | 0 | .
52.8698 | California Water Service Co. - Tesoro Viejo RWSP Liner Repair | 22713 | 16128 | 6585 | 15264 | 94.64% | 6232.2321 | 21496.2321 | 0 | -21496.2321 | 864 | 22713 | 0 | 0 | 0 | 15264 | 0 | 6232.2321 | 2025 | 0 | < 250k
52.8704 | City of Visalia - Solids Handling Improvements Project | 13744000 | 13491127 | 252873 | 820988.3 | 6.085% | 0 | 820988.3 | 1037950 | 216961.7 | 12670138.7 | 12706050 | 0 | 0 | 0 | 820988.3 | 1037950 | 0 | 2025 | 0 | .
52.8705 | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | 775000 | 719260 | 55740 | 285425.72 | 39.68% | 22119.4417 | 307545.1617 | 261232 | -46313.1617 | 433834.28 | 513768 | 0 | 0 | 0 | 285425.72 | 261232 | 22119.4417 | 2025 | 0 | .
52.8707 | County of Fresno - Westside Water Tank and Pump Station | 3693200 | 3461577 | 231623 | 1012057.14 | 29.24% | 67719.3403 | 1079776.4803 | 913135 | -166641.4803 | 2449519.86 | 2780065 | 0 | 0 | 0 | 1012057.14 | 913135 | 67719.3403 | 2025 | 0 | .
52.8708 | County of Fresno - CSA 44A Wastewater Improvements | 363833 | 333757 | 30076 | 7682.19 | 2.302% | 0 | 7682.19 | 0 | -7682.19 | 326074.81 | 363833 | 0 | 0 | 0 | 7682.19 | 0 | 0 | 2025 | 0 | .
52.8711 | California Water Service Co. - Tesoro Viejo ARV Replacement | 6860 | 6315 | 545 | 4568.81 | 72.35% | 394.2995 | 4963.1095 | 0 | -4963.1095 | 1746.19 | 6860 | 0 | 0 | 0 | 4568.81 | 0 | 394.2995 | 2025 | 0 | < 250k
52.8713 | City of Visalia - Remove & Replace Chain and Flight Mechanic | 218842 | 190439 | 28403 | 927.5 | 0.487% | 0 | 927.5 | 0 | -927.5 | 189511.5 | 218842 | 0 | 0 | 0 | 927.5 | 0 | 0 | 2025 | 0 | < 250k
52.8714 | New England Sheet Metal and Mechanical Co. - VCH Digging Water Line T&M | 5084.94 | 4465.61 | 619.33 | 4465.61 | 100% | 619.33 | 5084.94 | 5084.94 | 0 | 0 | 0 | 0 | 0 | 0 | 4465.61 | 5084.94 | 619.33 | 2025 | 0 | < 250k
Fresno Area - Open Jobs Totals |  | 120267354.99 | 112437598.18 | 7829756.81 | 89053141.85 |  | 6921052.8886 | 95974194.7386 | 96615921.65 | 641726.9114 | 23384456.33 | 23651433.34 | 51150072.54 | 56363057.85 | 4576143.6198 | 37903069.31 | 40252863.8 | 2344909.2688
Fresno Area - Closed Jobs
52.8567 | City of Modesto - Grayson Well 69 | 3059858.99 | 3128023.93 | -68164.94 | 3128023.93 | 100% | -68164.94 | 3059858.99 | 3059858.99 | 0 | 0 | 0 | 3093625.26 | 3018499.27 | -83000 | 34398.67 | 41359.72 | 14835.06 | 2021 | 2025 | .
52.8604 | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 5095690.97 | 4572503.23 | 523187.74 | 4572503.23 | 100% | 523187.74 | 5095690.97 | 5095690.97 | 0 | 0 | 0 | 3663663.49 | 4537408 | 329989.1327 | 908839.74 | 558282.97 | 193198.6073 | 2022 | 2025 | .
52.8628 | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 5213345.5 | 4745798.53 | 467546.97 | 4745798.53 | 100% | 467546.97 | 5213345.5 | 5213345.5 | 0 | 0 | 0 | 3841927.99 | 4344899 | 197224.7538 | 903870.54 | 868446.5 | 270322.2162 | 2023 | 2025 | .
52.8631 | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 2560650.14 | 2448658.26 | 111991.88 | 2448658.26 | 100% | 111991.88 | 2560650.14 | 2560650.14 | 0 | 0 | 0 | 2249693.14 | 2130066.81 | 73003.7005 | 198965.12 | 430583.33 | 38988.1795 | 2023 | 2025 | .
52.8652 | California Water Service Co. - Salinas 77 Booster Station | 1290184 | 1039376.08 | 250807.92 | 1039376.08 | 100% | 250807.92 | 1290184 | 1290184 | 0 | 0 | 0 | 985944.49 | 1202385 | 170698.8374 | 53431.59 | 87799 | 80109.0826 | 2024 | 2025 | .
52.8658 | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1870914.99 | 1633530.21 | 237384.78 | 1633530.21 | 100% | 237384.78 | 1870914.99 | 1870914.99 | 0 | 0 | 0 | 1521618.77 | 1789732.45 | 145886.6054 | 111911.44 | 81182.54 | 91498.1746 | 2023 | 2025 | .
52.8663 | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1641800 | 1379688.28 | 262111.72 | 1379688.28 | 100% | 262111.72 | 1641800 | 1641800 | 0 | 0 | 0 | 406865.39 | 507750 | 42676.9508 | 972822.89 | 1134050 | 219434.7692 | 2024 | 2025 | .
52.8667 | California Water Service Co. - Cal Water Salinas Station 33 | 314085.77 | 290726.11 | 23359.66 | 290726.11 | 100% | 23359.66 | 314085.77 | 314085.77 | 0 | 0 | 0 | 285347.35 | 201644.15 | 26868.8653 | 5378.76 | 112441.62 | -3509.2053 | 2024 | 2025 | .
52.867 | California Water Service Co. - Cal Water - King City Station 10 | 274166.01 | 267282.05 | 6883.96 | 267282.05 | 100% | 6883.96 | 274166.01 | 274166.01 | 0 | 0 | 0 | 121115.51 | 0 | 10404.4356 | 146166.54 | 274166.01 | -3520.4756 | 2024 | 2025 | .
52.8674 | City of Hanford - WWTP Standby Influent Pump Install | 279244 | 251088.2 | 28155.8 | 251088.2 | 100% | 28155.8 | 279244 | 279244 | 0 | 0 | 0 | 184739.62 | 279244 | 15534.5836 | 66348.58 | 0 | 12621.2164 | 2024 | 2025 | .
52.8677 | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 796055.3 | 689831.96 | 106223.34 | 689831.96 | 100% | 106223.34 | 796055.3 | 796055.3 | 0 | 0 | 0 | 33286.03 | 0 | 0 | 656545.93 | 796055.3 | 106223.34 | 2024 | 2025 | .
52.868 | City of Orange Cove - Orange Cove West Clarifier T&M | 29838.25 | 26088.33 | 3749.92 | 26088.33 | 100% | 3749.92 | 29838.25 | 29838.25 | 0 | 0 | 0 | 6514.21 | 0 | 0 | 19574.12 | 29838.25 | 3749.92 | 2024 | 2025 | < 250k
52.8682 | Fresno Overhead 2025 | 0 | 1121157.1 | -1121157.1 | 1121157.1 | 100% | -1121157.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121157.1 | 0 | -1121157.1 | 2025 | 2025 | OH
52.8683 | Fresno Estimating 2025 | 0 | 415452.52 | -415452.52 | 415452.52 | 100% | -415452.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415452.52 | 0 | -415452.52 | 2025 | 2025 | OH
52.8684 | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 50568.05 | 45291.39 | 5276.66 | 45291.39 | 100% | 5276.66 | 50568.05 | 50568.05 | 0 | 0 | 0 | 0 | 0 | 0 | 45291.39 | 50568.05 | 5276.66 | 2025 | 2025 | < 250k
52.8685 | Malaga County Water Dist. - Malaga County Water District | 451254 | 382067.32 | 69186.68 | 382067.32 | 100% | 69186.68 | 451254 | 451254 | 0 | 0 | 0 | 0 | 0 | 0 | 382067.32 | 451254 | 69186.68 | 2025 | 2025 | .
52.8686 | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 23957 | 7505.26 | 16451.74 | 7505.26 | 100% | 16451.74 | 23957 | 23957 | 0 | 0 | 0 | 6290.87 | 0 | 15372.2567 | 1214.39 | 23957 | 1079.4833 | 2024 | 2025 | < 250k
52.8688 | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 132492.2 | 116972.75 | 15519.45 | 116972.75 | 100% | 15519.45 | 132492.2 | 132492.2 | 0 | 0 | 0 | 0 | 0 | 0 | 116972.75 | 132492.2 | 15519.45 | 2025 | 2025 | < 250k
52.8689 | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 16665.83 | 16095.58 | 570.25 | 16095.58 | 100% | 570.25 | 16665.83 | 16665.83 | 0 | 0 | 0 | 0 | 0 | 0 | 16095.58 | 16665.83 | 570.25 | 2025 | 2025 | < 250k
52.869 | City of Dinuba - WWTP Rake Replacement | 14151.97 | 13155.83 | 996.14 | 13155.83 | 100% | 996.14 | 14151.97 | 14151.97 | 0 | 0 | 0 | 0 | 0 | 0 | 13155.83 | 14151.97 | 996.14 | 2025 | 2025 | < 250k
52.8691 | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 11302.84 | 8287.82 | 3015.02 | 8287.82 | 100% | 3015.02 | 11302.84 | 11302.84 | 0 | 0 | 0 | 0 | 0 | 0 | 8287.82 | 11302.84 | 3015.02 | 2025 | 2025 | < 250k
52.8693 | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 1120704.2 | 663140.99 | 457563.21 | 663140.99 | 100% | 457563.21 | 1120704.2 | 1120704.2 | 0 | 0 | 0 | 0 | 0 | 0 | 663140.99 | 1120704.2 | 457563.21 | 2025 | 2025 | .
52.8694 | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 43047.45 | 38541.99 | 4505.46 | 38541.99 | 100% | 4505.46 | 43047.45 | 43047.45 | 0 | 0 | 0 | 0 | 0 | 0 | 38541.99 | 43047.45 | 4505.46 | 2025 | 2025 | < 250k
52.8695 | Lyles Services Co. - LSC GO Trash Enclosure | 13769 | 13024.37 | 744.63 | 13024.37 | 100% | 744.63 | 13769 | 13769 | 0 | 0 | 0 | 0 | 0 | 0 | 13024.37 | 13769 | 744.63 | 2025 | 2025 | < 250k
52.8696 | American Paving Co. - Hot Tap for APC- Tule River Parkway | 1059.22 | 887.65 | 171.57 | 887.65 | 100% | 171.57 | 1059.22 | 1059.22 | 0 | 0 | 0 | 0 | 0 | 0 | 887.65 | 1059.22 | 171.57 | 2025 | 2025 | < 250k
52.8699 | City of Hanford - WWTP Repair T&M | 3001.12 | 2948.91 | 52.21 | 2948.91 | 100% | 52.21 | 3001.12 | 3001.12 | 0 | 0 | 0 | 0 | 0 | 0 | 2948.91 | 3001.12 | 52.21 | 2025 | 2025 | < 250k
52.87 | Lyles Services Co. - LSC GO Misc. Work | 5297 | 4446.13 | 850.87 | 4446.13 | 100% | 850.87 | 5297 | 5297 | 0 | 0 | 0 | 0 | 0 | 0 | 4446.13 | 5297 | 850.87 | 2025 | 2025 | < 250k
52.8701 | County of Fresno - 47 Water | 13433.85 | 12421.08 | 1012.77 | 12421.08 | 100% | 1012.77 | 13433.85 | 13433.85 | 0 | 0 | 0 | 0 | 0 | 0 | 12421.08 | 13433.85 | 1012.77 | 2025 | 2025 | < 250k
52.8702 | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M | 5626.78 | 4725.28 | 901.5 | 4725.28 | 100% | 901.5 | 5626.78 | 5626.78 | 0 | 0 | 0 | 0 | 0 | 0 | 4725.28 | 5626.78 | 901.5 | 2025 | 2025 | < 250k
52.8703 | County of Fresno - CSA 47 Egret Point Water Line Repair | 14402.18 | 12571.54 | 1830.64 | 12571.54 | 100% | 1830.64 | 14402.18 | 14402.18 | 0 | 0 | 0 | 0 | 0 | 0 | 12571.54 | 14402.18 | 1830.64 | 2025 | 2025 | < 250k
52.8706 | City of Hanford - WWTP Weld Repair T&M 2 | 2868.6 | 2435.78 | 432.82 | 2435.78 | 100% | 432.82 | 2868.6 | 2868.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2435.78 | 2868.6 | 432.82 | 2025 | 2025 | < 250k
52.8709 | County of Fresno - 47.1 Water | 17765.14 | 14874.36 | 2890.78 | 14874.36 | 100% | 2890.78 | 17765.14 | 17765.14 | 0 | 0 | 0 | 0 | 0 | 0 | 14874.36 | 17765.14 | 2890.78 | 2025 | 2025 | < 250k
52.871 | City of Dinuba - WWTP Bar Screen Motor Bracket Repair | 4064.54 | 3514.84 | 549.7 | 3514.84 | 100% | 549.7 | 4064.54 | 4064.54 | 0 | 0 | 0 | 0 | 0 | 0 | 3514.84 | 4064.54 | 549.7 | 2025 | 2025 | < 250k
52.8715 | New England Sheet Metal and Mechanical Co. - Vitro Glass Plant Concrete Pad T&M | 10001.43 | 8585.44 | 1415.99 | 8585.44 | 100% | 1415.99 | 10001.43 | 10001.43 | 0 | 0 | 0 | 0 | 0 | 0 | 8585.44 | 10001.43 | 1415.99 | 2025 | 2025 | < 250k
Fresno Area - Closed Jobs Totals |  | 24381266.32 | 23380699.1 | 1000567.22 | 23380699.1 |  | 1000567.22 | 24381266.32 | 24381266.32 | 0 | 0 | 0 | 16400632.12 | 18011628.68 | 944660.1219 | 6980066.98 | 6369637.64 | 55907.0981
Fresno Area - Grand Totals |  | 144648621.31 | 135818297.28 | 8830324.03 | 112433840.95 |  | 7921620.1086 | 120355461.0586 | 120997187.97 | 641726.9114 | 23384456.33 | 23651433.34 | 67550704.66 | 74374686.53 | 5520803.7416 | 44883136.29 | 46622501.44 | 2400816.3669
East Bay Area - Open Jobs
53.2007 | Union Sanitary Dist. - Phase 1B Secondary Clarifiers | 324530134 | 291530134 | 33000000 | 404852.16 | 0.1389% | 0 | 404852.16 | 0 | -404852.16 | 291125281.84 | 324530134 | 0 | 0 | 0 | 404852.16 | 0 | 0 | 2025 | 0 | .
0
East Bay Area - Open Jobs Totals |  | 324530134 | 291530134 | 33000000 | 404852.16 |  | 0 | 404852.16 | 0 | -404852.16 | 291125281.84 | 324530134 | 0 | 0 | 0 | 404852.16 | 0 | 0
East Bay Area - Closed Jobs
53.2004 | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 1173753.47 | 980791.05 | 192962.42 | 980791.05 | 100% | 192962.42 | 1173753.47 | 1173753.47 | 0 | 0 | 0 | 21928.48 | 0 | 0 | 958862.57 | 1173753.47 | 192962.42 | 2024 | 2025 | .
53.2005 | East Bay Overhead 2025 | 0 | 279281.96 | -279281.96 | 279281.96 | 100% | -279281.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279281.96 | 0 | -279281.96 | 2025 | 2025 | OH
53.2006 | East Bay Estimating 2026 | 0 | 304986.32 | -304986.32 | 304986.32 | 100% | -304986.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304986.32 | 0 | -304986.32 | 2025 | 2025 | OH
East Bay Area - Closed Jobs Totals |  | 1173753.47 | 1565059.33 | -391305.86 | 1565059.33 |  | -391305.86 | 1173753.47 | 1173753.47 | 0 | 0 | 0 | 21928.48 | 0 | 0 | 1543130.85 | 1173753.47 | -391305.86
East Bay - Grand Totals |  | 325703887.47 | 293095193.33 | 32608694.14 | 1969911.49 |  | -391305.86 | 1578605.63 | 1173753.47 | -404852.16 | 291125281.84 | 324530134 | 21928.48 | 0 | 0 | 1947983.01 | 1173753.47 | -391305.86
Bakersfield Area - Open Jobs
54.9033 | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 118278.58 | 104550.27 | 13728.31 | 104550.27 | 100% | 13728.31 | 118278.58 | 118278.58 | 0 | 0 | 0 | 82942.93 | 93909.8 | 10966.87 | 21607.34 | 24368.78 | 2761.44 | 2021 | 0 | < 250k
54.9135 | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 9470658.62 | 9050951.86 | 419706.76 | 9050951.86 | 100% | 419706.76 | 9470658.62 | 9470658.62 | 0 | 0 | 0 | 7371036.33 | 6071589.31 | 0 | 1679915.53 | 3399069.31 | 419706.76 | 2021 | 0 | .
54.9257 | City of Guadalupe - Highway 1 Lift Station | 1471328 | 1426328 | 45000 | 762211.05 | 53.44% | 24047.4121 | 786258.4621 | 890983 | 104724.5379 | 664116.95 | 580345 | 14035.83 | 0 | 0 | 748175.22 | 890983 | 24047.4121 | 2023 | 0 | .
54.9268 | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 949567.99 | 884567.99 | 65000 | 844648.28 | 95.49% | 62066.612 | 906714.892 | 907298 | 583.108 | 39919.71 | 42269.99 | 788053.77 | 894533 | 71013.0668 | 56594.51 | 12765 | -8946.4548 | 2023 | 0 | .
54.9269 | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 625819.17 | 549817.74 | 76001.43 | 549817.74 | 100% | 76001.43 | 625819.17 | 625819.17 | 0 | 0 | 0 | 306021.41 | 340270.46 | 34249.05 | 243796.33 | 285548.71 | 41752.38 | 2023 | 0 | .
54.9285 | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 462022 | 387022 | 75000 | 312939.77 | 80.86% | 60643.7948 | 373583.5648 | 427226 | 53642.4352 | 74082.23 | 34796 | 186052.75 | 205930 | 35686.2378 | 126887.02 | 221296 | 24957.557 | 2023 | 0 | .
54.9313 | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 7886885.04 | 6876885.04 | 1010000 | 6449205.22 | 93.78% | 947187.1689 | 7396392.3889 | 7886885 | 490492.6111 | 427679.82 | 0.04 | 1921139.11 | 2129585.82 | 197714.5111 | 4528066.11 | 5757299.18 | 749472.6578 | 2024 | 0 | .
54.933 | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 324900 | 307641 | 17259 | 306221.41 | 99.54% | 17179.3594 | 323400.7694 | 324900 | 1499.2306 | 1419.59 | 0 | 181448.27 | 237460 | 10642.1273 | 124773.14 | 87440 | 6537.2322 | 2024 | 0 | .
54.9336 | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 25191176.64 | 23271176.64 | 1920000 | 12340864.27 | 53.03% | 1018189.1429 | 13359053.4129 | 14176592.91 | 817539.4971 | 10930312.37 | 11014583.73 | 2120057.55 | 2584469.7 | 0 | 10220806.72 | 11592123.21 | 1018189.1429 | 2024 | 0 | .
54.9337 | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 4104848 | 3944848 | 160000 | 1509066.73 | 38.25% | 61206.5856 | 1570273.3156 | 520441.66 | -1049831.6556 | 2435781.27 | 3584406.34 | 153011.71 | 0 | 0 | 1356055.02 | 520441.66 | 61206.5856 | 2024 | 0 | .
54.9343 | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 6881300 | 5981300 | 900000 | 3415344.08 | 57.1% | 513903.2772 | 3929247.3572 | 3954560 | 25312.6428 | 2565955.92 | 2926740 | 600191.79 | 737745 | 0 | 2815152.29 | 3216815 | 513903.2772 | 2024 | 0 | .
54.9356 | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 1298330 | 913330 | 385000 | 775780.75 | 84.94% | 327018.2615 | 1102799.0115 | 685017 | -417782.0115 | 137549.25 | 613313 | 62884.76 | 63200 | 0 | 712895.99 | 621817 | 327018.2615 | 2024 | 0 | .
54.9366 | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1230131 | 1080131 | 150000 | 923220.5 | 85.47% | 128209.5181 | 1051430.0181 | 1160831 | 109400.9819 | 156910.5 | 69300 | 5513.06 | 0 | 0 | 917707.44 | 1160831 | 128209.5181 | 2024 | 0 | .
54.9369 | California Water Service Co. - PFAS Treatment Program Project | 28550624.7 | 26179781.7 | 2370843 | 2787466.66 | 10.65% | 252433.1904 | 3039899.8504 | 2927422.95 | -112476.9004 | 23392315.04 | 25623201.75 | 1242.45 | 0 | 0 | 2786224.21 | 2927422.95 | 252433.1904 | 2024 | 0 | .
54.9373 | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 1524766 | 1393326 | 131440 | 50303.97 | 3.61% | 0 | 50303.97 | 0 | -50303.97 | 1343022.03 | 1524766 | 0 | 0 | 0 | 50303.97 | 0 | 0 | 2025 | 0 | .
54.9389 | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 299780 | 314780 | -15000 | 311891.85 | 99.08% | -15000 | 296891.85 | 291620 | -5271.85 | 2888.15 | 8160 | 0 | 0 | 0 | 311891.85 | 291620 | -15000 | 2025 | 0 | .
54.9391 | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 532604.57 | 512057.34 | 20547.23 | 512057.34 | 100% | 20547.23 | 532604.57 | 532604.57 | 0 | 0 | 0 | 0 | 0 | 0 | 512057.34 | 532604.57 | 20547.23 | 2025 | 0 | .
54.9395 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 1795652.66 | 1693652.66 | 102000 | 1349601.92 | 79.69% | 81279.5912 | 1430881.5112 | 1374448.17 | -56433.3412 | 344050.74 | 421204.49 | 0 | 0 | 0 | 1349601.92 | 1374448.17 | 81279.5912 | 2025 | 0 | .
54.9396 | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | 157746.09 | 157746.09 | 0 | 157746.09 | 100% | 0 | 157746.09 | 0 | -157746.09 | 0 | 157746.09 | 0 | 0 | 0 | 157746.09 | 0 | 0 | 2025 | 0 | < 250k
54.9397 | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 3690645 | 3390645 | 300000 | 1035065.41 | 30.53% | 91581.2841 | 1126646.6941 | 1033150.21 | -93496.4841 | 2355579.59 | 2657494.79 | 0 | 0 | 0 | 1035065.41 | 1033150.21 | 91581.2841 | 2025 | 0 | .
54.9403 | Lost Hills Utility Dist. - WTP Improvements | 381600 | 338101 | 43499 | 129004.89 | 38.16% | 16597.3591 | 145602.2491 | 140100 | -5502.2491 | 209096.11 | 241500 | 0 | 0 | 0 | 129004.89 | 140100 | 16597.3591 | 2025 | 0 | .
54.9404 | Cawelo Water Dist. - Reuse of Produced Water | 3720000 | 3585392 | 134608 | 1939024.63 | 54.08% | 72797.6822 | 2011822.3122 | 1746890 | -264932.3122 | 1646367.37 | 1973110 | 0 | 0 | 0 | 1939024.63 | 1746890 | 72797.6822 | 2025 | 0 | .
54.9405 | Semitropic Water Storage Dist. - Pump Platform Replacement Project | 942000 | 812000 | 130000 | 577796.16 | 71.16% | 92504.3113 | 670300.4713 | 746125 | 75824.5287 | 234203.84 | 195875 | 0 | 0 | 0 | 577796.16 | 746125 | 92504.3113 | 2025 | 0 | .
54.9406 | California Water Service Co. - Emergency PACL leak repair | 1120.65 | 1120.65 | 0 | 1120.65 | 100% | 0 | 1120.65 | 0 | -1120.65 | 0 | 1120.65 | 0 | 0 | 0 | 1120.65 | 0 | 0 | 2025 | 0 | < 250k
54.9408 | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line | 3777777 | 3537185 | 240592 | 41652.43 | 1.178% | 0 | 41652.43 | 0 | -41652.43 | 3495532.57 | 3777777 | 0 | 0 | 0 | 41652.43 | 0 | 0 | 2025 | 0 | .
54.9411 | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation | 103300 | 78300 | 25000 | 71370.85 | 91.15% | 22787.6277 | 94158.4777 | 103000 | 8841.5223 | 6929.15 | 300 | 0 | 0 | 0 | 71370.85 | 103000 | 22787.6277 | 2025 | 0 | < 250k
54.9412 | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork | 116752.04 | 115708.88 | 1043.16 | 115708.88 | 100% | 1043.16 | 116752.04 | 116752.04 | 0 | 0 | 0 | 0 | 0 | 0 | 115708.88 | 116752.04 | 1043.16 | 2025 | 0 | < 250k
54.9413 | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork | 149366.83 | 132138.74 | 17228.09 | 132138.74 | 100% | 17228.09 | 149366.83 | 149366.83 | 0 | 0 | 0 | 0 | 0 | 0 | 132138.74 | 149366.83 | 17228.09 | 2025 | 0 | < 250k
54.9414 | Cawelo Water Dist. - Cawelo Diversion Structure Rehab | 337485.68 | 337485.68 | 0 | 337485.68 | 100% | 0 | 337485.68 | 0 | -337485.68 | 0 | 337485.68 | 0 | 0 | 0 | 337485.68 | 0 | 0 | 2025 | 0 | .
54.9416 | California Water Service Co. - BK 147 Station Improvements | 1260000 | 1132398 | 127602 | 7257.82 | 0.6409% | 0 | 7257.82 | 0 | -7257.82 | 1125140.18 | 1260000 | 0 | 0 | 0 | 7257.82 | 0 | 0 | 2025 | 0 | .
54.9417 | County of Santa Barbara-Public Works - Laguna WWTP WAS Pipe Modifications | 48439 | 42893 | 5546 | 2299.41 | 5.361% | 0 | 2299.41 | 0 | -2299.41 | 40593.59 | 48439 | 0 | 0 | 0 | 2299.41 | 0 | 0 | 2025 | 0 | < 250k
54.9418 | GenerateUpcycle - Organics Waste Processing Facility | 15739 | 15739 | 0 | 15739 | 100% | 0 | 15739 | 0 | -15739 | 0 | 15739 | 0 | 0 | 0 | 15739 | 0 | 0 | 2025 | 0 | < 250k
54.9421 | Nipomo Community Service Dist. - Tefft Emergency Pipe Repair | 3703.18 | 3703.18 | 0 | 3703.18 | 100% | 0 | 3703.18 | 0 | -3703.18 | 0 | 3703.18 | 0 | 0 | 0 | 3703.18 | 0 | 0 | 2025 | 0 | < 250k
Bakersfield Area - Open Jobs Totals |  | 107424347.44 | 98552703.46 | 8871643.98 | 46923257.49 |  | 4322887.1587 | 51246144.6487 | 50310970.71 | -935173.9387 | 51629445.97 | 57113376.73 | 13793631.72 | 13358693.09 | 360271.863 | 33129625.77 | 36952277.62 | 3962615.2956
Bakersfield Area - Closed Jobs
54.9099 | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 55712110 | 45328892.68 | 10383217.32 | 45328892.68 | 100% | 10383217.32 | 55712110 | 55712110 | 0 | 0 | 0 | 45063061.29 | 55369229 | 10372751.5815 | 265831.39 | 342881 | 10465.7385 | 2020 | 2025 | .
54.9172 | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 24160002.44 | 21018432.22 | 3141570.22 | 21018432.22 | 100% | 3141570.22 | 24160002.44 | 24160002.44 | 0 | 0 | 0 | 21046229.25 | 24154131.07 | 3107901.82 | -27797.03 | 5871.37 | 33668.4 | 2021 | 2025 | .
54.9216 | CA Dept. of Corr. - Water Treatment Improvements | 2472164.05 | 2286264.43 | 185899.62 | 2286264.43 | 100% | 185899.62 | 2472164.05 | 2472164.05 | 0 | 0 | 0 | 2054298.05 | 2312435 | 140849.7535 | 231966.38 | 159729.05 | 45049.8665 | 2022 | 2025 | .
54.9246 | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 1777852 | 1708475.32 | 69376.68 | 1708475.32 | 100% | 69376.68 | 1777852 | 1777852 | 0 | 0 | 0 | 1350527.55 | 1389025.21 | 69196.4543 | 357947.77 | 388826.79 | 180.2257 | 2022 | 2025 | .
54.9265 | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 223896.47 | 220754.51 | 3141.96 | 220754.51 | 100% | 3141.96 | 223896.47 | 223896.47 | 0 | 0 | 0 | 203244.51 | 191463.66 | 0 | 17510 | 32432.81 | 3141.96 | 2023 | 2025 | < 250k
54.9279 | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3216240.01 | 3153237.4 | 63002.61 | 3153237.4 | 100% | 63002.61 | 3216240.01 | 3216240.01 | 0 | 0 | 0 | 2754167.5 | 2243686.4 | -15000 | 399069.9 | 972553.61 | 78002.61 | 2023 | 2025 | .
54.9289 | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 44560 | 25097.25 | 19462.75 | 25097.25 | 100% | 19462.75 | 44560 | 44560 | 0 | 0 | 0 | 13506.19 | 14176 | 669.81 | 11591.06 | 30384 | 18792.94 | 2023 | 2025 | < 250k
54.9292 | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 4300 | 1313.45 | 2986.55 | 1313.45 | 100% | 2986.55 | 4300 | 4300 | 0 | 0 | 0 | 1313.45 | 4300 | 2986.55 | 0 | 0 | 0 | 2023 | 2025 | < 250k
54.9309 | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3968668.9 | 3790858.34 | 177810.56 | 3790858.34 | 100% | 177810.56 | 3968668.9 | 3968668.9 | 0 | 0 | 0 | 1941399.17 | 2378548.71 | 62853.4158 | 1849459.17 | 1590120.19 | 114957.1442 | 2024 | 2025 | .
54.9323 | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 110661.47 | 94483.21 | 16178.26 | 94483.21 | 100% | 16178.26 | 110661.47 | 110661.47 | 0 | 0 | 0 | 85064.63 | 16235.09 | 0 | 9418.58 | 94426.38 | 16178.26 | 2024 | 2025 | < 250k
54.9329 | Kern Water Bank Authority - Valve Replacement Parts | 18201.12 | 16466.72 | 1734.4 | 16466.72 | 100% | 1734.4 | 18201.12 | 18201.12 | 0 | 0 | 0 | 0 | 0 | 0 | 16466.72 | 18201.12 | 1734.4 | 2025 | 2025 | < 250k
54.9333 | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 427464.77 | 371915.26 | 55549.51 | 371915.26 | 100% | 55549.51 | 427464.77 | 427464.77 | 0 | 0 | 0 | 152091.76 | 166980.44 | 14888.68 | 219823.5 | 260484.33 | 40660.83 | 2024 | 2025 | .
54.9338 | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 175884.64 | 119186.11 | 56698.53 | 119186.11 | 100% | 56698.53 | 175884.64 | 175884.64 | 0 | 0 | 0 | 105814.13 | 162416 | 54179.7977 | 13371.98 | 13468.64 | 2518.7323 | 2024 | 2025 | < 250k
54.9341 | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1251279 | 1063532.4 | 187746.6 | 1063532.4 | 100% | 187746.6 | 1251279 | 1251279 | 0 | 0 | 0 | 197572.74 | 180080 | 9297.3859 | 865959.66 | 1071199 | 178449.2141 | 2024 | 2025 | .
54.9342 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 199161.5 | 124146.3 | 75015.2 | 124146.3 | 100% | 75015.2 | 199161.5 | 199161.5 | 0 | 0 | 0 | 119458.81 | 174865 | 41394.1127 | 4687.49 | 24296.5 | 33621.0873 | 2024 | 2025 | < 250k
54.9347 | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 7100 | 3227.7 | 3872.3 | 3227.7 | 100% | 3872.3 | 7100 | 7100 | 0 | 0 | 0 | 0 | 0 | 0 | 3227.7 | 7100 | 3872.3 | 2025 | 2025 | < 250k
54.9349 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 290129 | 197889.31 | 92239.69 | 197889.31 | 100% | 92239.69 | 290129 | 290129 | 0 | 0 | 0 | 106438.55 | 156414.25 | 4519.6837 | 91450.76 | 133714.75 | 87720.0063 | 2024 | 2025 | .
54.935 | Kern Water Bank Authority - Construct New Well 18P01 | 129965.06 | 120318.68 | 9646.38 | 120318.68 | 100% | 9646.38 | 129965.06 | 129965.06 | 0 | 0 | 0 | 10110.6 | 0 | 0 | 110208.08 | 129965.06 | 9646.38 | 2024 | 2025 | < 250k
54.9351 | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 153298.79 | 136808.3 | 16490.49 | 136808.3 | 100% | 16490.49 | 153298.79 | 153298.79 | 0 | 0 | 0 | 136808.3 | 105656.18 | 0 | 0 | 47642.61 | 16490.49 | 2024 | 2025 | < 250k
54.9353 | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 2008.42 | 1117.5 | 890.92 | 1117.5 | 100% | 890.92 | 2008.42 | 2008.42 | 0 | 0 | 0 | 1117.5 | 0 | 0 | 0 | 2008.42 | 890.92 | 2024 | 2025 | < 250k
54.9354 | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 9571.2 | 8230.83 | 1340.37 | 8230.83 | 100% | 1340.37 | 9571.2 | 9571.2 | 0 | 0 | 0 | 12351.11 | 14274.54 | 1923.43 | -4120.28 | -4703.34 | -583.06 | 2024 | 2025 | < 250k
54.9355 | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 2806.42 | 1815.23 | 991.19 | 1815.23 | 100% | 991.19 | 2806.42 | 2806.42 | 0 | 0 | 0 | 1815.23 | 0 | 0 | 0 | 2806.42 | 991.19 | 2024 | 2025 | < 250k
54.9357 | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 1760.42 | 889.66 | 870.76 | 889.66 | 100% | 870.76 | 1760.42 | 1760.42 | 0 | 0 | 0 | 889.66 | 0 | 0 | 0 | 1760.42 | 870.76 | 2024 | 2025 | < 250k
54.9358 | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1147640 | 1125399.83 | 22240.17 | 1125399.83 | 100% | 22240.17 | 1147640 | 1147640 | 0 | 0 | 0 | 320292.15 | 268994 | 15917.5507 | 805107.68 | 878646 | 6322.6193 | 2024 | 2025 | .
54.936 | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1855.92 | 1144.88 | 711.04 | 1144.88 | 100% | 711.04 | 1855.92 | 1855.92 | 0 | 0 | 0 | 1144.88 | 0 | 0 | 0 | 1855.92 | 711.04 | 2024 | 2025 | < 250k
54.9361 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 108668.35 | 107074.87 | 1593.48 | 107074.87 | 100% | 1593.48 | 108668.35 | 108668.35 | 0 | 0 | 0 | 0 | 0 | 0 | 107074.87 | 108668.35 | 1593.48 | 2025 | 2025 | < 250k
54.9362 | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 425035.04 | 375601.24 | 49433.8 | 375601.24 | 100% | 49433.8 | 425035.04 | 425035.04 | 0 | 0 | 0 | 162458.93 | 0 | 0 | 213142.31 | 425035.04 | 49433.8 | 2024 | 2025 | .
54.9363 | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 1855.92 | 777.55 | 1078.37 | 777.55 | 100% | 1078.37 | 1855.92 | 1855.92 | 0 | 0 | 0 | 777.55 | 0 | 0 | 0 | 1855.92 | 1078.37 | 2024 | 2025 | < 250k
54.9365 | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 2216.42 | 1263.33 | 953.09 | 1263.33 | 100% | 953.09 | 2216.42 | 2216.42 | 0 | 0 | 0 | 1263.33 | 0 | 0 | 0 | 2216.42 | 953.09 | 2024 | 2025 | < 250k
54.9367 | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 2540.42 | 1602.33 | 938.09 | 1602.33 | 100% | 938.09 | 2540.42 | 2540.42 | 0 | 0 | 0 | 1602.33 | 0 | 0 | 0 | 2540.42 | 938.09 | 2024 | 2025 | < 250k
54.9368 | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 15697.91 | 13653.62 | 2044.29 | 13653.62 | 100% | 2044.29 | 15697.91 | 15697.91 | 0 | 0 | 0 | 13653.62 | 15697.91 | 2044.29 | 0 | 0 | 0 | 2024 | 2025 | < 250k
54.937 | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 1760.42 | 889.64 | 870.78 | 889.64 | 100% | 870.78 | 1760.42 | 1760.42 | 0 | 0 | 0 | 889.64 | 0 | 0 | 0 | 1760.42 | 870.78 | 2024 | 2025 | < 250k
54.9371 | Bakersfield Overhead 2025 | 0 | 1267652.77 | -1267652.77 | 1267652.77 | 100% | -1267652.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267652.77 | 0 | -1267652.77 | 2025 | 2025 | OH
54.9372 | Bakersfield Estimating 2025 | 0 | 588792.6 | -588792.6 | 588792.6 | 100% | -588792.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588792.6 | 0 | -588792.6 | 2025 | 2025 | OH
54.9374 | City of Santa Maria - WWTP Trickling Filter Repairs | 32962 | 19986.45 | 12975.55 | 19986.45 | 100% | 12975.55 | 32962 | 32962 | 0 | 0 | 0 | 0 | 0 | 0 | 19986.45 | 32962 | 12975.55 | 2025 | 2025 | < 250k
54.9375 | City of Santa Maria - WWTP Clarifier Repairs | 8232.73 | 4545.48 | 3687.25 | 4545.48 | 100% | 3687.25 | 8232.73 | 8232.73 | 0 | 0 | 0 | 0 | 0 | 0 | 4545.48 | 8232.73 | 3687.25 | 2025 | 2025 | < 250k
54.9379 | Semitropic Water Storage Dist. - Delta System Pipe Repair | 41679.77 | 36111.95 | 5567.82 | 36111.95 | 100% | 5567.82 | 41679.77 | 41679.77 | 0 | 0 | 0 | 0 | 0 | 0 | 36111.95 | 41679.77 | 5567.82 | 2025 | 2025 | < 250k
54.938 | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 22446.19 | 18064.72 | 4381.47 | 18064.72 | 100% | 4381.47 | 22446.19 | 22446.19 | 0 | 0 | 0 | 0 | 0 | 0 | 18064.72 | 22446.19 | 4381.47 | 2025 | 2025 | < 250k
54.9381 | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 58900 | 28875.38 | 30024.62 | 28875.38 | 100% | 30024.62 | 58900 | 58900 | 0 | 0 | 0 | 0 | 0 | 0 | 28875.38 | 58900 | 30024.62 | 2025 | 2025 | < 250k
54.9382 | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 143799 | 108690.45 | 35108.55 | 108690.45 | 100% | 35108.55 | 143799 | 143799 | 0 | 0 | 0 | 0 | 0 | 0 | 108690.45 | 143799 | 35108.55 | 2025 | 2025 | < 250k
54.9383 | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 17542.44 | 15759.76 | 1782.68 | 15759.76 | 100% | 1782.68 | 17542.44 | 17542.44 | 0 | 0 | 0 | 0 | 0 | 0 | 15759.76 | 17542.44 | 1782.68 | 2025 | 2025 | < 250k
54.9384 | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 79531.98 | 70340.57 | 9191.41 | 70340.57 | 100% | 9191.41 | 79531.98 | 79531.98 | 0 | 0 | 0 | 0 | 0 | 0 | 70340.57 | 79531.98 | 9191.41 | 2025 | 2025 | < 250k
54.9385 | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 102913.84 | 98598.77 | 4315.07 | 98598.77 | 100% | 4315.07 | 102913.84 | 102913.84 | 0 | 0 | 0 | 0 | 0 | 0 | 98598.77 | 102913.84 | 4315.07 | 2025 | 2025 | < 250k
54.9386 | Kern Valley State Prison - Arsenic Pipe Leak Repair | 96086 | 75784.74 | 20301.26 | 75784.74 | 100% | 20301.26 | 96086 | 96086 | 0 | 0 | 0 | 0 | 0 | 0 | 75784.74 | 96086 | 20301.26 | 2025 | 2025 | < 250k
54.9387 | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 22619.54 | 19011.65 | 3607.89 | 19011.65 | 100% | 3607.89 | 22619.54 | 22619.54 | 0 | 0 | 0 | 0 | 0 | 0 | 19011.65 | 22619.54 | 3607.89 | 2025 | 2025 | < 250k
54.9388 | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 7454.07 | 6535.41 | 918.66 | 6535.41 | 100% | 918.66 | 7454.07 | 7454.07 | 0 | 0 | 0 | 0 | 0 | 0 | 6535.41 | 7454.07 | 918.66 | 2025 | 2025 | < 250k
54.939 | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 101491.67 | 96329.49 | 5162.18 | 96329.49 | 100% | 5162.18 | 101491.67 | 101491.67 | 0 | 0 | 0 | 0 | 0 | 0 | 96329.49 | 101491.67 | 5162.18 | 2025 | 2025 | < 250k
54.9392 | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 217648.89 | 208346.69 | 9302.2 | 208346.69 | 100% | 9302.2 | 217648.89 | 217648.89 | 0 | 0 | 0 | 0 | 0 | 0 | 208346.69 | 217648.89 | 9302.2 | 2025 | 2025 | < 250k
54.9393 | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 31523.02 | 27539.82 | 3983.2 | 27539.82 | 100% | 3983.2 | 31523.02 | 31523.02 | 0 | 0 | 0 | 0 | 0 | 0 | 27539.82 | 31523.02 | 3983.2 | 2025 | 2025 | < 250k
54.9394 | City of Arvin - Haven Drive Lateral Repair | 15966.99 | 14039.55 | 1927.44 | 14039.55 | 100% | 1927.44 | 15966.99 | 15966.99 | 0 | 0 | 0 | 0 | 0 | 0 | 14039.55 | 15966.99 | 1927.44 | 2025 | 2025 | < 250k
54.9398 | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 14300 | 8192.79 | 6107.21 | 8192.79 | 100% | 6107.21 | 14300 | 14300 | 0 | 0 | 0 | 0 | 0 | 0 | 8192.79 | 14300 | 6107.21 | 2025 | 2025 | < 250k
54.9399 | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 24775 | 11291.59 | 13483.41 | 11291.59 | 100% | 13483.41 | 24775 | 24775 | 0 | 0 | 0 | 0 | 0 | 0 | 11291.59 | 24775 | 13483.41 | 2025 | 2025 | < 250k
54.94 | Arvin Edison Water Storage Dist. - FFPP Core Drilling | 800.69 | 771.32 | 29.37 | 771.32 | 100% | 29.37 | 800.69 | 800.69 | 0 | 0 | 0 | 0 | 0 | 0 | 771.32 | 800.69 | 29.37 | 2025 | 2025 | < 250k
54.9401 | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R | 247539.61 | 236312.57 | 11227.04 | 236312.57 | 100% | 11227.04 | 247539.61 | 247539.61 | 0 | 0 | 0 | 0 | 0 | 0 | 236312.57 | 247539.61 | 11227.04 | 2025 | 2025 | < 250k
54.9407 | Semitropic Water Storage Dist. - North Plant Emergency Repair | 31296.85 | 25667.34 | 5629.51 | 25667.34 | 100% | 5629.51 | 31296.85 | 31296.85 | 0 | 0 | 0 | 0 | 0 | 0 | 25667.34 | 31296.85 | 5629.51 | 2025 | 2025 | < 250k
54.9409 | Nipomo CSD Osage Emergency Waterline Repair | 20123.71 | 17411.71 | 2712 | 17411.71 | 100% | 2712 | 20123.71 | 20123.71 | 0 | 0 | 0 | 0 | 0 | 0 | 17411.71 | 20123.71 | 2712 | 2025 | 2025 | < 250k
54.941 | SWID - Burbank St. Repair | 8241.55 | 6965.65 | 1275.9 | 6965.65 | 100% | 1275.9 | 8241.55 | 8241.55 | 0 | 0 | 0 | 0 | 0 | 0 | 6965.65 | 8241.55 | 1275.9 | 2025 | 2025 | < 250k
Bakersfield Area - Closed Jobs Totals |  | 97414231.62 | 84432379.32 | 12981852.3 | 84432379.32 |  | 12981852.3 | 97414231.62 | 97414231.62 | 0 | 0 | 0 | 75859362.41 | 89318608.46 | 13886374.3159 | 8573016.91 | 8095623.16 | -904522.0159
Bakersfield Area - Grand Totals |  | 204838579.06 | 182985082.78 | 21853496.28 | 131355636.81 |  | 17304739.4587 | 148660376.2687 | 147725202.33 | -935173.9387 | 51629445.97 | 57113376.73 | 89652994.13 | 102677301.55 | 14246646.1789 | 41702642.68 | 45047900.78 | 3058093.2798
Murrieta Area - Open Jobs
55.109 | LA Dept of Water and Power - Silverlake | 5235272.36 | 3834064.05 | 1401208.31 | 3834064.05 | 100% | 1401208.31 | 5235272.36 | 5235272.36 | 0 | 0 | 0 | 3617796.45 | 4974161.54 | 1356365.09 | 216267.6 | 261110.82 | 44843.22 | 2012 | 0 | .
55.1191 | Inland Empire Utilities - IEUA RP-5 Liquids Exp. & Solids Treat. Facility | 341443133.71 | 337732635.71 | 3710498 | 299179624.84 | 88.58% | 3286935.529 | 302466560.369 | 296634984.51 | -5831575.859 | 38553010.87 | 44808149.2 | 282667835.02 | 285899505.28 | 6702671.5016 | 16511789.82 | 10735479.23 | -3415735.9726 | 2020 | 0 | .
55.1192 | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6651803.53 | 6401803.53 | 250000 | 6393992.69 | 99.88% | 249694.975 | 6643687.665 | 6645760.51 | 2072.845 | 7810.84 | 6043.02 | 5962693.73 | 6385785.76 | 334963.8396 | 431298.96 | 259974.75 | -85268.8646 | 2020 | 0 | .
55.12 | East County Advanced Water Purification Project - Package 1 | 197175877 | 189971137.49 | 7204739.51 | 189971137.49 | 100% | 7204739.51 | 197175877 | 197175877 | 0 | 0 | 0 | 136204938.09 | 140379771 | 4174832.91 | 53766199.4 | 56796106 | 3029906.6 | 2020 | 0 | .
55.1202 | LA County Sanitation District - Oxygen Generation Project | 16396051.58 | 15220642.58 | 1175409 | 9590124.35 | 63.01% | 740594.1249 | 10330718.4749 | 10912272.58 | 581554.1051 | 5630518.23 | 5483779 | 8229572.13 | 10369938.28 | 647450.7063 | 1360552.22 | 542334.3 | 93143.4186 | 2020 | 0 | .
55.1204 | East County Advanced Water Purification Project - Package 3 | 57142227 | 55213329.21 | 1928897.79 | 55213329.21 | 100% | 1928897.79 | 57142227 | 57142227 | 0 | 0 | 0 | 38160537.22 | 39787580 | 1627042.78 | 17052791.99 | 17354647 | 301855.01 | 2020 | 0 | .
55.1227 | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 41504206.39 | 37154206.39 | 4350000 | 36953022.96 | 99.46% | 4326445.5224 | 41279468.4824 | 41483406.39 | 203937.9076 | 201183.43 | 20800 | 29332771.27 | 34411945.6 | 3409470.3388 | 7620251.69 | 7071460.79 | 916975.1837 | 2022 | 0 | .
55.1233 | Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 126077.16 | 126077.16 | 0 | 126077.16 | 100% | 0 | 126077.16 | 123617 | -2460.16 | 0 | 2460.16 | 76329.8 | 84758.64 | 8428.84 | 49747.36 | 38858.36 | -8428.84 | 2024 | 0 | .
55.1248 | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 5759301.81 | 4934301.81 | 825000 | 3621770.22 | 73.4% | 605548.778 | 4227318.998 | 4861991.81 | 634672.812 | 1312531.59 | 897310 | 314753.09 | 711429.5 | 0 | 3307017.13 | 4150562.31 | 605548.778 | 2024 | 0 | .
55.1249 | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 147525113 | 139703905 | 7821208 | 15046313.77 | 10.77% | 842355.4777 | 15888669.2477 | 15047042.84 | -841626.4077 | 124657591.23 | 132478070.16 | 941255.62 | 0 | 0 | 14105058.15 | 15047042.84 | 842355.4777 | 2024 | 0 | .
55.1254 | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 158952.89 | 156561.66 | 2391.23 | 156561.66 | 100% | 2391.23 | 158952.89 | 158952.89 | 0 | 0 | 0 | 0 | 0 | 0 | 156561.66 | 158952.89 | 2391.23 | 2025 | 0 | .
55.1255 | City of Riverside - RWQCP Emergency Repair | 14160.81 | 14160.81 | 0 | 14160.81 | 100% | 0 | 14160.81 | 0 | -14160.81 | 0 | 14160.81 | 0 | 0 | 0 | 14160.81 | 0 | 0 | 2025 | 0 | < 250k
55.1256 | Anaergia Technologies LLC - City of Riverside - OPS | 2888100 | 2713100 | 175000 | 94989.88 | 3.501% | 0 | 94989.88 | 101150 | 6160.12 | 2618110.12 | 2786950 | 0 | 0 | 0 | 94989.88 | 101150 | 0 | 2025 | 0 | .
Murrieta Area - Open Jobs Totals |  | 822020277.24 | 793175925.4 | 28844351.84 | 620195169.09 |  | 20588811.2471 | 640783980.3371 | 635522554.89 | -5261425.4471 | 172980756.31 | 186497722.35 | 505508482.42 | 523004875.6 | 18261226.0062 | 114686686.67 | 112517679.29 | 2327585.2408
Murrieta Area - Closed Jobs
55.123 | Anaergia Technologies - VVWRA - DAF 3 Replacement | 2273682.69 | 1665145.3 | 608537.39 | 1665145.3 | 100% | 608537.39 | 2273682.69 | 2273682.69 | 0 | 0 | 0 | 1665145.3 | 2273682.69 | 480252.0335 | 0 | 0 | 128285.3565 | 2023 | 2025 | .
55.1231 | City of Corona - WRF 1 Aeration System Improvements | 4046200 | 3321856.36 | 724343.64 | 3321856.36 | 100% | 724343.64 | 4046200 | 4046200 | 0 | 0 | 0 | 3306207.75 | 4027535 | 627907.3954 | 15648.61 | 18665 | 96436.2446 | 2023 | 2025 | .
55.1238 | Anaergia Technologies LLC - East County Package 5 | 34207.53 | 32500.86 | 1706.67 | 32500.86 | 100% | 1706.67 | 34207.53 | 34207.53 | 0 | 0 | 0 | 26100.05 | 34207.53 | 8107.48 | 6400.81 | 0 | -6400.81 | 2023 | 2025 | < 250k
55.125 | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 184557.17 | 48293.94 | 136263.23 | 48293.94 | 100% | 136263.23 | 184557.17 | 184557.17 | 0 | 0 | 0 | 46539.64 | 184557.17 | 101052.1598 | 1754.3 | 0 | 35211.0702 | 2024 | 2025 | < 250k
55.1251 | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 322982.96 | 284221.86 | 38761.1 | 284221.86 | 100% | 38761.1 | 322982.96 | 322982.96 | 0 | 0 | 0 | 0 | 0 | 0 | 284221.86 | 322982.96 | 38761.1 | 2025 | 2025 | .
55.1252 | Murrieta Overhead 2025 | 0 | 1958826.45 | -1958826.45 | 1958826.45 | 100% | -1958826.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1958826.45 | 0 | -1958826.45 | 2025 | 2025 | OH
55.1253 | Murrieta Estimating 2025 | 0 | 475814.03 | -475814.03 | 475814.03 | 100% | -475814.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475814.03 | 0 | -475814.03 | 2025 | 2025 | OH
Murrieta Area - Closed Jobs Totals |  | 6861630.35 | 7786658.8 | -925028.45 | 7786658.8 |  | -925028.45 | 6861630.35 | 6861630.35 | 0 | 0 | 0 | 5043992.74 | 6519982.39 | 1217319.0687 | 2742666.06 | 341647.96 | -2142347.5187
Murrieta Area - Grand Totals |  | 828881907.59 | 800962584.2 | 27919323.39 | 627981827.89 |  | 19663782.7971 | 647645610.6871 | 642384185.24 | -5261425.4471 | 172980756.31 | 186497722.35 | 510552475.16 | 529524857.99 | 19478545.0749 | 117429352.73 | 112859327.25 | 185237.7221
San Diego Area - Open Jobs
57.0003 | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 38165419.5 | 35758333.5 | 2407086 | 6316909.13 | 17.67% | 425225.1725 | 6742134.3025 | 6863233.25 | 121098.9475 | 29441424.37 | 31302186.25 | 901841.91 | 990201.09 | 96385.4118 | 5415067.22 | 5873032.16 | 328839.7607 | 2024 | 0 | .
57.0004 | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 40106224.63 | 37896367.63 | 2209857 | 750298.86 | 1.98% | 0 | 750298.86 | 900072.76 | 149773.9 | 37146068.77 | 39206151.87 | 686907.74 | 900072.76 | 0 | 63391.12 | 0 | 0 | 2024 | 0 | .
57.0007 | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | 196248.4 | 196248.4 | 0 | 196248.4 | 100% | 0 | 196248.4 | 153858.36 | -42390.04 | 0 | 42390.04 | 0 | 0 | 0 | 196248.4 | 153858.36 | 0 | 2025 | 0 | < 250k
57.0008 | Imperial Irrigation Dist. - El Centro Generating Station WWTP | 2876047 | 2743982 | 132065 | 262382.86 | 9.562% | 0 | 262382.86 | 266758 | 4375.14 | 2481599.14 | 2609289 | 0 | 0 | 0 | 262382.86 | 266758 | 0 | 2025 | 0 | .
San Diego Area - Open Jobs Totals |  | 81343939.53 | 76594931.53 | 4749008 | 7525839.25 |  | 425225.1725 | 7951064.4225 | 8183922.37 | 232857.9475 | 69069092.28 | 73160017.16 | 1588749.65 | 1890273.85 | 96385.4118 | 5937089.6 | 6293648.52 | 328839.7607
San Diego Area - Closed Jobs
57.0005 | San Diego Overhead 2025 | 0 | 92874.26 | -92874.26 | 92874.26 | 100% | -92874.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92874.26 | 0 | -92874.26 | 2025 | 2025 | OH
57.0006 | San Diego Estimating 2025 | 0 | 13743.76 | -13743.76 | 13743.76 | 100% | -13743.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13743.76 | 0 | -13743.76 | 2025 | 2025 | OH
San Diego Area - Closed Jobs Totals |  | 0 | 106618.02 | -106618.02 | 106618.02 |  | -106618.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106618.02 | 0 | -106618.02
San Diego - Grand Totals |  | 81343939.53 | 76701549.55 | 4642389.98 | 7632457.27 |  | 318607.1525 | 7951064.4225 | 8183922.37 | 232857.9475 | 69069092.28 | 73160017.16 | 1588749.65 | 1890273.85 | 96385.4118 | 6043707.62 | 6293648.52 | 222221.7407
Los Angeles Area - Open Jobs
58.0003 | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 22525189 | 21217174 | 1308015 | 11034781.79 | 52.01% | 680281.9312 | 11715063.7212 | 11889201.76 | 174138.0388 | 10182392.21 | 10635987.24 | 2381456.48 | 2988736.9 | 151508.8135 | 8653325.31 | 8900464.86 | 528773.1176 | 2024 | 0 | .
Los Angeles Area - Open Jobs Totals |  | 22525189 | 21217174 | 1308015 | 11034781.79 |  | 680281.9312 | 11715063.7212 | 11889201.76 | 174138.0388 | 10182392.21 | 10635987.24 | 2381456.48 | 2988736.9 | 151508.8135 | 8653325.31 | 8900464.86 | 528773.1176
Los Angeles Area - Closed Jobs
58.0004 | Los Angeles Overhead 2025 | 0 | 147282.12 | -147282.12 | 147282.12 | 100% | -147282.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147282.12 | 0 | -147282.12 | 2025 | 2025 | OH
58.0005 | Los Angeles Estimating 2025 | 0 | 135037.09 | -135037.09 | 135037.09 | 100% | -135037.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135037.09 | 0 | -135037.09 | 2025 | 2025 | OH
Los Angeles Area - Closed Jobs Totals |  | 0 | 282319.21 | -282319.21 | 282319.21 |  | -282319.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282319.21 | 0 | -282319.21
Los Angeles - Grand Totals |  | 22525189 | 21499493.21 | 1025695.79 | 11317101 |  | 397962.7212 | 11715063.7212 | 11889201.76 | 174138.0388 | 10182392.21 | 10635987.24 | 2381456.48 | 2988736.9 | 151508.8135 | 8935644.52 | 8900464.86 | 246453.9076
System Integration - Open Jobs
56.1004 | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 373425 | 269840 | 103585 | 236373.73 | 87.6% | 90738.1145 | 327111.8445 | 371550 | 44438.1555 | 33466.27 | 1875 | 152881.54 | 29675 | 51359.9627 | 83492.19 | 341875 | 39378.1518 | 2024 | 0 | .
56.1005 | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 135000 | 68025 | 66975 | 51037.42 | 75.03% | 50249.6318 | 101287.0518 | 135000 | 33712.9482 | 16987.58 | 0 | 15913.33 | 0 | 14525.3272 | 35124.09 | 135000 | 35724.3046 | 2024 | 0 | < 250k
56.101 | Placer County Water Agency -PCWA Time & Material Contract | 49250 | 36461.94 | 12788.06 | 36461.94 | 100% | 12788.06 | 49250 | 49250 | 0 | 0 | 0 | 0 | 0 | 0 | 36461.94 | 49250 | 12788.06 | 2025 | 0 | < 250k
56.1015 | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 160000 | 142358.95 | 17641.05 | 142358.95 | 100% | 17641.05 | 160000 | 160000 | 0 | 0 | 0 | 100113.78 | 27000 | 29395.3303 | 42245.17 | 133000 | -11754.2803 | 2024 | 0 | < 250k
56.1017 | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 102868 | 114895 | -12027 | 95450.46 | 83.08% | -12027 | 83423.46 | 99118 | 15694.54 | 19444.54 | 3750 | 42712.89 | 0 | 19016.5728 | 52737.57 | 99118 | -31043.5728 | 2024 | 0 | < 250k
56.1018 | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 153913 | 71045 | 82868 | 41991.15 | 59.11% | 48979.1346 | 90970.2846 | 50000 | -40970.2846 | 29053.85 | 103913 | 18131.9 | 0 | 31982.9546 | 23859.25 | 50000 | 16996.18 | 2024 | 0 | < 250k
56.1032 | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 85000 | 82975 | 2025 | 35024.34 | 42.21% | 854.767 | 35879.107 | 0 | -35879.107 | 47950.66 | 85000 | 8938.56 | 0 | 1044.5898 | 26085.78 | 0 | -189.8229 | 2024 | 0 | < 250k
56.1036 | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 276000 | 209024 | 66976 | 107051.95 | 51.22% | 34301.8572 | 141353.8072 | 48000 | -93353.8072 | 101972.05 | 228000 | 52637.25 | 0 | 17815.6493 | 54414.7 | 48000 | 16486.2079 | 2024 | 0 | .
56.1037 | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 36491 | 21674.2 | 14816.8 | 21674.2 | 100% | 14816.8 | 36491 | 36491 | 0 | 0 | 0 | 2024.38 | 2362.5 | 338.12 | 19649.82 | 34128.5 | 14478.68 | 2024 | 0 | < 250k
56.1038 | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 95000 | 117376 | -22376 | 100049.89 | 85.24% | -22376 | 77673.89 | 0 | -77673.89 | 17326.11 | 95000 | 54820.17 | 0 | 6303.4542 | 45229.72 | 0 | -28679.4542 | 2024 | 0 | < 250k
56.1039 | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 375000 | 332284 | 42716 | 324049.23 | 97.52% | 41657.3982 | 365706.6282 | 330000 | -35706.6282 | 8234.77 | 45000 | 44619.13 | 0 | 4521.8913 | 279430.1 | 330000 | 37135.507 | 2024 | 0 | .
56.1042 | Trabuco Canyon Water Dist. - SCADA Integration Services | 277565 | 218288 | 59277 | 172683.27 | 79.11% | 46892.8489 | 219576.1189 | 217715 | -1861.1189 | 45604.73 | 59850 | 88143.14 | 105595 | 34822.2181 | 84540.13 | 112120 | 12070.6307 | 2024 | 0 | .
56.1043 | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 336610 | 311391 | 25219 | 214994.3 | 69.04% | 17412.0037 | 232406.3037 | 0 | -232406.3037 | 96396.7 | 336610 | 37458.88 | 0 | 4449.6548 | 177535.42 | 0 | 12962.3489 | 2024 | 0 | .
56.1046 | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 77120 | 79956 | -2836 | 77765.8 | 97.26% | -2836 | 74929.8 | 75120 | 190.2 | 2190.2 | 2000 | 9466.4 | 0 | 1603.6473 | 68299.4 | 75120 | -4439.6473 | 2024 | 0 | < 250k
56.1047 | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 2394758 | 2040555 | 354203 | 1602869.63 | 78.55% | 278228.8307 | 1881098.4607 | 1905218.25 | 24119.7893 | 437685.37 | 489539.75 | 60536.16 | 0 | 0 | 1542333.47 | 1905218.25 | 278228.8307 | 2024 | 0 | .
56.1048 | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 200000 | 161119 | 38881 | 157916.15 | 98.01% | 38108.093 | 196024.243 | 187500 | -8524.243 | 3202.85 | 12500 | 20789.35 | 0 | 34643.7429 | 137126.8 | 187500 | 3464.35 | 2024 | 0 | < 250k
56.1049 | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 308725 | 248873 | 59852 | 214423.06 | 86.16% | 51567.0603 | 265990.1203 | 291725 | 25734.8797 | 34449.94 | 17000 | 127480.78 | 137812.5 | 74409.071 | 86942.28 | 153912.5 | -22842.0107 | 2024 | 0 | .
56.105 | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 3792559 | 3365567 | 426992 | 925847.53 | 27.51% | 117462.9679 | 1043310.4979 | 675979.5 | -367330.9979 | 2439719.47 | 3116579.5 | 54464.62 | 0 | 0 | 871382.91 | 675979.5 | 117462.9679 | 2024 | 0 | .
56.1055 | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 120891 | 92848 | 28043 | 78736.44 | 84.8% | 23780.8675 | 102517.3075 | 120891 | 18373.6925 | 14111.56 | 0 | 14271.01 | 0 | 2514.9896 | 64465.43 | 120891 | 21265.878 | 2024 | 0 | < 250k
56.1059 | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 399389 | 329206 | 70183 | 235841.92 | 71.64% | 50278.8329 | 286120.7529 | 0 | -286120.7529 | 93364.08 | 399389 | 26703.38 | 0 | 0 | 209138.54 | 0 | 50278.8329 | 2024 | 0 | .
56.106 | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 404663 | 322491 | 82172 | 145563.36 | 45.14% | 37090.1278 | 182653.4878 | 0 | -182653.4878 | 176927.64 | 404663 | 36446.56 | 0 | 10941.5619 | 109116.8 | 0 | 26148.5659 | 2024 | 0 | .
56.1063 | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 108000 | 97921 | 10079 | 74040.41 | 75.61% | 7620.973 | 81661.383 | 10000 | -71661.383 | 23880.59 | 98000 | 17607.81 | 0 | 2968.0708 | 56432.6 | 10000 | 4652.9021 | 2024 | 0 | < 250k
56.1066 | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 595000 | 531490 | 63510 | 476030.06 | 89.57% | 56882.856 | 532912.916 | 570000 | 37087.084 | 55459.94 | 25000 | 12471.13 | 0 | 0 | 463558.93 | 570000 | 56882.856 | 2024 | 0 | .
56.1067 | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 478000 | 415878 | 62122 | 104751.99 | 25.19% | 15647.3849 | 120399.3749 | 217000 | 96600.6251 | 311126.01 | 261000 | 4066.38 | 0 | 0 | 100685.61 | 217000 | 15647.3849 | 2024 | 0 | .
56.1073 | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 122210 | 114047 | 8163 | 108855.81 | 95.45% | 7791.4367 | 116647.2467 | 0 | -116647.2467 | 5191.19 | 122210 | 0 | 0 | 0 | 108855.81 | 0 | 7791.4367 | 2025 | 0 | < 250k
56.1075 | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 27665.92 | 27665.92 | 0 | 27665.92 | 100% | 0 | 27665.92 | 0 | -27665.92 | 0 | 27665.92 | 0 | 0 | 0 | 27665.92 | 0 | 0 | 2025 | 0 | .
56.1078 | City of Napa - On-Call Control Systems Integrator Services | 25356.25 | 25356.25 | 0 | 25356.25 | 100% | 0 | 25356.25 | 17050.24 | -8306.01 | 0 | 8306.01 | 0 | 0 | 0 | 25356.25 | 17050.24 | 0 | 2025 | 0 | < 250k
56.1081 | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 179690 | 159785 | 19905 | 156744.37 | 98.1% | 19526.2176 | 176270.5876 | 164416.35 | -11854.2376 | 3040.63 | 15273.65 | 0 | 0 | 0 | 156744.37 | 164416.35 | 19526.2176 | 2025 | 0 | < 250k
56.1083 | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 717010 | 656363 | 60647 | 347967.35 | 53.01% | 32151.6842 | 380119.0342 | 153616.75 | -226502.2842 | 308395.65 | 563393.25 | 0 | 0 | 0 | 347967.35 | 153616.75 | 32151.6842 | 2025 | 0 | .
56.1085 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 80000 | 66955 | 13045 | 1090.31 | 1.628% | 0 | 1090.31 | 0 | -1090.31 | 65864.69 | 80000 | 0 | 0 | 0 | 1090.31 | 0 | 0 | 2025 | 0 | < 250k
56.1086 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 376000 | 295102 | 80898 | 12732.69 | 4.315% | 0 | 12732.69 | 0 | -12732.69 | 282369.31 | 376000 | 0 | 0 | 0 | 12732.69 | 0 | 0 | 2025 | 0 | .
56.1087 | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 49369 | 43026 | 6343 | 39121.54 | 90.93% | 5767.3948 | 44888.9348 | 37977 | -6911.9348 | 3904.46 | 11392 | 0 | 0 | 0 | 39121.54 | 37977 | 5767.3948 | 2025 | 0 | < 250k
56.1088 | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 117985 | 85405 | 32580 | 66827.49 | 78.25% | 25493.1166 | 92320.6066 | 0 | -92320.6066 | 18577.51 | 117985 | 0 | 0 | 0 | 66827.49 | 0 | 25493.1166 | 2025 | 0 | < 250k
System Integration - Open Jobs Totals |  | 13030513.17 | 11155247.26 | 1875265.91 | 6459348.91 |  | 1106490.5096 | 7565839.4196 | 5923618.09 | -1642221.3296 | 4695898.35 | 7106895.08 | 1002698.53 | 302445 | 342656.8085 | 5456650.38 | 5621173.09 | 763833.7011
System Integration - Closed Jobs
56.1002 | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 185000 | 114485.82 | 70514.18 | 114485.82 | 100% | 70514.18 | 185000 | 185000 | 0 | 0 | 0 | 113841.61 | 170000 | 50745.2395 | 644.21 | 15000 | 19768.9405 | 2024 | 2025 | < 250k
56.1003 | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 332901 | 223395.74 | 109505.26 | 223395.74 | 100% | 109505.26 | 332901 | 332901 | 0 | 0 | 0 | 155093.29 | 175000 | 64460.9863 | 68302.45 | 157901 | 45044.2737 | 2023 | 2025 | .
56.1007 | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 16814 | 19362.98 | -2548.98 | 19362.98 | 100% | -2548.98 | 16814 | 16814 | 0 | 0 | 0 | 14316.6 | 13319 | 3177.441 | 5046.38 | 3495 | -5726.421 | 2024 | 2025 | < 250k
56.1008 | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 55000 | 30551.92 | 24448.08 | 30551.92 | 100% | 24448.08 | 55000 | 55000 | 0 | 0 | 0 | 30425.18 | 55000 | 23094.0224 | 126.74 | 0 | 1354.0576 | 2024 | 2025 | < 250k
56.1010.01 | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 9569 | 7097.1 | 2471.9 | 7097.1 | 100% | 2471.9 | 9569 | 9569 | 0 | 0 | 0 | 2465.37 | 0 | 619.6471 | 4631.73 | 9569 | 1852.2529 | 2024 | 2025 | < 250k
56.1016 | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 150064.25 | 110083.62 | 39980.63 | 110083.62 | 100% | 39980.63 | 150064.25 | 150064.25 | 0 | 0 | 0 | 57071.14 | 71814.5 | 14743.36 | 53012.48 | 78249.75 | 25237.27 | 2024 | 2025 | < 250k
56.1019 | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 193845 | 143764.58 | 50080.42 | 143764.58 | 100% | 50080.42 | 193845 | 193845 | 0 | 0 | 0 | 20442.52 | 0 | 4594.7943 | 123322.06 | 193845 | 45485.6257 | 2024 | 2025 | < 250k
56.1021 | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 244760 | 116752.52 | 128007.48 | 116752.52 | 100% | 128007.48 | 244760 | 244760 | 0 | 0 | 0 | 113715.41 | 0 | 38878.5393 | 3037.11 | 244760 | 89128.9407 | 2024 | 2025 | < 250k
56.1022 | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 88093.56 | 0 | 0 | -88093.56 | 0 | 0 | 2024 | 2025 | < 250k
56.1023 | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 220390 | 150504.73 | 69885.27 | 150504.73 | 100% | 69885.27 | 220390 | 220390 | 0 | 0 | 0 | 112097.3 | 172000 | 40095.3125 | 38407.43 | 48390 | 29789.9575 | 2024 | 2025 | < 250k
56.103 | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 689578.64 | 689578.64 | 0 | 689578.64 | 100% | 0 | 689578.64 | 689578.64 | 0 | 0 | 0 | 122107.57 | 77500 | 18034.019 | 567471.07 | 612078.64 | -18034.019 | 2024 | 2025 | .
56.1041 | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 20016.78 | 20016.78 | 0 | 20016.78 | 100% | 0 | 20016.78 | 20016.78 | 0 | 0 | 0 | 9127.13 | 0 | 7002.238 | 10889.65 | 20016.78 | -7002.238 | 2024 | 2025 | < 250k
56.1051 | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 136875 | 98718.18 | 38156.82 | 98718.18 | 100% | 38156.82 | 136875 | 136875 | 0 | 0 | 0 | 39254.31 | 0 | 16220.5398 | 59463.87 | 136875 | 21936.2802 | 2024 | 2025 | < 250k
56.1052 | San Jose Water - Williams Back ATS Replacement | 8887 | 6400.94 | 2486.06 | 6400.94 | 100% | 2486.06 | 8887 | 8887 | 0 | 0 | 0 | 5914.69 | 0 | 369.0936 | 486.25 | 8887 | 2116.9664 | 2024 | 2025 | < 250k
56.1053 | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 35000 | 19964.78 | 15035.22 | 19964.78 | 100% | 15035.22 | 35000 | 35000 | 0 | 0 | 0 | 5710.5 | 0 | 4187.3606 | 14254.28 | 35000 | 10847.8594 | 2024 | 2025 | < 250k
56.1054 | AIC - Riverside Public Works - Digester 5 Rehab | 37648.03 | 37648.03 | 0 | 37648.03 | 100% | 0 | 37648.03 | 37648.03 | 0 | 0 | 0 | 10750.06 | 0 | 0 | 26897.97 | 37648.03 | 0 | 2024 | 2025 | < 250k
56.1056 | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan | 98280.63 | 98280.63 | 0 | 98280.63 | 100% | 0 | 98280.63 | 98280.63 | 0 | 0 | 0 | 31429.81 | 0 | 20551.5757 | 66850.82 | 98280.63 | -20551.5757 | 2024 | 2025 | < 250k
56.1057 | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 16238.75 | 0 | 0 | -16238.75 | 0 | 0 | 2024 | 2025 | < 250k
56.1061 | San Jose Water - PLC System Assessment | 11269 | 5582.66 | 5686.34 | 5582.66 | 100% | 5686.34 | 11269 | 11269 | 0 | 0 | 0 | 5081.1 | 0 | 5163.8304 | 501.56 | 11269 | 522.5096 | 2024 | 2025 | < 250k
56.1062 | AIC - SCADA System Upgrade - City of Brentwood | 409988.07 | 409988.07 | 0 | 409988.07 | 100% | 0 | 409988.07 | 409988.07 | 0 | 0 | 0 | 26225.9 | 0 | 0 | 383762.17 | 409988.07 | 0 | 2024 | 2025 | .
56.1064 | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 435153 | 202266.4 | 232886.6 | 202266.4 | 100% | 232886.6 | 435153 | 435153 | 0 | 0 | 0 | 124401.21 | 0 | 69496.4896 | 77865.19 | 435153 | 163390.1104 | 2024 | 2025 | .
56.1065 | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 226400.8 | 192023.81 | 34376.99 | 192023.81 | 100% | 34376.99 | 226400.8 | 226400.8 | 0 | 0 | 0 | 15862.63 | 0 | 0 | 176161.18 | 226400.8 | 34376.99 | 2024 | 2025 | < 250k
56.1069 | AIC - City of Brentwood - Brentwood, City of - On-Call Agreement | 2525 | 3821.46 | -1296.46 | 3821.46 | 100% | -1296.46 | 2525 | 2525 | 0 | 0 | 0 | 0 | 0 | 0 | 3821.46 | 2525 | -1296.46 | 2025 | 2025 | < 250k
56.1071 | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 34000 | 3596.56 | 30403.44 | 3596.56 | 100% | 30403.44 | 34000 | 34000 | 0 | 0 | 0 | 316.5 | 0 | 0 | 3280.06 | 34000 | 30403.44 | 2024 | 2025 | < 250k
56.1072 | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 65960 | 41538.84 | 24421.16 | 41538.84 | 100% | 24421.16 | 65960 | 65960 | 0 | 0 | 0 | 1242.1 | 0 | 0 | 40296.74 | 65960 | 24421.16 | 2024 | 2025 | < 250k
56.1074 | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 12650 | 10641.86 | 2008.14 | 10641.86 | 100% | 2008.14 | 12650 | 12650 | 0 | 0 | 0 | 6757.28 | 0 | 1239.6881 | 3884.58 | 12650 | 768.4519 | 2024 | 2025 | < 250k
56.1076 | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 19200 | 11577.77 | 7622.23 | 11577.77 | 100% | 7622.23 | 19200 | 19200 | 0 | 0 | 0 | 604.81 | 0 | 0 | 10972.96 | 19200 | 7622.23 | 2024 | 2025 | < 250k
56.1077 | System Integration Overhead 2025 | 0 | 4370841.4 | -4370841.4 | 4370841.4 | 100% | -4370841.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4370841.4 | 0 | -4370841.4 | 2025 | 2025 | OH
56.1079 | AIC - San Jose Water Co - Montevina PLC Upgrade | 29235.63 | 29235.63 | 0 | 29235.63 | 100% | 0 | 29235.63 | 29235.63 | 0 | 0 | 0 | 0 | 0 | 0 | 29235.63 | 29235.63 | 0 | 2025 | 2025 | < 250k
56.108 | AIC - San Jose Water Co - PLC System Assessment | 359469 | 359469 | 0 | 359469 | 100% | 0 | 359469 | 359469 | 0 | 0 | 0 | 0 | 0 | 0 | 359469 | 359469 | 0 | 2025 | 2025 | .
56.1082 | City of Clovis - Pump Station E New Pump 5 VFD Startup | 19800 | 20583.04 | -783.04 | 20583.04 | 100% | -783.04 | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 20583.04 | 19800 | -783.04 | 2025 | 2025 | < 250k
56.1084 | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 8000 | 4228.13 | 3771.87 | 4228.13 | 100% | 3771.87 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 4228.13 | 8000 | 3771.87 | 2025 | 2025 | < 250k
56.1102 | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 19815.94 | 19815.94 | 0 | 19815.94 | 100% | 0 | 19815.94 | 19815.94 | 0 | 0 | 0 | 0 | 0 | 0 | 19815.94 | 19815.94 | 0 | 2025 | 2025 | < 250k
56.1103 | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 55855.24 | 55855.24 | 0 | 55855.24 | 100% | 0 | 55855.24 | 55855.24 | 0 | 0 | 0 | 0 | 0 | 0 | 55855.24 | 55855.24 | 0 | 2025 | 2025 | < 250k
56.1104 | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 9500.31 | 9500.31 | 0 | 9500.31 | 100% | 0 | 9500.31 | 9500.31 | 0 | 0 | 0 | 0 | 0 | 0 | 9500.31 | 9500.31 | 0 | 2025 | 2025 | < 250k
56.1105 | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 30502.53 | 30502.53 | 0 | 30502.53 | 100% | 0 | 30502.53 | 30502.53 | 0 | 0 | 0 | 0 | 0 | 0 | 30502.53 | 30502.53 | 0 | 2025 | 2025 | < 250k
56.1106 | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 54742.18 | 54742.18 | 0 | 54742.18 | 100% | 0 | 54742.18 | 54742.18 | 0 | 0 | 0 | 0 | 0 | 0 | 54742.18 | 54742.18 | 0 | 2025 | 2025 | < 250k
56.1107 | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 3429.06 | 3429.06 | 0 | 3429.06 | 100% | 0 | 3429.06 | 3429.06 | 0 | 0 | 0 | 0 | 0 | 0 | 3429.06 | 3429.06 | 0 | 2025 | 2025 | < 250k
56.1108 | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 20729.84 | 20729.84 | 0 | 20729.84 | 100% | 0 | 20729.84 | 20729.84 | 0 | 0 | 0 | 0 | 0 | 0 | 20729.84 | 20729.84 | 0 | 2025 | 2025 | < 250k
56.1109 | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 14772.26 | 14772.26 | 0 | 14772.26 | 100% | 0 | 14772.26 | 14772.26 | 0 | 0 | 0 | 0 | 0 | 0 | 14772.26 | 14772.26 | 0 | 2025 | 2025 | < 250k
56.111 | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 4596.42 | 4596.42 | 0 | 4596.42 | 100% | 0 | 4596.42 | 4596.42 | 0 | 0 | 0 | 0 | 0 | 0 | 4596.42 | 4596.42 | 0 | 2025 | 2025 | < 250k
56.1111 | AIC - California American Water - Luzern Well Treatment Design | 17210.01 | 17210.01 | 0 | 17210.01 | 100% | 0 | 17210.01 | 17210.01 | 0 | 0 | 0 | 0 | 0 | 0 | 17210.01 | 17210.01 | 0 | 2025 | 2025 | < 250k
56.1112 | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 27241.58 | 27241.58 | 0 | 27241.58 | 100% | 0 | 27241.58 | 27241.58 | 0 | 0 | 0 | 0 | 0 | 0 | 27241.58 | 27241.58 | 0 | 2025 | 2025 | < 250k
56.1113 | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 49233.44 | 49233.44 | 0 | 49233.44 | 100% | 0 | 49233.44 | 49233.44 | 0 | 0 | 0 | 0 | 0 | 0 | 49233.44 | 49233.44 | 0 | 2025 | 2025 | < 250k
56.1115 | AIC - UC Davis - WWTP Annual Instrument Calibrations | 5895.77 | 5895.77 | 0 | 5895.77 | 100% | 0 | 5895.77 | 5895.77 | 0 | 0 | 0 | 0 | 0 | 0 | 5895.77 | 5895.77 | 0 | 2025 | 2025 | < 250k
56.1119 | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 22184.06 | 22184.06 | 0 | 22184.06 | 100% | 0 | 22184.06 | 22184.06 | 0 | 0 | 0 | 0 | 0 | 0 | 22184.06 | 22184.06 | 0 | 2025 | 2025 | < 250k
56.112 | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 1045.63 | 1045.63 | 0 | 1045.63 | 100% | 0 | 1045.63 | 1045.63 | 0 | 0 | 0 | 0 | 0 | 0 | 1045.63 | 1045.63 | 0 | 2025 | 2025 | < 250k
56.1121 | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 22824.38 | 22824.38 | 0 | 22824.38 | 100% | 0 | 22824.38 | 22824.38 | 0 | 0 | 0 | 0 | 0 | 0 | 22824.38 | 22824.38 | 0 | 2025 | 2025 | < 250k
56.1122 | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 6289.38 | 6289.38 | 0 | 6289.38 | 100% | 0 | 6289.38 | 6289.38 | 0 | 0 | 0 | 0 | 0 | 0 | 6289.38 | 6289.38 | 0 | 2025 | 2025 | < 250k
56.1123 | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 3772.82 | 3772.82 | 0 | 3772.82 | 100% | 0 | 3772.82 | 3772.82 | 0 | 0 | 0 | 0 | 0 | 0 | 3772.82 | 3772.82 | 0 | 2025 | 2025 | < 250k
56.1124 | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 28950 | 28950 | 0 | 28950 | 100% | 0 | 28950 | 28950 | 0 | 0 | 0 | 0 | 0 | 0 | 28950 | 28950 | 0 | 2025 | 2025 | < 250k
56.1125 | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 14229.38 | 14229.38 | 0 | 14229.38 | 100% | 0 | 14229.38 | 14229.38 | 0 | 0 | 0 | 0 | 0 | 0 | 14229.38 | 14229.38 | 0 | 2025 | 2025 | < 250k
56.1126 | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 9526.88 | 9526.88 | 0 | 9526.88 | 100% | 0 | 9526.88 | 9526.88 | 0 | 0 | 0 | 0 | 0 | 0 | 9526.88 | 9526.88 | 0 | 2025 | 2025 | < 250k
56.1127 | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 6519.07 | 6519.07 | 0 | 6519.07 | 100% | 0 | 6519.07 | 6519.07 | 0 | 0 | 0 | 0 | 0 | 0 | 6519.07 | 6519.07 | 0 | 2025 | 2025 | < 250k
56.1128 | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 4793.13 | 4793.13 | 0 | 4793.13 | 100% | 0 | 4793.13 | 4793.13 | 0 | 0 | 0 | 0 | 0 | 0 | 4793.13 | 4793.13 | 0 | 2025 | 2025 | < 250k
56.1129 | AIC - RMCSD - VEEAM SFTWR | 133.75 | 133.75 | 0 | 133.75 | 100% | 0 | 133.75 | 133.75 | 0 | 0 | 0 | 0 | 0 | 0 | 133.75 | 133.75 | 0 | 2025 | 2025 | < 250k
56.113 | System Integration Division Estimating 2025 | 0 | 267.5 | -267.5 | 267.5 | 100% | -267.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267.5 | 0 | -267.5 | 2025 | 2025 | OH
56.1131 | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 2388.75 | 2388.75 | 0 | 2388.75 | 100% | 0 | 2388.75 | 2388.75 | 0 | 0 | 0 | 0 | 0 | 0 | 2388.75 | 2388.75 | 0 | 2025 | 2025 | < 250k
56.1132 | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 585 | 585 | 0 | 585 | 100% | 0 | 585 | 585 | 0 | 0 | 0 | 0 | 0 | 0 | 585 | 585 | 0 | 2025 | 2025 | < 250k
56.1133 | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 2827.5 | 2827.5 | 0 | 2827.5 | 100% | 0 | 2827.5 | 2827.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2827.5 | 2827.5 | 0 | 2025 | 2025 | < 250k
56.1134 | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 965.51 | 965.51 | 0 | 965.51 | 100% | 0 | 965.51 | 965.51 | 0 | 0 | 0 | 0 | 0 | 0 | 965.51 | 965.51 | 0 | 2025 | 2025 | < 250k
56.1135 | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 112.5 | 112.5 | 0 | 112.5 | 100% | 0 | 112.5 | 112.5 | 0 | 0 | 0 | 0 | 0 | 0 | 112.5 | 112.5 | 0 | 2025 | 2025 | < 250k
56.1141 | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 2827.5 | 2827.5 | 0 | 2827.5 | 100% | 0 | 2827.5 | 2827.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2827.5 | 2827.5 | 0 | 2025 | 2025 | < 250k
System Integration - Closed Jobs Totals |  | 4511779.65 | 7995768.94 | -3483989.29 | 7995768.94 |  | -3483989.29 | 4511779.65 | 4511779.65 | 0 | 0 | 0 | 1128586.33 | 734633.5 | 382674.1773 | 6867182.61 | 3777146.15 | -3866663.4673
System Integration - Grand Totals |  | 17542292.82 | 19151016.2 | -1608723.38 | 14455117.85 |  | -2377498.7804 | 12077619.0696 | 10435397.74 | -1642221.3296 | 4695898.35 | 7106895.08 | 2131284.86 | 1037078.5 | 725330.9858 | 12323832.99 | 9398319.24 | -3102829.7662
50 Jobs
50.0541 | W.M. Lyles Co. - General Overhead | 0 | 3642039.89 | -3642039.89 | 3642039.89 | 100% | -3642039.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3642039.89 | 0 | -3642039.89 | 50 | 50
50.0542 | W.M. Lyles Co. - General Estimating | 0 | 100487.45 | -100487.45 | 100487.45 | 100% | -100487.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100487.45 | 0 | -100487.45 | 50 | 50
50.0543 | American Paving | 7051.01 | 7051.01 | 0 | 7051.01 | 100% | 0 | 7051.01 | 7051.01 | 0 | 0 | 0 | 0 | 0 | 0 | 7051.01 | 7051.01 | 0 | 50 | 50
50.0544 | Lyles Services Co. | 13555.8 | 13555.8 | 0 | 13555.8 | 100% | 0 | 13555.8 | 13555.8 | 0 | 0 | 0 | 0 | 0 | 0 | 13555.8 | 13555.8 | 0 | 50 | 50
50.0545 | New England Sheet Metal and Mechanical Co. | 2226.16 | 2226.16 | 0 | 2226.16 | 100% | 0 | 2226.16 | 2226.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2226.16 | 2226.16 | 0 | 50 | 50
50.0546 | Lyles Utility Construction, LLC | 11256.72 | 10468.06 | 788.66 | 10468.06 | 100% | 788.66 | 11256.72 | 11256.72 | 0 | 0 | 0 | 0 | 0 | 0 | 10468.06 | 11256.72 | 788.66 | 50 | 50
50.0551 | Advanced Integration & Controls | 5457.42 | 5457.42 | 0 | 5457.42 | 100% | 0 | 5457.42 | 5457.42 | 0 | 0 | 0 | 0 | 0 | 0 | 5457.42 | 5457.42 | 0 | 50 | 50
50 Jobs Totals |  | 39547.11 | 3781285.79 | -3741738.68 | 3781285.79 |  | -3741738.68 | 39547.11 | 39547.11 | 0 | 0 | 0 | 0 | 0 | 0 | 3781285.79 | 39547.11 | -3741738.68
Open Jobs Totals |  | 1859122840 | 1734839582.43 | 124283257.57 | 1041534998.27 |  | 65410179.6972 | 1106945177.9672 | 1107424084.26 | 478906.2928 | 693304584.16 | 751698755.74 | 737998939.53 | 774452969.05 | 35006187.3047 | 303536058.74 | 332971115.21 | 30403992.3925 |  |  |  | 7279602.9381 | 23124389.4544 | - | - | #REF!
Closed Job Totals |  | 152608093.41 | 147840152.81 | 4767940.6 | 147840152.81 |  | 4767940.6 | 152608093.41 | 152608093.41 | 0 | 0 | 0 | 112492442.67 | 130560851.56 | 17890185.9346 | 35347710.14 | 22047241.85 | -13122245.3346 |  |  |  | -339414.4033 | -12782830.9313 | - | - | 152608093.41
Grand Totals |  | 2011730933.41 | 1882679735.24 | 129051198.17 | 1189375151.08 |  | 70178120.2972 | 1259553271.3772 | 1260032177.67 | 478906.2928 | 693304584.16 | 751698755.74 | 850491382.2 | 905013820.61 | 52896373.2393 | 338883768.88 | 355018357.06 | 17281747.0579 |  |  |  | 6940188.5348 | 10341558.5231 | - | - | 2011730933.41
Proof of GAAP Basis Profit/Loss:
| - This is a Joint Venture job - The work is being performed on a T&M basis and additional work will be completed in the new year. | [7 empty] | Billed Revenue |  |  | 355018357.06
| - This job is not complete, additional work to be completed in the new year | [7 empty] | Prior WIP |  | 1626065.1707
[9 empty] | Current WIP |  | -478906.2928 | 1147158.8779
[9 empty] | GAAP Revenue |  | 1147158.8779 | 356165515.9379
[9 empty] | Costs YTD |  |  | -338883768.88
[9 empty] | GAAP Profit/Loss |  |  | 17281747.0579
[9 empty] | Variance |  |  | -3.7253e-08
52.8446 - This job is not complete, additional work to be completed in the new year
52.8528 - This job is not complete, additional work to be completed in the new year
52.8563 - AECOM/Lyles Joint Venture. The work is being performed on a T&M basis and additional work will be completed in the new year.
54.9118 - This job is not complete, additional work to be completed in the new year
51.1108 - AECOM/Lyles Joint Venture. The work is being performed on a T&M basis and additional work will be completed in the new year.
51.1118 - Work is complete on this job but was left open pending owner approval of final change orders so project can be billed 100% - minor supervision time to also be charged in new year
55.1090 - Webcor/Obayashi/Lyles Joint Venture. The work is being performed on a T&M basis and additional work will be completed in the new year.
55.1159 - This job is not complete, additional work to be completed in the new year
55.1184 - This job is not complete, additional work to be completed in the new year
55.1200 - AECOM/Lyles Joint Venture. The work is being performed on a T&M basis and additional work will be completed in the new year.
55.1204 - AECOM/Lyles Joint Venture. The work is being performed on a T&M basis and additional work will be completed in the new year.
| Bonus Totals | 2024557298.82 | 1893652246.83 | 130905051.99 | 1189375151.08 |  | 71040611.8231 |  | 1260032177.67 |  | 704277095.75 | 764525121.15 | 850491382.2 | 905013820.61 |  | 338883768.88 | 355018357.06
| Variance Check | 12826365.41 | 10972511.59 | 1853853.82 | 0 |  | 862491.5259 |  | 0 |  | 10972511.59 | 12826365.41 | 0 | 0 | -52896373.2393 | 0 | 0
0
Formulas:
PY JTD BILLINGS = +[PY JTD COSTS]
PY JTD PROFIT = +[PY JTD COSTS]
Note on F6: Cindy Jordan: From Timberline Job Cost Summary jpVII - JTD COSTS
Note on P6: TThornton: PY JTD GAAP Profits

## Bonus WIP
W.M. Lyles Co.
WORK IN PROCESS - BONUS
For the Month Period Ended 12/31/2025
|  | AMOUNT | REMAINING | TOTAL | COSTS | ESTIMATED | TOTAL | TOTAL | % OF |  | OVER
|  | BILLED | TO BE | ESTIMATED | INCURED | COSTS TO | ESTIMATED | ESTIMATED | COMPLETION | PROFIT / | (UNDER)
| JOB | TO DATE | BILLED | CONTRACT | TO DATE | COMPLETE | COSTS | PROFIT | COST/COST | LOSS | BILLING
| 51.1108 | 94045647.86 | 150450.14 | 94196098 | 89805617.8 | 2211.2 | 89807829 | 4388269 | 100% | 4320758.91 | -80728.85
| 51.1129 | 96918206.9 | 29565373.94 | 126483580.84 | 87315159.22 | 27918421.62 | 115233580.84 | 11250000 | 75.77% | 9058793.1561 | 544254.5239
| 51.1137 | 1121900.01 | 190251.45 | 1312151.46 | 1042229.29 | 156282.17 | 1198511.46 | 113640 | 86.96% | 98821.6971 | -19150.9771
| 51.1144 | 9667725.77 | 5301840.23 | 14969566 | 8406760.8 | 5432856.2 | 13839617 | 1129949 | 60.74% | 686378.1678 | 574586.8022
| 51.1146 | 60980234 | 0 | 60980234 | 40950686.5 | 3246167.53 | 44196854.03 | 16783379.97 | 92.66% | 15724392.0373 | 4305155.4627
| 51.1151 | 5009265.21 | 5648934.79 | 10658200 | 4923435.18 | 5155916.82 | 10079352 | 578848 | 48.85% | 282748.3956 | -196918.3656
| 51.1152 | 15610649.01 | 4363840.33 | 19974489.34 | 13474808.54 | 5154139.8 | 18628948.34 | 1345541 | 72.33% | 973265.2121 | 1162575.2579
| 51.1153 | 549548.83 | 13275.85 | 562824.68 | 334550.81 | 119969.87 | 454520.68 | 108304 | 73.61% | 79717.365 | 135280.655
| 51.1154 | 13340008 | 23827 | 13363835 | 11872342.6 | 616492.4 | 12488835 | 875000 | 95.06% | 831806.952 | 635858.448
| 51.1158 | 32282 | 72164 | 104446 | 56960.69 | 47485.31 | 104446 | 0 | 54.54% | 0 | -24678.69
| 51.1159 | 732995 | 466005 | 1199000 | 790051.12 | 289188.88 | 1079240 | 119760 | 73.2% | 87669.5843 | -144725.7043
| 51.116 | 223725 | 1533275 | 1757000 | 250518.05 | 1439481.95 | 1690000 | 67000 | 14.82% | 0 | -26793.05
| 51.1161 | 745707.2 | 10102892.25 | 10848599.45 | 601852.17 | 9659400.28 | 10261252.45 | 587347 | 5.865% | 0 | 143855.03
| 51.1162 | 0 | 6029750 | 6029750 | 85941.38 | 5759321.62 | 5845263 | 184487 | 1.47% | 0 | -85941.38
| 51.1164 | 0 | 387260 | 387260 | 4363.25 | 379023.75 | 383387 | 3873 | 1.138% | 0 | -4363.25
| 51.1165 | 0 | 5304500 | 5304500 | 23330.33 | 4863112.67 | 4886443 | 418057 | 0.4775% | 0 | -23330.33
| 52.8563 | 1134038.13 | 40144.6 | 1174182.73 | 859077.05 | 21713.05 | 880790.1 | 293392.63 | 97.53% | 293385.24 | -18424.16
| 52.8566 | 1242053 | 17345 | 1259398 | 1023821.05 | 5576.95 | 1029398 | 230000 | 99.46% | 228753.9334 | -10521.9834
| 52.8586 | 12611349 | 0 | 12611349 | 10565460.74 | 95888.26 | 10661349 | 1950000 | 99.1% | 1932461.6841 | 113426.5759
| 52.8634 | 12576768.04 | 1315954.7 | 13892722.74 | 11707058.24 | 1483664.5 | 13190722.74 | 702000 | 88.75% | 623040.5298 | 246669.2702
| 52.8636 | 3065635.6 | 576561.4 | 3642197 | 3367047.36 | 149.64 | 3367197 | 275000 | 100% | 274987.7789 | -576399.5389
| 52.8637 | 26148625 | 115952.65 | 26264577.65 | 24374299.03 | 240278.62 | 24614577.65 | 1650000 | 99.02% | 1633893.2957 | 140432.6743
| 52.864 | 34176041.86 | 4470321.3 | 38646363.16 | 32158781.48 | 4614258.68 | 36773040.16 | 1873323 | 87.45% | 1638259.571 | 379000.809
| 52.8668 | 349622.76 | 62228.24 | 411851 | 357710.67 | 19285.33 | 376996 | 34855 | 94.88% | 33071.9833 | -41159.8933
| 52.8678 | 1142122 | 98199 | 1240321 | 926007.31 | 236313.69 | 1162321 | 78000 | 79.67% | 62141.6719 | 153973.0181
| 52.8687 | 827811.95 | 50142.05 | 877954 | 740629.43 | 50142.05 | 790771.48 | 87182.52 | 93.66% | 81654.3612 | 5528.1588
| 52.8692 | 55135.37 | 0 | 55135.37 | 49682.49 | 0 | 49682.49 | 5452.88 | 100% | 5452.88 | 0
| 52.8697 | 1069317 | 318683 | 1388000 | 772187.73 | 553294.27 | 1325482 | 62518 | 58.26% | 36421.1906 | 260708.0794
| 52.8698 | 0 | 22713 | 22713 | 15264 | 864 | 16128 | 6585 | 94.64% | 6232.2321 | -21496.2321
| 52.8704 | 1037950 | 12706050 | 13744000 | 820988.3 | 12670138.7 | 13491127 | 252873 | 6.085% | 0 | 216961.7
| 52.8705 | 261232 | 513768 | 775000 | 285425.72 | 433834.28 | 719260 | 55740 | 39.68% | 22119.4417 | -46313.1617
| 52.8707 | 913135 | 2780065 | 3693200 | 1012057.14 | 2449519.86 | 3461577 | 231623 | 29.24% | 67719.3403 | -166641.4803
| 52.8708 | 0 | 363833 | 363833 | 7682.19 | 326074.81 | 333757 | 30076 | 2.302% | 0 | -7682.19
| 52.8711 | 0 | 6860 | 6860 | 4568.81 | 1746.19 | 6315 | 545 | 72.35% | 394.2995 | -4963.1095
| 52.8713 | 0 | 218842 | 218842 | 927.5 | 189511.5 | 190439 | 28403 | 0.487% | 0 | -927.5
| 52.8714 | 5084.94 | 0 | 5084.94 | 4465.61 | 0 | 4465.61 | 619.33 | 100% | 619.33 | 0
| 53.2007 | 0 | 324530134 | 324530134 | 404852.16 | 291125281.84 | 291530134 | 33000000 | 0.1389% | 0 | -404852.16
| 54.9033 | 118278.58 | 0 | 118278.58 | 104550.27 | 0 | 104550.27 | 13728.31 | 100% | 13728.31 | 0
| 54.9135 | 9470658.62 | 0 | 9470658.62 | 9050951.86 | 0 | 9050951.86 | 419706.76 | 100% | 419706.76 | 0
| 54.9257 | 890983 | 580345 | 1471328 | 762211.05 | 664116.95 | 1426328 | 45000 | 53.44% | 24047.4121 | 104724.5379
| 54.9268 | 907298 | 42269.99 | 949567.99 | 844648.28 | 39919.71 | 884567.99 | 65000 | 95.49% | 65000 | -2350.28
| 54.9269 | 625819.17 | 0 | 625819.17 | 549817.74 | 41752.38 | 591570.12 | 34249.05 | 92.94% | 34249.05 | 41752.38
| 54.9285 | 427226 | 34796 | 462022 | 312939.77 | 74082.23 | 387022 | 75000 | 80.86% | 60643.7948 | 53642.4352
| 54.9313 | 7886885 | 0.04 | 7886885.04 | 6449205.22 | 427679.82 | 6876885.04 | 1010000 | 93.78% | 947187.1689 | 490492.6111
| 54.933 | 324900 | 0 | 324900 | 306221.41 | 1419.59 | 307641 | 17259 | 99.54% | 17179.3594 | 1499.2306
| 54.9336 | 14176592.91 | 11014583.73 | 25191176.64 | 12340864.27 | 10930312.37 | 23271176.64 | 1920000 | 53.03% | 1018189.1429 | 817539.4971
| 54.9337 | 520441.66 | 3584406.34 | 4104848 | 1509066.73 | 2435781.27 | 3944848 | 160000 | 38.25% | 61206.5856 | -1049831.6556
| 54.9343 | 3954560 | 2926740 | 6881300 | 3415344.08 | 2565955.92 | 5981300 | 900000 | 57.1% | 513903.2772 | 25312.6428
| 54.9356 | 685017 | 613313 | 1298330 | 775780.75 | 137549.25 | 913330 | 385000 | 84.94% | 327018.2615 | -417782.0115
| 54.9366 | 1160831 | 69300 | 1230131 | 923220.5 | 156910.5 | 1080131 | 150000 | 85.47% | 128209.5181 | 109400.9819
| 54.9369 | 2927422.95 | 25623201.75 | 28550624.7 | 2787466.66 | 23392315.04 | 26179781.7 | 2370843 | 10.65% | 0 | 139956.29
| 54.9373 | 0 | 1524766 | 1524766 | 50303.97 | 1343022.03 | 1393326 | 131440 | 3.61% | 0 | -50303.97
| 54.9389 | 291620 | 8160 | 299780 | 311891.85 | 2888.15 | 314780 | -15000 | 99.08% | -15000 | -5271.85
| 54.9391 | 532604.57 | 0 | 532604.57 | 512057.34 | 0 | 512057.34 | 20547.23 | 100% | 20547.23 | 0
| 54.9395 | 1374448.17 | 421204.49 | 1795652.66 | 1349601.92 | 344050.74 | 1693652.66 | 102000 | 79.69% | 81279.5912 | -56433.3412
| 54.9396 | 0 | 157746.09 | 157746.09 | 157746.09 | 0 | 157746.09 | 0 | 100% | 0 | -157746.09
| 54.9397 | 1033150.21 | 2657494.79 | 3690645 | 1035065.41 | 2355579.59 | 3390645 | 300000 | 30.53% | 91581.2841 | -93496.4841
| 54.9403 | 140100 | 241500 | 381600 | 129004.89 | 209096.11 | 338101 | 43499 | 38.16% | 16597.3591 | -5502.2491
| 54.9404 | 1746890 | 1973110 | 3720000 | 1939024.63 | 1646367.37 | 3585392 | 134608 | 54.08% | 72797.6822 | -264932.3122
| 54.9405 | 746125 | 195875 | 942000 | 577796.16 | 234203.84 | 812000 | 130000 | 71.16% | 92504.3113 | 75824.5287
| 54.9406 | 0 | 1120.65 | 1120.65 | 1120.65 | 0 | 1120.65 | 0 | 100% | 0 | -1120.65
| 54.9408 | 0 | 3777777 | 3777777 | 41652.43 | 3495532.57 | 3537185 | 240592 | 1.178% | 0 | -41652.43
| 54.9411 | 103000 | 300 | 103300 | 71370.85 | 6929.15 | 78300 | 25000 | 91.15% | 22787.6277 | 8841.5223
| 54.9412 | 116752.04 | 0 | 116752.04 | 115708.88 | 0 | 115708.88 | 1043.16 | 100% | 1043.16 | 0
| 54.9413 | 149366.83 | 0 | 149366.83 | 132138.74 | 0 | 132138.74 | 17228.09 | 100% | 17228.09 | 0
| 54.9414 | 0 | 358674.83 | 358674.83 | 337485.68 | 1189.15 | 338674.83 | 20000 | 99.65% | 19929.7763 | -357415.4563
| 54.9416 | 0 | 1260000 | 1260000 | 7257.82 | 1125140.18 | 1132398 | 127602 | 0.6409% | 0 | -7257.82
| 54.9417 | 0 | 48439 | 48439 | 2299.41 | 40593.59 | 42893 | 5546 | 5.361% | 0 | -2299.41
| 54.9418 | 0 | 15739 | 15739 | 15739 | 0 | 15739 | 0 | 100% | 0 | -15739
| 54.9421 | 0 | 3703.18 | 3703.18 | 3703.18 | 0 | 3703.18 | 0 | 100% | 0 | -3703.18
| 55.109 | 5235272.36 | 164727.64 | 5400000 | 3834064.05 | 65935.95 | 3900000 | 1500000 | 98.31% | 1474640.0192 | -73431.7092
| 55.1191 | 296634984.51 | 44808149.2 | 341443133.71 | 299179624.84 | 38553010.87 | 337732635.71 | 3710498 | 88.58% | 3710498 | -6255138.33
| 55.1192 | 6645760.51 | 6043.02 | 6651803.53 | 6393992.69 | 7810.84 | 6401803.53 | 250000 | 99.88% | 250000 | 1767.82
| 55.12 | 197175877 | 900000 | 198075877 | 189971137.49 | 4739.51 | 189975877 | 8100000 | 100% | 7779994.28 | -575254.77
| 55.1202 | 10912272.58 | 5483779 | 16396051.58 | 9590124.35 | 5630518.23 | 15220642.58 | 1175409 | 63.01% | 740594.1249 | 581554.1051
| 55.1204 | 57142227 | 580000 | 57722227 | 55213329.21 | 8897.79 | 55222227 | 2500000 | 99.98% | 2362039.01 | -433141.22
| 55.1227 | 41483406.39 | 20800 | 41504206.39 | 36953022.96 | 201183.43 | 37154206.39 | 4350000 | 99.46% | 4326445.5224 | 203937.9076
| 55.1233 | 123617 | 9714570 | 9838187 | 126077.16 | 9712109.84 | 9838187 | 0 | 1.282% | 8429 | -10889.16
| 55.1248 | 4861991.81 | 897310 | 5759301.81 | 3621770.22 | 1312531.59 | 4934301.81 | 825000 | 73.4% | 605548.778 | 634672.812
| 55.1249 | 15047042.84 | 132478070.16 | 147525113 | 15046313.77 | 124657591.23 | 139703905 | 7821208 | 10.77% | 0 | 729.07
| 55.1254 | 158952.89 | 312943.36 | 471896.25 | 156561.66 | 315334.59 | 471896.25 | 0 | 33.18% | 0 | 2391.23
| 55.1255 | 0 | 14160.81 | 14160.81 | 14160.81 | 0 | 14160.81 | 0 | 100% | 0 | -14160.81
| 55.1256 | 101150 | 2786950 | 2888100 | 94989.88 | 2618110.12 | 2713100 | 175000 | 3.501% | 0 | 6160.12
| 57.0003 | 6863233.25 | 31302186.25 | 38165419.5 | 6316909.13 | 29441424.37 | 35758333.5 | 2407086 | 17.67% | 123922.1725 | 422401.9475
| 57.0004 | 900072.76 | 39206151.87 | 40106224.63 | 750298.86 | 37146068.77 | 37896367.63 | 2209857 | 1.98% | 0 | 149773.9
| 57.0007 | 153858.36 | 8771.64 | 162630 | 196248.4 | 0 | 196248.4 | -33618.4 | 100% | -33618.4 | -8771.64
| 57.0008 | 266758 | 2609289 | 2876047 | 262382.86 | 2481599.14 | 2743982 | 132065 | 9.562% | 0 | 4375.14
| 58.0003 | 11889201.76 | 10635987.24 | 22525189 | 11034781.79 | 10182392.21 | 21217174 | 1308015 | 52.01% | 680281.9312 | 174138.0388
| 56.1004 | 371550 | 1875 | 373425 | 236373.73 | 33466.27 | 269840 | 103585 | 87.6% | 90738.1145 | 44438.1555
| 56.1005 | 135000 | 0 | 135000 | 51037.42 | 16987.58 | 68025 | 66975 | 75.03% | 50249.6318 | 33712.9482
| 56.101 | 49250 | 0 | 49250 | 36461.94 | 0 | 36461.94 | 12788.06 | 100% | 12788.06 | 0
| 56.1015 | 160000 | 70000 | 230000 | 142358.95 | 61161.05 | 203520 | 26480 | 69.95% | 18522.3319 | -881.2819
| 56.1017 | 99118 | 3750 | 102868 | 95450.46 | 19444.54 | 114895 | -12027 | 83.08% | -12027 | 15694.54
| 56.1018 | 50000 | 103913 | 153913 | 41991.15 | 29053.85 | 71045 | 82868 | 59.11% | 48979.1346 | -40970.2846
| 56.1032 | 0 | 85000 | 85000 | 35024.34 | 47950.66 | 82975 | 2025 | 42.21% | 854.767 | -35879.107
| 56.1036 | 48000 | 228000 | 276000 | 107051.95 | 101972.05 | 209024 | 66976 | 51.22% | 34301.8572 | -93353.8072
| 56.1037 | 36491 | 0 | 36491 | 21674.2 | 0 | 21674.2 | 14816.8 | 100% | 14816.8 | 0
| 56.1038 | 0 | 95000 | 95000 | 100049.89 | 17326.11 | 117376 | -22376 | 85.24% | -22376 | -77673.89
| 56.1039 | 330000 | 45000 | 375000 | 324049.23 | 8234.77 | 332284 | 42716 | 97.52% | 41657.3982 | -35706.6282
| 56.1042 | 217715 | 59850 | 277565 | 172683.27 | 45604.73 | 218288 | 59277 | 79.11% | 46892.8489 | -1861.1189
| 56.1043 | 0 | 336610 | 336610 | 214994.3 | 96396.7 | 311391 | 25219 | 69.04% | 17412.0037 | -232406.3037
| 56.1046 | 75120 | 2000 | 77120 | 77765.8 | 2190.2 | 79956 | -2836 | 97.26% | -2836 | 190.2
| 56.1047 | 1905218.25 | 489539.75 | 2394758 | 1602869.63 | 437685.37 | 2040555 | 354203 | 78.55% | 278228.8307 | 24119.7893
| 56.1048 | 187500 | 12500 | 200000 | 157916.15 | 3202.85 | 161119 | 38881 | 98.01% | 38108.093 | -8524.243
| 56.1049 | 291725 | 17000 | 308725 | 214423.06 | 34449.94 | 248873 | 59852 | 86.16% | 51567.0603 | 25734.8797
| 56.105 | 675979.5 | 3116579.5 | 3792559 | 925847.53 | 2439719.47 | 3365567 | 426992 | 27.51% | 117462.9679 | -367330.9979
| 56.1055 | 120891 | 0 | 120891 | 78736.44 | 14111.56 | 92848 | 28043 | 84.8% | 23780.8675 | 18373.6925
| 56.1059 | 0 | 399389 | 399389 | 235841.92 | 93364.08 | 329206 | 70183 | 71.64% | 50278.8329 | -286120.7529
| 56.106 | 0 | 404663 | 404663 | 145563.36 | 176927.64 | 322491 | 82172 | 45.14% | 37090.1278 | -182653.4878
| 56.1063 | 10000 | 98000 | 108000 | 74040.41 | 23880.59 | 97921 | 10079 | 75.61% | 7620.973 | -71661.383
| 56.1066 | 570000 | 25000 | 595000 | 476030.06 | 55459.94 | 531490 | 63510 | 89.57% | 56882.856 | 37087.084
| 56.1067 | 217000 | 261000 | 478000 | 104751.99 | 311126.01 | 415878 | 62122 | 25.19% | 15647.3849 | 96600.6251
| 56.1073 | 0 | 122210 | 122210 | 108855.81 | 5191.19 | 114047 | 8163 | 95.45% | 7791.4367 | -116647.2467
| 56.1075 | 0 | 950000 | 950000 | 27665.92 | 751382.08 | 779048 | 170952 | 3.551% | 0 | -27665.92
| 56.1078 | 17050.24 | 8306.01 | 25356.25 | 25356.25 | 0 | 25356.25 | 0 | 100% | 0 | -8306.01
| 56.1081 | 164416.35 | 15273.65 | 179690 | 156744.37 | 3040.63 | 159785 | 19905 | 98.1% | 19526.2176 | -11854.2376
| 56.1083 | 153616.75 | 563393.25 | 717010 | 347967.35 | 308395.65 | 656363 | 60647 | 53.01% | 32151.6842 | -226502.2842
| 56.1085 | 0 | 80000 | 80000 | 1090.31 | 65864.69 | 66955 | 13045 | 1.628% | 0 | -1090.31
| 56.1086 | 0 | 376000 | 376000 | 12732.69 | 282369.31 | 295102 | 80898 | 4.315% | 0 | -12732.69
| 56.1087 | 37977 | 11392 | 49369 | 39121.54 | 3904.46 | 43026 | 6343 | 90.93% | 5767.3948 | -6911.9348
| 56.1088 | 0 | 117985 | 117985 | 66827.49 | 18577.51 | 85405 | 32580 | 78.25% | 25493.1166 | -92320.6066
|  | 1107424084.26 | 764525121.15 | 1871949205.41 | 1041534998.27 | 704277095.75 | 1745812094.02 | 126137111.39 |  | 66272671.2231 | -383585.2331
Proof of Construction Basis WIP:
[7 empty] | YTD Costs |  |  | 338883768.88
Prior year adjustment
[7 empty] | YTD Profit |  |  | 12136213.6583
[7 empty] | YTD Amount Billed |  |  | -355018357.06
[7 empty] | WIP |  |  | -3998374.5217
|  | -2.1048e-07 |  |  | 2.5332e-07 |  |  |  |  | 0.0051393 |  | Column K should equal zero; variance check

## Bonus
W.M. Lyles Co. | [27 empty] | W.M. Lyles Co.
PROFIT AND LOSS BY JOB - BONUS BASIS | [27 empty] | PROFIT AND LOSS BY JOB (GAAP Basis)
FISCAL YEAR ENDING 12/31/25 | [27 empty] | FISCAL YEAR ENDING 12/31/25
For the Month Period Ended 12/31/2025 | [27 empty] | For the 3 Months Period Ended 3/31/25
|  |  |  | (input cell if not 100% complete) |  |  | (input cell if not 100% complete) | [5 empty] | (Input cell) | (Input cell) | (Input cell)
|  | CONTRACT | EST. TOTAL | EXPECTED |  | COST / | JOB TO DATE | JOB TO DATE |  |  | EST. COST TO | CONTRACT | PY JTD COSTS | PY JTD BILLINGS | PY JTD PROFIT |  |  |  | Fiscal Y/E | Fiscal Y/E |  | Prior Year | Prior Month |  |  |  |  | CONTRACT | EST. TOTAL | EXPECTED | COST / | JOB TO DATE | JOB TO DATE |  | EST. COST TO | CONTRACT | PY JTD PROFIT
JOB |  | AMOUNT | COSTS | PROFIT | JTD JOB COST | COST | PROFIT/LOSS | EARNED REV. | JTD BILLED | CURRENT WIP | COMPLETE | BALANCE | 2024-12-31 | 2024-12-31 | 2024-12-31 | YTD COSTS | YTD BILLINGS | YTD PROFITS | Job Open | Job Closes |  | GAAP Profit | YTD Profit |  |  |  |  | AMOUNT | COSTS | PROFIT | COST | PROFIT/LOSS | EARNED REV. | CURRENT WIP | COMPLETE | BALANCE | 2024-12-31 | YTD PROFITS
Rocklin Area - Open Jobs
51.1108 | City of Stockton - RWCF Phase 2A/2B | 94196098 | 89807829 | 4388269 | 89805617.8 | 100% | 4320758.91 | 94126376.71 | 94045647.86 | -80728.85 | 2211.2 | 150450.14 | 88519194.97 | 92554957.54 | 4328399.75 | 1286422.83 | 1490690.32 | -7640.84 | 2019 |  | . | 4035762.57 | -7449.41 | -191.43 | - | - | 150450.14 | 94045647.86 | 89805617.8 | 4240030.06 | 100% | 4240030.06 | 94045647.86 | 0 | 0 | 0 | 4035762.57 | 204267.49
51.1129 | Union Sanit. Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin | 126483580.84 | 115233580.84 | 11250000 | 87315159.22 | 75.77% | 9058793.1561 | 96373952.3761 | 96918206.9 | 544254.5239 | 27918421.62 | 29565373.94 | 63757070.67 | 66921921.33 | 7950623.3602 | 23558088.55 | 29996285.57 | 1108169.7959 | 2022 |  | . | 6957477.3602 | 1046498.818 | 61670.9778 | - | - | #REF! | 126483580.84 | 115233580.84 | 11250000 | 75.77% | 8524386.1561 | 95839545.3761 | 1078661.5239 | 27918421.62 | 29565373.94 | 6957477.3602 | 1566908.7959
51.1137 | CA Water Service Co. - Bear Gulch Pump Station 18 | 1312151.46 | 1198511.46 | 113640 | 1042229.29 | 86.96% | 98821.6971 | 1141050.9871 | 1121900.01 | -19150.9771 | 156282.17 | 190251.45 | 271684.42 | 78558 | 27243.5887 | 770544.87 | 1043342.01 | 71578.1085 | 2023 |  | . | 27243.5887 | 69534.5908 | 2043.5177 | - | - | -59668082.54 | 1312151.46 | 1198511.46 | 113640 | 86.96% | 98821.6971 | 1141050.9871 | -19150.9771 | 156282.17 | 190251.45 | 90331.4512 | 8490.246
51.1144 | Silicon Valley Clean Water - FEP Improvements Project | 14969566 | 13839617 | 1129949 | 8406760.8 | 60.74% | 686378.1678 | 9093138.9678 | 9667725.77 | 574586.8022 | 5432856.2 | 5301840.23 | 1353379.42 | 1514359.61 | 90331.4512 | 7053381.38 | 8153366.16 | 596046.7166 | 2023 |  | . | 90331.4512 | 583236.08 | 12810.6366 | - | - | #REF! | 14969566 | 13839617 | 1129949 | 60.74% | 686378.1678 | 9093138.9678 | 574586.8022 | 5432856.2 | 5301840.23 | 12859.3892 | 673518.7786
51.1146 | National Carbon Technologies, LLC - Aymium Williams Production Facility | 60980234 | 44196854.03 | 16783379.97 | 40950686.5 | 92.66% | 15724392.0373 | 56675078.5373 | 60980234 | 4305155.4627 | 3246167.53 | 0 | 4561081.21 | 9363858.45 | 1082047.42 | 36389605.29 | 51616375.55 | 14642344.6173 | 2023 |  | . | 0 | 12567243.872 | 2075100.7452 | - | - | #REF! | 60980234 | 44196854.03 | 16783379.97 | 92.66% | 15550675.419 | 56501361.919 | 4478872.081 | 3246167.53 | 0 | 94320.4226 | 15456354.9964
51.1151 | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 10658200 | 10079352 | 578848 | 4923435.18 | 48.85% | 282748.3956 | 5206183.5756 | 5009265.21 | -196918.3656 | 5155916.82 | 5648934.79 | 187144.08 | 0 | 0 | 4736291.1 | 5009265.21 | 282748.3956 | 2024 |  | . | 0 | 237121.1834 | 45627.2123 | - | - | 8901200 | 10658200 | 10079352 | 578848 | 48.85% | 282748.3956 | 5206183.5756 | -196918.3656 | 5155916.82 | 5648934.79 | #REF! | #REF!
51.1152 | Mozingo Construction Inc - ElD Sly Park Intertie Project | 19974489.34 | 18628948.34 | 1345541 | 13474808.54 | 72.33% | 973265.2121 | 14448073.7521 | 15610649.01 | 1162575.2579 | 5154139.8 | 4363840.33 | 1446770.9 | 2807450 | 0 | 12028037.64 | 12803199.01 | 973265.2121 | 2024 |  | . | 0 | 886014.5356 | 87250.6765 | - | - | 19974489.34 | 19974489.34 | 18628948.34 | 1345541 | 72.33% | 973265.2121 | 14448073.7521 | 1162575.2579 | 5154139.8 | 4363840.33 | 0 | 973265.2121
51.1153 | Linda County Water Dist. - Aeration Blower Replacement | 562824.68 | 454520.68 | 108304 | 334550.81 | 73.61% | 79717.365 | 414268.175 | 549548.83 | 135280.655 | 119969.87 | 13275.85 | 98963.36 | 116846.83 | 12859.3892 | 235587.45 | 432702 | 66857.9758 | 2024 |  | . | 12859.3892 | 69213.4232 | -2355.4474 | - | - | -367418259.95 | 562824.68 | 454520.68 | 108304 | 73.61% | 79717.365 | 414268.175 | 135280.655 | 119969.87 | 13275.85 | 0 | 79717.365
51.1154 | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 13363835 | 12488835 | 875000 | 11872342.6 | 95.06% | 831806.952 | 12704149.552 | 13340008 | 635858.448 | 616492.4 | 23827 | 2378559.16 | 3186935 | 0 | 9493783.44 | 10153073 | 831806.952 | 2024 |  | . | 94320.4226 | 808730.1128 | 23076.8391 | - | - | 13363835 | 13363835 | 12488835 | 875000 | 95.06% | 831806.952 | 12704149.552 | 635858.448 | 616492.4 | 23827 | 0 | 831806.952
51.1158 | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 104446 | 104446 | 0 | 56960.69 | 54.54% | 0 | 56960.69 | 32282 | -24678.69 | 47485.31 | 72164 |  |  |  | 56960.69 | 32282 | 0 | 2025 |  | < 250k |  | 0 | 0 | - | - |  | 104446 | 104446 | 0 | 54.54% | 0 | 56960.69 | -24678.69 | 47485.31 | 72164 | 0 | 0
51.1159 | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 1199000 | 1079240 | 119760 | 790051.12 | 73.2% | 87669.5843 | 877720.7043 | 732995 | -144725.7043 | 289188.88 | 466005 |  |  |  | 790051.12 | 732995 | 87669.5843 | 2025 |  | . |  | 78896.8713 | 8772.713 | - | -
51.116 | City of Galt Public Works - Industrial WWTP Expansion | 1757000 | 1690000 | 67000 | 250518.05 | 14.82% | 0 | 250518.05 | 223725 | -26793.05 | 1439481.95 | 1533275 |  |  |  | 250518.05 | 223725 | 0 | 2025 |  | . |  | 0 | 0 | - | -
51.1161 | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | 10848599.45 | 10261252.45 | 587347 | 601852.17 | 5.865% | 0 | 601852.17 | 745707.2 | 143855.03 | 9659400.28 | 10102892.25 |  |  |  | 601852.17 | 745707.2 | 0 | 2025 |  | . |  | 0 | 0 | - | -
51.1162 | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project | 6029750 | 5845263 | 184487 | 85941.38 | 1.47% | 0 | 85941.38 | 0 | -85941.38 | 5759321.62 | 6029750 |  |  |  | 85941.38 | 0 | 0 | 2025 |  | . |  | 0 | 0 | - | -
51.1164 | CA Water Service Co. - Stockton Roofing | 387260 | 383387 | 3873 | 4363.25 | 1.138% | 0 | 4363.25 | 0 | -4363.25 | 379023.75 | 387260 |  |  |  | 4363.25 | 0 | 0 | 2025 |  | . |  |  | 0 | - | -
51.1165 | City of Yuba City - WTP Aquifer Storage and Recovery Well No. 3 | 5304500 | 4886443 | 418057 | 23330.33 | 0.4775% | 0 | 23330.33 | 0 | -23330.33 | 4863112.67 | 5304500 |  |  |  | 23330.33 | 0 | 0 | 2025 |  | . |  |  | 0 | - | -
[9 empty] | 0 | [14 empty] | 0 | - | - | 0
Rocklin Area - Open Job Totals |  | 368131534.77 | 330178079.8 | 37953454.97 | 259938607.73 |  | 32144351.4772 | 292082959.2072 | 298977894.79 | 6894935.5828 | 70239472.07 | 69153639.98 | 162573848.19 | 176544886.76 | 13491504.9592 | 97364759.54 | 122433008.03 | 18652846.518 |  |  |  |  | 15004219.8295 | 3648626.6885 | - | - | 150450.14 | 342454975.18 | 306030283.15 | 36424692.03 |  | 31267829.4247 | 289450380.8547 | 7825086.7353 | 47847731.72 | 45179507.59 | #REF! | #REF!
[24 empty] | 0 | - | - | 0
Rocklin Area - Closed Jobs | [23 empty] | 0 | - | - | 0
51.1133 | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 372738 | 331855.28 | 40882.72 | 331855.28 | 100% | 40882.72 | 372738 | 372738 | 0 | 0 | 0 | 303125.41 | 326664 | 17359.5806 | 28729.87 | 46074 | 23523.1394 | 2023 | 2025 | . | 17359.5806 | 23523.1394 | 0 | - | - | 372738 | 372738 | 331855.28 | 40882.72 | 100% | 40882.72 | 372738 | 0 | 0 | 0 | 77778.0991 | -36895.3791
51.1136 | Union Sanitary Dist - USD Plant Misc. Improvements | 5483550 | 4531817.86 | 951732.14 | 4531817.86 | 100% | 951732.14 | 5483550 | 5483550 | 0 | 0 | 0 | 4229332.84 | 5133927.2 | 758905.7861 | 302485.02 | 349622.8 | 192826.3539 | 2023 | 2025 | . | 758905.7861 | 461110.1613 | -268283.8074 | - | - | 1516360.21 | 5483550 | 4531817.86 | 951732.14 | 100% | 951732.14 | 5483550 | 0 | 0 | 0 | 4426.359 | 947305.781
51.1138 | CA Water Service Co. - Bear Gulch Pump Station 21 | 1120182.07 | 1167704.15 | -47522.08 | 1167704.15 | 100% | -47522.08 | 1120182.07 | 1120182.07 | 0 | 0 | 0 | 786902.05 | 831943.71 | 77778.0991 | 380802.1 | 288238.36 | -125300.1791 | 2023 | 2025 | . | 77778.0991 | -125300.1791 | 0 | - | - | 0 | 1120182.07 | 1167704.15 | -47522.08 | 100% | -47522.08 | 1120182.07 | 0 | 0 | 0 | 758905.7861 | -806427.8661
51.1139 | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 61902 | 56994.44 | 4907.56 | 56994.44 | 100% | 4907.56 | 61902 | 61902 | 0 | 0 | 0 | 56994.44 | 61902 | 4426.359 | 0 | 0 | 481.201 | 2023 | 2025 | < 250k | 4426.359 | 5781.371 | -5300.17 | - | - | #REF! | 61902 | 56994.44 | 4907.56 | 100% | 4907.56 | 61902 | 0 | 0 | 0 | 0 | 4907.56
51.1141 | City of Colfax - WWTP Algae Reduction Project | 3967189.79 | 3835094.73 | 132095.06 | 3835094.73 | 100% | 132095.06 | 3967189.79 | 3967189.79 | 0 | 0 | 0 | 3109905.76 | 3392862.8 | 79920.2987 | 725188.97 | 574326.99 | 52174.7613 | 2023 | 2025 | . | 79920.2987 | 52174.7613 | 0 | - | - | -382239779.73 | 3967189.79 | 3835094.73 | 132095.06 | 100% | 132095.06 | 3967189.79 | 0 | 0 | 0 | 0 | 132095.06
51.1143 | Olivehurst Plumas Lake Manganese Filter Expansion | 1991231.37 | 1758132.57 | 233098.8 | 1758132.57 | 100% | 233098.8 | 1991231.37 | 1991231.37 | 0 | 0 | 0 | 1730690.97 | 1955683.37 | 226011.7629 | 27441.6 | 35548 | 7087.0371 | 2023 | 2025 | . | 226011.7629 | 7087.0371 | 0 | - | - | 1991231.37 | 1991231.37 | 1758132.57 | 233098.8 | 100% | 233098.8 | 1991231.37 | 0 | 0 | 0 | 1459158.2509 | -1226059.4509
51.1147 | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 2742860.08 | 2548724.92 | 194135.16 | 2548724.92 | 100% | 194135.16 | 2742860.08 | 2742860.08 | 0 | 0 | 0 | 1749912.32 | 1894059.69 | 128284.5352 | 798812.6 | 848800.39 | 65850.6248 | 2023 | 2025 | . | 128284.5352 | 65962.1248 | -111.5 | - | - | 2742860.08 | 2742860.08 | 2548724.92 | 194135.16 | 100% | 194135.16 | 2742860.08 | 0 | 0 | 0 | #REF! | #REF!
51.115 | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 2486231.58 | 2239435.14 | 246796.44 | 2239435.14 | 100% | 246796.44 | 2486231.58 | 2486231.58 | 0 | 0 | 0 | 2071076.8 | 2378955.76 | 166471.8295 | 168358.34 | 107275.82 | 80324.6105 | 2024 | 2025 | . | 166471.8295 | 80324.6105 | 0 | - | - | 1226833.58 | 2486231.58 | 2239435.14 | 246796.44 | 100% | 246796.44 | 2486231.58 | 0 | 0 | 0 | 0 | 246796.44
51.1156 | Rocklin Overhead 2025 |  | 1426058.69 | -1426058.69 | 1426058.69 | 100% | -1426058.69 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1426058.69 | 0 | -1426058.69 | 2025 | 2025 | OH |  | -1249321.23 | -176737.46 | - | - |  | 0 | 1426058.69 | -1426058.69 | 100% | -1426058.69 | 0 | 0 | 0 | 0 | 194465.74 | -1620524.43
51.1157 | Rocklin Estimating 2025 |  | 613546.52 | -613546.52 | 613546.52 | 100% | -613546.52 | 0 | 0 | 0 | 0 | 0 |  |  |  | 613546.52 | 0 | -613546.52 | 2025 | 2025 | OH |  | -552390.55 | -61155.97 | - | - |  | 0 | 613546.52 | -613546.52 | 100% | -613546.52 | 0 | 0 | 0 | 0 | 223974.5063 | -837521.0263
[24 empty] | 0 | - | - | 0
Rocklin Area - Closed Totals |  | 18225884.89 | 18509364.3 | -283479.41 | 18509364.3 |  | -283479.41 | 18225884.89 | 18225884.89 | 0 | 0 | 0 | 14037940.59 | 15975998.53 | 1459158.2509 | 4471423.71 | 2249886.36 | -1742637.6609 |  |  |  |  | 103771.4942 | -1846409.155 | - | - | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rocklin Area - Grand Totals |  | 386357419.66 | 348687444.1 | 37669975.56 | 278447972.03 |  | 31860872.0672 | 310308844.0972 | 317203779.68 | 6894935.5828 | 70239472.07 | 69153639.98 | 176611788.78 | 192520885.29 | 14950663.2101 | 101836183.25 | 124682894.39 | 16910208.8571 |  |  |  |  | 15107991.3237 | 1802217.5334 | - | - | 150450.14 | 342454975.18 | 306030283.15 | 36424692.03 |  | 31267829.4247 | 289450380.8547 | 7825086.7353 | 47847731.72 | 45179507.59 | #REF! | #REF!
[24 empty] | 0 | - | - | 0
Fresno Area - Open Jobs | [23 empty] | 0 | - | - | 0
52.8563 | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 1174182.73 | 880790.1 | 293392.63 | 859077.05 | 97.53% | 293385.24 | 1152462.29 | 1134038.13 | -18424.16 | 21713.05 | 40144.6 | 720866.75 | 915332.49 | 264189.76 | 138210.3 | 218705.64 | 29195.48 | 2021 |  | . | 194465.74 | 29163.93 | 31.55 | - | - | 40144.6 | 1134038.13 | 859077.05 | 274961.08 | 100% | 274961.08 | 1134038.13 | 0 | 0 | 0 | 194465.74 | 80495.34
52.8566 | City of Visalia - Water Reclamation Facility RPGS SCR System | 1259398 | 1029398 | 230000 | 1023821.05 | 99.46% | 228753.9334 | 1252574.9834 | 1242053 | -10521.9834 | 5576.95 | 17345 | 994790.56 | 1242053 | 223974.5063 | 29030.49 | 0 | 4779.4271 | 2021 |  | . | 223974.5063 | 4779.4271 | 0 | - | - | 0 | 1259398 | 1029398 | 230000 | 99.46% | 228753.9334 | 1252574.9834 | -10521.9834 | 5576.95 | 17345 | 223974.5063 | 4779.4271
52.8586 | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 12611349 | 10661349 | 1950000 | 10565460.74 | 99.1% | 1932461.6841 | 12497922.4241 | 12611349 | 113426.5759 | 95888.26 | 0 | 10233292.71 | 12384954 | 1757780.0079 | 332168.03 | 226395 | 174681.6762 | 2022 |  | . | 1757780.0079 | 143241.8481 | 31439.8281 | - | - | -1281373.74 | 12611349 | 10661349 | 1950000 | 99.1% | 1932461.6841 | 12497922.4241 | 113426.5759 | 95888.26 | 0 | 277972.0115 | 1654489.6726
52.8634 | City of Huron - Water Treatment Plant Imp. Phase 2 | 13892722.74 | 13190722.74 | 702000 | 11707058.24 | 88.75% | 623040.5298 | 12330098.7698 | 12576768.04 | 246669.2702 | 1483664.5 | 1315954.7 | 5213426.62 | 5564075.37 | 277972.0115 | 6493631.62 | 7012692.67 | 345068.5183 | 2023 |  | . | 277972.0115 | 294632.3535 | 50436.1648 | - | - | 13480871.74 | 13892722.74 | 13190722.74 | 702000 | 88.75% | 623040.5298 | 12330098.7698 | 246669.2702 | 1483664.5 | 1315954.7 | 5273.0464 | 617767.4834
52.8636 | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 3642197 | 3367197 | 275000 | 3367047.36 | 100% | 274987.7789 | 3642035.1389 | 3065635.6 | -576399.5389 | 149.64 | 576561.4 | 1456799.54 | 1731771.2 | 204319.7111 | 1910247.82 | 1333864.4 | 70668.0678 | 2023 |  | . | 204319.7111 | 94375.756 | -23707.6882 | - | - | 2401876 | 3642197 | 3367197 | 275000 | 100% | 274987.7789 | 3642035.1389 | -576399.5389 | 149.64 | 576561.4 | 0 | 274987.7789
52.8637 | Root Creek Water Dist. - Groundwater Blending & Arsenic | 26264577.65 | 24614577.65 | 1650000 | 24374299.03 | 99.02% | 1633893.2957 | 26008192.3257 | 26148625 | 140432.6743 | 240278.62 | 115952.65 | 19441814.99 | 20860138 | 1208391.7577 | 4932484.04 | 5288487 | 425501.538 | 2023 |  | . | 1208391.7577 | 397926.4632 | 27575.0748 | - | - | #REF! | 26264577.65 | 24614577.65 | 1650000 | 99.02% | 1633893.2957 | 26008192.3257 | 140432.6743 | 240278.62 | 115952.65 | #REF! | #REF!
52.864 | City of Dos Palos - WTP Replacement Project | 38646363.16 | 36773040.16 | 1873323 | 32158781.48 | 87.45% | 1638259.571 | 33797041.051 | 34176041.86 | 379000.809 | 4614258.68 | 4470321.3 | 13034452.74 | 13664733.79 | 703966.8389 | 19124328.74 | 20511308.07 | 934292.7322 | 2023 |  | . | 703966.8389 | 825614.7556 | 108677.9766 | - | - | #REF! | 38646363.16 | 36773040.16 | 1873323 | 87.45% | 1638259.571 | 33797041.051 | 379000.809 | 4614258.68 | 4470321.3 | #REF! | #REF!
52.8668 | California Water Service Co. - Cal Water - Salinas Station 57 | 411851 | 376996 | 34855 | 357710.67 | 94.88% | 33071.9833 | 390782.6533 | 349622.76 | -41159.8933 | 19285.33 | 62228.24 | 49065 | 0 | 0 | 308645.67 | 349622.76 | 33071.9833 | 2024 |  | . | 5273.0464 | 29828.7333 | 3243.25 | - | - | 389138 | 411851 | 376996 | 34855 | 94.88% | 33071.9833 | 390782.6533 | -41159.8933 | 19285.33 | 62228.24 | 0 | 33071.9833
52.8678 | City of Chowcilla - Well 15 & Generator Improvement Projects | 1240321 | 1162321 | 78000 | 926007.31 | 79.67% | 62141.6719 | 988148.9819 | 1142122 | 153973.0181 | 236313.69 | 98199 | 5563.63 | 0 | 0 | 920443.68 | 1142122 | 62141.6719 | 2024 |  | . | 0 | 30522.5907 | 31619.0812 | - | - | 465321 | 1240321 | 1162321 | 78000 | 79.67% | 62141.6719 | 988148.9819 | 153973.0181 | 236313.69 | 98199 | 0 | 62141.6719
52.8687 | California Water Service Co. - Salinas Station 205 | 877954 | 790771.48 | 87182.52 | 740629.43 | 93.66% | 81654.3612 | 822283.7912 | 827811.95 | 5528.1588 | 50142.05 | 50142.05 |  |  |  | 740629.43 | 827811.95 | 81654.3612 | 2025 |  | . |  | 75218.5469 | 6435.8143 | - | - |  | 877954 | 790771.48 | 87182.52 | 93.66% | 81654.3612 | 822283.7912 | 5528.1588 | 50142.05 | 50142.05 | 0 | 81654.3612
52.8692 | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 55135.37 | 49682.49 | 5452.88 | 49682.49 | 100% | 5452.88 | 55135.37 | 55135.37 | 0 | 0 | 0 |  |  |  | 49682.49 | 55135.37 | 5452.88 | 2025 |  | < 250k |  | 5452.88 | 0 | - | - |  | 55135.37 | 49682.49 | 5452.88 | 100% | 5452.88 | 55135.37 | 0 | 0 | 0 | -83000 | 88452.88
52.8697 | City of Tulare - Industrial WWTP Dewatering Improvements Pro | 1388000 | 1325482 | 62518 | 772187.73 | 58.26% | 36421.1906 | 808608.9206 | 1069317 | 260708.0794 | 553294.27 | 318683 |  |  |  | 772187.73 | 1069317 | 36421.1906 | 2025 |  | . |  | 26699.3242 | 9721.8664 | - | -
52.8698 | California Water Service Co. - Tesoro Viejo RWSP Liner Repair | 22713 | 16128 | 6585 | 15264 | 94.64% | 6232.2321 | 21496.2321 | 0 | -21496.2321 | 864 | 22713 |  |  |  | 15264 | 0 | 6232.2321 | 2025 |  | < 250k |  |  | 6232.2321 | - | -
52.8704 | City of Visalia - Solids Handling Improvements Project | 13744000 | 13491127 | 252873 | 820988.3 | 6.085% | 0 | 820988.3 | 1037950 | 216961.7 | 12670138.7 | 12706050 |  |  |  | 820988.3 | 1037950 | 0 | 2025 |  | . |  | 0 | 0 | - | -
52.8705 | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | 775000 | 719260 | 55740 | 285425.72 | 39.68% | 22119.4417 | 307545.1617 | 261232 | -46313.1617 | 433834.28 | 513768 |  |  |  | 285425.72 | 261232 | 22119.4417 | 2025 |  | . |  | 0 | 22119.4417 | - | -
52.8707 | County of Fresno - Westside Water Tank and Pump Station | 3693200 | 3461577 | 231623 | 1012057.14 | 29.24% | 67719.3403 | 1079776.4803 | 913135 | -166641.4803 | 2449519.86 | 2780065 |  |  |  | 1012057.14 | 913135 | 67719.3403 | 2025 |  | . |  | 0 | 67719.3403 | - | -
52.8708 | County of Fresno - CSA 44A Wastewater Improvements | 363833 | 333757 | 30076 | 7682.19 | 2.302% | 0 | 7682.19 | 0 | -7682.19 | 326074.81 | 363833 |  |  |  | 7682.19 | 0 | 0 | 2025 |  | . |  | 0 | 0 | - | -
52.8711 | California Water Service Co. - Tesoro Viejo ARV Replacement | 6860 | 6315 | 545 | 4568.81 | 72.35% | 394.2995 | 4963.1095 | 0 | -4963.1095 | 1746.19 | 6860 |  |  |  | 4568.81 | 0 | 394.2995 | 2025 |  | < 250k |  |  | 394.2995 | - | -
52.8713 | City of Visalia - Remove & Replace Chain and Flight Mechanic | 218842 | 190439 | 28403 | 927.5 | 0.487% | 0 | 927.5 | 0 | -927.5 | 189511.5 | 218842 |  |  |  | 927.5 | 0 | 0 | 2025 |  | < 250k |  |  | 0 | - | -
52.8714 | New England Sheet Metal and Mechanical Co. - VCH Digging Water Line T&M | 5084.94 | 4465.61 | 619.33 | 4465.61 | 100% | 619.33 | 5084.94 | 5084.94 | 0 | 0 | 0 |  |  |  | 4465.61 | 5084.94 | 619.33 | 2025 |  | < 250k |  |  | 619.33 | - | -
[24 empty] | 0 | - | - |  | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 145886.6054 | -145886.6054
Fresno Area - Open Jobs Totals |  | 120293584.59 | 112445396.23 | 7848188.36 | 89053141.85 |  | 6940608.7635 | 95993750.6135 | 96615921.65 | 622171.0365 | 23392254.38 | 23677662.94 | 51150072.54 | 56363057.85 | 4640594.5933 | 37903069.31 | 40252863.8 | 2300014.1702 |  |  |  |  | 1640651.5083 | 659362.6619 | - | - | 26229.6 | 100035907.05 | 92875132.57 | 7160774.48 | 95.88% | 6788678.7692 | 92918253.6192 | 410949.0908 | 6745557.72 | 6706704.34 | #REF! | #REF!
[24 empty] | 0 | - | - | 0
Fresno Area - Closed Jobs | [23 empty] | 0 | - | - | 0
52.8567 | City of Modesto - Grayson Well 69 | 3059858.99 | 3128023.93 | -68164.94 | 3128023.93 | 100% | -68164.94 | 3059858.99 | 3059858.99 | 0 | 0 | 0 | 3093625.26 | 3018499.27 | -83000 | 34398.67 | 41359.72 | 14835.06 | 2021 | 2025 | . | -83000 | 14835.06 | 0 | - | - | 1188944 | 3059858.99 | 3128023.93 | -68164.94 | 100% | -68164.94 | 3059858.99 | 0 | 0 | 0 | 145886.6054 | -214051.5454
52.8604 | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 5095690.97 | 4572503.23 | 523187.74 | 4572503.23 | 100% | 523187.74 | 5095690.97 | 5095690.97 | 0 | 0 | 0 | 3663663.49 | 4537408 | 329989.1327 | 908839.74 | 558282.97 | 193198.6073 | 2022 | 2025 | . | 329989.1327 | 193198.6073 | 0 | - | - | 3453890.97 | 5095690.97 | 4572503.23 | 523187.74 | 100% | 523187.74 | 5095690.97 | 0 | 0 | 0 | 42676.9508 | 480510.7892
52.8628 | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 5213345.5 | 4745798.53 | 467546.97 | 4745798.53 | 100% | 467546.97 | 5213345.5 | 5213345.5 | 0 | 0 | 0 | 3841927.99 | 4344899 | 197224.7538 | 903870.54 | 868446.5 | 270322.2162 | 2023 | 2025 | . | 197224.7538 | 227105.5716 | 43216.6446 | - | - | 4417290.2 | 5213345.5 | 4745798.53 | 467546.97 | 100% | 467546.97 | 5213345.5 | 0 | 0 | 0 | 0 | 467546.97
52.8631 | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 2560650.14 | 2448658.26 | 111991.88 | 2448658.26 | 100% | 111991.88 | 2560650.14 | 2560650.14 | 0 | 0 | 0 | 2249693.14 | 2130066.81 | 73003.7005 | 198965.12 | 430583.33 | 38988.1795 | 2023 | 2025 | . | 73003.7005 | 43734.1447 | -4745.9653 | - | - | 2530811.89 | 2560650.14 | 2448658.26 | 111991.88 | 100% | 111991.88 | 2560650.14 | 0 | 0 | 0 | 0 | 111991.88
52.8652 | California Water Service Co. - Salinas 77 Booster Station | 1290184 | 1039376.08 | 250807.92 | 1039376.08 | 100% | 250807.92 | 1290184 | 1290184 | 0 | 0 | 0 | 985944.49 | 1202385 | 170698.8374 | 53431.59 | 87799 | 80109.0826 | 2024 | 2025 | . | 170698.8374 | 80109.0826 | 0 | - | - | 976098.23 | 1290184 | 1039376.08 | 250807.92 | 100% | 250807.92 | 1290184 | 0 | 0 | 0 | 26868.8653 | 223939.0547
52.8658 | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 1870914.99 | 1633530.21 | 237384.78 | 1633530.21 | 100% | 237384.78 | 1870914.99 | 1870914.99 | 0 | 0 | 0 | 1521618.77 | 1789732.45 | 148751 | 111911.44 | 81182.54 | 88633.78 | 2023 | 2025 | . | 145886.6054 | 88633.78 | 0 | - | - | 0 | 1870914.99 | 1633530.21 | 237384.78 | 100% | 237384.78 | 1870914.99 | 0 | 0 | 0 | 145886.6054 | 91498.1746
52.8663 | Root Creek Water Dist. - Ag Well 277 Conversion Project | 1641800 | 1379688.28 | 262111.72 | 1379688.28 | 100% | 262111.72 | 1641800 | 1641800 | 0 | 0 | 0 | 406865.39 | 507750 | 42676.9508 | 972822.89 | 1134050 | 219434.7692 | 2024 | 2025 | . | 42676.9508 | 211731.7546 | 7703.0145 | - | - | 1591231.95 | 1641800 | 1379688.28 | 262111.72 | 100% | 262111.72 | 1641800 | 0 | 0 | 0 | 0 | 262111.72
52.8667 | California Water Service Co. - Cal Water Salinas Station 33 | 314085.77 | 290726.11 | 23359.66 | 290726.11 | 100% | 23359.66 | 314085.77 | 314085.77 | 0 | 0 | 0 | 285347.35 | 201644.15 | 26868.8653 | 5378.76 | 112441.62 | -3509.2053 | 2024 | 2025 | . | 26868.8653 | -3509.2053 | 0 | - | - | -1327714.23 | 314085.77 | 290726.11 | 23359.66 | 100% | 23359.66 | 314085.77 | 0 | 0 | 0 | 42676.9508 | -19317.2908
52.867 | California Water Service Co. - Cal Water - King City Station 10 | 274166.01 | 267282.05 | 6883.96 | 267282.05 | 100% | 6883.96 | 274166.01 | 274166.01 | 0 | 0 | 0 | 121115.51 | 0 | 10404.4356 | 146166.54 | 274166.01 | -3520.4756 | 2024 | 2025 | . | 10404.4356 | -3520.4756 | 0 | - | - | -39919.76 | 274166.01 | 267282.05 | 6883.96 | 100% | 6883.96 | 274166.01 | 0 | 0 | 0 | 26868.8653 | -19984.9053
52.8674 | City of Hanford - WWTP Standby Influent Pump Install | 279244 | 251088.2 | 28155.8 | 251088.2 | 100% | 28155.8 | 279244 | 279244 | 0 | 0 | 0 | 184739.62 | 279244 | 15534.5836 | 66348.58 | 0 | 12621.2164 | 2024 | 2025 | . | 15534.5836 | 12621.2164 | 0 | - | - | 279244 | 279244 | 251088.2 | 28155.8 | 100% | 28155.8 | 279244 | 0 | 0 | 0 | 170698.8374 | -142543.0374
52.8677 | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 796055.3 | 689831.96 | 106223.34 | 689831.96 | 100% | 106223.34 | 796055.3 | 796055.3 | 0 | 0 | 0 | 33286.03 | 0 | 0 | 656545.93 | 796055.3 | 106223.34 | 2024 | 2025 | . | 0 | 82416.0939 | 23807.2461 | - | - | 781903.33 | 796055.3 | 689831.96 | 106223.34 | 100% | 106223.34 | 796055.3 | 0 | 0 | 0 | 0 | 106223.34
52.868 | City of Orange Cove - Orange Cove West Clarifier T&M | 29838.25 | 26088.33 | 3749.92 | 26088.33 | 100% | 3749.92 | 29838.25 | 29838.25 | 0 | 0 | 0 | 6514.21 | 0 | 0 | 19574.12 | 29838.25 | 3749.92 | 2024 | 2025 | < 250k | 0 | 3749.92 | 0 | - | - | 29838.25 | 29838.25 | 26088.33 | 3749.92 | 100% | 3749.92 | 29838.25 | 0 | 0 | 0 | 0 | 3749.92
52.8682 | Fresno Overhead 2025 |  | 1121157.1 | -1121157.1 | 1121157.1 | 100% | -1121157.1 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1121157.1 | 0 | -1121157.1 | 2025 | 2025 | OH |  | -965154.37 | -156002.73 | - | - |  | 0 | 1121157.1 | -1121157.1 | 100% | -1121157.1 | 0 | 0 | 0 | 0 | 0 | -1121157.1
52.8683 | Fresno Estimating 2025 |  | 415452.52 | -415452.52 | 415452.52 | 100% | -415452.52 | 0 | 0 | 0 | 0 | 0 |  |  |  | 415452.52 | 0 | -415452.52 | 2025 | 2025 | OH |  | -350911.38 | -64541.14 | - | - |  | 0 | 415452.52 | -415452.52 | 100% | -415452.52 | 0 | 0 | 0 | 0 | 0 | -415452.52
52.8684 | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 50568.05 | 45291.39 | 5276.66 | 45291.39 | 100% | 5276.66 | 50568.05 | 50568.05 | 0 | 0 | 0 |  |  |  | 45291.39 | 50568.05 | 5276.66 | 2025 | 2025 | < 250k |  | 4446.63 | 830.03 | - | -
52.8685 | Malaga County Water Dist. - Malaga County Water District | 451254 | 382067.32 | 69186.68 | 382067.32 | 100% | 69186.68 | 451254 | 451254 | 0 | 0 | 0 |  |  |  | 382067.32 | 451254 | 69186.68 | 2025 | 2025 | . |  | 26847.9027 | 42338.7773 | - | - |  | 451254 | 382067.32 | 69186.68 | 100% | 69186.68 | 451254 | 0 | 0 | 0 | 0 | 69186.68
52.8686 | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 23957 | 7505.26 | 16451.74 | 7505.26 | 100% | 16451.74 | 23957 | 23957 | 0 | 0 | 0 | 6290.87 | 0 | 15372.2567 | 1214.39 | 23957 | 1079.4833 | 2024 | 2025 | < 250k | 15372.2567 | 1079.4833 | 0 | - | - | 23957 | 23957 | 7505.26 | 16451.74 | 100% | 16451.74 | 23957 | 0 | 0 | 0 | 145886.6054 | -129434.8654
52.8688 | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 132492.2 | 116972.75 | 15519.45 | 116972.75 | 100% | 15519.45 | 132492.2 | 132492.2 | 0 | 0 | 0 |  |  |  | 116972.75 | 132492.2 | 15519.45 | 2025 | 2025 | < 250k |  | 15519.45 | 0 | - | - |  | 132492.2 | 116972.75 | 15519.45 | 100% | 15519.45 | 132492.2 | 0 | 0 | 0 | 0 | 15519.45
52.8689 | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 16665.83 | 16095.58 | 570.25 | 16095.58 | 100% | 570.25 | 16665.83 | 16665.83 | 0 | 0 | 0 |  |  |  | 16095.58 | 16665.83 | 570.25 | 2025 | 2025 | < 250k |  | 570.25 | 0 | - | - |  | 16665.83 | 16095.58 | 570.25 | 100% | 570.25 | 16665.83 | 0 | 0 | 0 | 5520803.7416 | -5520233.4916
52.869 | City of Dinuba - WWTP Rake Replacement | 14151.97 | 13155.83 | 996.14 | 13155.83 | 100% | 996.14 | 14151.97 | 14151.97 | 0 | 0 | 0 |  |  |  | 13155.83 | 14151.97 | 996.14 | 2025 | 2025 | < 250k |  | 996.14 | 0 | - | - |  | 14151.97 | 13155.83 | 996.14 | 100% | 996.14 | 14151.97 | 0 | 0 | 0 | #REF! | #REF!
52.8691 | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 11302.84 | 8287.82 | 3015.02 | 8287.82 | 100% | 3015.02 | 11302.84 | 11302.84 | 0 | 0 | 0 |  |  |  | 8287.82 | 11302.84 | 3015.02 | 2025 | 2025 | < 250k |  | 3015.02 | 0 | - | - |  | 11302.84 | 8287.82 | 3015.02 | 100% | 3015.02 | 11302.84 | 0 | 0 | 0 | #REF! | #REF!
52.8693 | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 1120704.2 | 663140.99 | 457563.21 | 663140.99 | 100% | 457563.21 | 1120704.2 | 1120704.2 | 0 | 0 | 0 |  |  |  | 663140.99 | 1120704.2 | 457563.21 | 2025 | 2025 | . |  | 412543.4073 | 45019.8027 | - | - |  | 1120704.2 | 663140.99 | 457563.21 | 100% | 457563.21 | 1120704.2 | 0 | 0 | 0 | #REF! | #REF!
52.8694 | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 43047.45 | 38541.99 | 4505.46 | 38541.99 | 100% | 4505.46 | 43047.45 | 43047.45 | 0 | 0 | 0 |  |  |  | 38541.99 | 43047.45 | 4505.46 | 2025 | 2025 | < 250k |  | 4505.46 | 0 | - | - |  | 43047.45 | 38541.99 | 4505.46 | 100% | 4505.46 | 43047.45 | 0 | 0 | 0 | 0 | 4505.46
52.8695 | Lyles Services Co. - LSC GO Trash Enclosure | 13769 | 13024.37 | 744.63 | 13024.37 | 100% | 744.63 | 13769 | 13769 | 0 | 0 | 0 |  |  |  | 13024.37 | 13769 | 744.63 | 2025 | 2025 | < 250k |  | 744.63 | 0 | - | - |  | 13769 | 13024.37 | 744.63 | 100% | 744.63 | 13769 | 0 | 0 | 0 | 0 | 744.63
52.8696 | American Paving Co. - Hot Tap for APC- Tule River Parkway | 1059.22 | 887.65 | 171.57 | 887.65 | 100% | 171.57 | 1059.22 | 1059.22 | 0 | 0 | 0 |  |  |  | 887.65 | 1059.22 | 171.57 | 2025 | 2025 | < 250k |  | 171.57 | 0 | - | -
52.8699 | City of Hanford - WWTP Repair T&M | 3001.12 | 2948.91 | 52.21 | 2948.91 | 100% | 52.21 | 3001.12 | 3001.12 | 0 | 0 | 0 |  |  |  | 2948.91 | 3001.12 | 52.21 | 2025 | 2025 | < 250k |  | 52.21 | 0 | - | -
52.87 | Lyles Services Co. - LSC GO Misc. Work | 5297 | 4446.13 | 850.87 | 4446.13 | 100% | 850.87 | 5297 | 5297 | 0 | 0 | 0 |  |  |  | 4446.13 | 5297 | 850.87 | 2025 | 2025 | < 250k |  | 334.6549 | 516.2151 | - | -
52.8701 | County of Fresno - 47 Water | 13433.85 | 12421.08 | 1012.77 | 12421.08 | 100% | 1012.77 | 13433.85 | 13433.85 | 0 | 0 | 0 |  |  |  | 12421.08 | 13433.85 | 1012.77 | 2025 | 2025 | < 250k |  | 1247.66 | -234.89 | - | -
52.8702 | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M | 5626.78 | 4725.28 | 901.5 | 4725.28 | 100% | 901.5 | 5626.78 | 5626.78 | 0 | 0 | 0 |  |  |  | 4725.28 | 5626.78 | 901.5 | 2025 | 2025 | < 250k |  | 901.5 | 0 | - | -
52.8703 | County of Fresno - CSA 47 Egret Point Water Line Repair | 14402.18 | 12571.54 | 1830.64 | 12571.54 | 100% | 1830.64 | 14402.18 | 14402.18 | 0 | 0 | 0 |  |  |  | 12571.54 | 14402.18 | 1830.64 | 2025 | 2025 | < 250k |  | 2171.92 | -341.28 | - | -
52.8706 | City of Hanford - WWTP Weld Repair T&M 2 | 2868.6 | 2435.78 | 432.82 | 2435.78 | 100% | 432.82 | 2868.6 | 2868.6 | 0 | 0 | 0 |  |  |  | 2435.78 | 2868.6 | 432.82 | 2025 | 2025 | < 250k |  | 432.82 | 0 | - | -
52.8709 | County of Fresno - 47.1 Water | 17765.14 | 14874.36 | 2890.78 | 14874.36 | 100% | 2890.78 | 17765.14 | 17765.14 | 0 | 0 | 0 |  |  |  | 14874.36 | 17765.14 | 2890.78 | 2025 | 2025 | < 250k |  | 3065.56 | -174.78 | - | -
52.871 | City of Dinuba - WWTP Bar Screen Motor Bracket Repair | 4064.54 | 3514.84 | 549.7 | 3514.84 | 100% | 549.7 | 4064.54 | 4064.54 | 0 | 0 | 0 |  |  |  | 3514.84 | 4064.54 | 549.7 | 2025 | 2025 | < 250k |  | 549.7 | 0 | - | -
52.8715 | New England Sheet Metal and Mechanical Co. - Vitro Glass Plant Concrete Pad T&M | 10001.43 | 8585.44 | 1415.99 | 8585.44 | 100% | 1415.99 | 10001.43 | 10001.43 | 0 | 0 | 0 |  |  |  | 8585.44 | 10001.43 | 1415.99 | 2025 | 2025 | < 250k |  |  | 1415.99 | - | -
[24 empty] | 0 | - | -
Fresno Area - Closed Jobs Totals |  | 24381266.32 | 23380699.1 | 1000567.22 | 23380699.1 |  | 1000567.22 | 24381266.32 | 24381266.32 | 0 | 0 | 0 | 16400632.12 | 18011628.68 | 947524.5165 | 6980066.98 | 6369637.64 | 53042.7035 |  |  |  | 0 | 431040.8687 | -377998.1651 | - | - | 0 | 1580348.55 | 2893190.69 | -1312842.14 |  | -1312842.14 | 1580348.55 | 0 | 0 | 0 | 316585.4428 | -1629427.5828
Fresno Area - Grand Totals |  | 144674850.91 | 135826095.33 | 8848755.58 | 112433840.95 |  | 7941175.9835 | 120375016.9335 | 120997187.97 | 622171.0365 | 23392254.38 | 23677662.94 | 67550704.66 | 74374686.53 | 5588119.1098 | 44883136.29 | 46622501.44 | 2353056.8737 |  |  |  |  | 2071692.377 | 281364.4967 | - | - | 26229.6 | 101616255.6 | 95768323.26 | 5847932.34 |  | 5475836.6292 | 94498602.1692 | 410949.0908 | 6745557.72 | 6706704.34 | #REF! | #REF!
[24 empty] | 0 | - | - | 0
East Bay Area - Open Jobs | [23 empty] | 0 | - | - | 0
53.2007 | Union Sanitary Dist. - Phase 1B Secondary Clarifiers | 324530134 | 291530134 | 33000000 | 404852.16 | 0.1389% | 0 | 404852.16 | 0 | -404852.16 | 291125281.84 | 324530134 |  |  |  | 404852.16 | 0 | 0 | 2025 |  | . |  | 0 | 0 | - | -
[24 empty] | 0 | - | - | 0
East Bay Area - Open Jobs Totals |  | 324530134 | 291530134 | 33000000 | 404852.16 |  | 0 | 404852.16 | 0 | -404852.16 | 291125281.84 | 324530134 | 0 | 0 | 0 | 404852.16 | 0 | 0 |  |  |  |  | -369273.7769 | 369273.7769 | - | - | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | 0 | - | - | 0
East Bay Area - Closed Jobs | [23 empty] | 0 | - | - | 0
53.2004 | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 1173753.47 | 980791.05 | 192962.42 | 980791.05 | 100% | 192962.42 | 1173753.47 | 1173753.47 | 0 | 0 | 0 | 21928.48 | 0 | 0 | 958862.57 | 1173753.47 | 192962.42 | 2024 | 2025 | . | 0 | 178062.1531 | 14900.2669 | - | - | 1173753.47 | 1173753.47 | 980791.05 | 192962.42 | 100% | 192962.42 | 1173753.47 | 0 | 0 | 0 | 0 | 192962.42
53.2005 | East Bay Overhead 2025 |  | 279281.96 | -279281.96 | 279281.96 | 100% | -279281.96 | 0 | 0 | 0 | 0 | 0 |  |  |  | 279281.96 | 0 | -279281.96 | 2025 | 2025 | OH |  | -242386.71 | -36895.25 | - | - |  | 0 | 279281.96 | -279281.96 | 100% | -279281.96 | 0 | 0 | 0 | 0 | 0 | -279281.96
53.2006 | East Bay Estimating 2026 |  | 304986.32 | -304986.32 | 304986.32 | 100% | -304986.32 | 0 | 0 | 0 | 0 | 0 |  |  |  | 304986.32 | 0 | -304986.32 | 2025 | 2025 | OH |  | -304949.22 | -37.1 | - | - |  | 0 | 304986.32 | -304986.32 | 100% | -304986.32 | 0 | 0 | 0 | 0 | 0 | -304986.32
[24 empty] | 0 | - | - | 0
East Bay Area - Closed Jobs Totals |  | 1173753.47 | 1565059.33 | -391305.86 | 1565059.33 |  | -391305.86 | 1173753.47 | 1173753.47 | 0 | 0 | 0 | 21928.48 | 0 | 0 | 1543130.85 | 1173753.47 | -391305.86 |  |  |  |  | 0 | -391305.86 | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
East Bay - Grand Totals |  | 325703887.47 | 293095193.33 | 32608694.14 | 1969911.49 |  | -391305.86 | 1578605.63 | 1173753.47 | -404852.16 | 291125281.84 | 324530134 | 0 | 0 | 0 | 1947983.01 | 1173753.47 | -391305.86 |  |  |  |  | -369273.7769 | -22032.0831 | - | - | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | 0 | - | - | 0
Bakersfield Area - Open Jobs | [23 empty] | 0 | - | - | 0
54.9033 | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 118278.58 | 104550.27 | 13728.31 | 104550.27 | 100% | 13728.31 | 118278.58 | 118278.58 | 0 | 0 | 0 | 82942.93 | 93909.8 | 10966.87 | 21607.34 | 24368.78 | 2761.44 | 2021 |  | < 250k | 10966.87 | 0 | 2761.44 | - | - | 0 | 118278.58 | 104550.27 | 13728.31 | 100% | 13728.31 | 118278.58 | 0 | 0 | 0 | 10966.87 | 2761.44
54.9135 | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 9470658.62 | 9050951.86 | 419706.76 | 9050951.86 | 100% | 419706.76 | 9470658.62 | 9470658.62 | 0 | 0 | 0 | 7371036.33 | 6071589.31 | 551994.3651 | 1679915.53 | 3399069.31 | -132287.6051 | 2021 |  | . | 0 | 17174.9929 | -149462.5979 | - | - | 7999330.62 | 9470658.62 | 9050951.86 | 419706.76 | 100% | 419706.76 | 9470658.62 | 0 | 0 | 0 | 0 | 419706.76
54.9257 | City of Guadalupe - Highway 1 Lift Station | 1471328 | 1426328 | 45000 | 762211.05 | 53.44% | 24047.4121 | 786258.4621 | 890983 | 104724.5379 | 664116.95 | 580345 | 14035.83 | 0 | 0 | 748175.22 | 890983 | 24047.4121 | 2023 |  | . | 0 | 18415.846 | 5631.5661 | - | - | 1009306 | 1471328 | 1426328 | 45000 | 53.44% | 24047.4121 | 786258.4621 | 104724.5379 | 664116.95 | 580345 | 34249.05 | -10201.6379
54.9268 | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 949567.99 | 884567.99 | 65000 | 844648.28 | 95.49% | 65000 | 909648.28 | 907298 | -2350.28 | 39919.71 | 42269.99 | 788053.77 | 894533 | 71013.0668 | 56594.51 | 12765 | -6013.0668 | 2023 |  | . | 71013.0668 | -6013.0668 | 0 | - | - | 624667.99 | 949567.99 | 884567.99 | 65000 | 95.49% | 62066.612 | 906714.892 | 583.108 | 39919.71 | 42269.99 | 197714.5111 | -135647.8992
54.9269 | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 625819.17 | 591570.12 | 34249.05 | 549817.74 | 92.94% | 34249.05 | 584066.79 | 625819.17 | 41752.38 | 41752.38 | 0 | 306021.41 | 340270.46 | 34249.05 | 243796.33 | 285548.71 | 0 | 2023 |  | . | 34249.05 | -0.05 | 0.05 | - | - | 0 | 625819.17 | 591570.12 | 34249.05 | 92.94% | 31831.7891 | 581649.5291 | 44169.6409 | 41752.38 | 0 | 34249.05 | -2417.2609
54.9285 | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 462022 | 387022 | 75000 | 312939.77 | 80.86% | 60643.7948 | 373583.5648 | 427226 | 53642.4352 | 74082.23 | 34796 | 186052.75 | 205930 | 35686.2378 | 126887.02 | 221296 | 24957.557 | 2023 |  | . | 35686.2378 | 24327.244 | 630.313 | - | - | -6419278 | 462022 | 387022 | 75000 | 80.86% | 60643.7948 | 373583.5648 | 53642.4352 | 74082.23 | 34796 | 0 | 60643.7948
54.9313 | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 7886885.04 | 6876885.04 | 1010000 | 6449205.22 | 93.78% | 947187.1689 | 7396392.3889 | 7886885 | 490492.6111 | 427679.82 | 0.04 | 1921139.11 | 2129585.82 | 197714.5111 | 4528066.11 | 5757299.18 | 749472.6578 | 2024 |  | . | 197714.5111 | 502485.7567 | 246986.9011 | - | - | #REF! | 7886885.04 | 6876885.04 | 1010000 | 93.78% | 947187.1689 | 7396392.3889 | 490492.6111 | 427679.82 | 0.04 | 0 | 947187.1689
54.933 | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 324900 | 307641 | 17259 | 306221.41 | 99.54% | 17179.3594 | 323400.7694 | 324900 | 1499.2306 | 1419.59 | 0 | 181448.27 | 237460 | 10642.1273 | 124773.14 | 87440 | 6537.2322 | 2024 |  | . | 10642.1273 | 5219.1306 | 1318.1015 | - | - | -1199866 | 324900 | 307641 | 17259 | 99.54% | 17179.3594 | 323400.7694 | 1499.2306 | 1419.59 | 0 | 0 | 17179.3594
54.9336 | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 25191176.64 | 23271176.64 | 1920000 | 12340864.27 | 53.03% | 1018189.1429 | 13359053.4129 | 14176592.91 | 817539.4971 | 10930312.37 | 11014583.73 | 2120057.55 | 2584469.7 | 0 | 10220806.72 | 11592123.21 | 1018189.1429 | 2024 |  | . | 0 | 771113.4647 | 247075.6782 | - | - | 24658572.07 | 25191176.64 | 23271176.64 | 1920000 | 53.03% | 1018189.1429 | 13359053.4129 | 817539.4971 | 10930312.37 | 11014583.73 | #REF! | #REF!
54.9337 | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 4104848 | 3944848 | 160000 | 1509066.73 | 38.25% | 61206.5856 | 1570273.3156 | 520441.66 | -1049831.6556 | 2435781.27 | 3584406.34 | 153011.71 | 0 | 0 | 1356055.02 | 520441.66 | 61206.5856 | 2024 |  | . | 0 | 61357.3057 | -150.7201 | - | - | 2309195.34 | 4104848 | 3944848 | 160000 | 38.25% | 61206.5856 | 1570273.3156 | -1049831.6556 | 2435781.27 | 3584406.34 | #REF! | #REF!
54.9343 | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 6881300 | 5981300 | 900000 | 3415344.08 | 57.1% | 513903.2772 | 3929247.3572 | 3954560 | 25312.6428 | 2565955.92 | 2926740 | 600191.79 | 737745 | 0 | 2815152.29 | 3216815 | 513903.2772 | 2024 |  | . | 0 | 422212.9603 | 91690.3169 | - | - | 3161300 | 6881300 | 5981300 | 900000 | 57.1% | 513903.2772 | 3929247.3572 | 25312.6428 | 2565955.92 | 2926740 | 0 | 513903.2772
54.9356 | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 1298330 | 913330 | 385000 | 775780.75 | 84.94% | 327018.2615 | 1102799.0115 | 685017 | -417782.0115 | 137549.25 | 613313 | 62884.76 | 63200 | 0 | 712895.99 | 621817 | 327018.2615 | 2024 |  | . | 0 | 192031.9493 | 134986.3122 | - | - | #REF! | 1298330 | 913330 | 385000 | 84.94% | 327018.2615 | 1102799.0115 | -417782.0115 | 137549.25 | 613313 | 0 | 327018.2615
54.9366 | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 1230131 | 1080131 | 150000 | 923220.5 | 85.47% | 128209.5181 | 1051430.0181 | 1160831 | 109400.9819 | 156910.5 | 69300 | 5513.06 | 0 | 0 | 917707.44 | 1160831 | 128209.5181 | 2024 |  | . | 0 | 65624.2704 | 62585.2477 | - | - | #REF! | 1230131 | 1080131 | 150000 | 85.47% | 128209.5181 | 1051430.0181 | 109400.9819 | 156910.5 | 69300 | 0 | 128209.5181
54.9369 | California Water Service Co. - PFAS Treatment Program Project | 28550624.7 | 26179781.7 | 2370843 | 2787466.66 | 10.65% | 0 | 2787466.66 | 2927422.95 | 139956.29 | 23392315.04 | 25623201.75 | 1242.45 | 0 | 0 | 2786224.21 | 2927422.95 | 0 | 2024 |  | . | 0 | 0 | 0 | - | - | #REF! | 28550624.7 | 26179781.7 | 2370843 | 10.65% | 252433.1904 | 3039899.8504 | -112476.9004 | 23392315.04 | 25623201.75 | 0 | 252433.1904
54.9373 | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 1524766 | 1393326 | 131440 | 50303.97 | 3.61% | 0 | 50303.97 | 0 | -50303.97 | 1343022.03 | 1524766 |  |  |  | 50303.97 | 0 | 0 | 2025 |  | . |  | 0 | 0 | - | - |  | 1524766 | 1393326 | 131440 | 3.61% | 0 | 50303.97 | -50303.97 | 1343022.03 | 1524766 | 0 | 0
54.9389 | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 299780 | 314780 | -15000 | 311891.85 | 99.08% | -15000 | 296891.85 | 291620 | -5271.85 | 2888.15 | 8160 |  |  |  | 311891.85 | 291620 | -15000 | 2025 |  | . |  | -15000 | 0 | - | -
54.9391 | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 532604.57 | 512057.34 | 20547.23 | 512057.34 | 100% | 20547.23 | 532604.57 | 532604.57 | 0 | 0 | 0 |  |  |  | 512057.34 | 532604.57 | 20547.23 | 2025 |  | . |  | 19322.9185 | 1224.3115 | - | -
54.9395 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 1795652.66 | 1693652.66 | 102000 | 1349601.92 | 79.69% | 81279.5912 | 1430881.5112 | 1374448.17 | -56433.3412 | 344050.74 | 421204.49 |  |  |  | 1349601.92 | 1374448.17 | 81279.5912 | 2025 |  | . |  | 22223.6704 | 59055.9208 | - | -
54.9396 | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | 157746.09 | 157746.09 | 0 | 157746.09 | 100% | 0 | 157746.09 | 0 | -157746.09 | 0 | 157746.09 |  |  |  | 157746.09 | 0 | 0 | 2025 |  | < 250k |  | 0 | 0 | - | -
54.9397 | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 3690645 | 3390645 | 300000 | 1035065.41 | 30.53% | 91581.2841 | 1126646.6941 | 1033150.21 | -93496.4841 | 2355579.59 | 2657494.79 |  |  |  | 1035065.41 | 1033150.21 | 91581.2841 | 2025 |  | . |  | 73613.2108 | 17968.0733 | - | -
54.9403 | Lost Hills Utility Dist. - WTP Improvements | 381600 | 338101 | 43499 | 129004.89 | 38.16% | 16597.3591 | 145602.2491 | 140100 | -5502.2491 | 209096.11 | 241500 |  |  |  | 129004.89 | 140100 | 16597.3591 | 2025 |  | . |  | 0 | 16597.3591 | - | -
54.9404 | Cawelo Water Dist. - Reuse of Produced Water | 3720000 | 3585392 | 134608 | 1939024.63 | 54.08% | 72797.6822 | 2011822.3122 | 1746890 | -264932.3122 | 1646367.37 | 1973110 |  |  |  | 1939024.63 | 1746890 | 72797.6822 | 2025 |  | . |  | 42196.4584 | 30601.2238 | - | -
54.9405 | Semitropic Water Storage Dist. - Pump Platform Replacement Project | 942000 | 812000 | 130000 | 577796.16 | 71.16% | 92504.3113 | 670300.4713 | 746125 | 75824.5287 | 234203.84 | 195875 |  |  |  | 577796.16 | 746125 | 92504.3113 | 2025 |  | . |  | 0 | 92504.3113 | - | -
54.9406 | California Water Service Co. - Emergency PACL leak repair | 1120.65 | 1120.65 | 0 | 1120.65 | 100% | 0 | 1120.65 | 0 | -1120.65 | 0 | 1120.65 |  |  |  | 1120.65 | 0 | 0 | 2025 |  | < 250k |  |  | 0 | - | -
54.9408 | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line | 3777777 | 3537185 | 240592 | 41652.43 | 1.178% | 0 | 41652.43 | 0 | -41652.43 | 3495532.57 | 3777777 |  |  |  | 41652.43 | 0 | 0 | 2025 |  | . |  | 0 | 0 | - | -
54.9411 | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation | 103300 | 78300 | 25000 | 71370.85 | 91.15% | 22787.6277 | 94158.4777 | 103000 | 8841.5223 | 6929.15 | 300 |  |  |  | 71370.85 | 103000 | 22787.6277 | 2025 |  | < 250k |  | 22875.2724 | -87.6447 | - | -
54.9412 | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork | 116752.04 | 115708.88 | 1043.16 | 115708.88 | 100% | 1043.16 | 116752.04 | 116752.04 | 0 | 0 | 0 |  |  |  | 115708.88 | 116752.04 | 1043.16 | 2025 |  | < 250k |  | 5212.8916 | -4169.7316 | - | -
54.9413 | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork | 149366.83 | 132138.74 | 17228.09 | 132138.74 | 100% | 17228.09 | 149366.83 | 149366.83 | 0 | 0 | 0 |  |  |  | 132138.74 | 149366.83 | 17228.09 | 2025 |  | < 250k |  | 9987.386 | 7240.704 | - | -
54.9414 | Cawelo Water Dist. - Cawelo Diversion Structure Rehab | 358674.83 | 338674.83 | 20000 | 337485.68 | 99.65% | 19929.7763 | 357415.4563 | 0 | -357415.4563 | 1189.15 | 358674.83 |  |  |  | 337485.68 | 0 | 19929.7763 | 2025 |  | . |  | 0 | 19929.7763 | - | -
54.9416 | California Water Service Co. - BK 147 Station Improvements | 1260000 | 1132398 | 127602 | 7257.82 | 0.6409% | 0 | 7257.82 | 0 | -7257.82 | 1125140.18 | 1260000 |  |  |  | 7257.82 | 0 | 0 | 2025 |  | . |  | 0 | 0 | - | -
54.9417 | County of Santa Barbara-Public Works - Laguna WWTP WAS Pipe Modifications | 48439 | 42893 | 5546 | 2299.41 | 5.361% | 0 | 2299.41 | 0 | -2299.41 | 40593.59 | 48439 |  |  |  | 2299.41 | 0 | 0 | 2025 |  | < 250k |  |  | 0 | - | -
54.9418 | GenerateUpcycle - Organics Waste Processing Facility | 15739 | 15739 | 0 | 15739 | 100% | 0 | 15739 | 0 | -15739 | 0 | 15739 |  |  |  | 15739 | 0 | 0 | 2025 |  | < 250k |  | 0 | 0 | - | -
54.9421 | Nipomo Community Service Dist. - Tefft Emergency Pipe Repair | 3703.18 | 3703.18 | 0 | 3703.18 | 100% | 0 | 3703.18 | 0 | -3703.18 | 0 | 3703.18 |  |  |  | 3703.18 | 0 | 0 | 2025 |  | < 250k |  |  | 0 | - | -
[24 empty] | 0 | - | -
Bakersfield Area - Open Jobs Totals |  | 107445536.59 | 98595644.99 | 8849891.6 | 46923257.49 |  | 4051564.7526 | 50974822.2426 | 50310970.71 | -663851.5326 | 51672387.5 | 57134565.88 | 13793631.72 | 13358693.09 | 912266.2281 | 33129625.77 | 36952277.62 | 3139298.5245 |  |  |  |  | 815171.6664 | 2324126.8581 | - | - | 21189.15 | 90090635.74 | 82393409.62 | 7697226.12 |  | 3877351.1821 | 44059943.7421 | 16970.1479 | 42210817.06 | 46013721.85 | #REF! | #REF!
[24 empty] | 0 | - | - | 0
Bakersfield Area - Closed Jobs | [23 empty] | 0 | - | - | 0
54.9099 | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 55712110 | 45328892.68 | 10383217.32 | 45328892.68 | 100% | 10383217.32 | 55712110 | 55712110 | 0 | 0 | 0 | 45063061.29 | 55369229 | 10372751.5815 | 265831.39 | 342881 | 10465.7385 | 2020 | 2025 | . | 10372751.5815 | 0 | 10465.7385 | - | - | 53239945.95 | 55712110 | 45328892.68 | 10383217.32 | 100% | 10383217.32 | 55712110 | 0 | 0 | 0 | 140849.7535 | 10242367.5665
54.9172 | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 24160002.44 | 21018432.22 | 3141570.22 | 21018432.22 | 100% | 3141570.22 | 24160002.44 | 24160002.44 | 0 | 0 | 0 | 21046229.25 | 24154131.07 | 3076351.4492 | -27797.03 | 5871.37 | 65218.7708 | 2021 | 2025 | . | 3107901.82 | 65218.7708 | 0 | - | - | 0 | 24160002.44 | 21018432.22 | 3141570.22 | 100% | 3141570.22 | 24160002.44 | 0 | 0 | 0 | 3107901.82 | 33668.4
54.9216 | CA Dept. of Corr. - Water Treatment Improvements | 2472164.05 | 2286264.43 | 185899.62 | 2286264.43 | 100% | 185899.62 | 2472164.05 | 2472164.05 | 0 | 0 | 0 | 2054298.05 | 2312435 | 140849.7535 | 231966.38 | 159729.05 | 45049.8665 | 2022 | 2025 | . | 140849.7535 | 45246.5965 | -196.73 | - | - | 2467864.05 | 2472164.05 | 2286264.43 | 185899.62 | 100% | 185899.62 | 2472164.05 | 0 | 0 | 0 | 669.81 | 185229.81
54.9246 | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 1777852 | 1708475.32 | 69376.68 | 1708475.32 | 100% | 69376.68 | 1777852 | 1777852 | 0 | 0 | 0 | 1350527.55 | 1389025.21 | 69196.4543 | 357947.77 | 388826.79 | 180.2257 | 2022 | 2025 | . | 69196.4543 | -9196.4543 | 9376.68 | - | - | 1773552 | 1777852 | 1708475.32 | 69376.68 | 100% | 69376.68 | 1777852 | 0 | 0 | 0 | 669.81 | 68706.87
54.9265 | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 223896.47 | 220754.51 | 3141.96 | 220754.51 | 100% | 3141.96 | 223896.47 | 223896.47 | 0 | 0 | 0 | 203244.51 | 191463.66 | 0 | 17510 | 32432.81 | 3141.96 | 2023 | 2025 | < 250k | 0 | 3141.96 | 0 | - | - | 219596.47 | 223896.47 | 220754.51 | 3141.96 | 100% | 3141.96 | 223896.47 | 0 | 0 | 0 | 669.81 | 2472.15
54.9279 | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 3216240.01 | 3153237.4 | 63002.61 | 3153237.4 | 100% | 63002.61 | 3216240.01 | 3216240.01 | 0 | 0 | 0 | 2754167.5 | 2243686.4 | -15000 | 399069.9 | 972553.61 | 78002.61 | 2023 | 2025 | . | -15000 | 78002.61 | 0 | - | - | 3105578.54 | 3216240.01 | 3153237.4 | 63002.61 | 100% | 63002.61 | 3216240.01 | 0 | 0 | 0 | 2986.55 | 60016.06
54.9289 | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 44560 | 25097.25 | 19462.75 | 25097.25 | 100% | 19462.75 | 44560 | 44560 | 0 | 0 | 0 | 13506.19 | 14176 | 669.81 | 11591.06 | 30384 | 18792.94 | 2023 | 2025 | < 250k | 669.81 | 18792.94 | 0 | - | - | 0 | 44560 | 25097.25 | 19462.75 | 100% | 19462.75 | 44560 | 0 | 0 | 0 | 0 | 19462.75
54.9292 | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 4300 | 1313.45 | 2986.55 | 1313.45 | 100% | 2986.55 | 4300 | 4300 | 0 | 0 | 0 | 1313.45 | 4300 | 2986.55 | 0 | 0 | 0 | 2023 | 2025 | < 250k | 2986.55 | 0 | 0 | - | - | 0 | 4300 | 1313.45 | 2986.55 | 100% | 2986.55 | 4300 | 0 | 0 | 0 | -15000 | 17986.55
54.9309 | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 3968668.9 | 3790858.34 | 177810.56 | 3790858.34 | 100% | 177810.56 | 3968668.9 | 3968668.9 | 0 | 0 | 0 | 1941399.17 | 2378548.71 | 62853.4158 | 1849459.17 | 1590120.19 | 114957.1442 | 2024 | 2025 | . | 62853.4158 | 96568.7634 | 18388.3808 | - | - | 3678539.9 | 3968668.9 | 3790858.34 | 177810.56 | 100% | 177810.56 | 3968668.9 | 0 | 0 | 0 | 54179.7977 | 123630.7623
54.9323 | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 110661.47 | 94483.21 | 16178.26 | 94483.21 | 100% | 16178.26 | 110661.47 | 110661.47 | 0 | 0 | 0 | 85064.63 | 16235.09 | 0 | 9418.58 | 94426.38 | 16178.26 | 2024 | 2025 | < 250k | 0 | 16178.26 | 0 | - | - | -65223.17 | 110661.47 | 94483.21 | 16178.26 | 100% | 16178.26 | 110661.47 | 0 | 0 | 0 | 62853.4158 | -46675.1558
54.9329 | Kern Water Bank Authority - Valve Replacement Parts | 18201.12 | 16466.72 | 1734.4 | 16466.72 | 100% | 1734.4 | 18201.12 | 18201.12 | 0 | 0 | 0 |  |  |  | 16466.72 | 18201.12 | 1734.4 | 2025 | 2025 | < 250k |  | 1734.4 | 0 | - | -
54.9333 | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 427464.77 | 371915.26 | 55549.51 | 371915.26 | 100% | 55549.51 | 427464.77 | 427464.77 | 0 | 0 | 0 | 152091.76 | 166980.44 | 14888.68 | 219823.5 | 260484.33 | 40660.83 | 2024 | 2025 | . | 14888.68 | 43760.8 | -3099.97 | - | - | -823814.23 | 427464.77 | 371915.26 | 55549.51 | 100% | 55549.51 | 427464.77 | 0 | 0 | 0 | 0 | 55549.51
54.9338 | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 175884.64 | 119186.11 | 56698.53 | 119186.11 | 100% | 56698.53 | 175884.64 | 175884.64 | 0 | 0 | 0 | 105814.13 | 162416 | 54179.7977 | 13371.98 | 13468.64 | 2518.7323 | 2024 | 2025 | < 250k | 54179.7977 | 2518.7323 | 0 | - | - | 0 | 175884.64 | 119186.11 | 56698.53 | 100% | 56698.53 | 175884.64 | 0 | 0 | 0 | 669.81 | 56028.72
54.9341 | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 1251279 | 1063532.4 | 187746.6 | 1063532.4 | 100% | 187746.6 | 1251279 | 1251279 | 0 | 0 | 0 | 197572.74 | 180080 | 0 | 865959.66 | 1071199 | 187746.6 | 2024 | 2025 | . | 9297.3859 | 181979.4229 | 5767.1771 | - | - | 1249423.08 | 1251279 | 1063532.4 | 187746.6 | 100% | 187746.6 | 1251279 | 0 | 0 | 0 | 0 | 187746.6
54.9342 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 199161.5 | 124146.3 | 75015.2 | 124146.3 | 100% | 75015.2 | 199161.5 | 199161.5 | 0 | 0 | 0 | 119458.81 | 174865 | 41394.1127 | 4687.49 | 24296.5 | 33621.0873 | 2024 | 2025 | < 250k | 41394.1127 | 33621.0873 | 0 | - | - | 0 | 199161.5 | 124146.3 | 75015.2 | 100% | 75015.2 | 199161.5 | 0 | 0 | 0 | 2986.55 | 72028.65
54.9347 | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 7100 | 3227.7 | 3872.3 | 3227.7 | 100% | 3872.3 | 7100 | 7100 | 0 | 0 | 0 |  |  |  | 3227.7 | 7100 | 3872.3 | 2025 | 2025 | < 250k |  | 3872.3 | 0 | - | - |  | 7100 | 3227.7 | 3872.3 | 100% | 3872.3 | 7100 | 0 | 0 | 0 | 62853.4158 | -58981.1158
54.9349 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 290129 | 197889.31 | 92239.69 | 197889.31 | 100% | 92239.69 | 290129 | 290129 | 0 | 0 | 0 | 106438.55 | 156414.25 | 4519.6837 | 91450.76 | 133714.75 | 87720.0063 | 2024 | 2025 | . | 4519.6837 | 87720.0063 | 0 | - | - | 90967.5 | 290129 | 197889.31 | 92239.69 | 100% | 92239.69 | 290129 | 0 | 0 | 0 | 0 | 92239.69
54.935 | Kern Water Bank Authority - Construct New Well 18P01 | 129965.06 | 120318.68 | 9646.38 | 120318.68 | 100% | 9646.38 | 129965.06 | 129965.06 | 0 | 0 | 0 | 10110.6 | 0 | 0 | 110208.08 | 129965.06 | 9646.38 | 2024 | 2025 | < 250k | 0 | 9646.38 | 0 | - | - | 127158.64 | 129965.06 | 120318.68 | 9646.38 | 100% | 9646.38 | 129965.06 | 0 | 0 | 0 | 4519.6837 | 5126.6963
54.9351 | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 153298.79 | 136808.3 | 16490.49 | 136808.3 | 100% | 16490.49 | 153298.79 | 153298.79 | 0 | 0 | 0 | 136808.3 | 105656.18 | 11095.2671 | 0 | 47642.61 | 5395.2229 | 2024 | 2025 | < 250k | 0 | 5395.2229 | 0 | - | - | 146198.79 | 153298.79 | 136808.3 | 16490.49 | 100% | 16490.49 | 153298.79 | 0 | 0 | 0 | 0 | 16490.49
54.9353 | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 2008.42 | 1117.5 | 890.92 | 1117.5 | 100% | 890.92 | 2008.42 | 2008.42 | 0 | 0 | 0 | 1117.5 | 0 | 0 | 0 | 2008.42 | 890.92 | 2024 | 2025 | < 250k | 0 | 890.92 | 0 | - | - | -151290.37 | 2008.42 | 1117.5 | 890.92 | 100% | 890.92 | 2008.42 | 0 | 0 | 0 | 62853.4158 | -61962.4958
54.9354 | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 9571.2 | 8230.83 | 1340.37 | 8230.83 | 100% | 1340.37 | 9571.2 | 9571.2 | 0 | 0 | 0 | 12351.11 | 14274.54 | 1923.43 | -4120.28 | -4703.34 | -583.06 | 2024 | 2025 | < 250k | 1923.43 | -583.06 | 0 | - | - | 12266.12 | 9571.2 | 8230.83 | 1340.37 | 100% | 1340.37 | 9571.2 | 0 | 0 | 0 | 0 | 1340.37
54.9355 | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 2806.42 | 1815.23 | 991.19 | 1815.23 | 100% | 991.19 | 2806.42 | 2806.42 | 0 | 0 | 0 | 1815.23 | 0 | 0 | 0 | 2806.42 | 991.19 | 2024 | 2025 | < 250k | 0 | 991.19 | 0 | - | - | -11468.12 | 2806.42 | 1815.23 | 991.19 | 100% | 991.19 | 2806.42 | 0 | 0 | 0 | 0 | 991.19
54.9357 | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 1760.42 | 889.66 | 870.76 | 889.66 | 100% | 870.76 | 1760.42 | 1760.42 | 0 | 0 | 0 | 889.66 | 0 | 0 | 0 | 1760.42 | 870.76 | 2024 | 2025 | < 250k | 0 | 870.76 | 0 | - | - | -1293069.58 | 1760.42 | 889.66 | 870.76 | 100% | 870.76 | 1760.42 | 0 | 0 | 0 | 14888.68 | -14017.92
54.9358 | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 1147640 | 1125399.83 | 22240.17 | 1125399.83 | 100% | 22240.17 | 1147640 | 1147640 | 0 | 0 | 0 | 320292.15 | 268994 | 15917.5507 | 805107.68 | 878646 | 6322.6193 | 2024 | 2025 | . | 15917.5507 | 6322.6193 | 0 | - | - | 1068108.02 | 1147640 | 1125399.83 | 22240.17 | 100% | 22240.17 | 1147640 | 0 | 0 | 0 | 0 | 22240.17
54.936 | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 1855.92 | 1144.88 | 711.04 | 1144.88 | 100% | 711.04 | 1855.92 | 1855.92 | 0 | 0 | 0 | 1144.88 | 0 | 0 | 0 | 1855.92 | 711.04 | 2024 | 2025 | < 250k | 0 | 711.04 | 0 | - | - | -1145784.08 | 1855.92 | 1144.88 | 711.04 | 100% | 711.04 | 1855.92 | 0 | 0 | 0 | 54179.7977 | -53468.7577
54.9361 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 108668.35 | 107074.87 | 1593.48 | 107074.87 | 100% | 1593.48 | 108668.35 | 108668.35 | 0 | 0 | 0 |  |  |  | 107074.87 | 108668.35 | 1593.48 | 2025 | 2025 | < 250k |  | 1593.48 | 0 | - | - |  | 108668.35 | 107074.87 | 1593.48 | 100% | 1593.48 | 108668.35 | 0 | 0 | 0 | 0 | 1593.48
54.9362 | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 425035.04 | 375601.24 | 49433.8 | 375601.24 | 100% | 49433.8 | 425035.04 | 425035.04 | 0 | 0 | 0 | 162458.93 | 0 | 18050.9922 | 213142.31 | 425035.04 | 31382.8078 | 2024 | 2025 | . | 0 | 31382.8078 | 0 | - | - | 423179.12 | 425035.04 | 375601.24 | 49433.8 | 100% | 49433.8 | 425035.04 | 0 | 0 | 0 | 9297.3859 | 40136.4141
54.9363 | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 1855.92 | 777.55 | 1078.37 | 777.55 | 100% | 1078.37 | 1855.92 | 1855.92 | 0 | 0 | 0 | 777.55 | 0 | 0 | 0 | 1855.92 | 1078.37 | 2024 | 2025 | < 250k | 0 | 1078.37 | 0 | - | - | -106144.08 | 1855.92 | 777.55 | 1078.37 | 100% | 1078.37 | 1855.92 | 0 | 0 | 0 | 41394.1127 | -40315.7427
54.9365 | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 2216.42 | 1263.33 | 953.09 | 1263.33 | 100% | 953.09 | 2216.42 | 2216.42 | 0 | 0 | 0 | 1263.33 | 0 | 0 | 0 | 2216.42 | 953.09 | 2024 | 2025 | < 250k | 0 | 953.09 | 0 | - | - | -422818.62 | 2216.42 | 1263.33 | 953.09 | 100% | 953.09 | 2216.42 | 0 | 0 | 0 | 0 | 953.09
54.9367 | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 2540.42 | 1602.33 | 938.09 | 1602.33 | 100% | 938.09 | 2540.42 | 2540.42 | 0 | 0 | 0 | 1602.33 | 0 | 0 | 0 | 2540.42 | 938.09 | 2024 | 2025 | < 250k | 0 | 938.09 | 0 | - | - | 324 | 2540.42 | 1602.33 | 938.09 | 100% | 938.09 | 2540.42 | 0 | 0 | 0 | 4519.6837 | -3581.5937
54.9368 | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 15697.91 | 13653.62 | 2044.29 | 13653.62 | 100% | 2044.29 | 15697.91 | 15697.91 | 0 | 0 | 0 | 13653.62 | 15697.91 | 2044.29 | 0 | 0 | 0 | 2024 | 2025 | < 250k | 2044.29 | 0 | 0 | - | - | -1209522.09 | 15697.91 | 13653.62 | 2044.29 | 100% | 2044.29 | 15697.91 | 0 | 0 | 0 | 0 | 2044.29
54.937 | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 1760.42 | 889.64 | 870.78 | 889.64 | 100% | 870.78 | 1760.42 | 1760.42 | 0 | 0 | 0 | 889.64 | 0 | 0 | 0 | 1760.42 | 870.78 | 2024 | 2025 | < 250k | 0 | 870.78 | 0 | - | - | -13937.49 | 1760.42 | 889.64 | 870.78 | 100% | 870.78 | 1760.42 | 0 | 0 | 0 | 0 | 870.78
54.9371 | Bakersfield Overhead 2025 |  | 1267652.77 | -1267652.77 | 1267652.77 | 100% | -1267652.77 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1267652.77 | 0 | -1267652.77 | 2025 | 2025 | OH |  | -1197386.64 | -70266.13 | - | - |  | 0 | 1267652.77 | -1267652.77 | 100% | -1267652.77 | 0 | 0 | 0 | 0 | 0 | -1267652.77
54.9372 | Bakersfield Estimating 2025 |  | 588792.6 | -588792.6 | 588792.6 | 100% | -588792.6 | 0 | 0 | 0 | 0 | 0 |  |  |  | 588792.6 | 0 | -588792.6 | 2025 | 2025 | OH |  | -549403.88 | -39388.72 | - | - |  | 0 | 588792.6 | -588792.6 | 100% | -588792.6 | 0 | 0 | 0 | 0 | 0 | -588792.6
54.9374 | City of Santa Maria - WWTP Trickling Filter Repairs | 32962 | 19986.45 | 12975.55 | 19986.45 | 100% | 12975.55 | 32962 | 32962 | 0 | 0 | 0 |  |  |  | 19986.45 | 32962 | 12975.55 | 2025 | 2025 | < 250k |  | 12975.55 | 0 | - | - |  | 32962 | 19986.45 | 12975.55 | 100% | 12975.55 | 32962 | 0 | 0 | 0 | 0 | 12975.55
54.9375 | City of Santa Maria - WWTP Clarifier Repairs | 8232.73 | 4545.48 | 3687.25 | 4545.48 | 100% | 3687.25 | 8232.73 | 8232.73 | 0 | 0 | 0 |  |  |  | 4545.48 | 8232.73 | 3687.25 | 2025 | 2025 | < 250k |  | 3687.25 | 0 | - | - |  | 8232.73 | 4545.48 | 3687.25 | 100% | 3687.25 | 8232.73 | 0 | 0 | 0 | 0 | 3687.25
54.9379 | Semitropic Water Storage Dist. - Delta System Pipe Repair | 41679.77 | 36111.95 | 5567.82 | 36111.95 | 100% | 5567.82 | 41679.77 | 41679.77 | 0 | 0 | 0 |  |  |  | 36111.95 | 41679.77 | 5567.82 | 2025 | 2025 | < 250k |  | 5567.82 | 0 | - | - |  | 41679.77 | 36111.95 | 5567.82 | 100% | 5567.82 | 41679.77 | 0 | 0 | 0 | 1923.43 | 3644.39
54.938 | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 22446.19 | 18064.72 | 4381.47 | 18064.72 | 100% | 4381.47 | 22446.19 | 22446.19 | 0 | 0 | 0 |  |  |  | 18064.72 | 22446.19 | 4381.47 | 2025 | 2025 | < 250k |  | 4381.47 | 0 | - | - |  | 22446.19 | 18064.72 | 4381.47 | 100% | 4381.47 | 22446.19 | 0 | 0 | 0 | 0 | 4381.47
54.9381 | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 58900 | 28875.38 | 30024.62 | 28875.38 | 100% | 30024.62 | 58900 | 58900 | 0 | 0 | 0 |  |  |  | 28875.38 | 58900 | 30024.62 | 2025 | 2025 | < 250k |  | 30024.62 | 0 | - | - |  | 58900 | 28875.38 | 30024.62 | 100% | 30024.62 | 58900 | 0 | 0 | 0 | 0 | 30024.62
54.9382 | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 143799 | 108690.45 | 35108.55 | 108690.45 | 100% | 35108.55 | 143799 | 143799 | 0 | 0 | 0 |  |  |  | 108690.45 | 143799 | 35108.55 | 2025 | 2025 | < 250k |  | 31476.8665 | 3631.6835 | - | - |  | 143799 | 108690.45 | 35108.55 | 100% | 35108.55 | 143799 | 0 | 0 | 0 | 0 | 35108.55
54.9383 | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 17542.44 | 15759.76 | 1782.68 | 15759.76 | 100% | 1782.68 | 17542.44 | 17542.44 | 0 | 0 | 0 |  |  |  | 15759.76 | 17542.44 | 1782.68 | 2025 | 2025 | < 250k |  | 1782.68 | 0 | - | - |  | 17542.44 | 15759.76 | 1782.68 | 100% | 1782.68 | 17542.44 | 0 | 0 | 0 | 4174832.91 | -4173050.23
54.9384 | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 79531.98 | 70340.57 | 9191.41 | 70340.57 | 100% | 9191.41 | 79531.98 | 79531.98 | 0 | 0 | 0 |  |  |  | 70340.57 | 79531.98 | 9191.41 | 2025 | 2025 | < 250k |  | 9191.41 | 0 | - | - |  | 79531.98 | 70340.57 | 9191.41 | 100% | 9191.41 | 79531.98 | 0 | 0 | 0 | 1356365.09 | -1347173.68
54.9385 | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 102913.84 | 98598.77 | 4315.07 | 98598.77 | 100% | 4315.07 | 102913.84 | 102913.84 | 0 | 0 | 0 |  |  |  | 98598.77 | 102913.84 | 4315.07 | 2025 | 2025 | < 250k |  | 4315.07 | 0 | - | - |  | 102913.84 | 98598.77 | 4315.07 | 100% | 4315.07 | 102913.84 | 0 | 0 | 0 | #REF! | #REF!
54.9386 | Kern Valley State Prison - Arsenic Pipe Leak Repair | 96086 | 75784.74 | 20301.26 | 75784.74 | 100% | 20301.26 | 96086 | 96086 | 0 | 0 | 0 |  |  |  | 75784.74 | 96086 | 20301.26 | 2025 | 2025 | < 250k |  | 20301.26 | 0 | - | - |  | 96086 | 75784.74 | 20301.26 | 100% | 20301.26 | 96086 | 0 | 0 | 0 | 6702671.5016 | -6682370.2416
54.9387 | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 22619.54 | 19011.65 | 3607.89 | 19011.65 | 100% | 3607.89 | 22619.54 | 22619.54 | 0 | 0 | 0 |  |  |  | 19011.65 | 22619.54 | 3607.89 | 2025 | 2025 | < 250k |  | 3607.89 | 0 | - | - |  | 22619.54 | 19011.65 | 3607.89 | 100% | 3607.89 | 22619.54 | 0 | 0 | 0 | #REF! | #REF!
54.9388 | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 7454.07 | 6535.41 | 918.66 | 6535.41 | 100% | 918.66 | 7454.07 | 7454.07 | 0 | 0 | 0 |  |  |  | 6535.41 | 7454.07 | 918.66 | 2025 | 2025 | < 250k |  | 918.66 | 0 | - | - |  | 7454.07 | 6535.41 | 918.66 | 100% | 918.66 | 7454.07 | 0 | 0 | 0 | 8428.84 | -7510.18
54.939 | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 101491.67 | 96329.49 | 5162.18 | 96329.49 | 100% | 5162.18 | 101491.67 | 101491.67 | 0 | 0 | 0 |  |  |  | 96329.49 | 101491.67 | 5162.18 | 2025 | 2025 | < 250k |  | 5162.18 | 0 | - | - |  | 101491.67 | 96329.49 | 5162.18 | 100% | 5162.18 | 101491.67 | 0 | 0 | 0 | 0 | 5162.18
54.9392 | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 217648.89 | 208346.69 | 9302.2 | 208346.69 | 100% | 9302.2 | 217648.89 | 217648.89 | 0 | 0 | 0 |  |  |  | 208346.69 | 217648.89 | 9302.2 | 2025 | 2025 | < 250k |  | 6751.9761 | 2550.2239 | - | -
54.9393 | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 31523.02 | 27539.82 | 3983.2 | 27539.82 | 100% | 3983.2 | 31523.02 | 31523.02 | 0 | 0 | 0 |  |  |  | 27539.82 | 31523.02 | 3983.2 | 2025 | 2025 | < 250k |  | 3983.2 | 0 | - | -
54.9394 | City of Arvin - Haven Drive Lateral Repair | 15966.99 | 14039.55 | 1927.44 | 14039.55 | 100% | 1927.44 | 15966.99 | 15966.99 | 0 | 0 | 0 |  |  |  | 14039.55 | 15966.99 | 1927.44 | 2025 | 2025 | < 250k |  | 1927.44 | 0 | - | -
54.9398 | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 14300 | 8192.79 | 6107.21 | 8192.79 | 100% | 6107.21 | 14300 | 14300 | 0 | 0 | 0 |  |  |  | 8192.79 | 14300 | 6107.21 | 2025 | 2025 | < 250k |  | 6107.21 | 0 | - | -
54.9399 | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 24775 | 11291.59 | 13483.41 | 11291.59 | 100% | 13483.41 | 24775 | 24775 | 0 | 0 | 0 |  |  |  | 11291.59 | 24775 | 13483.41 | 2025 | 2025 | < 250k |  | 13483.41 | 0 | - | -
54.94 | Arvin Edison Water Storage Dist. - FFPP Core Drilling | 800.69 | 771.32 | 29.37 | 771.32 | 100% | 29.37 | 800.69 | 800.69 | 0 | 0 | 0 |  |  |  | 771.32 | 800.69 | 29.37 | 2025 | 2025 | < 250k |  | 29.37 | 0 | - | -
54.9401 | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R | 247539.61 | 236312.57 | 11227.04 | 236312.57 | 100% | 11227.04 | 247539.61 | 247539.61 | 0 | 0 | 0 |  |  |  | 236312.57 | 247539.61 | 11227.04 | 2025 | 2025 | < 250k |  | 11227.04 | 0 | - | -
54.9407 | Semitropic Water Storage Dist. - North Plant Emergency Repair | 31296.85 | 25667.34 | 5629.51 | 25667.34 | 100% | 5629.51 | 31296.85 | 31296.85 | 0 | 0 | 0 |  |  |  | 25667.34 | 31296.85 | 5629.51 | 2025 | 2025 | < 250k |  | 5629.51 | 0 | - | -
54.9409 | Nipomo CSD Osage Emergency Waterline Repair | 20123.71 | 17411.71 | 2712 | 17411.71 | 100% | 2712 | 20123.71 | 20123.71 | 0 | 0 | 0 |  |  |  | 17411.71 | 20123.71 | 2712 | 2025 | 2025 | < 250k |  | 2712 | 0 | - | -
54.941 | SWID - Burbank St. Repair | 8241.55 | 6965.65 | 1275.9 | 6965.65 | 100% | 1275.9 | 8241.55 | 8241.55 | 0 | 0 | 0 |  |  |  | 6965.65 | 8241.55 | 1275.9 | 2025 | 2025 | < 250k |  | 1275.9 | 0 | - | -
[6 empty] | 0% |  | 0 |  | 0 | 0 | 0 | [11 empty] | 0 | - | - | 0
Bakersfield Area - Closed Jobs Totals |  | 97414231.62 | 84432379.32 | 12981852.3 | 84432379.32 |  | 12981852.3 | 97414231.62 | 97414231.62 | 0 | 0 | 0 | 75859362.41 | 89318608.46 | 13874672.8184 | 8573016.91 | 8095623.16 | -892820.5184 |  |  |  |  | 609161.0932 | -1501981.6116 | - | - | 0 | 41071704.19 | 38530480.89 | 2541223.3 |  | 2541223.3 | 41071704.19 | 0 | 0 | 0 | #REF! | #REF!
Bakersfield Area - Grand Totals |  | 204859768.21 | 183028024.31 | 21831743.9 | 131355636.81 |  | 17033417.0526 | 148389053.8626 | 147725202.33 | -663851.5326 | 51672387.5 | 57134565.88 | 89652994.13 | 102677301.55 | 14786939.0465 | 41702642.68 | 45047900.78 | 2246478.0061 |  |  |  |  | 1424332.7596 | 822145.2465 | - | - | 21189.15 | 131162339.93 | 120923890.51 | 10238449.42 |  | 6418574.4821 | 85131647.9321 | 16970.1479 | 42210817.06 | 46013721.85 | #REF! | #REF!
[24 empty] | 0 | - | - | 0
Northern Open Jobs Totals |  | 920400789.95 | 832749255.02 | 87651534.93 | 396319859.23 |  | 43136524.9933 | 439456384.2233 | 445904787.15 | 6448402.9267 | 436429395.79 | 474496002.8 | 227517552.45 | 246266637.7 | 19044365.7806 | 168802306.78 | 199638149.45 | 24092159.2127 |  |  |  |  | 17090769.2274 | 7001389.9853 | - | - | 920400789.95 | 532581517.97 | 481298825.34 | 51282692.63 |  | 41933859.376 | 426428578.216 | 8253005.974 | 96804106.5 | 97899933.78 | #REF! | #REF!
Northern Closed Job Totals |  | 141195136.3 | 127887502.05 | 13307634.25 | 127887502.05 |  | 13307634.25 | 141195136.3 | 141195136.3 | 0 | 0 | 0 | 106319863.6 | 123306235.67 | 16281355.5857 | 21567638.45 | 17888900.63 | -2973721.3357 |  |  |  |  | 1143973.456 | -4117694.7918 | - | - | 141195136.3 | 42652052.74 | 41423671.58 | 1228381.16 |  | 1228381.16 | 42652052.74 | 0 | 0 | 0 | #REF! | #REF!
Northern Area Totals |  | 1061595926.25 | 960636757.07 | 100959169.18 | 524207361.28 |  | 56444159.2433 | 580651520.5233 | 587099923.45 | 6448402.9267 | 436429395.79 | 474496002.8 | 333837416.05 | 369572873.37 | 35325721.3663 | 190369945.23 | 217527050.08 | 21118437.8769 |  |  |  |  | 18234742.6834 | 2883695.1936 | - | - | 1061595926.25 | 575233570.71 | 522722496.92 | 52511073.79 |  | 43162240.536 | 469080630.956 | 8253005.974 | 96804106.5 | 97899933.78 | #REF! | #REF!
[24 empty] | 0 | - | - | 0
Murrieta Area - Open Jobs | [23 empty] | 0 | - | - | 0
55.109 | LA Dept of Water and Power - Silverlake | 5400000 | 3900000 | 1500000 | 3834064.05 | 98.31% | 1474640.0192 | 5308704.0692 | 5235272.36 | -73431.7092 | 65935.95 | 164727.64 | 3617796.45 | 4974161.54 | 1463888.1686 | 216267.6 | 261110.82 | 10751.8507 | 2012 |  | . | 1356365.09 | 32706.4737 | -21954.623 | - | - | 164727.64 | 5235272.36 | 3834064.05 | 1401208.31 | 100% | 1401208.31 | 5235272.36 | 0 | 0 | 0 | 1356365.09 | 44843.22
55.1191 | Inland Empire Utilities - IEUA RP-5 Liquids Exp. & Solids Treat. Facility | 341443133.71 | 337732635.71 | 3710498 | 299179624.84 | 88.58% | 3710498 | 302890122.84 | 296634984.51 | -6255138.33 | 38553010.87 | 44808149.2 | 282667835.02 | 285899505.28 | 7900000 | 16511789.82 | 10735479.23 | -4189502 | 2020 |  | . | 6702671.5016 | -2689502 | -1500000 | - | - | 0 | 341443133.71 | 337732635.71 | 3710498 | 88.58% | 3286935.529 | 302466560.369 | -5831575.859 | 38553010.87 | 44808149.2 | 6702671.5016 | -3415735.9726
55.1192 | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 6651803.53 | 6401803.53 | 250000 | 6393992.69 | 99.88% | 250000 | 6643992.69 | 6645760.51 | 1767.82 | 7810.84 | 6043.02 | 5962693.73 | 6385785.76 | 350000 | 431298.96 | 259974.75 | -100000 | 2020 |  | . | 334963.8396 | -100000 | 0 | - | - | 0 | 6651803.53 | 6401803.53 | 250000 | 99.88% | 249694.975 | 6643687.665 | 2072.845 | 7810.84 | 6043.02 | 334963.8396 | -85268.8646
55.12 | East County Advanced Water Purification Project - Package 1 | 198075877 | 189975877 | 8100000 | 189971137.49 | 100% | 7779994.28 | 197751131.77 | 197175877 | -575254.77 | 4739.51 | 900000 | 136204938.09 | 140379771 | 5995115.13 | 53766199.4 | 56796106 | 1784879.15 | 2020 |  | . | 4174832.91 | 1688487.28 | 96391.87 | - | - | 900000 | 197175877 | 189971137.49 | 7204739.51 | 100% | 7204739.51 | 197175877 | 0 | 0 | 0 | 4174832.91 | 3029906.6
55.1202 | LA County Sanitation District - Oxygen Generation Project | 16396051.58 | 15220642.58 | 1175409 | 9590124.35 | 63.01% | 740594.1249 | 10330718.4749 | 10912272.58 | 581554.1051 | 5630518.23 | 5483779 | 8229572.13 | 10369938.28 | 647450.7063 | 1360552.22 | 542334.3 | 93143.4186 | 2020 |  | . | 647450.7063 | 91788.7149 | 1354.7037 | - | - | 0 | 16396051.58 | 15220642.58 | 1175409 | 63.01% | 740594.1249 | 10330718.4749 | 581554.1051 | 5630518.23 | 5483779 | 647450.7063 | 93143.4186
55.1204 | East County Advanced Water Purification Project - Package 3 | 57722227 | 55222227 | 2500000 | 55213329.21 | 99.98% | 2362039.01 | 57575368.22 | 57142227 | -433141.22 | 8897.79 | 580000 | 38160537.22 | 39787580 | 1917801.19 | 17052791.99 | 17354647 | 444237.82 | 2020 |  | . | 1627042.78 | 404480.12 | 39757.7 | - | - | 580000 | 57142227 | 55213329.21 | 1928897.79 | 100% | 1928897.79 | 57142227 | 0 | 0 | 0 | 1627042.78 | 301855.01
55.1227 | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 41504206.39 | 37154206.39 | 4350000 | 36953022.96 | 99.46% | 4326445.5224 | 41279468.4824 | 41483406.39 | 203937.9076 | 201183.43 | 20800 | 29332771.27 | 34411945.6 | 3399354.1719 | 7620251.69 | 7071460.79 | 927091.3505 | 2022 |  | . | 3409470.3388 | 907248.3922 | 19842.9584 | - | - | 0 | 41504206.39 | 37154206.39 | 4350000 | 99.46% | 4326445.5224 | 41279468.4824 | 203937.9076 | 201183.43 | 20800 | 3409470.3388 | 916975.1837
55.1233 | Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 9838187 | 9838187 | 0 | 126077.16 | 1.282% | 8429 | 134506.16 | 123617 | -10889.16 | 9712109.84 | 9714570 | 76329.8 | 84758.64 | 8428.84 | 49747.36 | 38858.36 | 0.16 | 2024 |  | . | 8428.84 | -10773.37 | 10773.53 | - | - | 4078885.19 | 9838187 | 9838187 | 0 | 1.282% | 0 | 126077.16 | -2460.16 | 9712109.84 | 9714570 | #REF! | #REF!
55.1248 | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 5759301.81 | 4934301.81 | 825000 | 3621770.22 | 73.4% | 605548.778 | 4227318.998 | 4861991.81 | 634672.812 | 1312531.59 | 897310 | 314753.09 | 711429.5 | 0 | 3307017.13 | 4150562.31 | 605548.778 | 2024 |  | . | 0 | 372419.2916 | 233129.4864 | - | - | #REF! | 5759301.81 | 4934301.81 | 825000 | 73.4% | 605548.778 | 4227318.998 | 634672.812 | 1312531.59 | 897310 | 0 | 605548.778
55.1249 | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 147525113 | 139703905 | 7821208 | 15046313.77 | 10.77% | 0 | 15046313.77 | 15047042.84 | 729.07 | 124657591.23 | 132478070.16 | 941255.62 | 0 | 0 | 14105058.15 | 15047042.84 | 0 | 2024 |  | . | 0 | 0 | 0 | - | - | #REF! | 147525113 | 139703905 | 7821208 | 10.77% | 842355.4777 | 15888669.2477 | -841626.4077 | 124657591.23 | 132478070.16 | #REF! | #REF!
55.1254 | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 471896.25 | 471896.25 | 0 | 156561.66 | 33.18% | 0 | 156561.66 | 158952.89 | 2391.23 | 315334.59 | 312943.36 |  |  |  | 156561.66 | 158952.89 | 0 | 2025 |  | . |  | 0 | 0 | - | -
55.1255 | City of Riverside - RWQCP Emergency Repair | 14160.81 | 14160.81 | 0 | 14160.81 | 100% | 0 | 14160.81 | 0 | -14160.81 | 0 | 14160.81 |  |  |  | 14160.81 | 0 | 0 | 2025 |  | < 250k |  | 0 | 0 | - | -
55.1256 | Anaergia Technologies LLC - City of Riverside - OPS | 2888100 | 2713100 | 175000 | 94989.88 | 3.501% | 0 | 94989.88 | 101150 | 6160.12 | 2618110.12 | 2786950 |  |  |  | 94989.88 | 101150 | 0 | 2025 |  | . |  | 0 | 0 | - | -
[24 empty] | 0 | - | - | 0
Murrieta Area - Open Jobs Totals |  | 833690058.08 | 803282943.08 | 30407115 | 620195169.09 |  | 21258188.7346 | 641453357.8246 | 635522554.89 | -5930802.9346 | 183087773.99 | 198167503.19 | 505508482.42 | 523004875.6 | 21682038.2067 | 114686686.67 | 112517679.29 | -423849.4721 |  |  |  |  | -1563048.0076 | 1139198.5355 | - | - | 11669780.84 | 828671173.38 | 800004212.77 | 28666960.61 |  | 20586420.0171 | 640515876.7571 | -5253424.7571 | 180074756.03 | 193408721.38 | #REF! | #REF!
[24 empty] | 0 | - | - | 0
Murrieta Area - Closed Jobs | [23 empty] | 0 | - | - | 0
55.123 | Anaergia Technologies - VVWRA - DAF 3 Replacement | 2273682.69 | 1665145.3 | 608537.39 | 1665145.3 | 100% | 608537.39 | 2273682.69 | 2273682.69 | 0 | 0 | 0 | 1665145.3 | 2273682.69 | 480252.0335 | 0 | 0 | 128285.3565 | 2023 | 2025 | . | 480252.0335 | 128285.3565 | 0 | - | - | -1772517.31 | 2273682.69 | 1665145.3 | 608537.39 | 100% | 608537.39 | 2273682.69 | 0 | 0 | 0 | 627907.3954 | -19370.0054
55.1231 | City of Corona - WRF 1 Aeration System Improvements | 4046200 | 3321856.36 | 724343.64 | 3321856.36 | 100% | 724343.64 | 4046200 | 4046200 | 0 | 0 | 0 | 3306207.75 | 4027535 | 627907.3954 | 15648.61 | 18665 | 96436.2446 | 2023 | 2025 | . | 627907.3954 | 96436.2446 | 0 | - | - | 0 | 4046200 | 3321856.36 | 724343.64 | 100% | 724343.64 | 4046200 | 0 | 0 | 0 | 627907.3954 | 96436.2446
55.1238 | Anaergia Technologies LLC - East County Package 5 | 34207.53 | 32500.86 | 1706.67 | 32500.86 | 100% | 1706.67 | 34207.53 | 34207.53 | 0 | 0 | 0 | 26100.05 | 34207.53 | 8107.48 | 6400.81 | 0 | -6400.81 | 2023 | 2025 | < 250k | 8107.48 | -5901.26 | -499.55 | - | - | 34207.53 | 34207.53 | 32500.86 | 1706.67 | 100% | 1706.67 | 34207.53 | 0 | 0 | 0 | 0 | 1706.67
55.125 | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 184557.17 | 48293.94 | 136263.23 | 48293.94 | 100% | 136263.23 | 184557.17 | 184557.17 | 0 | 0 | 0 | 46539.64 | 184557.17 | 101052.1598 | 1754.3 | 0 | 35211.0702 | 2024 | 2025 | < 250k | 101052.1598 | 35211.0702 | 0 | - | - | 0 | 184557.17 | 48293.94 | 136263.23 | 100% | 136263.23 | 184557.17 | 0 | 0 | 0 | 101052.1598 | 35211.0702
55.1251 | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 322982.96 | 284221.86 | 38761.1 | 284221.86 | 100% | 38761.1 | 322982.96 | 322982.96 | 0 | 0 | 0 |  |  |  | 284221.86 | 322982.96 | 38761.1 | 2025 | 2025 | . |  | 38761.1 | 0 | - | - |  | 322982.96 | 284221.86 | 38761.1 | 100% | 38761.1 | 322982.96 | 0 | 0 | 0 | 1217319.0687 | -1178557.9687
55.1252 | Murrieta Overhead 2025 |  | 1958826.45 | -1958826.45 | 1958826.45 | 100% | -1958826.45 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1958826.45 | 0 | -1958826.45 | 2025 | 2025 | OH |  | -1803846.56 | -154979.89 | - | - |  | 0 | 1958826.45 | -1958826.45 | 100% | -1958826.45 | 0 | 0 | 0 | 0 | #REF! | #REF!
55.1253 | Murrieta Estimating 2025 |  | 475814.03 | -475814.03 | 475814.03 | 100% | -475814.03 | 0 | 0 | 0 | 0 | 0 |  |  |  | 475814.03 | 0 | -475814.03 | 2025 | 2025 | OH |  | -456056.35 | -19757.68 | - | - |  | 0 | 475814.03 | -475814.03 | 100% | -475814.03 | 0 | 0 | 0 | 0 | #REF! | #REF!
[10 empty] | 0 | 0 | 0 | [11 empty] | 0 | - | - | 0
Murrieta Area - Closed Jobs Totals |  | 6861630.35 | 7786658.8 | -925028.45 | 7786658.8 |  | -925028.45 | 6861630.35 | 6861630.35 | 0 | 0 | 0 | 5043992.74 | 6519982.39 | 1217319.0687 | 2742666.06 | 341647.96 | -2142347.5187 |  |  |  |  | 292792.5113 | -2435140.03 | - | - | 0 | 4587947.66 | 6121513.5 | -1533565.84 |  | -1533565.84 | 4587947.66 | 0 | 0 | 0 | #REF! | #REF!
Murrieta Area - Grand Totals |  | 840551688.43 | 811069601.88 | 29482086.55 | 627981827.89 |  | 20333160.2846 | 648314988.1746 | 642384185.24 | -5930802.9346 | 183087773.99 | 198167503.19 | 510552475.16 | 529524857.99 | 22899357.2754 | 117429352.73 | 112859327.25 | -2566196.9908 |  |  |  |  | -1270255.4963 | -1295941.4945 | - | - | 11669780.84 | 833259121.04 | 806125726.27 | 27133394.77 |  | 19052854.1771 | 645103824.4171 | -5253424.7571 | 180074756.03 | 193408721.38 | #REF! | #REF!
[24 empty] | 0 | - | - | 0
San Diego Area - Open Jobs | [23 empty] | 0 | - | - | 0
57.0003 | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 38165419.5 | 35758333.5 | 2407086 | 6316909.13 | 17.67% | 123922.1725 | 6440831.3025 | 6863233.25 | 422401.9475 | 29441424.37 | 31302186.25 | 901841.91 | 990201.09 | 96385.4118 | 5415067.22 | 5873032.16 | 27536.7607 | 2024 |  | . | 96385.4118 | -0.15424 | 27536.9149 | - | - | 0 | 38165419.5 | 35758333.5 | 2407086 | 17.67% | 425225.1725 | 6742134.3025 | 121098.9475 | 29441424.37 | 31302186.25 | 96385.4118 | 328839.7607
57.0004 | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 40106224.63 | 37896367.63 | 2209857 | 750298.86 | 1.98% | 0 | 750298.86 | 900072.76 | 149773.9 | 37146068.77 | 39206151.87 | 686907.74 | 900072.76 | 0 | 63391.12 | 0 | 0 | 2024 |  | . | 0 | 0 | 0 | - | - | 0 | 40106224.63 | 37896367.63 | 2209857 | 1.98% | 0 | 750298.86 | 149773.9 | 37146068.77 | 39206151.87 | 0 | 0
57.0007 | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | 162630 | 196248.4 | -33618.4 | 196248.4 | 100% | -33618.4 | 162630 | 153858.36 | -8771.64 | 0 | 8771.64 |  |  |  | 196248.4 | 153858.36 | -33618.4 | 2025 |  | < 250k |  | -32235.1 | -1383.3 | - | -
57.0008 | Imperial Irrigation Dist. - El Centro Generating Station WWTP | 2876047 | 2743982 | 132065 | 262382.86 | 9.562% | 0 | 262382.86 | 266758 | 4375.14 | 2481599.14 | 2609289 |  |  |  | 262382.86 | 266758 | 0 | 2025 |  | . |  | 0 | 0 | - | -
[24 empty] | 0 | - | - | 0
San Diego Area - Open Jobs Totals |  | 81310321.13 | 76594931.53 | 4715389.6 | 7525839.25 |  | 90303.7725 | 7616143.0225 | 8183922.37 | 567779.3475 | 69069092.28 | 73126398.76 | 1588749.65 | 1890273.85 | 96385.4118 | 5937089.6 | 6293648.52 | -6081.6393 |  |  |  |  | -122610.2342 | 116528.5949 | - | - | -33618.4 | 78271644.13 | 73654701.13 | 4616943 |  | 425225.1725 | 7492433.1625 | 270872.8475 | 66587493.14 | 70508338.12 | 96385.4118 | 328839.7607
[24 empty] | 0 | - | - | 0
San Diego Area - Closed Jobs | [23 empty] | 0 | - | - | 0
57.0005 | San Diego Overhead 2025 |  | 92874.26 | -92874.26 | 92874.26 | 100% | -92874.26 | 0 | 0 | 0 | 0 | 0 |  |  |  | 92874.26 | 0 | -92874.26 | 2025 | 2025 | OH |  | -79963.66 | -12910.6 | - | - |  | 0 | 92874.26 | -92874.26 | 100% | -92874.26 | 0 | 0 | 0 | 0 | 0 | -92874.26
57.0006 | San Diego Estimating 2025 |  | 13743.76 | -13743.76 | 13743.76 | 100% | -13743.76 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13743.76 | 0 | -13743.76 | 2025 | 2025 | OH |  | -10411.32 | -3332.44 | - | - |  | 0 | 13743.76 | -13743.76 | 100% | -13743.76 | 0 | 0 | 0 | 0 | 0 | -13743.76
[24 empty] | 0 | - | - | 0
San Diego Area - Closed Jobs Totals |  | 0 | 106618.02 | -106618.02 | 106618.02 |  | -106618.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106618.02 | 0 | -106618.02 |  |  |  |  | 0 | -106618.02 | - | - | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
San Diego - Grand Totals |  | 81310321.13 | 76701549.55 | 4608771.58 | 7632457.27 |  | -16314.2475 | 7616143.0225 | 8183922.37 | 567779.3475 | 69069092.28 | 73126398.76 | 1588749.65 | 1890273.85 | 96385.4118 | 6043707.62 | 6293648.52 | -112699.6593 |  |  |  |  | -122610.2342 | 9910.5749 | - | - | -33618.4 | 78271644.13 | 73654701.13 | 4616943 | 0 | 425225.1725 | 7492433.1625 | 270872.8475 | 66587493.14 | 70508338.12 | 96385.4118 | 328839.7607
[24 empty] | 0 | - | - | 0
Los Angeles Area - Open Jobs | [23 empty] | 0 | - | - | 0
58.0003 | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 22525189 | 21217174 | 1308015 | 11034781.79 | 52.01% | 680281.9312 | 11715063.7212 | 11889201.76 | 174138.0388 | 10182392.21 | 10635987.24 | 2381456.48 | 2988736.9 | 0 | 8653325.31 | 8900464.86 | 680281.9312 | 2024 |  | . | 151508.8135 | 524404.3383 | 155877.5929 | - | - | 0 | 22525189 | 21217174 | 1308015 | 52.01% | 680281.9312 | 11715063.7212 | 174138.0388 | 10182392.21 | 10635987.24 | 151508.8135 | 528773.1176
[24 empty] | 0 | - | - | 0
Los Angeles Area - Open Jobs Totals |  | 22525189 | 21217174 | 1308015 | 11034781.79 |  | 680281.9312 | 11715063.7212 | 11889201.76 | 174138.0388 | 10182392.21 | 10635987.24 | 2381456.48 | 2988736.9 | 0 | 8653325.31 | 8900464.86 | 680281.9312 |  |  |  |  | 307817.8883 | 372464.0429 | - | - | 0 | 22525189 | 21217174 | 1308015 |  | 680281.9312 | 11715063.7212 | 174138.0388 | 10182392.21 | 10635987.24 | 151508.8135 | 528773.1176
[24 empty] | 0 | - | - | 0
Los Angeles Area - Closed Jobs | [23 empty] | 0 | - | - | 0
58.0004 | Los Angeles Overhead 2025 |  | 147282.12 | -147282.12 | 147282.12 | 100% | -147282.12 | 0 | 0 | 0 | 0 | 0 |  |  |  | 147282.12 | 0 | -147282.12 | 2025 | 2025 | OH |  | -139299.01 | -7983.11 | - | - |  | 0 | 147282.12 | -147282.12 | 100% | -147282.12 | 0 | 0 | 0 | 0 | 0 | -147282.12
58.0005 | Los Angeles Estimating 2025 |  | 135037.09 | -135037.09 | 135037.09 | 100% | -135037.09 | 0 | 0 | 0 | 0 | 0 |  |  |  | 135037.09 | 0 | -135037.09 | 2025 | 2025 | OH |  | -77287.44 | -57749.65 | - | - |  | 0 | 135037.09 | -135037.09 | 100% | -135037.09 | 0 | 0 | 0 | 0 | 0 | -135037.09
[24 empty] | 0 | - | - | 0
Los Angeles Area - Closed Jobs Totals |  | 0 | 282319.21 | -282319.21 | 282319.21 |  | -282319.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282319.21 | 0 | -282319.21 |  |  |  |  | 0 | -282319.21 | - | - | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Los Angeles - Grand Totals |  | 22525189 | 21499493.21 | 1025695.79 | 11317101 |  | 397962.7212 | 11715063.7212 | 11889201.76 | 174138.0388 | 10182392.21 | 10635987.24 | 2381456.48 | 2988736.9 | 0 | 8935644.52 | 8900464.86 | 397962.7212 |  |  |  |  | 307817.8883 | 90144.8329 | - | - | 0 | 22525189 | 21217174 | 1308015 |  | 680281.9312 | 11715063.7212 | 174138.0388 | 10182392.21 | 10635987.24 | 151508.8135 | 528773.1176
[24 empty] | 0 | - | - | 0
Southern Open Jobs Totals |  | 937525568.21 | 901095048.61 | 36430519.6 | 638755790.13 |  | 22028774.4383 | 660784564.5683 | 655595679.02 | -5188885.5483 | 262339258.48 | 281929889.19 | 509478688.55 | 527883886.35 | 21778423.6185 | 129277101.58 | 127711792.67 | 250350.8197 |  |  |  |  | -1377840.3535 | 1628191.1733 | - | - | #REF! | 929468006.51 | 894876087.9 | 34591918.61 |  | 21691927.1207 | 659723373.6407 | -4808413.8707 | 256844641.38 | 274553046.74 | #REF! | #REF!
Southern Closed Job Totals |  | 6861630.35 | 8175596.03 | -1313965.68 | 8175596.03 |  | -1313965.68 | 6861630.35 | 6861630.35 | 0 | 0 | 0 | 5043992.74 | 6519982.39 | 1217319.0687 | 3131603.29 | 341647.96 | -2531284.7487 |  |  |  |  | 292792.5113 | -2824077.26 | - | - | #REF! | 4587947.66 | 6121513.5 | -1533565.84 |  | -1533565.84 | 4587947.66 | 0 | 0 | 0 | #REF! | #REF!
Southern Area Totals |  | 944387198.56 | 909270644.64 | 35116553.92 | 646931386.16 |  | 20714808.7583 | 667646194.9183 | 662457309.37 | -5188885.5483 | 262339258.48 | 281929889.19 | 514522681.29 | 534403868.74 | 22995742.6873 | 132408704.87 | 128053440.63 | -2280933.929 |  |  |  |  | -1085047.8423 | -1195886.0867 | - | - | #REF! | 934055954.17 | 900997601.4 | 33058352.77 |  | 20158361.2807 | 664311321.3007 | -4808413.8707 | 256844641.38 | 274553046.74 | #REF! | #REF!
[23 empty] | 0 | 0 | - | - | #REF!
System Integration - Open Jobs | [22 empty] | 0 | 0 | - | - | 0
56.1004 | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 373425 | 269840 | 103585 | 236373.73 | 87.6% | 90738.1145 | 327111.8445 | 371550 | 44438.1555 | 33466.27 | 1875 | 152881.54 | 29675 | 51359.9627 | 83492.19 | 341875 | 39378.1518 | 2024 |  | . | 51359.9627 | 26327.1888 | 13050.963 | - | - | 0 | 373425 | 269840 | 103585 | 87.6% | 90738.1145 | 327111.8445 | 44438.1555 | 33466.27 | 1875 | 51359.9627 | 39378.1518
56.1005 | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 135000 | 68025 | 66975 | 51037.42 | 75.03% | 50249.6318 | 101287.0518 | 135000 | 33712.9482 | 16987.58 | 0 | 15913.33 | 0 | 0 | 35124.09 | 135000 | 50249.6318 | 2024 |  | < 250k | 14525.3272 | 50249.6318 | 0 | - | - | 0 | 135000 | 68025 | 66975 | 75.03% | 50249.6318 | 101287.0518 | 33712.9482 | 16987.58 | 0 | 14525.3272 | 35724.3046
56.101 | Placer County Water Agency -PCWA Time & Material Contract | 49250 | 36461.94 | 12788.06 | 36461.94 | 100% | 12788.06 | 49250 | 49250 | 0 | 0 | 0 |  |  |  | 36461.94 | 49250 | 12788.06 | 2025 |  | < 250k |  | 13783.75 | -995.69 | - | - | -53618 | 49250 | 36461.94 | 12788.06 | 100% | 12788.06 | 49250 | 0 | 0 | 0 | 29395.3303 | -16607.2703
56.1015 | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 230000 | 203520 | 26480 | 142358.95 | 69.95% | 18522.3319 | 160881.2819 | 160000 | -881.2819 | 61161.05 | 70000 | 100113.78 | 27000 | 29395.3303 | 42245.17 | 133000 | -10872.9984 | 2024 |  | < 250k | 29395.3303 | -10061.101 | -811.8974 | - | - | 145000 | 230000 | 203520 | 26480 | 69.95% | 18522.3319 | 160881.2819 | -881.2819 | 61161.05 | 70000 | 19016.5728 | -494.2408
56.1017 | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 102868 | 114895 | -12027 | 95450.46 | 83.08% | -12027 | 83423.46 | 99118 | 15694.54 | 19444.54 | 3750 | 42712.89 | 0 | 19016.5728 | 52737.57 | 99118 | -31043.5728 | 2024 |  | < 250k | 19016.5728 | -10075.0584 | -20968.5144 | - | - | #REF! | 102868 | 114895 | -12027 | 83.08% | -12027 | 83423.46 | 15694.54 | 19444.54 | 3750 | 1044.5898 | -13071.5898
56.1018 | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 153913 | 71045 | 82868 | 41991.15 | 59.11% | 48979.1346 | 90970.2846 | 50000 | -40970.2846 | 29053.85 | 103913 | 18131.9 | 0 | 31982.9546 | 23859.25 | 50000 | 16996.18 | 2024 |  | < 250k | 31982.9546 | 22451.2841 | -5455.104 | - | - | #REF! | 153913 | 71045 | 82868 | 59.11% | 48979.1346 | 90970.2846 | -40970.2846 | 29053.85 | 103913 | 17815.6493 | 31163.4853
56.1032 | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 85000 | 82975 | 2025 | 35024.34 | 42.21% | 854.767 | 35879.107 | 0 | -35879.107 | 47950.66 | 85000 | 8938.56 | 0 | 0 | 26085.78 | 0 | 854.767 | 2024 |  | < 250k | 1044.5898 | 1865.5291 | -1010.7621 | - | - | -192565 | 85000 | 82975 | 2025 | 42.21% | 854.767 | 35879.107 | -35879.107 | 47950.66 | 85000 | 4521.8913 | -3667.1243
56.1036 | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 276000 | 209024 | 66976 | 107051.95 | 51.22% | 34301.8572 | 141353.8072 | 48000 | -93353.8072 | 101972.05 | 228000 | 52637.25 | 0 | 0 | 54414.7 | 48000 | 34301.8572 | 2024 |  | . | 17815.6493 | 29663.3168 | 4638.5405 | - | - | -60610 | 276000 | 209024 | 66976 | 51.22% | 34301.8572 | 141353.8072 | -93353.8072 | 101972.05 | 228000 | 34822.2181 | -520.3609
56.1037 | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 36491 | 21674.2 | 14816.8 | 21674.2 | 100% | 14816.8 | 36491 | 36491 | 0 | 0 | 0 | 2024.38 | 2362.5 | 338.12 | 19649.82 | 34128.5 | 14478.68 | 2024 |  | < 250k | 338.12 | 7115.6835 | 7362.9965 | - | - | -40629 | 36491 | 21674.2 | 14816.8 | 100% | 14816.8 | 36491 | 0 | 0 | 0 | 4449.6548 | 10367.1452
56.1038 | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 95000 | 117376 | -22376 | 100049.89 | 85.24% | -22376 | 77673.89 | 0 | -77673.89 | 17326.11 | 95000 | 54820.17 | 0 | 6303.4542 | 45229.72 | 0 | -28679.4542 | 2024 |  | < 250k | 6303.4542 | -26757.4542 | -1922 | - | - | -2299758 | 95000 | 117376 | -22376 | 85.24% | -22376 | 77673.89 | -77673.89 | 17326.11 | 95000 | 1603.6473 | -23979.6473
56.1039 | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 375000 | 332284 | 42716 | 324049.23 | 97.52% | 41657.3982 | 365706.6282 | 330000 | -35706.6282 | 8234.77 | 45000 | 44619.13 | 0 | 0 | 279430.1 | 330000 | 41657.3982 | 2024 |  | . | 4521.8913 | 31507.6379 | 10149.7603 | - | - | 175000 | 375000 | 332284 | 42716 | 97.52% | 41657.3982 | 365706.6282 | -35706.6282 | 8234.77 | 45000 | 0 | 41657.3982
56.1042 | Trabuco Canyon Water Dist. - SCADA Integration Services | 277565 | 218288 | 59277 | 172683.27 | 79.11% | 46892.8489 | 219576.1189 | 217715 | -1861.1189 | 45604.73 | 59850 | 88143.14 | 105595 | 34822.2181 | 84540.13 | 112120 | 12070.6307 | 2024 |  | . | 34822.2181 | 11841.0806 | 229.5501 | - | - | -3514994 | 277565 | 218288 | 59277 | 79.11% | 46892.8489 | 219576.1189 | -1861.1189 | 45604.73 | 59850 | 74409.071 | -27516.2221
56.1043 | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 336610 | 311391 | 25219 | 214994.3 | 69.04% | 17412.0037 | 232406.3037 | 0 | -232406.3037 | 96396.7 | 336610 | 37458.88 | 0 | 0 | 177535.42 | 0 | 17412.0037 | 2024 |  | . | 4449.6548 | 8135.639 | 9276.3648 | - | - | 215719 | 336610 | 311391 | 25219 | 69.04% | 17412.0037 | 232406.3037 | -232406.3037 | 96396.7 | 336610 | 0 | 17412.0037
56.1046 | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 77120 | 79956 | -2836 | 77765.8 | 97.26% | -2836 | 74929.8 | 75120 | 190.2 | 2190.2 | 2000 | 9466.4 | 0 | 0 | 68299.4 | 75120 | -2836 | 2024 |  | < 250k | 1603.6473 | -2190 | -646 | - | - | -322269 | 77120 | 79956 | -2836 | 97.26% | -2836 | 74929.8 | 190.2 | 2190.2 | 2000 | 2514.9896 | -5350.9896
56.1047 | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 2394758 | 2040555 | 354203 | 1602869.63 | 78.55% | 278228.8307 | 1881098.4607 | 1905218.25 | 24119.7893 | 437685.37 | 489539.75 | 60536.16 | 0 | 0 | 1542333.47 | 1905218.25 | 278228.8307 | 2024 |  | . | 0 | 177980.7626 | 100248.0681 | - | - | 1990095 | 2394758 | 2040555 | 354203 | 78.55% | 278228.8307 | 1881098.4607 | 24119.7893 | 437685.37 | 489539.75 | 0 | 278228.8307
56.1048 | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 200000 | 161119 | 38881 | 157916.15 | 98.01% | 38108.093 | 196024.243 | 187500 | -8524.243 | 3202.85 | 12500 | 20789.35 | 0 | 0 | 137126.8 | 187500 | 38108.093 | 2024 |  | < 250k | 34643.7429 | 38765.1299 | -657.0369 | - | - | #REF! | 200000 | 161119 | 38881 | 98.01% | 38108.093 | 196024.243 | -8524.243 | 3202.85 | 12500 | 10941.5619 | 27166.531
56.1049 | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 308725 | 248873 | 59852 | 214423.06 | 86.16% | 51567.0603 | 265990.1203 | 291725 | 25734.8797 | 34449.94 | 17000 | 127480.78 | 137812.5 | 74409.071 | 86942.28 | 153912.5 | -22842.0107 | 2024 |  | . | 74409.071 | -28175.1459 | 5333.1352 | - | - | 200725 | 308725 | 248873 | 59852 | 86.16% | 51567.0603 | 265990.1203 | 25734.8797 | 34449.94 | 17000 | #REF! | #REF!
56.105 | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 3792559 | 3365567 | 426992 | 925847.53 | 27.51% | 117462.9679 | 1043310.4979 | 675979.5 | -367330.9979 | 2439719.47 | 3116579.5 | 54464.62 | 0 | 0 | 871382.91 | 675979.5 | 117462.9679 | 2024 |  | . | 0 | 119001.6696 | -1538.7017 | - | - | 3197559 | 3792559 | 3365567 | 426992 | 27.51% | 117462.9679 | 1043310.4979 | -367330.9979 | 2439719.47 | 3116579.5 | 2968.0708 | 114494.8971
56.1055 | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 120891 | 92848 | 28043 | 78736.44 | 84.8% | 23780.8675 | 102517.3075 | 120891 | 18373.6925 | 14111.56 | 0 | 14271.01 | 0 | 0 | 64465.43 | 120891 | 23780.8675 | 2024 |  | < 250k | 2514.9896 | 21426.9629 | 2353.9046 | - | - | 95534.75 | 120891 | 92848 | 28043 | 84.8% | 23780.8675 | 102517.3075 | 18373.6925 | 14111.56 | 0 | 0 | 23780.8675
56.1059 | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 399389 | 329206 | 70183 | 235841.92 | 71.64% | 50278.8329 | 286120.7529 | 0 | -286120.7529 | 93364.08 | 399389 | 26703.38 | 0 | 0 | 209138.54 | 0 | 50278.8329 | 2024 |  | . | 0 | 48483.9003 | 1794.9326 | - | - | 319389 | 399389 | 329206 | 70183 | 71.64% | 50278.8329 | 286120.7529 | -286120.7529 | 93364.08 | 399389 | 0 | 50278.8329
56.106 | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 404663 | 322491 | 82172 | 145563.36 | 45.14% | 37090.1278 | 182653.4878 | 0 | -182653.4878 | 176927.64 | 404663 | 36446.56 | 0 | 0 | 109116.8 | 0 | 37090.1278 | 2024 |  | . | 10941.5619 | 29822.4348 | 7267.6931 | - | - | 28663 | 404663 | 322491 | 82172 | 45.14% | 37090.1278 | 182653.4878 | -182653.4878 | 176927.64 | 404663 | 0 | 37090.1278
56.1063 | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 108000 | 97921 | 10079 | 74040.41 | 75.61% | 7620.973 | 81661.383 | 10000 | -71661.383 | 23880.59 | 98000 | 17607.81 | 0 | 0 | 56432.6 | 10000 | 7620.973 | 2024 |  | < 250k | 2968.0708 | 10183.7032 | -2562.7302 | - | - | #REF! | 108000 | 97921 | 10079 | 75.61% | 7620.973 | 81661.383 | -71661.383 | 23880.59 | 98000 | 0 | 7620.973
56.1066 | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 595000 | 531490 | 63510 | 476030.06 | 89.57% | 56882.856 | 532912.916 | 570000 | 37087.084 | 55459.94 | 25000 | 12471.13 | 0 | 0 | 463558.93 | 570000 | 56882.856 | 2024 |  | . | 0 | 118603.0651 | -61720.2092 | - | - | #REF! | 595000 | 531490 | 63510 | 89.57% | 56882.856 | 532912.916 | 37087.084 | 55459.94 | 25000 | #REF! | #REF!
56.1067 | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 478000 | 415878 | 62122 | 104751.99 | 25.19% | 15647.3849 | 120399.3749 | 217000 | 96600.6251 | 311126.01 | 261000 | 4066.38 | 0 | 0 | 100685.61 | 217000 | 15647.3849 | 2024 |  | . | 0 | 15509.5797 | 137.8051 | - | - | #REF! | 478000 | 415878 | 62122 | 25.19% | 15647.3849 | 120399.3749 | 96600.6251 | 311126.01 | 261000 | #REF! | #REF!
56.1073 | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 122210 | 114047 | 8163 | 108855.81 | 95.45% | 7791.4367 | 116647.2467 | 0 | -116647.2467 | 5191.19 | 122210 |  |  |  | 108855.81 | 0 | 7791.4367 | 2025 |  | < 250k |  | 7757.897 | 33.5397 | - | - | #REF! | 122210 | 114047 | 8163 | 95.45% | 7791.4367 | 116647.2467 | -116647.2467 | 5191.19 | 122210 | #REF! | #REF!
56.1075 | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 950000 | 779048 | 170952 | 27665.92 | 3.551% | 0 | 27665.92 | 0 | -27665.92 | 751382.08 | 950000 |  |  |  | 27665.92 | 0 | 0 | 2025 |  | . |  | 0 | 0 | - | - | -12080513.17 | 950000 | 779048 | 170952 | 3.551% | 0 | 27665.92 | -27665.92 | 751382.08 | 950000 | #REF! | #REF!
56.1078 | City of Napa - On-Call Control Systems Integrator Services | 25356.25 | 25356.25 | 0 | 25356.25 | 100% | 0 | 25356.25 | 17050.24 | -8306.01 | 0 | 8306.01 |  |  |  | 25356.25 | 17050.24 | 0 | 2025 |  | < 250k |  | 0 | 0 | - | - | 25356.25 | 25356.25 | 25356.25 | 0 | 100% | 0 | 25356.25 | -8306.01 | 0 | 8306.01 | #REF! | #REF!
56.1081 | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 179690 | 159785 | 19905 | 156744.37 | 98.1% | 19526.2176 | 176270.5876 | 164416.35 | -11854.2376 | 3040.63 | 15273.65 |  |  |  | 156744.37 | 164416.35 | 19526.2176 | 2025 |  | < 250k |  | 11244.7764 | 8281.4413 | - | - | 179690 | 179690 | 159785 | 19905 | 98.1% | 19526.2176 | 176270.5876 | -11854.2376 | 3040.63 | 15273.65 | #REF! | #REF!
56.1083 | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 717010 | 656363 | 60647 | 347967.35 | 53.01% | 32151.6842 | 380119.0342 | 153616.75 | -226502.2842 | 308395.65 | 563393.25 |  |  |  | 347967.35 | 153616.75 | 32151.6842 | 2025 |  | . |  | 20529.9788 | 11621.7053 | - | - | 717010 | 717010 | 656363 | 60647 | 53.01% | 32151.6842 | 380119.0342 | -226502.2842 | 308395.65 | 563393.25 | #REF! | #REF!
56.1085 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 80000 | 66955 | 13045 | 1090.31 | 1.628% | 0 | 1090.31 | 0 | -1090.31 | 65864.69 | 80000 |  |  |  | 1090.31 | 0 | 0 | 2025 |  | < 250k |  | 0 | 0 | - | -
56.1086 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 376000 | 295102 | 80898 | 12732.69 | 4.315% | 0 | 12732.69 | 0 | -12732.69 | 282369.31 | 376000 |  |  |  | 12732.69 | 0 | 0 | 2025 |  | . |  | 0 | 0 | - | -
56.1087 | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 49369 | 43026 | 6343 | 39121.54 | 90.93% | 5767.3948 | 44888.9348 | 37977 | -6911.9348 | 3904.46 | 11392 |  |  |  | 39121.54 | 37977 | 5767.3948 | 2025 |  | < 250k |  | 5767.3948 | 0 | - | -
56.1088 | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 117985 | 85405 | 32580 | 66827.49 | 78.25% | 25493.1166 | 92320.6066 | 0 | -92320.6066 | 18577.51 | 117985 |  |  |  | 66827.49 | 0 | 25493.1166 | 2025 |  | < 250k |  | 11576.9219 | 13916.1947 | - | -
[24 empty] | 0 | - | - | 0
System Integration - Open Jobs Totals |  | 14022847.25 | 11967790.39 | 2055056.86 | 6459348.91 |  | 1107371.7916 | 7566720.7016 | 5923618.09 | -1643102.6116 | 5508441.48 | 8099229.16 | 1002698.53 | 302445 | 247627.6836 | 5456650.38 | 5621173.09 | 859744.108 |  |  |  |  | -3534977.4059 | 4394721.5139 | - | - | 14022847.25 | 13399493.25 | 11477302.39 | 1922190.86 |  | 1076111.2802 | 7415688.1602 | -1530047.0702 | 5137725.51 | 7513852.16 | #REF! | #REF!
[23 empty] | 0 | 0 | - | - | 0
System Integration - Closed Jobs | [22 empty] | 0 | 0 | - | - | 0
56.1002 | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 185000 | 114485.82 | 70514.18 | 114485.82 | 100% | 70514.18 | 185000 | 185000 | 0 | 0 | 0 | 113841.61 | 170000 | 50745.2395 | 644.21 | 15000 | 19768.9405 | 2024 | 2025 | < 250k | 50745.2395 | 19768.9405 | 0 | - | - | -147901 | 185000 | 114485.82 | 70514.18 | 100% | 70514.18 | 185000 | 0 | 0 | 0 | 64460.9863 | 6053.1937
56.1003 | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 332901 | 223395.74 | 109505.26 | 223395.74 | 100% | 109505.26 | 332901 | 332901 | 0 | 0 | 0 | 155093.29 | 175000 | 64460.9863 | 68302.45 | 157901 | 45044.2737 | 2023 | 2025 | . | 64460.9863 | 13375.306 | 31668.9677 | - | - | 0 | 332901 | 223395.74 | 109505.26 | 100% | 109505.26 | 332901 | 0 | 0 | 0 | 64460.9863 | 45044.2737
56.1007 | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 16814 | 19362.98 | -2548.98 | 19362.98 | 100% | -2548.98 | 16814 | 16814 | 0 | 0 | 0 | 14316.6 | 13319 | 3177.441 | 5046.38 | 3495 | -5726.421 | 2024 | 2025 | < 250k | 3177.441 | -3177.441 | -2548.98 | - | - | 0 | 16814 | 19362.98 | -2548.98 | 100% | -2548.98 | 16814 | 0 | 0 | 0 | 3177.441 | -5726.421
56.1008 | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 55000 | 30551.92 | 24448.08 | 30551.92 | 100% | 24448.08 | 55000 | 55000 | 0 | 0 | 0 | 30425.18 | 55000 | 23094.0224 | 126.74 | 0 | 1354.0576 | 2024 | 2025 | < 250k | 23094.0224 | 1354.0576 | 0 | - | - | 55000 | 55000 | 30551.92 | 24448.08 | 100% | 24448.08 | 55000 | 0 | 0 | 0 | 64460.9863 | -40012.9063
56.1010.01 | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 9569 | 7097.1 | 2471.9 | 7097.1 | 100% | 2471.9 | 9569 | 9569 | 0 | 0 | 0 | 2465.37 | 0 | 619.6471 | 4631.73 | 9569 | 1852.2529 | 2024 | 2025 | < 250k | 619.6471 | 1852.2529 | 0 | - | - | 0 | 9569 | 7097.1 | 2471.9 | 100% | 2471.9 | 9569 | 0 | 0 | 0 | 3177.441 | -705.541
56.1016 | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 150064.25 | 110083.62 | 39980.63 | 110083.62 | 100% | 39980.63 | 150064.25 | 150064.25 | 0 | 0 | 0 | 57071.14 | 71814.5 | 14743.36 | 53012.48 | 78249.75 | 25237.27 | 2024 | 2025 | < 250k | 14743.36 | 25237.27 | 0 | - | - | #REF! | 150064.25 | 110083.62 | 39980.63 | 100% | 39980.63 | 150064.25 | 0 | 0 | 0 | #REF! | #REF!
56.1019 | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 193845 | 143764.58 | 50080.42 | 143764.58 | 100% | 50080.42 | 193845 | 193845 | 0 | 0 | 0 | 20442.52 | 0 | 0 | 123322.06 | 193845 | 50080.42 | 2024 | 2025 | < 250k | 4594.7943 | 36717.2037 | 13363.2163 | - | - | -50915 | 193845 | 143764.58 | 50080.42 | 100% | 50080.42 | 193845 | 0 | 0 | 0 | #REF! | #REF!
56.1021 | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 244760 | 116752.52 | 128007.48 | 116752.52 | 100% | 128007.48 | 244760 | 244760 | 0 | 0 | 0 | 113715.41 | 0 | 38878.5393 | 3037.11 | 244760 | 89128.9407 | 2024 | 2025 | < 250k | 38878.5393 | 89128.9407 | 0 | - | - | 94695.75 | 244760 | 116752.52 | 128007.48 | 100% | 128007.48 | 244760 | 0 | 0 | 0 | 23094.0224 | 104913.4576
56.1022 | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 0 | 0 | 0 |  | 0% |  | 0 | 0 | 0 | 0 | 0 | 88093.56 | 0 | 0 | -88093.56 | 0 | 0 | 2024 | 2025 | < 250k | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 619.6471 | -619.6471
56.1023 | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 220390 | 150504.73 | 69885.27 | 150504.73 | 100% | 69885.27 | 220390 | 220390 | 0 | 0 | 0 | 112097.3 | 172000 | 40095.3125 | 38407.43 | 48390 | 29789.9575 | 2024 | 2025 | < 250k | 40095.3125 | 29789.9575 | 0 | - | - | 211503 | 220390 | 150504.73 | 69885.27 | 100% | 69885.27 | 220390 | 0 | 0 | 0 | 7002.238 | 62883.032
56.103 | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 689578.64 | 689578.64 | 0 | 689578.64 | 100% | 0 | 689578.64 | 689578.64 | 0 | 0 | 0 | 122107.57 | 77500 | 0 | 567471.07 | 612078.64 | 0 | 2024 | 2025 | . | 18034.019 | 0 | 0 | - | - | 0 | 689578.64 | 689578.64 | 0 | 100% | 0 | 689578.64 | 0 | 0 | 0 | 40095.3125 | -40095.3125
56.1041 | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 20016.78 | 20016.78 | 0 | 20016.78 | 100% | 0 | 20016.78 | 20016.78 | 0 | 0 | 0 | 9127.13 | 0 | 7002.238 | 10889.65 | 20016.78 | -7002.238 | 2024 | 2025 | < 250k | 7002.238 | -7002.238 | 0 | - | - | -224743.22 | 20016.78 | 20016.78 | 0 | 100% | 0 | 20016.78 | 0 | 0 | 0 | 4594.7943 | -4594.7943
56.1051 | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 136875 | 98718.18 | 38156.82 | 98718.18 | 100% | 38156.82 | 136875 | 136875 | 0 | 0 | 0 | 39254.31 | 0 | 16220.5398 | 59463.87 | 136875 | 21936.2802 | 2024 | 2025 | < 250k | 16220.5398 | 3102.6571 | 18833.6231 | - | - | 99226.97 | 136875 | 98718.18 | 38156.82 | 100% | 38156.82 | 136875 | 0 | 0 | 0 | 4187.3606 | 33969.4594
56.1052 | San Jose Water - Williams Back ATS Replacement | 8887 | 6400.94 | 2486.06 | 6400.94 | 100% | 2486.06 | 8887 | 8887 | 0 | 0 | 0 | 5914.69 | 0 | 369.0936 | 486.25 | 8887 | 2116.9664 | 2024 | 2025 | < 250k | 369.0936 | 2116.9664 | 0 | - | - | -184958 | 8887 | 6400.94 | 2486.06 | 100% | 2486.06 | 8887 | 0 | 0 | 0 | 14743.36 | -12257.3
56.1053 | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 35000 | 19964.78 | 15035.22 | 19964.78 | 100% | 15035.22 | 35000 | 35000 | 0 | 0 | 0 | 5710.5 | 0 | 0 | 14254.28 | 35000 | 15035.22 | 2024 | 2025 | < 250k | 4187.3606 | 15035.22 | 0 | - | - | 26113 | 35000 | 19964.78 | 15035.22 | 100% | 15035.22 | 35000 | 0 | 0 | 0 | 14743.36 | 291.86
56.1054 | AIC - Riverside Public Works - Digester 5 Rehab | 37648.03 | 37648.03 | 0 | 37648.03 | 100% | 0 | 37648.03 | 37648.03 | 0 | 0 | 0 | 10750.06 | 0 | 0 | 26897.97 | 37648.03 | 0 | 2024 | 2025 | < 250k | 0 | 0 | 0 | - | - | 37648.03 | 37648.03 | 37648.03 | 0 | 100% | 0 | 37648.03 | 0 | 0 | 0 | 0 | 0
56.1056 | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan | 98280.63 | 98280.63 | 0 | 98280.63 | 100% | 0 | 98280.63 | 98280.63 | 0 | 0 | 0 | 31429.81 | 0 | 0 | 66850.82 | 98280.63 | 0 | 2024 | 2025 | < 250k | 20551.5757 | 0 | 0 | - | - | -38594.37 | 98280.63 | 98280.63 | 0 | 100% | 0 | 98280.63 | 0 | 0 | 0 | 18034.019 | -18034.019
56.1057 | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 0 | 0 | 0 |  | 0% |  | 0 | 0 | 0 | 0 | 0 | 16238.75 | 0 | 0 | -16238.75 | 0 | 0 | 2024 | 2025 | < 250k | 0 | 0 | 0 | - | - | -4511779.65 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 38878.5393 | -38878.5393
56.1061 | San Jose Water - PLC System Assessment | 11269 | 5582.66 | 5686.34 | 5582.66 | 100% | 5686.34 | 11269 | 11269 | 0 | 0 | 0 | 5081.1 | 0 | 5163.8304 | 501.56 | 11269 | 522.5096 | 2024 | 2025 | < 250k | 5163.8304 | 522.5096 | 0 | - | - | -388731 | 11269 | 5582.66 | 5686.34 | 100% | 5686.34 | 11269 | 0 | 0 | 0 | 4594.7943 | 1091.5457
56.1062 | AIC - SCADA System Upgrade - City of Brentwood | 409988.07 | 409988.07 | 0 | 409988.07 | 100% | 0 | 409988.07 | 409988.07 | 0 | 0 | 0 | 26225.9 | 0 | 0 | 383762.17 | 409988.07 | 0 | 2024 | 2025 | . | 0 | 0 | 0 | - | - | 409988.07 | 409988.07 | 409988.07 | 0 | 100% | 0 | 409988.07 | 0 | 0 | 0 | 0 | 0
56.1064 | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 435153 | 202266.4 | 232886.6 | 202266.4 | 100% | 232886.6 | 435153 | 435153 | 0 | 0 | 0 | 124401.21 | 0 | 69496.4896 | 77865.19 | 435153 | 163390.1104 | 2024 | 2025 | . | 69496.4896 | 163390.1104 | 0 | - | - | 435153 | 435153 | 202266.4 | 232886.6 | 100% | 232886.6 | 435153 | 0 | 0 | 0 | 0 | 232886.6
56.1065 | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 226400.8 | 192023.81 | 34376.99 | 192023.81 | 100% | 34376.99 | 226400.8 | 226400.8 | 0 | 0 | 0 | 15862.63 | 0 | 0 | 176161.18 | 226400.8 | 34376.99 | 2024 | 2025 | < 250k | 0 | 16147.5732 | 18229.4168 | - | - | 170545.56 | 226400.8 | 192023.81 | 34376.99 | 100% | 34376.99 | 226400.8 | 0 | 0 | 0 | 0 | 34376.99
56.1069 | AIC - City of Brentwood - Brentwood, City of - On-Call Agreement | 2525 | 3821.46 | -1296.46 | 3821.46 | 100% | -1296.46 | 2525 | 2525 | 0 | 0 | 0 |  |  |  | 3821.46 | 2525 | -1296.46 | 2025 | 2025 | < 250k |  | -1296.46 | 0 | - | - | 2525 | 2525 | 3821.46 | -1296.46 | 100% | -1296.46 | 2525 | 0 | 0 | 0 | 725330.9858 | -726627.4458
56.1071 | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 34000 | 3596.56 | 30403.44 | 3596.56 | 100% | 30403.44 | 34000 | 34000 | 0 | 0 | 0 | 316.5 | 0 | 0 | 3280.06 | 34000 | 30403.44 | 2024 | 2025 | < 250k | 0 | 30403.44 | 0 | - | - | 34000 | 34000 | 3596.56 | 30403.44 | 100% | 30403.44 | 34000 | 0 | 0 | 0 | 0 | 30403.44
56.1072 | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 65960 | 41538.84 | 24421.16 | 41538.84 | 100% | 24421.16 | 65960 | 65960 | 0 | 0 | 0 | 1242.1 | 0 | 0 | 40296.74 | 65960 | 24421.16 | 2024 | 2025 | < 250k | 0 | 7362.5362 | 17058.6238 | - | - | #REF! | 65960 | 41538.84 | 24421.16 | 100% | 24421.16 | 65960 | 0 | 0 | 0 | 0 | 24421.16
56.1074 | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 12650 | 10641.86 | 2008.14 | 10641.86 | 100% | 2008.14 | 12650 | 12650 | 0 | 0 | 0 | 6757.28 | 0 | 1239.6881 | 3884.58 | 12650 | 768.4519 | 2024 | 2025 | < 250k | 1239.6881 | 768.4519 | 0 | - | - | 12650 | 12650 | 10641.86 | 2008.14 | 100% | 2008.14 | 12650 | 0 | 0 | 0 | 38878.5393 | -36870.3993
56.1076 | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 19200 | 11577.77 | 7622.23 | 11577.77 | 100% | 7622.23 | 19200 | 19200 | 0 | 0 | 0 | 604.81 | 0 | 0 | 10972.96 | 19200 | 7622.23 | 2024 | 2025 | < 250k | 0 | 7622.23 | 0 | - | - | 19200 | 19200 | 11577.77 | 7622.23 | 100% | 7622.23 | 19200 | 0 | 0 | 0 | 0 | 7622.23
56.1077 | System Integration Overhead 2025 |  | 4370841.4 | -4370841.4 | 4370841.4 | 100% | -4370841.4 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4370841.4 | 0 | -4370841.4 | 2025 | 2025 | OH |  | -4370841.4 | 0 | - | - | -14772.26 | 0 | 4370841.4 | -4370841.4 | 100% | -4370841.4 | 0 | 0 | 0 | 0 | #REF! | #REF!
56.1079 | AIC - San Jose Water Co - Montevina PLC Upgrade | 29235.63 | 29235.63 | 0 | 29235.63 | 100% | 0 | 29235.63 | 29235.63 | 0 | 0 | 0 |  |  |  | 29235.63 | 29235.63 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 29235.63 | 29235.63 | 29235.63 | 0 | 100% | 0 | 29235.63 | 0 | 0 | 0 | 0 | 0
56.108 | AIC - San Jose Water Co - PLC System Assessment | 359469 | 359469 | 0 | 359469 | 100% | 0 | 359469 | 359469 | 0 | 0 | 0 |  |  |  | 359469 | 359469 | 0 | 2025 | 2025 | . |  | 0 | 0 | - | - | 359469 | 359469 | 359469 | 0 | 100% | 0 | 359469 | 0 | 0 | 0 | 0 | 0
56.1082 | City of Clovis - Pump Station E New Pump 5 VFD Startup | 19800 | 20583.04 | -783.04 | 20583.04 | 100% | -783.04 | 19800 | 19800 | 0 | 0 | 0 |  |  |  | 20583.04 | 19800 | -783.04 | 2025 | 2025 | < 250k |  | -783.04 | 0 | - | - | #VALUE! | 19800 | 20583.04 | -783.04 | 100% | -783.04 | 19800 | 0 | 0 | 0 | 342656.8085 | -343439.8485
56.1084 | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 8000 | 4228.13 | 3771.87 | 4228.13 | 100% | 3771.87 | 8000 | 8000 | 0 | 0 | 0 |  |  |  | 4228.13 | 8000 | 3771.87 | 2025 | 2025 | < 250k |  | 3771.87 | 0 | - | -
56.1102 | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 19815.94 | 19815.94 | 0 | 19815.94 | 100% | 0 | 19815.94 | 19815.94 | 0 | 0 | 0 |  |  |  | 19815.94 | 19815.94 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 19815.94 | 19815.94 | 19815.94 | 0 | 100% | 0 | 19815.94 | 0 | 0 | 0 | 0 | 0
56.1103 | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 55855.24 | 55855.24 | 0 | 55855.24 | 100% | 0 | 55855.24 | 55855.24 | 0 | 0 | 0 |  |  |  | 55855.24 | 55855.24 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 55855.24 | 55855.24 | 55855.24 | 0 | 100% | 0 | 55855.24 | 0 | 0 | 0 | 0 | 0
56.1104 | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 9500.31 | 9500.31 | 0 | 9500.31 | 100% | 0 | 9500.31 | 9500.31 | 0 | 0 | 0 |  |  |  | 9500.31 | 9500.31 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 9500.31 | 9500.31 | 9500.31 | 0 | 100% | 0 | 9500.31 | 0 | 0 | 0 | 0 | 0
56.1105 | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 30502.53 | 30502.53 | 0 | 30502.53 | 100% | 0 | 30502.53 | 30502.53 | 0 | 0 | 0 |  |  |  | 30502.53 | 30502.53 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 30502.53 | 30502.53 | 30502.53 | 0 | 100% | 0 | 30502.53 | 0 | 0 | 0 | 0 | 0
56.1106 | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 54742.18 | 54742.18 | 0 | 54742.18 | 100% | 0 | 54742.18 | 54742.18 | 0 | 0 | 0 |  |  |  | 54742.18 | 54742.18 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 54742.18 | 54742.18 | 54742.18 | 0 | 100% | 0 | 54742.18 | 0 | 0 | 0 | 0 | 0
56.1107 | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 3429.06 | 3429.06 | 0 | 3429.06 | 100% | 0 | 3429.06 | 3429.06 | 0 | 0 | 0 |  |  |  | 3429.06 | 3429.06 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 3429.06 | 3429.06 | 3429.06 | 0 | 100% | 0 | 3429.06 | 0 | 0 | 0 | 0 | 0
56.1108 | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 20729.84 | 20729.84 | 0 | 20729.84 | 100% | 0 | 20729.84 | 20729.84 | 0 | 0 | 0 |  |  |  | 20729.84 | 20729.84 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 20729.84 | 20729.84 | 20729.84 | 0 | 100% | 0 | 20729.84 | 0 | 0 | 0 | 0 | 0
56.1109 | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 14772.26 | 14772.26 | 0 | 14772.26 | 100% | 0 | 14772.26 | 14772.26 | 0 | 0 | 0 |  |  |  | 14772.26 | 14772.26 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 14772.26 | 14772.26 | 14772.26 | 0 | 100% | 0 | 14772.26 | 0 | 0 | 0 | 0 | 0
56.111 | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 4596.42 | 4596.42 | 0 | 4596.42 | 100% | 0 | 4596.42 | 4596.42 | 0 | 0 | 0 |  |  |  | 4596.42 | 4596.42 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 4596.42 | 4596.42 | 4596.42 | 0 | 100% | 0 | 4596.42 | 0 | 0 | 0 | 0 | 0
56.1111 | AIC - California American Water - Luzern Well Treatment Design | 17210.01 | 17210.01 | 0 | 17210.01 | 100% | 0 | 17210.01 | 17210.01 | 0 | 0 | 0 |  |  |  | 17210.01 | 17210.01 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 17210.01 | 17210.01 | 17210.01 | 0 | 100% | 0 | 17210.01 | 0 | 0 | 0 | 35006187.3047 | -35006187.3047
56.1112 | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 27241.58 | 27241.58 | 0 | 27241.58 | 100% | 0 | 27241.58 | 27241.58 | 0 | 0 | 0 |  |  |  | 27241.58 | 27241.58 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 27241.58 | 27241.58 | 27241.58 | 0 | 100% | 0 | 27241.58 | 0 | 0 | 0 | 17890185.9346 | -17890185.9346
56.1113 | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 49233.44 | 49233.44 | 0 | 49233.44 | 100% | 0 | 49233.44 | 49233.44 | 0 | 0 | 0 |  |  |  | 49233.44 | 49233.44 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 49233.44 | 49233.44 | 49233.44 | 0 | 100% | 0 | 49233.44 | 0 | 0 | 0 | 52896373.2393 | -52896373.2393
56.1115 | AIC - UC Davis - WWTP Annual Instrument Calibrations | 5895.77 | 5895.77 | 0 | 5895.77 | 100% | 0 | 5895.77 | 5895.77 | 0 | 0 | 0 |  |  |  | 5895.77 | 5895.77 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 5895.77 | 5895.77 | 5895.77 | 0 | 100% | 0 | 5895.77 | 0 | 0 | 0 | 0 | 0
56.1119 | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 22184.06 | 22184.06 | 0 | 22184.06 | 100% | 0 | 22184.06 | 22184.06 | 0 | 0 | 0 |  |  |  | 22184.06 | 22184.06 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | - | 22184.06 | 22184.06 | 22184.06 | 0 | 100% | 0 | 22184.06 | 0 | 0 | 0 | 0 | 0
56.112 | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 1045.63 | 1045.63 | 0 | 1045.63 | 100% | 0 | 1045.63 | 1045.63 | 0 | 0 | 0 |  |  |  | 1045.63 | 1045.63 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1121 | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 22824.38 | 22824.38 | 0 | 22824.38 | 100% | 0 | 22824.38 | 22824.38 | 0 | 0 | 0 |  |  |  | 22824.38 | 22824.38 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1122 | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 6289.38 | 6289.38 | 0 | 6289.38 | 100% | 0 | 6289.38 | 6289.38 | 0 | 0 | 0 |  |  |  | 6289.38 | 6289.38 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1123 | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 3772.82 | 3772.82 | 0 | 3772.82 | 100% | 0 | 3772.82 | 3772.82 | 0 | 0 | 0 |  |  |  | 3772.82 | 3772.82 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1124 | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 28950 | 28950 | 0 | 28950 | 100% | 0 | 28950 | 28950 | 0 | 0 | 0 |  |  |  | 28950 | 28950 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1125 | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 14229.38 | 14229.38 | 0 | 14229.38 | 100% | 0 | 14229.38 | 14229.38 | 0 | 0 | 0 |  |  |  | 14229.38 | 14229.38 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1126 | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 9526.88 | 9526.88 | 0 | 9526.88 | 100% | 0 | 9526.88 | 9526.88 | 0 | 0 | 0 |  |  |  | 9526.88 | 9526.88 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1127 | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 6519.07 | 6519.07 | 0 | 6519.07 | 100% | 0 | 6519.07 | 6519.07 | 0 | 0 | 0 |  |  |  | 6519.07 | 6519.07 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1128 | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 4793.13 | 4793.13 | 0 | 4793.13 | 100% | 0 | 4793.13 | 4793.13 | 0 | 0 | 0 |  |  |  | 4793.13 | 4793.13 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1129 | AIC - RMCSD - VEEAM SFTWR | 133.75 | 133.75 | 0 | 133.75 | 100% | 0 | 133.75 | 133.75 | 0 | 0 | 0 |  |  |  | 133.75 | 133.75 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.113 | System Integration Division Estimating 2025 |  | 267.5 | -267.5 | 267.5 | 100% | -267.5 | 0 | 0 | 0 | 0 | 0 |  |  |  | 267.5 | 0 | -267.5 | 2025 | 2025 | OH |  | -267.5 | 0 | - | -
56.1131 | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 2388.75 | 2388.75 | 0 | 2388.75 | 100% | 0 | 2388.75 | 2388.75 | 0 | 0 | 0 |  |  |  | 2388.75 | 2388.75 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1132 | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 585 | 585 | 0 | 585 | 100% | 0 | 585 | 585 | 0 | 0 | 0 |  |  |  | 585 | 585 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1133 | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 2827.5 | 2827.5 | 0 | 2827.5 | 100% | 0 | 2827.5 | 2827.5 | 0 | 0 | 0 |  |  |  | 2827.5 | 2827.5 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1134 | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 965.51 | 965.51 | 0 | 965.51 | 100% | 0 | 965.51 | 965.51 | 0 | 0 | 0 |  |  |  | 965.51 | 965.51 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1135 | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 112.5 | 112.5 | 0 | 112.5 | 100% | 0 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 112.5 | 112.5 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
56.1141 | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 2827.5 | 2827.5 | 0 | 2827.5 | 100% | 0 | 2827.5 | 2827.5 | 0 | 0 | 0 |  |  |  | 2827.5 | 2827.5 | 0 | 2025 | 2025 | < 250k |  | 0 | 0 | - | -
[24 empty] | 0 | - | - | 0
System Integration - Closed Jobs Totals |  | 4511779.65 | 7995768.94 | -3483989.29 | 7995768.94 |  | -3483989.29 | 4511779.65 | 4511779.65 | 0 | 0 | 0 | 1128586.33 | 734633.5 | 335306.4276 | 6867182.61 | 3777146.15 | -3819295.7176 |  |  |  |  | 381412.9795 | -4200708.6971 | - | - | 4511779.65 | 4395988.47 | 7883482.13 | -3487493.66 |  | -3487493.66 | 4395988.47 | 0 | 0 | 0 | #REF! | #REF!
System Integration - Grand Totals |  | 18534626.9 | 19963559.33 | -1428932.43 | 14455117.85 |  | -2376617.4984 | 12078500.3516 | 10435397.74 | -1643102.6116 | 5508441.48 | 8099229.16 | 1002698.53 | 302445 | 247627.6836 | 12323832.99 | 9398319.24 | -2959551.6097 |  |  |  |  | -3153564.4264 | 194012.8167 | - | - | 18534626.9 | 17795481.72 | 19360784.52 | -1565302.8 |  | -2411382.3798 | 11811676.6302 | -1530047.0702 | 5137725.51 | 7513852.16 | #REF! | #REF!
[24 empty] | 0 | - | - | 0
50 Jobs | [23 empty] | 0 | - | - | 0
50.0541 | W.M. Lyles Co. - General Overhead | 0 | 3642039.89 | -3642039.89 | 3642039.89 | 100% | -3642039.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3642039.89 | 0 | -3642039.89 | 50 | 50 |  |  | -3221414.38 | -420625.51 | - | - | 0 | 0 | 3642039.89 | -3642039.89 | 100% | -3642039.89 | 0 | 0 | 0 | 0 |  | -3642039.89
50.0542 | W.M. Lyles Co. - General Estimating | 0 | 100487.45 | -100487.45 | 100487.45 | 100% | -100487.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100487.45 | 0 | -100487.45 | 50 | 50 |  |  | -79728.23 | -20759.22 | - | - | 0 | 0 | 100487.45 | -100487.45 | 100% | -100487.45 | 0 | 0 | 0 | 0 |  | -100487.45
50.0543 | American Paving | 7051.01 | 7051.01 | 0 | 7051.01 | 100% | 0 | 7051.01 | 7051.01 | 0 | 0 | 0 | 0 | 0 | 0 | 7051.01 | 7051.01 | 0 | 50 | 50 |  |  | 0 | 0 | - | - | 7051.01 | 7051.01 | 7051.01 | 0 | 100% | 0 | 7051.01 | 0 | 0 | 0 |  | 0
50.0544 | Lyles Services Co. | 13555.8 | 13555.8 | 0 | 13555.8 | 100% | 0 | 13555.8 | 13555.8 | 0 | 0 | 0 | 0 | 0 | 0 | 13555.8 | 13555.8 | 0 | 50 | 50 |  |  | 0 | 0 | - | - | 13555.8 | 13555.8 | 13555.8 | 0 | 100% | 0 | 13555.8 | 0 | 0 | 0 |  | 0
50.0545 | New England Sheet Metal and Mechanical Co. | 2226.16 | 2226.16 | 0 | 2226.16 | 100% | 0 | 2226.16 | 2226.16 | 0 | 0 | 0 |  |  |  | 2226.16 | 2226.16 | 0 | 50 | 50 |  |  | 0 | 0 | - | - | #VALUE! | 2226.16 | 2226.16 | 0 | 100% | 0 | 2226.16 | 0 | 0 | 0 |  | 0
50.0546 | Lyles Utility Construction, LLC | 11256.72 | 10468.06 | 788.66 | 10468.06 | 100% | 788.66 | 11256.72 | 11256.72 | 0 | 0 | 0 | 0 | 0 | 0 | 10468.06 | 11256.72 | 788.66 | 50 | 50 |  |  | 788.66 | 0 | - | - | #VALUE! | 11256.72 | 10468.06 | 788.66 | 100% | 788.66 | 11256.72 | 0 | 0 | 0 |  | 788.66
50.0551 | Advanced Integration & Controls | 5457.42 | 5457.42 | 0 | 5457.42 | 100% | 0 | 5457.42 | 5457.42 | 0 | 0 | 0 |  |  |  | 5457.42 | 5457.42 | 0 | 50 | 50 |  |  | 0 | 0 | - | -
[24 empty] | 0 | - | - | #VALUE!
50 Jobs Totals |  | 39547.11 | 3781285.79 | -3741738.68 | 3781285.79 |  | -3741738.68 | 39547.11 | 39547.11 | 0 | 0 | 0 | 0 | 0 | 0 | 3781285.79 | 39547.11 | -3741738.68 |  |  |  |  | -3300353.95 | -441384.73 | - | - | #VALUE! | 34089.69 | 3775828.37 | -3741738.68 |  | -3741738.68 | 34089.69 | 0 | 0 | 0 | 0 | -3741738.68
[24 empty] | 0 | - | - | #VALUE!
Open Jobs Totals |  | 1871949205.41 | 1745812094.02 | 126137111.39 | 1041534998.27 |  | 66272671.2231 | 1107807669.4931 | 1107424084.26 | -383585.2331 | 704277095.75 | 764525121.15 | 737998939.53 | 774452969.05 | 41070417.0828 | 303536058.74 | 332971115.21 | 25202254.1404 |  |  |  |  | 12177951.4679 | 13024302.6725 | - | - | #VALUE! | 1475449017.73 | 1387652215.63 | 87796802.1 |  | 64701897.7769 | 1093567640.0169 | 1914545.0331 | 358786473.39 | 379966832.68 | #REF! | #REF!
Closed Job Totals |  | 152608093.41 | 147840152.81 | 4767940.6 | 147840152.81 |  | 4767940.6 | 152608093.41 | 152608093.41 | 0 | 0 | 0 | 112492442.67 | 130560851.56 | 17833981.0821 | 35347710.14 | 22047241.85 | -13066040.4821 |  |  |  |  | -1482175.0032 | -11583865.4789 | - | - | #VALUE! | 51670078.56 | 59204495.58 | -7534417.02 |  | -7534417.02 | 51670078.56 | 0 | 0 | 0 | #REF! | #REF!
Grand Totals |  | 2024557298.82 | 1893652246.83 | 130905051.99 | 1189375151.08 |  | 71040611.8231 | 1260415762.9031 | 1260032177.67 | -383585.2331 | 704277095.75 | 764525121.15 | 850491382.2 | 905013820.61 | 58904398.1649 | 338883768.88 | 355018357.06 | 12136213.6583 |  |  |  | 52896373.2393 | 10695776.4647 | 1440437.1936 | - | - | #VALUE! | 1527119096.29 | 1446856711.21 | 80262385.08 |  | 57167480.7569 | 1145237718.5769 | 1914545.0331 | 358786473.39 | 379966832.68 | #REF! | #REF!
[8 empty] | Proof of Construction Basis Profit/Loss: | [23 empty] | Proof of GAAP Basis Profit/Loss:
[8 empty] | Billed Revenue |  |  | 355018357.06 | [20 empty] | Billed Revenue |  |  | 355018357.06
[8 empty] | Prior WIP |  | -4381959.7549 | [21 empty] | Prior WIP |  | 1626065.1707
[8 empty] | Current WIP |  | 383585.2331 | -3998374.5217 | [20 empty] | Current WIP |  | -1914545.0331 | -288479.8624
[8 empty] | Construction Revenue |  | -3998374.5217 | 351019982.5383 | [20 empty] | GAAP Revenue |  | -288479.8624 | 354729877.1976
[8 empty] | YTD Costs |  |  | -338883768.88 | [20 empty] | Costs YTD |  |  | -338883768.88
[8 empty] | Construction Basis Profit/Loss |  |  | 12136213.6583 | [20 empty] | GAAP Profit/Loss |  |  | 15846108.3176
[8 empty] | Variance |  |  | 7.0781e-08 | [20 empty] | Variance |  |  | #REF!
Additional amounts recognized on Bonus Basis Schedule, but not on GAAP Basis Schedule:
51.1108 | City of Stockton - RWCF Phase 2A/2B | 150450.14 | 2211.2 | 148238.94 | [23 empty] | -484611837.12 | -435823024.03 | -48788813.09 |  | -13010639.5403 | -114315552.8003 | 1435638.7403 | -334518110.77 | -371731923.06 | #REF! | #REF!
52.8563 | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 40144.6 | 21713.05 | 18431.55
52.8636 | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | -13915 | -13915 | 0
54.9269 | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 0 | 41752.38 | -41752.38
54.9414 | Cawelo Water Dist. - Cawelo Diversion Structure Rehab | 21189.15 | 1189.15 | 20000
55.109 | LA Dept of Water and Power - Silverlake | 164727.64 | 65935.95 | 98791.69
55.12 | East County Advanced Water Purification Project - Package 1 | 900000 | 4739.51 | 895260.49
55.1204 | East County Advanced Water Purification Project - Package 3 | 580000 | 8897.79 | 571102.21
55.1233 | Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 9712109.84 | 9712109.84 | 0
55.1254 | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 312943.36 | 315334.59 | -2391.23
56.1015 | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 70000 | 61161.05 | 8838.95
56.1075 | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 922334.08 | 751382.08 | 170952
57.0007 | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | -33618.4 | 0 | -33618.4
Total Schedule Differences |  | 12826365.41 | 10972511.59 | 1853853.82
Bonus Basis Grand Total less Total Schedule Differences |  | 2011730933.41 | 1882679735.24 | 129051198.17
Totals Per GAAP Basis Profit and Loss Schedule |  | 2011730933.41 | 1882679735.24 | 129051198.17
Variance |  | 0 | 0 | 0
Explanations:
Job 51.1108 is associated with the Joint Venture agreement WML has with AECOM. This job represents the engineering staffs consulting services and construction work. For Bonus Basis, we recognized the total estimated services expected to provide. For GAAP, we only recognize the services already performed since there is no contract for this work.
Job 52.8563 is associated with the Joint Venture agreement WML has with AECOM. This job represents the engineering staffs consulting services and construction work. For Bonus Basis, we recognized the total estimated services expected to provide. For GAAP, we only recognize the services already performed since there is no contract for this work.
Job 52.8636 had a last minute GAAP contract amount change to $3,656,112 but bonus was left at original $3,642,197.
Job 54.9269 is a T&M job. For Bonus Basis, we recognized the estimated contract value and profits for the work performed. For GAAP, we only recognized the services performed & billed.
Job 54.9414 is a T&M job. For Bonus Basis, we recognized projected profit. For GAAP, we only recognized the profit on services performed & billed.
Job 55.1090 is associated with the Joint Venture agreement WML has with Webcor/Obayshi. This job represents the engineering staffs consulting service. For Bonus Basis, we recognized the total estimated consulting service expected to provide. For GAAP, we only recognize the services already performed since there is no contract for this work.
Job 55.1200 is associated with the Joint Venture agreement WML has with AECOM. This job represents the engineering staffs consulting services and construction work. For Bonus Basis, we recognized the total estimated services expected to provide. For GAAP, we only recognize the services already performed since there is no contract for this work.
Job 55.1204 is associated with the Joint Venture agreement WML has with AECOM. This job represents the engineering staffs consulting services and construction work. For Bonus Basis, we recognized the total estimated services expected to provide. For GAAP, we only recognize the services already performed since there is no contract for this work.
Job 55.1233 is associated with the Joint Venture agreement WML has with AECOM. This job represents the engineering staffs consulting services and construction work. For Bonus Basis, we recognized the total estimated services expected to provide. For GAAP, we only recognize the services already performed since there is no contract for this work.
Job 55.1254 is associated with the Joint Venture agreement WML has with AECOM. This job represents the engineering staffs consulting services and construction work. For Bonus Basis, we recognized the total estimated services expected to provide. For GAAP, we only recognize the services already performed since there is no contract for this work.
Job 56.1015 is expected to have a contract value of $230,000 but the current value is only $160,000.
Job 56.1075 is expected to have a contract value of $950,000 but for GAAP, we are only recognizing the profit on services performed & billed.
Job 57.0007 is a T&M job. For Bonus Basis, we recognized projected profit. For GAAP, we only recognized the profit on services performed & billed.
Formulas:
PY JTD BILLINGS = +[PY JTD COSTS]
PY JTD PROFIT = +[PY JTD COSTS]
PY JTD PROFIT = [PY JTD PROFIT]
Note on H5: Cindy Jordan: Timberline Job Summary Profits JTD

## Backlog
W. M. Lyles Co.
Construction Backlog and Remaining Profit
2025-12-31
Job | Description |  | Engineer's Contract | Earned Revenue | Construction Backlog | Expected Profit | JTD Profit | Remaining Profit | Percent Profit | Project Percent Complete
51.1108 | City of Stockton - RWCF Phase 2A/2B |  | 94196098 | 94126376.71 | 69721.29 | 4388269 | 4320758.91 | 67510.09 | 4.659% | 99.93%
51.1129 | Union Sanit. Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin |  | 126483580.84 | 96373952.3761 | 30109628.4639 | 11250000 | 9058793.1561 | 2191206.8439 | 8.894% | 76.19%
51.1137 | CA Water Service Co. - Bear Gulch Pump Station 18 |  | 1312151.46 | 1141050.9871 | 171100.4729 | 113640 | 98821.6971 | 14818.3029 | 8.661% | 86.96%
51.1144 | Silicon Valley Clean Water - FEP Improvements Project |  | 14969566 | 9093138.9678 | 5876427.0322 | 1129949 | 686378.1678 | 443570.8322 | 7.548% | 60.74%
51.1146 | National Carbon Technologies, LLC - Aymium Williams Production Facility |  | 60980234 | 56675078.5373 | 4305155.4627 | 16783379.97 | 15724392.0373 | 1058987.9327 | 27.52% | 92.94%
51.1151 | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade |  | 10658200 | 5206183.5756 | 5452016.4244 | 578848 | 282748.3956 | 296099.6044 | 5.431% | 48.85%
51.1152 | Mozingo Construction Inc - ElD Sly Park Intertie Project |  | 19974489.34 | 14448073.7521 | 5526415.5879 | 1345541 | 973265.2121 | 372275.7879 | 6.736% | 72.33%
51.1153 | Linda County Water Dist. - Aeration Blower Replacement |  | 562824.68 | 414268.175 | 148556.505 | 108304 | 79717.365 | 28586.635 | 19.24% | 73.61%
51.1154 | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 |  | 13363835 | 12704149.552 | 659685.448 | 875000 | 831806.952 | 43193.048 | 6.548% | 95.06%
51.1158 | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric |  | 104446 | 56960.69 | 47485.31 | 0 | 0 | 0 | 0% | 54.54%
51.1159 | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement |  | 1199000 | 877720.7043 | 321279.2957 | 119760 | 87669.5843 | 32090.4157 | 9.988% | 73.2%
51.116 | City of Galt Public Works - Industrial WWTP Expansion |  | 1757000 | 250518.05 | 1506481.95 | 67000 | 0 | 67000 | 3.813% | 14.26%
51.1161 | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project |  | 10848599.45 | 601852.17 | 10246747.28 | 587347 | 0 | 587347 | 5.414% | 5.548%
51.1162 | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project |  | 6029750 | 85941.38 | 5943808.62 | 184487 | 0 | 184487 | 3.06% | 1.425%
51.1164 | CA Water Service Co. - Stockton Roofing |  | 387260 | 4363.25 | 382896.75 | 3873 | 0 | 3873 | 1% | 1.127%
51.1165 | City of Yuba City - WTP Aquifer Storage and Recovery Well No. 3 |  | 5304500 | 23330.33 | 5281169.67 | 418057 | 0 | 418057 | 7.881% | 0.4398%
| Rocklin Subtotal |  | 368131534.77 | 292082959.2072 | 76048575.5628 | 37953454.97 | 32144351.4772 | 5809103.4928 | 10.31% | 79.34%
52.8563 | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 |  | 1174182.73 | 1152462.29 | 21720.44 | 293392.63 | 293385.24 | 7.39 | 24.99% | 98.15%
52.8566 | City of Visalia - Water Reclamation Facility RPGS SCR System |  | 1259398 | 1252574.9834 | 6823.0166 | 230000 | 228753.9334 | 1246.0666 | 18.26% | 99.46%
52.8586 | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 |  | 12611349 | 12497922.4241 | 113426.5759 | 1950000 | 1932461.6841 | 17538.3159 | 15.46% | 99.1%
52.8634 | City of Huron - Water Treatment Plant Imp. Phase 2 |  | 13892722.74 | 12330098.7698 | 1562623.9702 | 702000 | 623040.5298 | 78959.4702 | 5.053% | 88.75%
52.8636 | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project |  | 3642197 | 3642035.1389 | 161.8611 | 275000 | 274987.7789 | 12.2211 | 7.55% | 100%
52.8637 | Root Creek Water Dist. - Groundwater Blending & Arsenic |  | 26264577.65 | 26008192.3257 | 256385.3243 | 1650000 | 1633893.2957 | 16106.7043 | 6.282% | 99.02%
52.864 | City of Dos Palos - WTP Replacement Project |  | 38646363.16 | 33797041.051 | 4849322.109 | 1873323 | 1638259.571 | 235063.429 | 4.847% | 87.45%
52.8668 | California Water Service Co. - Cal Water - Salinas Station 57 |  | 411851 | 390782.6533 | 21068.3467 | 34855 | 33071.9833 | 1783.0167 | 8.463% | 94.88%
52.8678 | City of Chowcilla - Well 15 & Generator Improvement Projects |  | 1240321 | 988148.9819 | 252172.0181 | 78000 | 62141.6719 | 15858.3281 | 6.289% | 79.67%
52.8687 | California Water Service Co. - Salinas Station 205 |  | 877954 | 822283.7912 | 55670.2088 | 87182.52 | 81654.3612 | 5528.1588 | 9.93% | 93.66%
52.8692 | New England Sheet Metal and Mechanical Co. - Clovis South T&M |  | 55135.37 | 55135.37 | 0 | 5452.88 | 5452.88 | 0 | 9.89% | 100%
52.8697 | City of Tulare - Industrial WWTP Dewatering Improvements Pro |  | 1388000 | 808608.9206 | 579391.0794 | 62518 | 36421.1906 | 26096.8094 | 4.504% | 58.26%
52.8698 | California Water Service Co. - Tesoro Viejo RWSP Liner Repair |  | 22713 | 21496.2321 | 1216.7679 | 6585 | 6232.2321 | 352.7679 | 28.99% | 94.64%
52.8704 | City of Visalia - Solids Handling Improvements Project |  | 13744000 | 820988.3 | 12923011.7 | 252873 | 0 | 252873 | 1.84% | 5.973%
52.8705 | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster |  | 775000 | 307545.1617 | 467454.8383 | 55740 | 22119.4417 | 33620.5583 | 7.192% | 39.68%
52.8707 | County of Fresno - Westside Water Tank and Pump Station |  | 3693200 | 1079776.4803 | 2613423.5197 | 231623 | 67719.3403 | 163903.6597 | 6.272% | 29.24%
52.8708 | County of Fresno - CSA 44A Wastewater Improvements |  | 363833 | 7682.19 | 356150.81 | 30076 | 0 | 30076 | 8.266% | 2.111%
52.8711 | California Water Service Co. - Tesoro Viejo ARV Replacement |  | 6860 | 4963.1095 | 1896.8905 | 545 | 394.2995 | 150.7005 | 7.945% | 72.35%
52.8713 | City of Visalia - Remove & Replace Chain and Flight Mechanic |  | 218842 | 927.5 | 217914.5 | 28403 | 0 | 28403 | 12.98% | 0.4238%
52.8714 | New England Sheet Metal and Mechanical Co. - VCH Digging Water Line T&M |  | 5084.94 | 5084.94 | 0 | 619.33 | 619.33 | 0 | 12.18% | 100%
| Fresno Subtotal |  | 120293584.59 | 95993750.6135 | 24299833.9765 | 7848188.36 | 6940608.7635 | 907579.5965 | 6.524% | 79.8%
53.2007 | Union Sanitary Dist. - Phase 1B Secondary Clarifiers |  | 324530134 | 404852.16 | 324125281.84 | 33000000 | 0 | 33000000 | 10.17% | 0.1248%
| East Bay Subtotal |  | 324530134 | 404852.16 | 324125281.84 | 33000000 | 0 | 33000000 | 10.17% | 0.1248%
54.9033 | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 |  | 118278.58 | 118278.58 | 0 | 13728.31 | 13728.31 | 0 | 11.61% | 100%
54.9135 | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project |  | 9470658.62 | 9470658.62 | 0 | 419706.76 | 419706.76 | 0 | 4.432% | 100%
54.9257 | City of Guadalupe - Highway 1 Lift Station |  | 1471328 | 786258.4621 | 685069.5379 | 45000 | 24047.4121 | 20952.5879 | 3.058% | 53.44%
54.9268 | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement |  | 949567.99 | 909648.28 | 39919.71 | 65000 | 65000 | 0 | 6.845% | 95.8%
54.9269 | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 |  | 625819.17 | 584066.79 | 41752.38 | 34249.05 | 34249.05 | 0 | 5.473% | 93.33%
54.9285 | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement |  | 462022 | 373583.5648 | 88438.4352 | 75000 | 60643.7948 | 14356.2052 | 16.23% | 80.86%
54.9313 | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project |  | 7886885.04 | 7396392.3889 | 490492.6511 | 1010000 | 947187.1689 | 62812.8311 | 12.81% | 93.78%
54.933 | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep |  | 324900 | 323400.7694 | 1499.2306 | 17259 | 17179.3594 | 79.6406 | 5.312% | 99.54%
54.9336 | Palmdale Water Dist. - Pure Water AV - Demonstration Facility |  | 25191176.64 | 13359053.4129 | 11832123.2271 | 1920000 | 1018189.1429 | 901810.8571 | 7.622% | 53.03%
54.9337 | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project |  | 4104848 | 1570273.3156 | 2534574.6844 | 160000 | 61206.5856 | 98793.4144 | 3.898% | 38.25%
54.9343 | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 |  | 6881300 | 3929247.3572 | 2952052.6428 | 900000 | 513903.2772 | 386096.7228 | 13.08% | 57.1%
54.9356 | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond |  | 1298330 | 1102799.0115 | 195530.9885 | 385000 | 327018.2615 | 57981.7385 | 29.65% | 84.94%
54.9366 | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement |  | 1230131 | 1051430.0181 | 178700.9819 | 150000 | 128209.5181 | 21790.4819 | 12.19% | 85.47%
54.9369 | California Water Service Co. - PFAS Treatment Program Project |  | 28550624.7 | 2787466.66 | 25763158.04 | 2370843 | 0 | 2370843 | 8.304% | 9.763%
54.9373 | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement |  | 1524766 | 50303.97 | 1474462.03 | 131440 | 0 | 131440 | 8.62% | 3.299%
54.9389 | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project |  | 299780 | 296891.85 | 2888.15 | -15000 | -15000 | 0 | -5.004% | 99.04%
54.9391 | Arvin Edison Water Storage Dist. - HQ Concrete R&R |  | 532604.57 | 532604.57 | 0 | 20547.23 | 20547.23 | 0 | 3.858% | 100%
54.9395 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project |  | 1795652.66 | 1430881.5112 | 364771.1488 | 102000 | 81279.5912 | 20720.4088 | 5.68% | 79.69%
54.9396 | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction |  | 157746.09 | 157746.09 | 0 | 0 | 0 | 0 | 0% | 100%
54.9397 | Cawelo Water Dist. - Friant-Kern Canal Pump Station |  | 3690645 | 1126646.6941 | 2563998.3059 | 300000 | 91581.2841 | 208418.7159 | 8.129% | 30.53%
54.9403 | Lost Hills Utility Dist. - WTP Improvements |  | 381600 | 145602.2491 | 235997.7509 | 43499 | 16597.3591 | 26901.6409 | 11.4% | 38.16%
54.9404 | Cawelo Water Dist. - Reuse of Produced Water |  | 3720000 | 2011822.3122 | 1708177.6878 | 134608 | 72797.6822 | 61810.3178 | 3.618% | 54.08%
54.9405 | Semitropic Water Storage Dist. - Pump Platform Replacement Project |  | 942000 | 670300.4713 | 271699.5287 | 130000 | 92504.3113 | 37495.6887 | 13.8% | 71.16%
54.9406 | California Water Service Co. - Emergency PACL leak repair |  | 1120.65 | 1120.65 | 0 | 0 | 0 | 0 | 0% | 100%
54.9408 | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line |  | 3777777 | 41652.43 | 3736124.57 | 240592 | 0 | 240592 | 6.369% | 1.103%
54.9411 | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation |  | 103300 | 94158.4777 | 9141.5223 | 25000 | 22787.6277 | 2212.3723 | 24.2% | 91.15%
54.9412 | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork |  | 116752.04 | 116752.04 | 0 | 1043.16 | 1043.16 | 0 | 0.8935% | 100%
54.9413 | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork |  | 149366.83 | 149366.83 | 0 | 17228.09 | 17228.09 | 0 | 11.53% | 100%
54.9414 | Cawelo Water Dist. - Cawelo Diversion Structure Rehab |  | 358674.83 | 357415.4563 | 1259.3737 | 20000 | 19929.7763 | 70.2237 | 5.576% | 99.65%
54.9416 | California Water Service Co. - BK 147 Station Improvements |  | 1260000 | 7257.82 | 1252742.18 | 127602 | 0 | 127602 | 10.13% | 0.576%
54.9417 | County of Santa Barbara-Public Works - Laguna WWTP WAS Pipe Modifications |  | 48439 | 2299.41 | 46139.59 | 5546 | 0 | 5546 | 11.45% | 4.747%
54.9418 | GenerateUpcycle - Organics Waste Processing Facility |  | 15739 | 15739 | 0 | 0 | 0 | 0 | 0% | 100%
54.9421 | Nipomo Community Service Dist. - Tefft Emergency Pipe Repair |  | 3703.18 | 3703.18 | 0 | 0 | 0 | 0 | 0% | 100%
| Bakersfield Subtotal |  | 107445536.59 | 50974822.2426 | 56470714.3474 | 8849891.6 | 4051564.7526 | 4798326.8474 | 8.237% | 47.44%
Northern Subtotals |  |  | 920400789.95 | 439456384.2233 | 480944405.7267 | 87651534.93 | 43136524.9933 | 44515009.9367 | 9.523% | 47.75%
55.109 | LA Dept of Water and Power - Silverlake |  | 5400000 | 5308704.0692 | 91295.9308 | 1500000 | 1474640.0192 | 25359.9808 | 27.78% | 98.31%
55.1191 | Inland Empire Utilities - IEUA RP-5 Liquids Exp. & Solids Treat. Facility |  | 341443133.71 | 302890122.84 | 38553010.87 | 3710498 | 3710498 | 0 | 1.087% | 88.71%
55.1192 | Inland Empire Utilities - IEUA RP-1 Flare Improvements |  | 6651803.53 | 6643992.69 | 7810.84 | 250000 | 250000 | 0 | 3.758% | 99.88%
55.12 | East County Advanced Water Purification Project - Package 1 |  | 198075877 | 197751131.77 | 324745.23 | 8100000 | 7779994.28 | 320005.72 | 4.089% | 99.84%
55.1202 | LA County Sanitation District - Oxygen Generation Project |  | 16396051.58 | 10330718.4749 | 6065333.1051 | 1175409 | 740594.1249 | 434814.8751 | 7.169% | 63.01%
55.1204 | East County Advanced Water Purification Project - Package 3 |  | 57722227 | 57575368.22 | 146858.78 | 2500000 | 2362039.01 | 137960.99 | 4.331% | 99.75%
55.1227 | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project |  | 41504206.39 | 41279468.4824 | 224737.9076 | 4350000 | 4326445.5224 | 23554.4776 | 10.48% | 99.46%
55.1233 | Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) |  | 9838187 | 134506.16 | 9703680.84 | 0 | 8429 | -8429 | 0% | 1.367%
55.1248 | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation |  | 5759301.81 | 4227318.998 | 1531982.812 | 825000 | 605548.778 | 219451.222 | 14.32% | 73.4%
55.1249 | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 |  | 147525113 | 15046313.77 | 132478799.23 | 7821208 | 0 | 7821208 | 5.302% | 10.2%
55.1254 | JV w/City of Banning - Wastewater Treatment Plant Recycled Water |  | 471896.25 | 156561.66 | 315334.59 | 0 | 0 | 0 | 0% | 33.18%
55.1255 | City of Riverside - RWQCP Emergency Repair |  | 14160.81 | 14160.81 | 0 | 0 | 0 | 0 | 0% | 100%
55.1256 | Anaergia Technologies LLC - City of Riverside - OPS |  | 2888100 | 94989.88 | 2793110.12 | 175000 | 0 | 175000 | 6.059% | 3.289%
| Murrieta Subtotal |  | 833690058.08 | 641453357.8246 | 192236700.2554 | 30407115 | 21258188.7346 | 9148926.2654 | 3.647% | 76.94%
57.0003 | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 |  | 38165419.5 | 6440831.3025 | 31724588.1975 | 2407086 | 123922.1725 | 2283163.8275 | 6.307% | 16.88%
57.0004 | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project |  | 40106224.63 | 750298.86 | 39355925.77 | 2209857 | 0 | 2209857 | 5.51% | 1.871%
57.0007 | Anaergia Technologies, LLC - East County Package 5 - Phase 1B |  | 162630 | 162630 | 0 | -33618.4 | -33618.4 | 0 | -20.67% | 100%
57.0008 | Imperial Irrigation Dist. - El Centro Generating Station WWTP |  | 2876047 | 262382.86 | 2613664.14 | 132065 | 0 | 132065 | 4.592% | 9.123%
| San Diego Subtotal |  | 81310321.13 | 7616143.0225 | 73694178.1075 | 4715389.6 | 90303.7725 | 4625085.8275 | 5.799% | 9.367%
58.0003 | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement |  | 22525189 | 11715063.7212 | 10810125.2788 | 1308015 | 680281.9312 | 627733.0688 | 5.807% | 52.01%
| Los Angeles Subtotal |  | 22525189 | 11715063.7212 | 10810125.2788 | 1308015 | 680281.9312 | 627733.0688 | 5.807% | 52.01%
Southern Subtotals |  |  | 937525568.21 | 660784564.5683 | 276741003.6417 | 36430519.6 | 22028774.4383 | 14401745.1617 | 3.886% | 70.48%
Northern & Southern Subtotals |  |  | 1857926358.16 | 1100240948.7916 | 757685409.3684 | 124082054.53 | 65165299.4316 | 58916755.0984 | 6.679% | 59.22%
56.1004 | San Joaquin Electric - Liberty Ranch Sewer Pump Station |  | 373425 | 327111.8445 | 46313.1555 | 103585 | 90738.1145 | 12846.8855 | 27.74% | 87.6%
56.1005 | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold |  | 135000 | 101287.0518 | 33712.9482 | 66975 | 50249.6318 | 16725.3682 | 49.61% | 75.03%
56.101 | Placer County Water Agency -PCWA Time & Material Contract |  | 49250 | 49250 | 0 | 12788.06 | 12788.06 | 0 | 25.97% | 100%
56.1015 | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga |  | 230000 | 160881.2819 | 69118.7181 | 26480 | 18522.3319 | 7957.6681 | 11.51% | 69.95%
56.1017 | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport |  | 102868 | 83423.46 | 19444.54 | -12027 | -12027 | 0 | -11.69% | 81.1%
56.1018 | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas |  | 153913 | 90970.2846 | 62942.7154 | 82868 | 48979.1346 | 33888.8654 | 53.84% | 59.11%
56.1032 | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods |  | 85000 | 35879.107 | 49120.893 | 2025 | 854.767 | 1170.233 | 2.382% | 42.21%
56.1036 | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 |  | 276000 | 141353.8072 | 134646.1928 | 66976 | 34301.8572 | 32674.1428 | 24.27% | 51.22%
56.1037 | East Orange County Water District - EOCWD - On-Call SCADA Integration Services |  | 36491 | 36491 | 0 | 14816.8 | 14816.8 | 0 | 40.6% | 100%
56.1038 | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 |  | 95000 | 77673.89 | 17326.11 | -22376 | -22376 | 0 | -23.55% | 81.76%
56.1039 | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station |  | 375000 | 365706.6282 | 9293.3718 | 42716 | 41657.3982 | 1058.6018 | 11.39% | 97.52%
56.1042 | Trabuco Canyon Water Dist. - SCADA Integration Services |  | 277565 | 219576.1189 | 57988.8811 | 59277 | 46892.8489 | 12384.1511 | 21.36% | 79.11%
56.1043 | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh |  | 336610 | 232406.3037 | 104203.6963 | 25219 | 17412.0037 | 7806.9963 | 7.492% | 69.04%
56.1046 | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods |  | 77120 | 74929.8 | 2190.2 | -2836 | -2836 | 0 | -3.677% | 97.16%
56.1047 | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 |  | 2394758 | 1881098.4607 | 513659.5393 | 354203 | 278228.8307 | 75974.1693 | 14.79% | 78.55%
56.1048 | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement |  | 200000 | 196024.243 | 3975.757 | 38881 | 38108.093 | 772.907 | 19.44% | 98.01%
56.1049 | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 |  | 308725 | 265990.1203 | 42734.8797 | 59852 | 51567.0603 | 8284.9397 | 19.39% | 86.16%
56.105 | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat |  | 3792559 | 1043310.4979 | 2749248.5021 | 426992 | 117462.9679 | 309529.0321 | 11.26% | 27.51%
56.1055 | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project |  | 120891 | 102517.3075 | 18373.6925 | 28043 | 23780.8675 | 4262.1325 | 23.2% | 84.8%
56.1059 | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou |  | 399389 | 286120.7529 | 113268.2471 | 70183 | 50278.8329 | 19904.1671 | 17.57% | 71.64%
56.106 | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar |  | 404663 | 182653.4878 | 222009.5122 | 82172 | 37090.1278 | 45081.8722 | 20.31% | 45.14%
56.1063 | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project |  | 108000 | 81661.383 | 26338.617 | 10079 | 7620.973 | 2458.027 | 9.332% | 75.61%
56.1066 | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather |  | 595000 | 532912.916 | 62087.084 | 63510 | 56882.856 | 6627.144 | 10.67% | 89.57%
56.1067 | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto |  | 478000 | 120399.3749 | 357600.6251 | 62122 | 15647.3849 | 46474.6151 | 13% | 25.19%
56.1073 | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W |  | 122210 | 116647.2467 | 5562.7533 | 8163 | 7791.4367 | 371.5633 | 6.679% | 95.45%
56.1075 | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF |  | 950000 | 27665.92 | 922334.08 | 170952 | 0 | 170952 | 17.99% | 2.912%
56.1078 | City of Napa - On-Call Control Systems Integrator Services |  | 25356.25 | 25356.25 | 0 | 0 | 0 | 0 | 0% | 100%
56.1081 | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA |  | 179690 | 176270.5876 | 3419.4124 | 19905 | 19526.2176 | 378.7824 | 11.08% | 98.1%
56.1083 | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM |  | 717010 | 380119.0342 | 336890.9658 | 60647 | 32151.6842 | 28495.3158 | 8.458% | 53.01%
56.1085 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service |  | 80000 | 1090.31 | 78909.69 | 13045 | 0 | 13045 | 16.31% | 1.363%
56.1086 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service |  | 376000 | 12732.69 | 363267.31 | 80898 | 0 | 80898 | 21.52% | 3.386%
56.1087 | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters |  | 49369 | 44888.9348 | 4480.0652 | 6343 | 5767.3948 | 575.6052 | 12.85% | 90.93%
56.1088 | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo |  | 117985 | 92320.6066 | 25664.3934 | 32580 | 25493.1166 | 7086.8834 | 27.61% | 78.25%
| System Integration Subtotal |  | 14022847.25 | 7566720.7016 | 6456126.5484 | 2055056.86 | 1107371.7916 | 947685.0684 | 14.66% | 53.96%
WML Jobs Total |  |  | 1871949205.41 | 1107807669.4931 | 764141535.9169 | 126137111.39 | 66272671.2231 | 59864440.1669 | 6.738% | 59.18%
Area | JV Description | JV % Owned | WML % JV Contract | WML % Earned Revenue | WML % JV Backlog | WML % Expected Profit | WML % JTD Profit | WML % Remaining Profit | Percent Profit | Project Percent Complete
JOINT VENTURE
Rocklin | Stockton Phase 1 | 50% | 2754056 | 2754056 | 0 | 284545 | 284545 | 0 | 10.33% | 100%
Rocklin | Stockton Phase 2 | 50% | 112542778.5 | 112438999.5 | 103779 | 6418180.5 | 6418180.5 | 0 | 5.703% | 99.91%
Fresno | City of Santa Cruz - Graham Hill WTP | 50% | 5521233.5 | 5490375 | 30858.5 | 17258.5 | 17162.5 | 96 | 0.3126% | 99.44%
Murrieta | Silverlake | 25% | 91586461.5 | 90175346.75 | 1411114.75 | 6346256.75 | 6242676.75 | 103580 | 6.929% | 98.46%
Murrieta | East County Advanced Package 1 | 50% | 239937310 | 211769168.5 | 28168141.5 | 8546652 | 8546652 | 0 | 3.562% | 88.26%
Murrieta | East County Advanced Package 3 | 50% | 45865869.5 | 36465046 | 9400823.5 | -10262956 | -10262956 | 0 | -22.38% | 79.5%
Murrieta | City of Banning | 50% | 1999314 | 571506 | 1427808 | 0 | 0 | 0 | 0% | 28.59%
JV Total |  |  | 500207023 | 459664497.75 | 40542525.25 | 11349936.75 | 11246260.75 | 103676 | 2.269% | 91.89%
WML & JV Totals: |  |  | 2372156228.41 | 1567472167.2431 | 804684061.1669 | 137487048.14 | 77518931.9731 | 59968116.1669 | 5.796% | 66.08%
| Per Schedule |  | 1871949205.41 | 1107807669.4931 | 764141535.9169 | 126137111.39 | 66272671.2231 | 59864440.1669
| Variance |  | 0 | 0 | 0 | 0 | 0 | 0

## Job Summary
W. M. Lyles Co.
JOB SUMMARY REPORT
For the Month Period Ended 12/31/2025
|  |  | Expected |  |  | Actual
|  | % |  |  |  | JTD |  |  | PY JTD | YTD |  |  | Monthly Change | PM Expected
Job | Description | Complete | Revenue | Profit | Change In | Revenue | Cost | Profit | Profit | Revenue | Cost | Profit | In Profits | Profit
Rocklin Open Jobs
51.1108 | City of Stockton - RWCF Phase 2A/2B | 100% | 94196098 | 4388269 | 0 | 94126376.71 | 89805617.8 | 4320758.91 | 4328399.75 | 1278781.99 | 1286422.83 | -7640.84 | -191.43 | 4388269
51.1129 | Union Sanit. Dist - Enhanced Trtmnt & Site Upgrd Ph. 1A Aeration Basin | 75.77% | 126483580.84 | 11250000 | 0 | 96373952.3761 | 87315159.22 | 9058793.1561 | 7950623.3602 | 24666258.3459 | 23558088.55 | 1108169.7959 | 61670.9778 | 11250000
51.1137 | CA Water Service Co. - Bear Gulch Pump Station 18 | 86.96% | 1312151.46 | 113640 | 0 | 1141050.9871 | 1042229.29 | 98821.6971 | 27243.5887 | 842122.9785 | 770544.87 | 71578.1085 | 2043.5177 | 113640
51.1144 | Silicon Valley Clean Water - FEP Improvements Project | 60.74% | 14969566 | 1129949 | 0 | 9093138.9678 | 8406760.8 | 686378.1678 | 90331.4512 | 7649428.0966 | 7053381.38 | 596046.7166 | 12810.6366 | 1129949
51.1146 | National Carbon Technologies, LLC - Aymium Williams Production Facility | 92.66% | 60980234 | 16783379.97 | 1383379.97 | 56675078.5373 | 40950686.5 | 15724392.0373 | 1082047.42 | 51031949.9073 | 36389605.29 | 14642344.6173 | 2075100.7452 | 15400000
51.1151 | Sonoma Valley County Sanitation Dist. - Sonoma Valley Influent Effluent Upgrade | 48.85% | 10658200 | 578848 | 0 | 5206183.5756 | 4923435.18 | 282748.3956 | 0 | 5019039.4956 | 4736291.1 | 282748.3956 | 45627.2123 | 578848
51.1152 | Mozingo Construction Inc - ElD Sly Park Intertie Project | 72.33% | 19974489.34 | 1345541 | 0 | 14448073.7521 | 13474808.54 | 973265.2121 | 0 | 13001302.8521 | 12028037.64 | 973265.2121 | 87250.6765 | 1345541
51.1153 | Linda County Water Dist. - Aeration Blower Replacement | 73.61% | 562824.68 | 108304 | 0 | 414268.175 | 334550.81 | 79717.365 | 12859.3892 | 302445.4258 | 235587.45 | 66857.9758 | -2355.4474 | 108304
51.1154 | Keyes Community Services Dist. - TCP Treatment Impvmts Wells 7,8,9,10 | 95.06% | 13363835 | 875000 | 0 | 12704149.552 | 11872342.6 | 831806.952 | 0 | 10325590.392 | 9493783.44 | 831806.952 | 23076.8391 | 875000
51.1158 | Schneider Electric - City of Ceres WWTP Phase 1- Schneider Electric | 54.54% | 104446 | 0 | 0 | 56960.69 | 56960.69 | 0 | 0 | 56960.69 | 56960.69 | 0 | 0 | 0
51.1159 | El Dorado Irrigation Dist. - EID Reservoir A WTP Backwash-to-waste Valve Repalcement | 73.2% | 1199000 | 119760 | 0 | 877720.7043 | 790051.12 | 87669.5843 | 0 | 877720.7043 | 790051.12 | 87669.5843 | 8772.713 | 119760
51.116 | City of Galt Public Works - Industrial WWTP Expansion | 14.82% | 1757000 | 67000 | 0 | 250518.05 | 250518.05 | 0 | 0 | 250518.05 | 250518.05 | 0 | 0 | 67000
51.1161 | Sacramento Area Sewer Dist. - SASD Influent Pump Nos. 2 and 5 Installation Project | 5.865% | 10848599.45 | 587347 | 0 | 601852.17 | 601852.17 | 0 | 0 | 601852.17 | 601852.17 | 0 | 0 | 587347
51.1162 | City of Chico - Chico Primary Clarifiers No. 1-3 Rehabilitation Project | 1.47% | 6029750 | 184487 | 0 | 85941.38 | 85941.38 | 0 | 0 | 85941.38 | 85941.38 | 0 | 0 | 184487
51.1164 | CA Water Service Co. - Stockton Roofing | 1.138% | 387260 | 3873 | 3873 | 4363.25 | 4363.25 | 0 | 0 | 4363.25 | 4363.25 | 0 | 0
51.1165 | City of Yuba City - WTP Aquifer Storage and Recovery Well No. 3 | 0.4775% | 5304500 | 418057 | 418057 | 23330.33 | 23330.33 | 0 | 0 | 23330.33 | 23330.33 | 0 | 0
Rocklin Open Jobs Total |  |  | 368131534.77 | 37953454.97 | 1805309.97 | 292082959.2072 | 259938607.73 | 32144351.4772 | 13491504.9592 | 116017606.058 | 97364759.54 | 18652846.518 | 2313806.4408 | 35590246.95
Rocklin Closed Jobs
51.1133 | CA Water Service Co. - S. San Francisco St 1-A Pump Replacement | 100% | 372738 | 40882.72 | 0 | 372738 | 331855.28 | 40882.72 | 17359.5806 | 52253.0094 | 28729.87 | 23523.1394 | 0 | 40882.72
51.1136 | Union Sanitary Dist - USD Plant Misc. Improvements | 100% | 5483550 | 951732.14 | -281873.86 | 5483550 | 4531817.86 | 951732.14 | 758905.7861 | 495311.3739 | 302485.02 | 192826.3539 | -268283.8074 | 1233606
51.1138 | CA Water Service Co. - Bear Gulch Pump Station 21 | 100% | 1120182.07 | -47522.08 | 0 | 1120182.07 | 1167704.15 | -47522.08 | 77778.0991 | 255501.9209 | 380802.1 | -125300.1791 | 0 | -47522.08
51.1139 | CA Water Service Co. - Bear Gulch Pump Station 14/29 | 100% | 61902 | 4907.56 | -5300.17 | 61902 | 56994.44 | 4907.56 | 4426.359 | 481.201 | 0 | 481.201 | -5300.17 | 10207.73
51.1141 | City of Colfax - WWTP Algae Reduction Project | 100% | 3967189.79 | 132095.06 | 0 | 3967189.79 | 3835094.73 | 132095.06 | 79920.2987 | 777363.7313 | 725188.97 | 52174.7613 | 0 | 132095.06
51.1143 | Olivehurst Plumas Lake Manganese Filter Expansion | 100% | 1991231.37 | 233098.8 | 0 | 1991231.37 | 1758132.57 | 233098.8 | 226011.7629 | 34528.6371 | 27441.6 | 7087.0371 | 0 | 233098.8
51.1147 | City of Lodi-Public Works Dept. - Aeration Diffusers Replacement Project | 100% | 2742860.08 | 194135.16 | -111.5 | 2742860.08 | 2548724.92 | 194135.16 | 128284.5352 | 864663.2248 | 798812.6 | 65850.6248 | -111.5 | 194246.66
51.115 | Sacramento Co. Dept. of Water Resources - D49 Metro Air Park Storm Drain Pump Station Phase 2 | 100% | 2486231.58 | 246796.44 | 0 | 2486231.58 | 2239435.14 | 246796.44 | 166471.8295 | 248682.9505 | 168358.34 | 80324.6105 | 0 | 246796.44
51.1156 | Rocklin Overhead 2025 | 100% | 0 | -1426058.69 | -176737.46 | 0 | 1426058.69 | -1426058.69 | 0 | 0 | 1426058.69 | -1426058.69 | -176737.46 | -1249321.23
51.1157 | Rocklin Estimating 2025 | 100% | 0 | -613546.52 | -61155.97 | 0 | 613546.52 | -613546.52 | 0 | 0 | 613546.52 | -613546.52 | -61155.97 | -552390.55
Rocklin Closed Jobs Total |  |  | 18225884.89 | -283479.41 | -525178.96 | 18225884.89 | 18509364.3 | -283479.41 | 1459158.2509 | 2728786.0491 | 4471423.71 | -1742637.6609 | -511588.9074 | 799597.6
Rocklin Total |  |  | 386357419.66 | 37669975.56 | 1280131.01 | 310308844.0972 | 278447972.03 | 31860872.0672 | 14950663.2101 | 118746392.1071 | 101836183.25 | 16910208.8571 | 1802217.5334 | 36389844.55
| Contract Balance | 69153639.98 |  |  | Construction Backlog |  | 76048575.5628 |  |  | WIP | -5936502.2828
Fresno Open Jobs
52.8563 | City of Santa Cruz - Graham Hill WTP Facility Improvements - Phase 1 | 97.53% | 1174182.73 | 293392.63 | 0 | 1152462.29 | 859077.05 | 293385.24 | 264189.76 | 167405.78 | 138210.3 | 29195.48 | 31.55 | 293392.63
52.8566 | City of Visalia - Water Reclamation Facility RPGS SCR System | 99.46% | 1259398 | 230000 | 0 | 1252574.9834 | 1023821.05 | 228753.9334 | 223974.5063 | 33809.9171 | 29030.49 | 4779.4271 | 0 | 230000
52.8586 | Tesoro Viejo MMWC- WTP/WWTP/RWSP Phase B Expansion - Phase 1 | 99.1% | 12611349 | 1950000 | 0 | 12497922.4241 | 10565460.74 | 1932461.6841 | 1757780.0079 | 506849.7062 | 332168.03 | 174681.6762 | 31439.8281 | 1950000
52.8634 | City of Huron - Water Treatment Plant Imp. Phase 2 | 88.75% | 13892722.74 | 702000 | 0 | 12330098.7698 | 11707058.24 | 623040.5298 | 277972.0115 | 6838700.1383 | 6493631.62 | 345068.5183 | 50436.1648 | 702000
52.8636 | Anaergia Technologies, LLC - Anaergia M1W Digester Mixing Project | 100% | 3642197 | 275000 | -35000 | 3642035.1389 | 3367047.36 | 274987.7789 | 204319.7111 | 1980915.8878 | 1910247.82 | 70668.0678 | -23707.6882 | 310000
52.8637 | Root Creek Water Dist. - Groundwater Blending & Arsenic | 99.02% | 26264577.65 | 1650000 | 0 | 26008192.3257 | 24374299.03 | 1633893.2957 | 1208391.7577 | 5357985.578 | 4932484.04 | 425501.538 | 27575.0748 | 1650000
52.864 | City of Dos Palos - WTP Replacement Project | 87.45% | 38646363.16 | 1873323 | 0 | 33797041.051 | 32158781.48 | 1638259.571 | 703966.8389 | 20058621.4722 | 19124328.74 | 934292.7322 | 108677.9766 | 1873323
52.8668 | California Water Service Co. - Cal Water - Salinas Station 57 | 94.88% | 411851 | 34855 | -1145 | 390782.6533 | 357710.67 | 33071.9833 | 0 | 341717.6533 | 308645.67 | 33071.9833 | 3243.25 | 36000
52.8678 | City of Chowcilla - Well 15 & Generator Improvement Projects | 79.67% | 1240321 | 78000 | 0 | 988148.9819 | 926007.31 | 62141.6719 | 0 | 982585.3519 | 920443.68 | 62141.6719 | 31619.0812 | 78000
52.8687 | California Water Service Co. - Salinas Station 205 | 93.66% | 877954 | 87182.52 | 5760.52 | 822283.7912 | 740629.43 | 81654.3612 | 0 | 822283.7912 | 740629.43 | 81654.3612 | 6435.8143 | 81422
52.8692 | New England Sheet Metal and Mechanical Co. - Clovis South T&M | 100% | 55135.37 | 5452.88 | 0 | 55135.37 | 49682.49 | 5452.88 | 0 | 55135.37 | 49682.49 | 5452.88 | 0 | 5452.88
52.8697 | City of Tulare - Industrial WWTP Dewatering Improvements Pro | 58.26% | 1388000 | 62518 | 0 | 808608.9206 | 772187.73 | 36421.1906 | 0 | 808608.9206 | 772187.73 | 36421.1906 | 9721.8664 | 62518
52.8698 | California Water Service Co. - Tesoro Viejo RWSP Liner Repair | 94.64% | 22713 | 6585 | 6585 | 21496.2321 | 15264 | 6232.2321 | 0 | 21496.2321 | 15264 | 6232.2321 | 6232.2321
52.8704 | City of Visalia - Solids Handling Improvements Project | 6.085% | 13744000 | 252873 | 0 | 820988.3 | 820988.3 | 0 | 0 | 820988.3 | 820988.3 | 0 | 0 | 252873
52.8705 | California Water Service Co. - Visalia Station 200 - New Storage Tank & Booster | 39.68% | 775000 | 55740 | 0 | 307545.1617 | 285425.72 | 22119.4417 | 0 | 307545.1617 | 285425.72 | 22119.4417 | 22119.4417 | 55740
52.8707 | County of Fresno - Westside Water Tank and Pump Station | 29.24% | 3693200 | 231623 | 0 | 1079776.4803 | 1012057.14 | 67719.3403 | 0 | 1079776.4803 | 1012057.14 | 67719.3403 | 67719.3403 | 231623
52.8708 | County of Fresno - CSA 44A Wastewater Improvements | 2.302% | 363833 | 30076 | 0 | 7682.19 | 7682.19 | 0 | 0 | 7682.19 | 7682.19 | 0 | 0 | 30076
52.8711 | California Water Service Co. - Tesoro Viejo ARV Replacement | 72.35% | 6860 | 545 | 545 | 4963.1095 | 4568.81 | 394.2995 | 0 | 4963.1095 | 4568.81 | 394.2995 | 394.2995
52.8713 | City of Visalia - Remove & Replace Chain and Flight Mechanic | 0.487% | 218842 | 28403 | 28403 | 927.5 | 927.5 | 0 | 0 | 927.5 | 927.5 | 0 | 0
52.8714 | New England Sheet Metal and Mechanical Co. - VCH Digging Water Line T&M | 100% | 5084.94 | 619.33 | 619.33 | 5084.94 | 4465.61 | 619.33 | 0 | 5084.94 | 4465.61 | 619.33 | 619.33
Fresno Open Jobs Total |  |  | 120293584.59 | 7848188.36 | 5767.85 | 95993750.6135 | 89053141.85 | 6940608.7635 | 4640594.5933 | 40203083.4802 | 37903069.31 | 2300014.1702 | 342557.5617 | 7876251.88
Fresno Closed Jobs
52.8567 | City of Modesto - Grayson Well 69 | 100% | 3059858.99 | -68164.94 | 0 | 3059858.99 | 3128023.93 | -68164.94 | -83000 | 49233.73 | 34398.67 | 14835.06 | 0 | -68164.94
52.8604 | City of Atwater - Project No. 20-2, Well 20-A TCP Mitigation | 100% | 5095690.97 | 523187.74 | 0 | 5095690.97 | 4572503.23 | 523187.74 | 329989.1327 | 1102038.3473 | 908839.74 | 193198.6073 | 0 | 523187.74
52.8628 | City of Tulare - Well 4-3 Equipping & I Drive Pipeline Proj. | 100% | 5213345.5 | 467546.97 | 42546.97 | 5213345.5 | 4745798.53 | 467546.97 | 197224.7538 | 1174192.7562 | 903870.54 | 270322.2162 | 43216.6446 | 425000
52.8631 | Gunner Ranch, Inc. - Well 1 Equipping and Site Improvements | 100% | 2560650.14 | 111991.88 | -5008.12 | 2560650.14 | 2448658.26 | 111991.88 | 73003.7005 | 237953.2995 | 198965.12 | 38988.1795 | -4745.9653 | 117000
52.8652 | California Water Service Co. - Salinas 77 Booster Station | 100% | 1290184 | 250807.92 | 0 | 1290184 | 1039376.08 | 250807.92 | 170698.8374 | 133540.6726 | 53431.59 | 80109.0826 | 0 | 250807.92
52.8658 | California Water Service Co. - Visalia Station 98 Water Storage Tank & Booster Site | 100% | 1870914.99 | 237384.78 | 0 | 1870914.99 | 1633530.21 | 237384.78 | 148751 | 200545.22 | 111911.44 | 88633.78 | 0 | 237384.78
52.8663 | Root Creek Water Dist. - Ag Well 277 Conversion Project | 100% | 1641800 | 262111.72 | 2111.72 | 1641800 | 1379688.28 | 262111.72 | 42676.9508 | 1192257.6592 | 972822.89 | 219434.7692 | 7703.0145 | 260000
52.8667 | California Water Service Co. - Cal Water Salinas Station 33 | 100% | 314085.77 | 23359.66 | 0 | 314085.77 | 290726.11 | 23359.66 | 26868.8653 | 1869.5547 | 5378.76 | -3509.2053 | 0 | 23359.66
52.867 | California Water Service Co. - Cal Water - King City Station 10 | 100% | 274166.01 | 6883.96 | 0 | 274166.01 | 267282.05 | 6883.96 | 10404.4356 | 142646.0644 | 146166.54 | -3520.4756 | 0 | 6883.96
52.8674 | City of Hanford - WWTP Standby Influent Pump Install | 100% | 279244 | 28155.8 | 0 | 279244 | 251088.2 | 28155.8 | 15534.5836 | 78969.7964 | 66348.58 | 12621.2164 | 0 | 28155.8
52.8677 | Gunner Ranch, Inc. - CSA 22C Tank and PW2 Site Improvements | 100% | 796055.3 | 106223.34 | 18223.34 | 796055.3 | 689831.96 | 106223.34 | 0 | 762769.27 | 656545.93 | 106223.34 | 23807.2461 | 88000
52.868 | City of Orange Cove - Orange Cove West Clarifier T&M | 100% | 29838.25 | 3749.92 | 0 | 29838.25 | 26088.33 | 3749.92 | 0 | 23324.04 | 19574.12 | 3749.92 | 0 | 3749.92
52.8682 | Fresno Overhead 2025 | 100% | 0 | -1121157.1 | -156002.73 | 0 | 1121157.1 | -1121157.1 | 0 | 0 | 1121157.1 | -1121157.1 | -156002.73 | -965154.37
52.8683 | Fresno Estimating 2025 | 100% | 0 | -415452.52 | -64541.14 | 0 | 415452.52 | -415452.52 | 0 | 0 | 415452.52 | -415452.52 | -64541.14 | -350911.38
52.8684 | Lakeside Ditch Co. - Lakeland Radial Gate Repair (T&M) | 100% | 50568.05 | 5276.66 | 830.03 | 50568.05 | 45291.39 | 5276.66 | 0 | 50568.05 | 45291.39 | 5276.66 | 830.03 | 4446.63
52.8685 | Malaga County Water Dist. - Malaga County Water District | 100% | 451254 | 69186.68 | 34186.68 | 451254 | 382067.32 | 69186.68 | 0 | 451254 | 382067.32 | 69186.68 | 42338.7773 | 35000
52.8686 | Root Creek Water Dist. - Groundwater - 48-Inch RCP Repair | 100% | 23957 | 16451.74 | 0 | 23957 | 7505.26 | 16451.74 | 15372.2567 | 2293.8733 | 1214.39 | 1079.4833 | 0 | 16451.74
52.8688 | New England Sheet Metal and Mechanical Co. - Valley Children's Hospital NESM Trench Limits | 100% | 132492.2 | 15519.45 | 0 | 132492.2 | 116972.75 | 15519.45 | 0 | 132492.2 | 116972.75 | 15519.45 | 0 | 15519.45
52.8689 | City of Sanger - Public Works Dept. - City of Sanger WWTP- Remove and Install Valves T&M | 100% | 16665.83 | 570.25 | 0 | 16665.83 | 16095.58 | 570.25 | 0 | 16665.83 | 16095.58 | 570.25 | 0 | 570.25
52.869 | City of Dinuba - WWTP Rake Replacement | 100% | 14151.97 | 996.14 | 0 | 14151.97 | 13155.83 | 996.14 | 0 | 14151.97 | 13155.83 | 996.14 | 0 | 996.14
52.8691 | County of Fresno - Quail Lakes Repair at Bodega Bay Rd | 100% | 11302.84 | 3015.02 | 0 | 11302.84 | 8287.82 | 3015.02 | 0 | 11302.84 | 8287.82 | 3015.02 | 0 | 3015.02
52.8693 | New England Sheet Metal and Mechanical Co. - VCH Service Meter Connections | 100% | 1120704.2 | 457563.21 | 27563.21 | 1120704.2 | 663140.99 | 457563.21 | 0 | 1120704.2 | 663140.99 | 457563.21 | 45019.8027 | 430000
52.8694 | Pixley Public Utility District - Pixley WWTF - STM-Aerotor Repair | 100% | 43047.45 | 4505.46 | 0 | 43047.45 | 38541.99 | 4505.46 | 0 | 43047.45 | 38541.99 | 4505.46 | 0 | 4505.46
52.8695 | Lyles Services Co. - LSC GO Trash Enclosure | 100% | 13769 | 744.63 | 0 | 13769 | 13024.37 | 744.63 | 0 | 13769 | 13024.37 | 744.63 | 0 | 744.63
52.8696 | American Paving Co. - Hot Tap for APC- Tule River Parkway | 100% | 1059.22 | 171.57 | 0 | 1059.22 | 887.65 | 171.57 | 0 | 1059.22 | 887.65 | 171.57 | 0 | 171.57
52.8699 | City of Hanford - WWTP Repair T&M | 100% | 3001.12 | 52.21 | 0 | 3001.12 | 2948.91 | 52.21 | 0 | 3001.12 | 2948.91 | 52.21 | 0 | 52.21
52.87 | Lyles Services Co. - LSC GO Misc. Work | 100% | 5297 | 850.87 | 500.87 | 5297 | 4446.13 | 850.87 | 0 | 5297 | 4446.13 | 850.87 | 516.2151 | 350
52.8701 | County of Fresno - 47 Water | 100% | 13433.85 | 1012.77 | -234.89 | 13433.85 | 12421.08 | 1012.77 | 0 | 13433.85 | 12421.08 | 1012.77 | -234.89 | 1247.66
52.8702 | New England Sheet Metal and Mechanical Co. - FUSD Wilson Elementary T&M | 100% | 5626.78 | 901.5 | 0 | 5626.78 | 4725.28 | 901.5 | 0 | 5626.78 | 4725.28 | 901.5 | 0 | 901.5
52.8703 | County of Fresno - CSA 47 Egret Point Water Line Repair | 100% | 14402.18 | 1830.64 | -341.28 | 14402.18 | 12571.54 | 1830.64 | 0 | 14402.18 | 12571.54 | 1830.64 | -341.28 | 2171.92
52.8706 | City of Hanford - WWTP Weld Repair T&M 2 | 100% | 2868.6 | 432.82 | 0 | 2868.6 | 2435.78 | 432.82 | 0 | 2868.6 | 2435.78 | 432.82 | 0 | 432.82
52.8709 | County of Fresno - 47.1 Water | 100% | 17765.14 | 2890.78 | -174.78 | 17765.14 | 14874.36 | 2890.78 | 0 | 17765.14 | 14874.36 | 2890.78 | -174.78 | 3065.56
52.871 | City of Dinuba - WWTP Bar Screen Motor Bracket Repair | 100% | 4064.54 | 549.7 | 0 | 4064.54 | 3514.84 | 549.7 | 0 | 4064.54 | 3514.84 | 549.7 | 0 | 549.7
52.8715 | New England Sheet Metal and Mechanical Co. - Vitro Glass Plant Concrete Pad T&M | 100% | 10001.43 | 1415.99 | 1415.99 | 10001.43 | 8585.44 | 1415.99 | 0 | 10001.43 | 8585.44 | 1415.99 | 1415.99 | 0
Fresno Closed Jobs Total |  |  | 24381266.32 | 1000567.22 | -98924.13 | 24381266.32 | 23380699.1 | 1000567.22 | 947524.5165 | 7033109.6835 | 6980066.98 | 53042.7035 | -61193.0649 | 1065659.98
Fresno Total |  |  | 144674850.91 | 8848755.58 | -93156.28 | 120375016.9335 | 112433840.95 | 7941175.9835 | 5588119.1098 | 47236193.1637 | 44883136.29 | 2353056.8737 | 281364.4967 | 8941911.86
| Contract Balance | 23677662.94 |  |  | Construction Backlog |  | 24299833.9765 |  |  | WIP | 613691.7235
East Bay Open Jobs
53.2007 | Union Sanitary Dist. - Phase 1B Secondary Clarifiers | 0.1389% | 324530134 | 33000000 | 0 | 404852.16 | 404852.16 | 0 | 0 | 404852.16 | 404852.16 | 0 | 0 | 33000000
East Bay Open Jobs Total |  |  | 324530134 | 33000000 | 0 | 404852.16 | 404852.16 | 0 | 0 | 404852.16 | 404852.16 | 0 | 0 | 32636554.07
East Bay Closed Jobs
53.2004 | City of Millbrae - Millbrae Sludge Thickener & Digester No. 2 Rehab Project | 100% | 1173753.47 | 192962.42 | 9072.42 | 1173753.47 | 980791.05 | 192962.42 | 0 | 1151824.99 | 958862.57 | 192962.42 | 14900.2669 | 183890
53.2005 | East Bay Overhead 2025 | 100% | 0 | -279281.96 | -36895.25 | 0 | 279281.96 | -279281.96 | 0 | 0 | 279281.96 | -279281.96 | -36895.25 | -242386.71
53.2006 | East Bay Estimating 2026 | 100% | 0 | -304986.32 | -37.1 | 0 | 304986.32 | -304986.32 | 0 | 0 | 304986.32 | -304986.32 | -37.1 | -304949.22
East Bay Closed Jobs Total |  |  | 1173753.47 | -391305.86 | -27859.93 | 1173753.47 | 1565059.33 | -391305.86 | 0 | 1151824.99 | 1543130.85 | -391305.86 | -22032.0831 | 0
East Bay Total |  |  | 325703887.47 | 32608694.14 | -27859.93 | 1578605.63 | 1969911.49 | -391305.86 | 0 | 1556677.15 | 1947983.01 | -391305.86 | -22032.0831 | 32636554.07
| Contract Balance | 324530134 |  |  | Construction Backlog |  | 324125281.84 |  |  | WIP | 382923.68
Bakersfield Open Jobs
54.9033 | Semitropic WSD - Stored Water Recovery Unit Phase 2A, Amendment 8 | 100% | 118278.58 | 13728.31 | 2761.31 | 118278.58 | 104550.27 | 13728.31 | 10966.87 | 24368.78 | 21607.34 | 2761.44 | 2761.44 | 10967
54.9135 | Calif. Rail Bldrs LLC - North Kern WSD Canal 9-22 Relocation Project | 100% | 9470658.62 | 419706.76 | -214351.24 | 9470658.62 | 9050951.86 | 419706.76 | 551994.3651 | 1547627.9249 | 1679915.53 | -132287.6051 | -149462.5979 | 634058
54.9257 | City of Guadalupe - Highway 1 Lift Station | 53.44% | 1471328 | 45000 | 0 | 786258.4621 | 762211.05 | 24047.4121 | 0 | 772222.6321 | 748175.22 | 24047.4121 | 5631.5661 | 45000
54.9268 | Semitropic Water Storage Dist. - Amendment No. 23 Raw Water Processing Plant Pipeline Replacement | 95.49% | 949567.99 | 65000 | 0 | 909648.28 | 844648.28 | 65000 | 71013.0668 | 50581.4432 | 56594.51 | -6013.0668 | 0 | 65000
54.9269 | Semitropic Water Storage Dist. - Design & Construction of the Central TCP Facility-Phase 1 | 92.94% | 625819.17 | 34249.05 | 0.05 | 584066.79 | 549817.74 | 34249.05 | 34249.05 | 243796.33 | 243796.33 | 0 | 0.05 | 34249
54.9285 | Semitropic Water Storage Dist. - Emergency Radial Arm Gate Removal and Replacement | 80.86% | 462022 | 75000 | 0 | 373583.5648 | 312939.77 | 60643.7948 | 35686.2378 | 151844.577 | 126887.02 | 24957.557 | 630.313 | 75000
54.9313 | Granite Construction Co. - Granite Chumash Camp 4 Infrastructure Project | 93.78% | 7886885.04 | 1010000 | 130000 | 7396392.3889 | 6449205.22 | 947187.1689 | 197714.5111 | 5277538.7678 | 4528066.11 | 749472.6578 | 246986.9011 | 880000
54.933 | City of Bakersfield Public Works - Wastewater Treatment Plant No. 3 Septage Processing Unit Rep | 99.54% | 324900 | 17259 | 1259 | 323400.7694 | 306221.41 | 17179.3594 | 10642.1273 | 131310.3722 | 124773.14 | 6537.2322 | 1318.1015 | 16000
54.9336 | Palmdale Water Dist. - Pure Water AV - Demonstration Facility | 53.03% | 25191176.64 | 1920000 | 20000 | 13359053.4129 | 12340864.27 | 1018189.1429 | 0 | 11238995.8629 | 10220806.72 | 1018189.1429 | 247075.6782 | 1900000
54.9337 | City of Bakersfield Public Works - WWTP 3 Digester Gas Booster Blower Replacement Project | 38.25% | 4104848 | 160000 | 0 | 1570273.3156 | 1509066.73 | 61206.5856 | 0 | 1417261.6056 | 1356055.02 | 61206.5856 | -150.7201 | 160000
54.9343 | Tehachapi-Cummings County Water District - DB – Replace Diesel Engines PP2 and PP3 | 57.1% | 6881300 | 900000 | 50000 | 3929247.3572 | 3415344.08 | 513903.2772 | 0 | 3329055.5672 | 2815152.29 | 513903.2772 | 91690.3169 | 850000
54.9356 | North of River Sanitary Dist. No. 1 - WWTP Digester Gas Scrubber Vessel and Effluent Storage Pond | 84.94% | 1298330 | 385000 | 0 | 1102799.0115 | 775780.75 | 327018.2615 | 0 | 1039914.2515 | 712895.99 | 327018.2615 | 134986.3122 | 385000
54.9366 | City of Pismo Beach Community Development Dept. - WWTP Clarifier Equipment Replacement | 85.47% | 1230131 | 150000 | 60000 | 1051430.0181 | 923220.5 | 128209.5181 | 0 | 1045916.9581 | 917707.44 | 128209.5181 | 62585.2477 | 90000
54.9369 | California Water Service Co. - PFAS Treatment Program Project | 10.65% | 28550624.7 | 2370843 | 0 | 2787466.66 | 2787466.66 | 0 | 0 | 2786224.21 | 2786224.21 | 0 | 0 | 2370843
54.9373 | City of Guadalupe - Guadalupe Pioneer Lift Station Replacement | 3.61% | 1524766 | 131440 | 0 | 50303.97 | 50303.97 | 0 | 0 | 50303.97 | 50303.97 | 0 | 0 | 131440
54.9389 | City of Atascadero - Atascadero Lift Stations 4 & 11 Rehab Project | 99.08% | 299780 | -15000 | 0 | 296891.85 | 311891.85 | -15000 | 0 | 296891.85 | 311891.85 | -15000 | 0 | -15000
54.9391 | Arvin Edison Water Storage Dist. - HQ Concrete R&R | 100% | 532604.57 | 20547.23 | 547.23 | 532604.57 | 512057.34 | 20547.23 | 0 | 532604.57 | 512057.34 | 20547.23 | 1224.3115 | 20000
54.9395 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Siphon Pipe Replacement Project | 79.69% | 1795652.66 | 102000 | 72000 | 1430881.5112 | 1349601.92 | 81279.5912 | 0 | 1430881.5112 | 1349601.92 | 81279.5912 | 59055.9208 | 30000
54.9396 | Mojave Groundwater Storage LLC - Mojave Water Bank Northern Pipeline Facilities Construction | 100% | 157746.09 | 0 | -9546 | 157746.09 | 157746.09 | 0 | 0 | 157746.09 | 157746.09 | 0 | 0 | 9546
54.9397 | Cawelo Water Dist. - Friant-Kern Canal Pump Station | 30.53% | 3690645 | 300000 | 0 | 1126646.6941 | 1035065.41 | 91581.2841 | 0 | 1126646.6941 | 1035065.41 | 91581.2841 | 17968.0733 | 300000
54.9403 | Lost Hills Utility Dist. - WTP Improvements | 38.16% | 381600 | 43499 | 0 | 145602.2491 | 129004.89 | 16597.3591 | 0 | 145602.2491 | 129004.89 | 16597.3591 | 16597.3591 | 43499
54.9404 | Cawelo Water Dist. - Reuse of Produced Water | 54.08% | 3720000 | 134608 | 0 | 2011822.3122 | 1939024.63 | 72797.6822 | 0 | 2011822.3122 | 1939024.63 | 72797.6822 | 30601.2238 | 134608
54.9405 | Semitropic Water Storage Dist. - Pump Platform Replacement Project | 71.16% | 942000 | 130000 | 10000 | 670300.4713 | 577796.16 | 92504.3113 | 0 | 670300.4713 | 577796.16 | 92504.3113 | 92504.3113 | 120000
54.9406 | California Water Service Co. - Emergency PACL leak repair | 100% | 1120.65 | 0 | 0 | 1120.65 | 1120.65 | 0 | 0 | 1120.65 | 1120.65 | 0 | 0
54.9408 | Nipomo Community Service Dist. - Frontage Road Sewer Trunk Line | 1.178% | 3777777 | 240592 | 0 | 41652.43 | 41652.43 | 0 | 0 | 41652.43 | 41652.43 | 0 | 0 | 240592
54.9411 | Moorefield Construction Inc. - Hard Rock Tejon AEWSD Line Relocation | 91.15% | 103300 | 25000 | 0 | 94158.4777 | 71370.85 | 22787.6277 | 0 | 94158.4777 | 71370.85 | 22787.6277 | -87.6447 | 25000
54.9412 | Arvin Edison Water Storage Dist. - Sycamore Well 39 Earthwork | 100% | 116752.04 | 1043.16 | -4956.84 | 116752.04 | 115708.88 | 1043.16 | 0 | 116752.04 | 115708.88 | 1043.16 | -4169.7316 | 6000
54.9413 | Arvin Edison Water Storage Dist. - Tejon Well 102 Earthwork | 100% | 149366.83 | 17228.09 | 7228.09 | 149366.83 | 132138.74 | 17228.09 | 0 | 149366.83 | 132138.74 | 17228.09 | 7240.704 | 10000
54.9414 | Cawelo Water Dist. - Cawelo Diversion Structure Rehab | 99.65% | 358674.83 | 20000 | -5000 | 357415.4563 | 337485.68 | 19929.7763 | 0 | 357415.4563 | 337485.68 | 19929.7763 | 19929.7763 | 25000
54.9416 | California Water Service Co. - BK 147 Station Improvements | 0.6409% | 1260000 | 127602 | 0 | 7257.82 | 7257.82 | 0 | 0 | 7257.82 | 7257.82 | 0 | 0 | 127602
54.9417 | County of Santa Barbara-Public Works - Laguna WWTP WAS Pipe Modifications | 5.361% | 48439 | 5546 | 5546 | 2299.41 | 2299.41 | 0 | 0 | 2299.41 | 2299.41 | 0 | 0
54.9418 | GenerateUpcycle - Organics Waste Processing Facility | 100% | 15739 | 0 | -10000 | 15739 | 15739 | 0 | 0 | 15739 | 15739 | 0 | 0 | 10000
54.9421 | Nipomo Community Service Dist. - Tefft Emergency Pipe Repair | 100% | 3703.18 | 0 | 0 | 3703.18 | 3703.18 | 0 | 0 | 3703.18 | 3703.18 | 0 | 0
Bakersfield Open Jobs Total |  |  | 107445536.59 | 8849891.6 | 115487.6 | 50974822.2426 | 46923257.49 | 4051564.7526 | 912266.2281 | 36268924.2945 | 33129625.77 | 3139298.5245 | 884916.9126 | 17814944.48
Bakersfield Closed Jobs
54.9099 | Laguna County Sanitation Dist. - Phase 1 Plant Upgrade | 100% | 55712110 | 10383217.32 | 8217.32 | 55712110 | 45328892.68 | 10383217.32 | 10372751.5815 | 276297.1285 | 265831.39 | 10465.7385 | 10465.7385 | 10375000
54.9172 | Calif. Rail Bldrs LLC - SWSD Distribution System Conflict | 100% | 24160002.44 | 3141570.22 | 0 | 24160002.44 | 21018432.22 | 3141570.22 | 3076351.4492 | 37421.7408 | -27797.03 | 65218.7708 | 0 | 3141570.22
54.9216 | CA Dept. of Corr. - Water Treatment Improvements | 100% | 2472164.05 | 185899.62 | -196.73 | 2472164.05 | 2286264.43 | 185899.62 | 140849.7535 | 277016.2465 | 231966.38 | 45049.8665 | -196.73 | 186096.35
54.9246 | Kern County Water Agency - Well 38 & 39 Well Equiping Project | 100% | 1777852 | 69376.68 | 9376.68 | 1777852 | 1708475.32 | 69376.68 | 69196.4543 | 358127.9957 | 357947.77 | 180.2257 | 9376.68 | 60000
54.9265 | Semitropic Water Storage Dist. - Amendment No. 22 JPP Valve Control Modification | 100% | 223896.47 | 3141.96 | 0 | 223896.47 | 220754.51 | 3141.96 | 0 | 20651.96 | 17510 | 3141.96 | 0 | 3141.96
54.9279 | City of Bakersfield Public Works - Sewer Lift Station Rehabilitation | 100% | 3216240.01 | 63002.61 | 0 | 3216240.01 | 3153237.4 | 63002.61 | -15000 | 477072.51 | 399069.9 | 78002.61 | 0 | 63002.61
54.9289 | Michael K. Nunley & Assoc., Inc. - AMWC Sycamore & NWT Budgeting | 100% | 44560 | 19462.75 | 0 | 44560 | 25097.25 | 19462.75 | 669.81 | 30384 | 11591.06 | 18792.94 | 0 | 19462.75
54.9292 | Michael K. Nunley & Assoc., Inc. - Waterton WTP Budgeting | 100% | 4300 | 2986.55 | 0 | 4300 | 1313.45 | 2986.55 | 2986.55 | 0 | 0 | 0 | 0 | 2986.55
54.9309 | Teviston Community Services Dist. - Teviston Drought Resilience Water System Impr | 100% | 3968668.9 | 177810.56 | 12810.56 | 3968668.9 | 3790858.34 | 177810.56 | 62853.4158 | 1964416.3142 | 1849459.17 | 114957.1442 | 18388.3808 | 165000
54.9323 | Semitropic Water Storage Dist. - Buena Vista Water Storage District Turnout Valve Repair | 100% | 110661.47 | 16178.26 | 0 | 110661.47 | 94483.21 | 16178.26 | 0 | 25596.84 | 9418.58 | 16178.26 | 0 | 16178.26
54.9329 | Kern Water Bank Authority - Valve Replacement Parts | 100% | 18201.12 | 1734.4 | 0 | 18201.12 | 16466.72 | 1734.4 | 0 | 18201.12 | 16466.72 | 1734.4 | 0 | 1734.4
54.9333 | Semitropic Water Storage Dist. - SWSD 2 Hydro Turbine Repair Project | 100% | 427464.77 | 55549.51 | -3099.97 | 427464.77 | 371915.26 | 55549.51 | 14888.68 | 260484.33 | 219823.5 | 40660.83 | -3099.97 | 58649.48
54.9338 | Laguna County Sanitation Dist. - WWTP Storage Pond Slide Gates Replacement | 100% | 175884.64 | 56698.53 | 0 | 175884.64 | 119186.11 | 56698.53 | 54179.7977 | 15890.7123 | 13371.98 | 2518.7323 | 0 | 56698.53
54.9341 | Nipomo Community Service Dist. - Water Project Interconnection Improvements | 100% | 1251279 | 187746.6 | 415.6 | 1251279 | 1063532.4 | 187746.6 | 0 | 1053706.26 | 865959.66 | 187746.6 | 5767.1771 | 187331
54.9342 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehab Package 21 Remove and Replace | 100% | 199161.5 | 75015.2 | 0 | 199161.5 | 124146.3 | 75015.2 | 41394.1127 | 38308.5773 | 4687.49 | 33621.0873 | 0 | 75015.2
54.9347 | City of Guadalupe - Effluent Pump Station Flow Meter Installation | 100% | 7100 | 3872.3 | 0 | 7100 | 3227.7 | 3872.3 | 0 | 7100 | 3227.7 | 3872.3 | 0 | 3872.3
54.9349 | North of River Sanitary Dist. No. 1 - Sanitary Sewer Rehabilitation Package A | 100% | 290129 | 92239.69 | 0 | 290129 | 197889.31 | 92239.69 | 4519.6837 | 179170.7663 | 91450.76 | 87720.0063 | 0 | 92239.69
54.935 | Kern Water Bank Authority - Construct New Well 18P01 | 100% | 129965.06 | 9646.38 | 0 | 129965.06 | 120318.68 | 9646.38 | 0 | 119854.46 | 110208.08 | 9646.38 | 0 | 9646.38
54.9351 | Arvin Edison Water Storage Dist. - Forrest Frick Valve Replacement | 100% | 153298.79 | 16490.49 | 0 | 153298.79 | 136808.3 | 16490.49 | 11095.2671 | 5395.2229 | 0 | 5395.2229 | 0 | 16490.49
54.9353 | Kern Water Bank Authority - Cut In Valve at Well 18R01 | 100% | 2008.42 | 890.92 | 0 | 2008.42 | 1117.5 | 890.92 | 0 | 890.92 | 0 | 890.92 | 0 | 890.92
54.9354 | California Water Service Co. - Northeast Plant Lift Station Pipe Repair | 100% | 9571.2 | 1340.37 | 0 | 9571.2 | 8230.83 | 1340.37 | 1923.43 | -4703.34 | -4120.28 | -583.06 | 0 | 1340.37
54.9355 | Kern Water Bank Authority - Install Canal Valve at Well 17P01 | 100% | 2806.42 | 991.19 | 0 | 2806.42 | 1815.23 | 991.19 | 0 | 991.19 | 0 | 991.19 | 0 | 991.19
54.9357 | Kern Water Bank Authority - Install Canal Valve at Well 20A01 | 100% | 1760.42 | 870.76 | 0 | 1760.42 | 889.66 | 870.76 | 0 | 870.76 | 0 | 870.76 | 0 | 870.76
54.9358 | Arvin Edison Water Storage Dist. - Frick Unit - Phase I Turnout | 100% | 1147640 | 22240.17 | 0 | 1147640 | 1125399.83 | 22240.17 | 15917.5507 | 811430.2993 | 805107.68 | 6322.6193 | 0 | 22240.17
54.936 | Kern Water Bank Authority - Install Canal Valve at Well 20C01 | 100% | 1855.92 | 711.04 | 0 | 1855.92 | 1144.88 | 711.04 | 0 | 711.04 | 0 | 711.04 | 0 | 711.04
54.9361 | Semitropic Water Storage Dist. - Pond Poso Pumping Plant Pipe Repair | 100% | 108668.35 | 1593.48 | 0 | 108668.35 | 107074.87 | 1593.48 | 0 | 108668.35 | 107074.87 | 1593.48 | 0 | 1593.48
54.9362 | Cawelo Water Dist. - Remove and Replace 24” and 18” Well Line | 100% | 425035.04 | 49433.8 | 0 | 425035.04 | 375601.24 | 49433.8 | 18050.9922 | 244525.1178 | 213142.31 | 31382.8078 | 0 | 49433.8
54.9363 | Kern Water Bank Authority - Install Canal Valve at Well 21A02 | 100% | 1855.92 | 1078.37 | 0 | 1855.92 | 777.55 | 1078.37 | 0 | 1078.37 | 0 | 1078.37 | 0 | 1078.37
54.9365 | Kern Water Bank Authority - Install Canal Valve at Well 16J01 | 100% | 2216.42 | 953.09 | 0 | 2216.42 | 1263.33 | 953.09 | 0 | 953.09 | 0 | 953.09 | 0 | 953.09
54.9367 | Kern Water Bank Authority - Install Canal Valve at Well 15N01 | 100% | 2540.42 | 938.09 | 0 | 2540.42 | 1602.33 | 938.09 | 0 | 938.09 | 0 | 938.09 | 0 | 938.09
54.9368 | North of River Sanitary Dist. No. 1 - Wilson Ave Sewer Repair | 100% | 15697.91 | 2044.29 | 0 | 15697.91 | 13653.62 | 2044.29 | 2044.29 | 0 | 0 | 0 | 0 | 2044.29
54.937 | Kern Water Bank Authority - Install Canal Valve at Well 20L01 | 100% | 1760.42 | 870.78 | 0 | 1760.42 | 889.64 | 870.78 | 0 | 870.78 | 0 | 870.78 | 0 | 870.78
54.9371 | Bakersfield Overhead 2025 | 100% | 0 | -1267652.77 | -70266.13 | 0 | 1267652.77 | -1267652.77 | 0 | 0 | 1267652.77 | -1267652.77 | -70266.13 | -1197386.64
54.9372 | Bakersfield Estimating 2025 | 100% | 0 | -588792.6 | -39388.72 | 0 | 588792.6 | -588792.6 | 0 | 0 | 588792.6 | -588792.6 | -39388.72 | -549403.88
54.9374 | City of Santa Maria - WWTP Trickling Filter Repairs | 100% | 32962 | 12975.55 | 0 | 32962 | 19986.45 | 12975.55 | 0 | 32962 | 19986.45 | 12975.55 | 0 | 12975.55
54.9375 | City of Santa Maria - WWTP Clarifier Repairs | 100% | 8232.73 | 3687.25 | 0 | 8232.73 | 4545.48 | 3687.25 | 0 | 8232.73 | 4545.48 | 3687.25 | 0 | 3687.25
54.9379 | Semitropic Water Storage Dist. - Delta System Pipe Repair | 100% | 41679.77 | 5567.82 | 0 | 41679.77 | 36111.95 | 5567.82 | 0 | 41679.77 | 36111.95 | 5567.82 | 0 | 5567.82
54.938 | Cawelo Water Dist. - CWD Pump Station Pipe Repair | 100% | 22446.19 | 4381.47 | 0 | 22446.19 | 18064.72 | 4381.47 | 0 | 22446.19 | 18064.72 | 4381.47 | 0 | 4381.47
54.9381 | Kern Sanitation Authority - KSA Trickling Filter Bracket Replacement | 100% | 58900 | 30024.62 | 0 | 58900 | 28875.38 | 30024.62 | 0 | 58900 | 28875.38 | 30024.62 | 0 | 30024.62
54.9382 | Laguna County Sanitation Dist. - Laguna WWTP Flow Meter FIT-7000 Replacement | 100% | 143799 | 35108.55 | 2108.55 | 143799 | 108690.45 | 35108.55 | 0 | 143799 | 108690.45 | 35108.55 | 3631.6835 | 33000
54.9383 | Semitropic Water Storage Dist. - Amendment No. 19 Operate 300 CFS RWPP 2025 | 100% | 17542.44 | 1782.68 | 0 | 17542.44 | 15759.76 | 1782.68 | 0 | 17542.44 | 15759.76 | 1782.68 | 0 | 1782.68
54.9384 | Shafter-Wasco Irrigation Dist. - 7th Street Pipe Repair | 100% | 79531.98 | 9191.41 | 0 | 79531.98 | 70340.57 | 9191.41 | 0 | 79531.98 | 70340.57 | 9191.41 | 0 | 9191.41
54.9385 | Westside Water Authority - Pump Station A - Electrical Controls and Civil | 100% | 102913.84 | 4315.07 | 0 | 102913.84 | 98598.77 | 4315.07 | 0 | 102913.84 | 98598.77 | 4315.07 | 0 | 4315.07
54.9386 | Kern Valley State Prison - Arsenic Pipe Leak Repair | 100% | 96086 | 20301.26 | 0 | 96086 | 75784.74 | 20301.26 | 0 | 96086 | 75784.74 | 20301.26 | 0 | 20301.26
54.9387 | City of Santa Maria - Santa Maria WWTP Digester Pipe Modifications | 100% | 22619.54 | 3607.89 | 0 | 22619.54 | 19011.65 | 3607.89 | 0 | 22619.54 | 19011.65 | 3607.89 | 0 | 3607.89
54.9388 | Arvin Edison Water Storage Dist. - Tejon Spreading Ground Pipe Installation | 100% | 7454.07 | 918.66 | 0 | 7454.07 | 6535.41 | 918.66 | 0 | 7454.07 | 6535.41 | 918.66 | 0 | 918.66
54.939 | Arvin Edison Water Storage Dist. - Bar Screen Concrete Collection Pads | 100% | 101491.67 | 5162.18 | 0 | 101491.67 | 96329.49 | 5162.18 | 0 | 101491.67 | 96329.49 | 5162.18 | 0 | 5162.18
54.9392 | Arvin Edison Water Storage Dist. - Tejon Spreading Grounds Basin Repairs | 100% | 217648.89 | 9302.2 | 2302.2 | 217648.89 | 208346.69 | 9302.2 | 0 | 217648.89 | 208346.69 | 9302.2 | 2550.2239 | 7000
54.9393 | East Niles Community Service Dist. - Freeway Tank and College Ave Repairs | 100% | 31523.02 | 3983.2 | 0 | 31523.02 | 27539.82 | 3983.2 | 0 | 31523.02 | 27539.82 | 3983.2 | 0 | 3983.2
54.9394 | City of Arvin - Haven Drive Lateral Repair | 100% | 15966.99 | 1927.44 | 0 | 15966.99 | 14039.55 | 1927.44 | 0 | 15966.99 | 14039.55 | 1927.44 | 0 | 1927.44
54.9398 | County of Santa Barbara Public Works - Laguna CSD - C-Channel Installation | 100% | 14300 | 6107.21 | 0 | 14300 | 8192.79 | 6107.21 | 0 | 14300 | 8192.79 | 6107.21 | 0 | 6107.21
54.9399 | City of Atascadero - Atascadero Lift Station 6 Pipe Replacement | 100% | 24775 | 13483.41 | 0 | 24775 | 11291.59 | 13483.41 | 0 | 24775 | 11291.59 | 13483.41 | 0 | 13483.41
54.94 | Arvin Edison Water Storage Dist. - FFPP Core Drilling | 100% | 800.69 | 29.37 | 0 | 800.69 | 771.32 | 29.37 | 0 | 800.69 | 771.32 | 29.37 | 0 | 29.37
54.9401 | Arvin Edison Water Storage Dist. - FFPP Modernization Concrete R&R | 100% | 247539.61 | 11227.04 | 0 | 247539.61 | 236312.57 | 11227.04 | 0 | 247539.61 | 236312.57 | 11227.04 | 0 | 11227.04
54.9407 | Semitropic Water Storage Dist. - North Plant Emergency Repair | 100% | 31296.85 | 5629.51 | 0 | 31296.85 | 25667.34 | 5629.51 | 0 | 31296.85 | 25667.34 | 5629.51 | 0 | 5629.51
54.9409 | Nipomo CSD Osage Emergency Waterline Repair | 100% | 20123.71 | 2712 | 0 | 20123.71 | 17411.71 | 2712 | 0 | 20123.71 | 17411.71 | 2712 | 0 | 2712
54.941 | SWID - Burbank St. Repair | 100% | 8241.55 | 1275.9 | 0 | 8241.55 | 6965.65 | 1275.9 | 0 | 8241.55 | 6965.65 | 1275.9 | 0 | 1275.9
Bakersfield Closed Jobs Total |  |  | 97414231.62 | 12981852.3 | -77720.64 | 97414231.62 | 84432379.32 | 12981852.3 | 13874672.8184 | 7680196.3916 | 8573016.91 | -892820.5184 | -62771.6661 | 3979032.46
Bakersfield Total |  |  | 204859768.21 | 21831743.9 | 37766.96 | 148389053.8626 | 131355636.81 | 17033417.0526 | 14786939.0465 | 43949120.6861 | 41702642.68 | 2246478.0061 | 822145.2465 | 21793976.94
| Contract Balance | 57134565.88 |  |  | Construction Backlog |  | 56470714.3474 |  |  | WIP | -1098780.0974
Northern Open Jobs Totals |  |  | 920400789.95 | 87651534.93 | 1926565.42 | 439456384.2233 | 396319859.23 | 43136524.9933 | 19044365.7806 | 192894465.9927 | 168802306.78 | 24092159.2127 | 3541280.9151 | 93917997.38
Northern Closed Job Totals |  |  | 141195136.3 | 13307634.25 | -729683.66 | 141195136.3 | 127887502.05 | 13307634.25 | 16281355.5857 | 18593917.1143 | 21567638.45 | -2973721.3357 | -657585.7215 | 5844290.04
Nothern Area Totals |  |  | 1061595926.25 | 100959169.18 | 1196881.76 | 580651520.5233 | 524207361.28 | 56444159.2433 | 35325721.3663 | 211488383.1069 | 190369945.23 | 21118437.8769 | 2883695.1936 | 99762287.42
| Contract Balance | 474496002.8 |  |  | Construction Backlog |  | 480944405.7267 |  |  | WIP | -6038666.9767
Murrieta Open Jobs
55.109 | LA Dept of Water and Power - Silverlake | 98.31% | 5400000 | 1500000 | 3027.8 | 5308704.0692 | 3834064.05 | 1474640.0192 | 1463888.1686 | 227019.4507 | 216267.6 | 10751.8507 | -21954.623 | 1496972.2
55.1191 | Inland Empire Utilities - IEUA RP-5 Liquids Exp. & Solids Treat. Facility | 88.58% | 341443133.71 | 3710498 | -1500000 | 302890122.84 | 299179624.84 | 3710498 | 7900000 | 12322287.82 | 16511789.82 | -4189502 | -1500000 | 5210498
55.1192 | Inland Empire Utilities - IEUA RP-1 Flare Improvements | 99.88% | 6651803.53 | 250000 | 0 | 6643992.69 | 6393992.69 | 250000 | 350000 | 331298.96 | 431298.96 | -100000 | 0 | 250000
55.12 | East County Advanced Water Purification Project - Package 1 | 100% | 198075877 | 8100000 | 0 | 197751131.77 | 189971137.49 | 7779994.28 | 5995115.13 | 55551078.55 | 53766199.4 | 1784879.15 | 96391.87 | 8100000
55.1202 | LA County Sanitation District - Oxygen Generation Project | 63.01% | 16396051.58 | 1175409 | 0 | 10330718.4749 | 9590124.35 | 740594.1249 | 647450.7063 | 1453695.6386 | 1360552.22 | 93143.4186 | 1354.7037 | 1175409
55.1204 | East County Advanced Water Purification Project - Package 3 | 99.98% | 57722227 | 2500000 | 0 | 57575368.22 | 55213329.21 | 2362039.01 | 1917801.19 | 17497029.81 | 17052791.99 | 444237.82 | 39757.7 | 2500000
55.1227 | Eastern Municipal Water District - MVRWRF Plant 2B Equipping and Flow Diversion Project | 99.46% | 41504206.39 | 4350000 | 0 | 41279468.4824 | 36953022.96 | 4326445.5224 | 3399354.1719 | 8547343.0405 | 7620251.69 | 927091.3505 | 19842.9584 | 4350000
55.1233 | Veolia Water West Operating Services, Inc. - Rialto Solids Handling Design-Build Project (Design Phase) | 1.282% | 9838187 | 0 | 2344.53 | 134506.16 | 126077.16 | 8429 | 8428.84 | 49747.52 | 49747.36 | 0.16 | 10773.53 | -2344.53
55.1248 | Anaergia Technologies LLC - City of Riverside - Digester 5 Rehabilitation | 73.4% | 5759301.81 | 825000 | 100000 | 4227318.998 | 3621770.22 | 605548.778 | 0 | 3912565.908 | 3307017.13 | 605548.778 | 233129.4864 | 725000
55.1249 | Inland Empire Utilities - IEUA - RP-1 Solids Thickening Project - EN22044 | 10.77% | 147525113 | 7821208 | 0 | 15046313.77 | 15046313.77 | 0 | 0 | 14105058.15 | 14105058.15 | 0 | 0 | 7821208
55.1254 | JV w/City of Banning - Wastewater Treatment Plant Recycled Water | 33.18% | 471896.25 | 0 | 0 | 156561.66 | 156561.66 | 0 | 0 | 156561.66 | 156561.66 | 0 | 0 | 0
55.1255 | City of Riverside - RWQCP Emergency Repair | 100% | 14160.81 | 0 | 0 | 14160.81 | 14160.81 | 0 | 0 | 14160.81 | 14160.81 | 0 | 0 | 0
55.1256 | Anaergia Technologies LLC - City of Riverside - OPS | 3.501% | 2888100 | 175000 | 0 | 94989.88 | 94989.88 | 0 | 0 | 94989.88 | 94989.88 | 0 | 0 | 175000
Murrieta Open Jobs Total |  |  | 833690058.08 | 30407115 | -1394627.67 | 641453357.8246 | 620195169.09 | 21258188.7346 | 21682038.2067 | 114262837.1979 | 114686686.67 | -423849.4721 | -1120704.3745 | 29541839.76
Murrieta Closed Jobs
55.123 | Anaergia Technologies - VVWRA - DAF 3 Replacement | 100% | 2273682.69 | 608537.39 | 0 | 2273682.69 | 1665145.3 | 608537.39 | 480252.0335 | 128285.3565 | 0 | 128285.3565 | 0 | 608537.39
55.1231 | City of Corona - WRF 1 Aeration System Improvements | 100% | 4046200 | 724343.64 | 0 | 4046200 | 3321856.36 | 724343.64 | 627907.3954 | 112084.8546 | 15648.61 | 96436.2446 | 0 | 724343.64
55.1238 | Anaergia Technologies LLC - East County Package 5 | 100% | 34207.53 | 1706.67 | -499.55 | 34207.53 | 32500.86 | 1706.67 | 8107.48 | 0 | 6400.81 | -6400.81 | -499.55 | 2206.22
55.125 | Anaergia Technologies LLC - VVWRA Digester Dome No. 1 Repair | 100% | 184557.17 | 136263.23 | 0 | 184557.17 | 48293.94 | 136263.23 | 101052.1598 | 36965.3702 | 1754.3 | 35211.0702 | 0 | 136263.23
55.1251 | Woodard & Curran, Inc. - VVWRA Magnesium Hydroxide Feed System Upgrade | 100% | 322982.96 | 38761.1 | 0 | 322982.96 | 284221.86 | 38761.1 | 0 | 322982.96 | 284221.86 | 38761.1 | 0 | 38761.1
55.1252 | Murrieta Overhead 2025 | 100% | 0 | -1958826.45 | -154979.89 | 0 | 1958826.45 | -1958826.45 | 0 | 0 | 1958826.45 | -1958826.45 | -154979.89 | -1803846.56
55.1253 | Murrieta Estimating 2025 | 100% | 0 | -475814.03 | -19757.68 | 0 | 475814.03 | -475814.03 | 0 | 0 | 475814.03 | -475814.03 | -19757.68 | -456056.35
Murrieta Closed Jobs Total |  |  | 6861630.35 | -925028.45 | -175237.12 | 6861630.35 | 7786658.8 | -925028.45 | 1217319.0687 | 600318.5413 | 2742666.06 | -2142347.5187 | -175237.12 | 1510111.58
Murrieta Total |  |  | 840551688.43 | 29482086.55 | -1569864.79 | 648314988.1746 | 627981827.89 | 20333160.2846 | 22899357.2754 | 114863155.7392 | 117429352.73 | -2566196.9908 | -1295941.4945 | 31051951.34
| Contract Balance | 198167503.19 |  |  | Construction Backlog |  | 192236700.2554 |  |  | WIP | 2003828.4846
San Diego Open Jobs
57.0003 | Moulton Niguel Water Dist. - Advanced Water Treatment Facility Salinity Management System - Ph 1 | 17.67% | 38165419.5 | 2407086 | 0 | 6440831.3025 | 6316909.13 | 123922.1725 | 96385.4118 | 5442603.9807 | 5415067.22 | 27536.7607 | 27536.9149 | 2407086
57.0004 | Santa Margarita Water Dist. - Oso Creek Water Reclamation Plant Optimization Project | 1.98% | 40106224.63 | 2209857 | 0 | 750298.86 | 750298.86 | 0 | 0 | 63391.12 | 63391.12 | 0 | 0 | 2209857
57.0007 | Anaergia Technologies, LLC - East County Package 5 - Phase 1B | 100% | 162630 | -33618.4 | -1383.3 | 162630 | 196248.4 | -33618.4 | 0 | 162630 | 196248.4 | -33618.4 | -1383.3 | -32235.1
57.0008 | Imperial Irrigation Dist. - El Centro Generating Station WWTP | 9.562% | 2876047 | 132065 | 0 | 262382.86 | 262382.86 | 0 | 0 | 262382.86 | 262382.86 | 0 | 0 | 132065
San Diego Open Jobs Total |  |  | 81310321.13 | 4715389.6 | -1383.3 | 7616143.0225 | 7525839.25 | 90303.7725 | 96385.4118 | 5931007.9607 | 5937089.6 | -6081.6393 | 26153.6149 | 4626397.92
San Diego Closed Jobs
57.0005 | San Diego Overhead 2025 | 100% | 0 | -92874.26 | -12910.6 | 0 | 92874.26 | -92874.26 | 0 | 0 | 92874.26 | -92874.26 | -12910.6 | -79963.66
57.0006 | San Diego Estimating 2025 | 100% | 0 | -13743.76 | -3332.44 | 0 | 13743.76 | -13743.76 | 0 | 0 | 13743.76 | -13743.76 | -3332.44 | -10411.32
San Diego Closed Jobs Total |  |  | 0 | -106618.02 | -16243.04 | 0 | 106618.02 | -106618.02 | 0 | 0 | 106618.02 | -106618.02 | -16243.04 | 0
San Diego Total |  |  | 81310321.13 | 4608771.58 | -17626.34 | 7616143.0225 | 7632457.27 | -16314.2475 | 96385.4118 | 5931007.9607 | 6043707.62 | -112699.6593 | 9910.5749 | 4626397.92
| Contract Balance | 73126398.76 |  |  | Construction Backlog |  | 73694178.1075 |  |  | WIP | -362640.5575
Los Angeles Open Jobs
58.0003 | Los Angeles County Sanitation Dist. - Los Coyotes WRP Process Air Compressor Replacement | 52.01% | 22525189 | 1308015 | 0 | 11715063.7212 | 11034781.79 | 680281.9312 | 0 | 9333607.2412 | 8653325.31 | 680281.9312 | 155877.5929 | 1308015
Los Angeles Open Jobs Total |  |  | 22525189 | 1308015 | 0 | 11715063.7212 | 11034781.79 | 680281.9312 | 0 | 9333607.2412 | 8653325.31 | 680281.9312 | 155877.5929 | 1091428.55
Los Angeles Closed Jobs
58.0004 | Los Angeles Overhead 2025 | 100% | 0 | -147282.12 | -7983.11 | 0 | 147282.12 | -147282.12 | 0 | 0 | 147282.12 | -147282.12 | -7983.11 | -139299.01
58.0005 | Los Angeles Estimating 2025 | 100% | 0 | -135037.09 | -57749.65 | 0 | 135037.09 | -135037.09 | 0 | 0 | 135037.09 | -135037.09 | -57749.65 | -77287.44
Los Angeles Closed Jobs Total |  |  | 0 | -282319.21 | -65732.76 | 0 | 282319.21 | -282319.21 | 0 | 0 | 282319.21 | -282319.21 | -65732.76 | 0
Los Angeles Total |  |  | 22525189 | 1025695.79 | -65732.76 | 11715063.7212 | 11317101 | 397962.7212 | 0 | 9333607.2412 | 8935644.52 | 397962.7212 | 90144.8329 | 1091428.55
| Contract Balance | 10635987.24 |  |  | Construction Backlog |  | 10810125.2788 |  |  | WIP | 433142.3812
Southern Open Jobs Totals |  |  | 937525568.21 | 36430519.6 | -1396010.97 | 660784564.5683 | 638755790.13 | 22028774.4383 | 21778423.6185 | 129527452.3997 | 129277101.58 | 250350.8197 | -938673.1667 | 35259666.23
Southern Closed Job Totals |  |  | 6861630.35 | -1313965.68 | -257212.92 | 6861630.35 | 8175596.03 | -1313965.68 | 1217319.0687 | 600318.5413 | 3131603.29 | -2531284.7487 | -257212.92 | 1510111.58
Southern Area Totals |  |  | 944387198.56 | 35116553.92 | -1653223.89 | 667646194.9183 | 646931386.16 | 20714808.7583 | 22995742.6873 | 130127770.941 | 132408704.87 | -2280933.929 | -1195886.0867 | 36769777.81
| Contract Balance | 281929889.19 |  |  | Construction Backlog |  | 276741003.6417 |  |  | WIP | 2074330.3083
System Integration - Open Jobs
WML Holds the Contract
AIC Holds the Contract
56.1004 | San Joaquin Electric - Liberty Ranch Sewer Pump Station | 87.6% | 373425 | 103585 | 10615 | 327111.8445 | 236373.73 | 90738.1145 | 51359.9627 | 122870.3418 | 83492.19 | 39378.1518 | 13050.963 | 92970
56.1005 | SD Electric, Inc. - Stormwater Evacuation Lines & Outfall Manifold | 75.03% | 135000 | 66975 | 0 | 101287.0518 | 51037.42 | 50249.6318 | 0 | 85373.7218 | 35124.09 | 50249.6318 | 0 | 66975
56.101 | Placer County Water Agency -PCWA Time & Material Contract | 100% | 49250 | 12788.06 | -995.69 | 49250 | 36461.94 | 12788.06 | 0 | 49250 | 36461.94 | 12788.06 | -995.69 | 13783.75
56.1015 | Mike Brown Electric Co. - Riverside Ponds & Headworks Mitigation – City of Calistoga | 69.95% | 230000 | 26480 | -2976 | 160881.2819 | 142358.95 | 18522.3319 | 29395.3303 | 31372.1716 | 42245.17 | -10872.9984 | -811.8974 | 29456
56.1017 | Bay Tech Engineering - SDDS Gate Valves Replacement – SF International Airport | 83.08% | 102868 | -12027 | -21368 | 83423.46 | 95450.46 | -12027 | 19016.5728 | 21693.9972 | 52737.57 | -31043.5728 | -20968.5144 | 9341
56.1018 | CM Controls - Salinas AG Industrial Phase 1 – City of Salinas | 59.11% | 153913 | 82868 | -9973 | 90970.2846 | 41991.15 | 48979.1346 | 31982.9546 | 40855.43 | 23859.25 | 16996.18 | -5455.104 | 92841
56.1032 | Newtron - Watsonville, City of - Zone 2 Water Res & AirportBPS Mods | 42.21% | 85000 | 2025 | -5147 | 35879.107 | 35024.34 | 854.767 | 0 | 26940.547 | 26085.78 | 854.767 | -1010.7621 | 7172
56.1036 | Darrel Varni Electric, Inc. - GSW, San Benito Co. Sewer Pump Station No. 2 | 51.22% | 276000 | 66976 | 3142 | 141353.8072 | 107051.95 | 34301.8572 | 0 | 88716.5572 | 54414.7 | 34301.8572 | 4638.5405 | 63834
56.1037 | East Orange County Water District - EOCWD - On-Call SCADA Integration Services | 100% | 36491 | 14816.8 | -608.2 | 36491 | 21674.2 | 14816.8 | 338.12 | 34128.5 | 19649.82 | 14478.68 | 7362.9965 | 15425
56.1038 | Troxell JH Electrical Inc - Keyes CSD TCP Treatment Impvmts Wells 7,8,9,10 | 85.24% | 95000 | -22376 | -1922 | 77673.89 | 100049.89 | -22376 | 6303.4542 | 16550.2658 | 45229.72 | -28679.4542 | -1922 | -20454
56.1039 | Sac Valley Electrica Inc - Placer County - Creekview Ranch Sewer Lift Station | 97.52% | 375000 | 42716 | 8890 | 365706.6282 | 324049.23 | 41657.3982 | 0 | 321087.4982 | 279430.1 | 41657.3982 | 10149.7603 | 33826
56.1042 | Trabuco Canyon Water Dist. - SCADA Integration Services | 79.11% | 277565 | 59277 | 0 | 219576.1189 | 172683.27 | 46892.8489 | 34822.2181 | 96610.7607 | 84540.13 | 12070.6307 | 229.5501 | 59277
56.1043 | SD Electirc, Inc - Morgan Hill, City of - Sanitary Sewer Lift Station K & F Reh | 69.04% | 336610 | 25219 | 8792 | 232406.3037 | 214994.3 | 17412.0037 | 0 | 194947.4237 | 177535.42 | 17412.0037 | 9276.3648 | 16427
56.1046 | California Water Service Co. - SSF-1 - Visalia St. 97 Panelboard Mods | 97.26% | 77120 | -2836 | -646 | 74929.8 | 77765.8 | -2836 | 0 | 65463.4 | 68299.4 | -2836 | -646 | -2190
56.1047 | SD Electric, Inc - Lathrop, City of - Consolidated Treatment Facility Ph. 3 | 78.55% | 2394758 | 354203 | 103672 | 1881098.4607 | 1602869.63 | 278228.8307 | 0 | 1820562.3007 | 1542333.47 | 278228.8307 | 100248.0681 | 250531
56.1048 | Blocka Construction, Inc - West Bay Sanitary District - Telemetry Panel Replacement | 98.01% | 200000 | 38881 | -1028.92 | 196024.243 | 157916.15 | 38108.093 | 0 | 175234.893 | 137126.8 | 38108.093 | -657.0369 | 39909.92
56.1049 | East Orange County Water District - SCADA Field Site RTU Prog Ph.1 | 86.16% | 308725 | 59852 | 5000 | 265990.1203 | 214423.06 | 51567.0603 | 74409.071 | 64100.2693 | 86942.28 | -22842.0107 | 5333.1352 | 54852
56.105 | Collins Electric - Watsonville, City of - WWTF Electrical System Hazard Mitigat | 27.51% | 3792559 | 426992 | -11632 | 1043310.4979 | 925847.53 | 117462.9679 | 0 | 988845.8779 | 871382.91 | 117462.9679 | -1538.7017 | 438624
56.1055 | Strategic Mechanical, Inc - Tranquility Irrigation District - Tranquility Well 8 Project | 84.8% | 120891 | 28043 | 1129 | 102517.3075 | 78736.44 | 23780.8675 | 0 | 88246.2975 | 64465.43 | 23780.8675 | 2353.9046 | 26914
56.1059 | Fusion Electric, Inc - San Francisco Utilities Commission (SFPUC) - Moccasin Compou | 71.64% | 399389 | 70183 | 1347 | 286120.7529 | 235841.92 | 50278.8329 | 0 | 259417.3729 | 209138.54 | 50278.8329 | 1794.9326 | 68836
56.106 | Fusion Electric, Inc - Stockton, City of - N4 Pump Station Improvement Plans of Mar | 45.14% | 404663 | 82172 | 921 | 182653.4878 | 145563.36 | 37090.1278 | 0 | 146206.9278 | 109116.8 | 37090.1278 | 7267.6931 | 81251
56.1063 | Bay Tech Engineering - West Bay Sanitary District - Stowe Lane Pump Station Project | 75.61% | 108000 | 10079 | -4977 | 81661.383 | 74040.41 | 7620.973 | 0 | 64053.573 | 56432.6 | 7620.973 | -2562.7302 | 15056
56.1066 | CM Controls - City of Larkspur and Ross Valley Sanitary District – Heather | 89.57% | 595000 | 63510 | -73727 | 532912.916 | 476030.06 | 56882.856 | 0 | 520441.786 | 463558.93 | 56882.856 | -61720.2092 | 137237
56.1067 | Fusion Electric - Woodland Lift Station Rehabilitation - City of Modesto | 25.19% | 478000 | 62122 | -242 | 120399.3749 | 104751.99 | 15647.3849 | 0 | 116332.9949 | 100685.61 | 15647.3849 | 137.8051 | 62364
56.1073 | California Water Service Co. - Stockton Station 66-02 Panelboard Replacement - California W | 95.45% | 122210 | 8163 | -161 | 116647.2467 | 108855.81 | 7791.4367 | 0 | 116647.2467 | 108855.81 | 7791.4367 | 33.5397 | 8324
56.1075 | California Water Service Co. -Pkg 1 Bakersfield & Arden PFAS RF | 3.551% | 950000 | 170952 | -6048 | 27665.92 | 27665.92 | 0 | 0 | 27665.92 | 27665.92 | 0 | 0 | 177000
56.1078 | City of Napa - On-Call Control Systems Integrator Services | 100% | 25356.25 | 0 | -43573.5 | 25356.25 | 25356.25 | 0 | 0 | 25356.25 | 25356.25 | 0 | 0 | 43573.5
56.1081 | Rancho Murieta Community Service District - RFP for Replacement of WTP SCADA | 98.1% | 179690 | 19905 | 7826 | 176270.5876 | 156744.37 | 19526.2176 | 0 | 176270.5876 | 156744.37 | 19526.2176 | 8281.4413 | 12079
56.1083 | West Valley Water District - Furnish Planning Services for SCADA, Instrumentation, and SM | 53.01% | 717010 | 60647 | 1445 | 380119.0342 | 347967.35 | 32151.6842 | 0 | 380119.0342 | 347967.35 | 32151.6842 | 11621.7053 | 59202
56.1085 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (CTS) - California Water Service | 1.628% | 80000 | 13045 | -285 | 1090.31 | 1090.31 | 0 | 0 | 1090.31 | 1090.31 | 0 | 0 | 13330
56.1086 | Bullert Industrial Electric, Inc - Pkg 3 Chico PFAS RFP (WVC) - California Water Service | 4.315% | 376000 | 80898 | 1454 | 12732.69 | 12732.69 | 0 | 0 | 12732.69 | 12732.69 | 0 | 0 | 79444
56.1087 | San Gabrial Valley Water Companyy - WNOU Plant Replacement Flow Transmitters | 90.93% | 49369 | 6343 | 0 | 44888.9348 | 39121.54 | 5767.3948 | 0 | 44888.9348 | 39121.54 | 5767.3948 | 0 | 6343
56.1088 | California Water Service Company - Salinas District Station 304 Panelboard Replacement - Califo | 78.25% | 117985 | 32580 | 496 | 92320.6066 | 66827.49 | 25493.1166 | 0 | 92320.6066 | 66827.49 | 25493.1166 | 13916.1947 | 32084
System Integration - Open Jobs Totals |  |  | 14022847.25 | 2055056.86 | -30581.31 | 7566720.7016 | 6459348.91 | 1107371.7916 | 247627.6836 | 6316394.488 | 5456650.38 | 859744.108 | 97407.949 | -2110445.61
System Integration - Closed Jobs
56.1002 | San Joaquin Electric - Bowman WTP Phase 3 Improvements - Placer County Water Agency | 100% | 185000 | 70514.18 | 0 | 185000 | 114485.82 | 70514.18 | 50745.2395 | 20413.1505 | 644.21 | 19768.9405 | 0 | 70514.18
56.1003 | Con J. Franke Electric, Inc. - Well 22 GAC Water Treatment | 100% | 332901 | 109505.26 | 25631.26 | 332901 | 223395.74 | 109505.26 | 64460.9863 | 113346.7237 | 68302.45 | 45044.2737 | 31668.9677 | 83874
56.1007 | Fusion Electric - Waterman WTP Ozone System Improvements - City of Fairfield | 100% | 16814 | -2548.98 | -2548.98 | 16814 | 19362.98 | -2548.98 | 3177.441 | -680.041 | 5046.38 | -5726.421 | -2548.98 | 0
56.1008 | SD Electric, Inc. - Treatment Plant Seismic Retrofit of Secondary Clarifiers | 100% | 55000 | 24448.08 | 0 | 55000 | 30551.92 | 24448.08 | 23094.0224 | 1480.7976 | 126.74 | 1354.0576 | 0 | 24448.08
56.1010.01 | Placer County Water Agency - Auburn WTP Removal of 531s from Filter Control Panels | 100% | 9569 | 2471.9 | 0 | 9569 | 7097.1 | 2471.9 | 619.6471 | 6483.9829 | 4631.73 | 1852.2529 | 0 | 2471.9
56.1016 | Trabuco Canyon Water Dist. - On-Call Services - Trabuco Canyon Water District | 100% | 150064.25 | 39980.63 | 0 | 150064.25 | 110083.62 | 39980.63 | 14743.36 | 78249.75 | 53012.48 | 25237.27 | 0 | 39980.63
56.1019 | Conco-West - Monte Vista Collection Subdivision (Onsite) - Stanislaus Co. | 100% | 193845 | 50080.42 | 10097.42 | 193845 | 143764.58 | 50080.42 | 0 | 173402.48 | 123322.06 | 50080.42 | 13363.2163 | 39983
56.1021 | Darrel Varni Electric, Inc. - City of Santa Cruz – Rail Trail Segment 7 – Phase 2 | 100% | 244760 | 128007.48 | 0 | 244760 | 116752.52 | 128007.48 | 38878.5393 | 92166.0507 | 3037.11 | 89128.9407 | 0 | 128007.48
56.1022 | W.M. Lyles Co. - Graham Hill WTP Facility Improvements - City of Santa Cruz | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88093.56 | -88093.56 | 0 | 0 | 0
56.1023 | Cal Electro Inc. - 13th Street OC Pumping Plant Upgrade | 100% | 220390 | 69885.27 | 0 | 220390 | 150504.73 | 69885.27 | 40095.3125 | 68197.3875 | 38407.43 | 29789.9575 | 0 | 69885.27
56.103 | AIC - Core Electrical Services, Inc. - Corte Madera, Town of - Paradise PS RehabiProject | 100% | 689578.64 | 0 | 0 | 689578.64 | 689578.64 | 0 | 0 | 567471.07 | 567471.07 | 0 | 0 | 0
56.1041 | AIC - Irvin Rranch District - MWRP Fueling Facility CP-100 Programming | 100% | 20016.78 | 0 | 0 | 20016.78 | 20016.78 | 0 | 7002.238 | 3887.412 | 10889.65 | -7002.238 | 0 | 0
56.1051 | Las Gallinas Valley Sanitary District - PE Pump Variable Frequency Drives | 100% | 136875 | 38156.82 | 15038.82 | 136875 | 98718.18 | 38156.82 | 16220.5398 | 81400.1502 | 59463.87 | 21936.2802 | 18833.6231 | 23118
56.1052 | San Jose Water - Williams Back ATS Replacement | 100% | 8887 | 2486.06 | 0 | 8887 | 6400.94 | 2486.06 | 369.0936 | 2603.2164 | 486.25 | 2116.9664 | 0 | 2486.06
56.1053 | Bay Tech Engineering - San Francisco Public Utilities Commission (SFPUC) - Geary Un | 100% | 35000 | 15035.22 | 0 | 35000 | 19964.78 | 15035.22 | 0 | 29289.5 | 14254.28 | 15035.22 | 0 | 15035.22
56.1054 | AIC - Riverside Public Works - Digester 5 Rehab | 100% | 37648.03 | 0 | 0 | 37648.03 | 37648.03 | 0 | 0 | 26897.97 | 26897.97 | 0 | 0 | 0
56.1056 | AIC - Irvine Ranch Water District - Michelson Water Recycling Plan | 100% | 98280.63 | 0 | 0 | 98280.63 | 98280.63 | 0 | 0 | 66850.82 | 66850.82 | 0 | 0 | 0
56.1057 | A-C Electric Company - Caltrans District 06 - Olive Avenue Pumping Plant | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16238.75 | -16238.75 | 0 | 0 | 0
56.1061 | San Jose Water - PLC System Assessment | 100% | 11269 | 5686.34 | 0 | 11269 | 5582.66 | 5686.34 | 5163.8304 | 1024.0696 | 501.56 | 522.5096 | 0 | 5686.34
56.1062 | AIC - SCADA System Upgrade - City of Brentwood | 100% | 409988.07 | 0 | 0 | 409988.07 | 409988.07 | 0 | 0 | 383762.17 | 383762.17 | 0 | 0 | 0
56.1064 | South Orange County Water Agency - CTP & JBL SCADA Upgrade | 100% | 435153 | 232886.6 | 0 | 435153 | 202266.4 | 232886.6 | 69496.4896 | 241255.3004 | 77865.19 | 163390.1104 | 0 | 232886.6
56.1065 | TNT Industrial Contractors Inc. - WWTF Sodium Hypochlorite Improvements / Chlorine Contact | 100% | 226400.8 | 34376.99 | 16815.37 | 226400.8 | 192023.81 | 34376.99 | 0 | 210538.17 | 176161.18 | 34376.99 | 18229.4168 | 17561.62
56.1069 | AIC - City of Brentwood - Brentwood, City of - On-Call Agreement | 100% | 2525 | -1296.46 | 0 | 2525 | 3821.46 | -1296.46 | 0 | 2525 | 3821.46 | -1296.46 | 0 | -1296.46
56.1071 | San Jose Water Co. - 3 Mile Station 3000 Amp Switchboard | 100% | 34000 | 30403.44 | 0 | 34000 | 3596.56 | 30403.44 | 0 | 33683.5 | 3280.06 | 30403.44 | 0 | 30403.44
56.1072 | Bullert Industrial Electric, Inc. - Washwater Equalizer Tank Replacement Project – Paradise Irri | 100% | 65960 | 24421.16 | 14200.16 | 65960 | 41538.84 | 24421.16 | 0 | 64717.9 | 40296.74 | 24421.16 | 17058.6238 | 10221
56.1074 | San Gabriel Valley Water Co. - Power Monitor Replacement at B24 Hydro – San Gabriel Valley | 100% | 12650 | 2008.14 | 0 | 12650 | 10641.86 | 2008.14 | 1239.6881 | 4653.0319 | 3884.58 | 768.4519 | 0 | 2008.14
56.1076 | San Jose Water Co. - Saratoga Plant Feed Pump 1 VFD Replacement | 100% | 19200 | 7622.23 | 0 | 19200 | 11577.77 | 7622.23 | 0 | 18595.19 | 10972.96 | 7622.23 | 0 | 7622.23
56.1077 | System Integration Overhead 2025 | 100% | 0 | -4370841.4 | 0 | 0 | 4370841.4 | -4370841.4 | 0 | 0 | 4370841.4 | -4370841.4 | 0 | -4370841.4
56.1079 | AIC - San Jose Water Co - Montevina PLC Upgrade | 100% | 29235.63 | 0 | 0 | 29235.63 | 29235.63 | 0 | 0 | 29235.63 | 29235.63 | 0 | 0 | 0
56.108 | AIC - San Jose Water Co - PLC System Assessment | 100% | 359469 | 0 | 0 | 359469 | 359469 | 0 | 0 | 359469 | 359469 | 0 | 0 | 0
56.1082 | City of Clovis - Pump Station E New Pump 5 VFD Startup | 100% | 19800 | -783.04 | 0 | 19800 | 20583.04 | -783.04 | 0 | 19800 | 20583.04 | -783.04 | 0 | -783.04
56.1084 | South Orange County Water Authority - PLC Programming Support - South Orange County Wastewater Aut | 100% | 8000 | 3771.87 | 0 | 8000 | 4228.13 | 3771.87 | 0 | 8000 | 4228.13 | 3771.87 | 0 | 3771.87
56.1102 | AIC - San Benito County Water District - West Hills WTP Exp. - San Benito County WD - Royal | 100% | 19815.94 | 0 | 0 | 19815.94 | 19815.94 | 0 | 0 | 19815.94 | 19815.94 | 0 | 0 | 0
56.1103 | AIC - Willitts Equipment & Engineering Co., Inc. - Washington & S. Union PP Repair- Caltrans District | 100% | 55855.24 | 0 | 0 | 55855.24 | 55855.24 | 0 | 0 | 55855.24 | 55855.24 | 0 | 0 | 0
56.1104 | AIC - Monterey Mechanical Co. - Tunnel SCADA Integration Config - Caltrans Distric | 100% | 9500.31 | 0 | 0 | 9500.31 | 9500.31 | 0 | 0 | 9500.31 | 9500.31 | 0 | 0 | 0
56.1105 | AIC - Koch & Koch, Inc. - Monte Vista Tank Replacement Project – Placer Coun | 100% | 30502.53 | 0 | 0 | 30502.53 | 30502.53 | 0 | 0 | 30502.53 | 30502.53 | 0 | 0 | 0
56.1106 | AIC - Cal Signal Corp - SR211 Fernbridge Eel River Bridge Seismic Gates - | 100% | 54742.18 | 0 | 0 | 54742.18 | 54742.18 | 0 | 0 | 54742.18 | 54742.18 | 0 | 0 | 0
56.1107 | AIC - San Joaquin Electric - Pkg 4 Livermore & Stockton PFAS RFP – California W | 100% | 3429.06 | 0 | 0 | 3429.06 | 3429.06 | 0 | 0 | 3429.06 | 3429.06 | 0 | 0 | 0
56.1108 | AIC - City of Davis - Programming and Panel Modifications at Turnout Sit | 100% | 20729.84 | 0 | 0 | 20729.84 | 20729.84 | 0 | 0 | 20729.84 | 20729.84 | 0 | 0 | 0
56.1109 | AIC - Fusion Electric, Inc.. - Moccasin WWTP Replacement - San Francisco Public U | 100% | 14772.26 | 0 | 0 | 14772.26 | 14772.26 | 0 | 0 | 14772.26 | 14772.26 | 0 | 0 | 0
56.111 | AIC - Al Fresco Landscape Management Inc. - East Garrison Autodialer Replacement - County of M | 100% | 4596.42 | 0 | 0 | 4596.42 | 4596.42 | 0 | 0 | 4596.42 | 4596.42 | 0 | 0 | 0
56.1111 | AIC - California American Water - Luzern Well Treatment Design | 100% | 17210.01 | 0 | 0 | 17210.01 | 17210.01 | 0 | 0 | 17210.01 | 17210.01 | 0 | 0 | 0
56.1112 | AIC - Westside Water Authority - Pump Station A On-Site Support - Westside Water Au | 100% | 27241.58 | 0 | 0 | 27241.58 | 27241.58 | 0 | 0 | 27241.58 | 27241.58 | 0 | 0 | 0
56.1113 | AIC - Central Sierra Electric Co., Inc. - Industrial WWTF - City of Gonzales - Central Sierr | 100% | 49233.44 | 0 | 0 | 49233.44 | 49233.44 | 0 | 0 | 49233.44 | 49233.44 | 0 | 0 | 0
56.1115 | AIC - UC Davis - WWTP Annual Instrument Calibrations | 100% | 5895.77 | 0 | 0 | 5895.77 | 5895.77 | 0 | 0 | 5895.77 | 5895.77 | 0 | 0 | 0
56.1119 | AIC - SD Electric Inc. - Chrysler Stormwater Pump Station Switchboard - Cit | 100% | 22184.06 | 0 | 0 | 22184.06 | 22184.06 | 0 | 0 | 22184.06 | 22184.06 | 0 | 0 | 0
56.112 | AIC - Strategic Mechanical - Construction Plans for 2-Water Booster Pump Statio | 100% | 1045.63 | 0 | 0 | 1045.63 | 1045.63 | 0 | 0 | 1045.63 | 1045.63 | 0 | 0 | 0
56.1121 | AIC - San Joaquin Electric, Inc. -WQCF Sludge Thickener and Dewatering Unit No. 3 Pro | 100% | 22824.38 | 0 | 0 | 22824.38 | 22824.38 | 0 | 0 | 22824.38 | 22824.38 | 0 | 0 | 0
56.1122 | AIC - West Bay Sanitary District - West Bay Sanitary District - Soft Starter Retrofit | 100% | 6289.38 | 0 | 0 | 6289.38 | 6289.38 | 0 | 0 | 6289.38 | 6289.38 | 0 | 0 | 0
56.1123 | AIC - UC Davis - Landfill Flare PLC & SCADA Integration - UC Davis | 100% | 3772.82 | 0 | 0 | 3772.82 | 3772.82 | 0 | 0 | 3772.82 | 3772.82 | 0 | 0 | 0
56.1124 | AIC - Cupertino Electric Inc.- Eagle Rock Aggregrates Oakland Terminal - Port of | 100% | 28950 | 0 | 0 | 28950 | 28950 | 0 | 0 | 28950 | 28950 | 0 | 0 | 0
56.1125 | AIC - Fowler Electric Services Inc. - Third Street Pump Station - San Rafael Sanitation | 100% | 14229.38 | 0 | 0 | 14229.38 | 14229.38 | 0 | 0 | 14229.38 | 14229.38 | 0 | 0 | 0
56.1126 | AIC - Fowler Electric Services Inc. - Parr Tank and Pipeline Project – North Gualala Wat | 100% | 9526.88 | 0 | 0 | 9526.88 | 9526.88 | 0 | 0 | 9526.88 | 9526.88 | 0 | 0 | 0
56.1127 | AIC - Auburn Constructors, LLC - Colfax Water Treatment Plant Replacement Project – Placer Co | 100% | 6519.07 | 0 | 0 | 6519.07 | 6519.07 | 0 | 0 | 6519.07 | 6519.07 | 0 | 0 | 0
56.1128 | AIC - Con J. Franke Electric Inc. - San Joaquin Pipeline Valve and Safe Entry Improvements Phase | 100% | 4793.13 | 0 | 0 | 4793.13 | 4793.13 | 0 | 0 | 4793.13 | 4793.13 | 0 | 0 | 0
56.1129 | AIC - RMCSD - VEEAM SFTWR | 100% | 133.75 | 0 | 0 | 133.75 | 133.75 | 0 | 0 | 133.75 | 133.75 | 0 | 0 | 0
56.113 | System Integration Division Estimating 2025 | 100% | 0 | -267.5 | 0 | 0 | 267.5 | -267.5 | 0 | 0 | 267.5 | -267.5 | 0 | -267.5
56.1131 | AIC - North Star Construction - Sweeney Ranch Pump Station Pumps & Temp Electrical – Sacrame | 100% | 2388.75 | 0 | 0 | 2388.75 | 2388.75 | 0 | 0 | 2388.75 | 2388.75 | 0 | 0 | 0
56.1132 | AIC - UC Davis - CABA Well Pump Station Rehabilitation – UC Davis | 100% | 585 | 0 | 0 | 585 | 585 | 0 | 0 | 585 | 585 | 0 | 0 | 0
56.1133 | AIC - UC Davis - CABA Ag Pump Station Rehabilitation – UC Davis | 100% | 2827.5 | 0 | 0 | 2827.5 | 2827.5 | 0 | 0 | 2827.5 | 2827.5 | 0 | 0 | 0
56.1134 | AIC - Cupertino Electric Inc. - Headworks (Cupertino Troubleshooting Project) - San Francisc | 100% | 965.51 | 0 | 0 | 965.51 | 965.51 | 0 | 0 | 965.51 | 965.51 | 0 | 0 | 0
56.1135 | AIC - San Joaquin Electric - Lurline Check and Siphon Replacement Project - Glenn-Colusa | 100% | 112.5 | 0 | 0 | 112.5 | 112.5 | 0 | 0 | 112.5 | 112.5 | 0 | 0 | 0
56.1141 | AIC - Blocka Construction Inc. - Glenview Reservoir Recoating and Tank Improvements - San Jos | 100% | 2827.5 | 0 | 0 | 2827.5 | 2827.5 | 0 | 0 | 2827.5 | 2827.5 | 0 | 0 | 0
System Integration - Closed Jobs Totals |  |  | 4511779.65 | -3483989.29 | 79234.05 | 4511779.65 | 7995768.94 | -3483989.29 | 335306.4276 | 3047886.8924 | 6867182.61 | -3819295.7176 | 96604.8677 | 632860.44
System Integration Total |  |  | 18534626.9 | -1428932.43 | 48652.74 | 12078500.3516 | 14455117.85 | -2376617.4984 | 582934.1113 | 9364281.3803 | 12323832.99 | -2959551.6097 | 194012.8167 | -1477585.17
| Contract Balance | 8099229.16 |  |  | Construction Backlog |  | 6456126.5484 |  |  | WIP | -34037.8584
50 Jobs
50.0541 | W.M. Lyles Co. - General Overhead | 100% | 0 | -3642039.89 | -420625.51 | 0 | 3642039.89 | -3642039.89 | 0 | 0 | 3642039.89 | -3642039.89 | -420625.51 | -3221414.38
50.0542 | W.M. Lyles Co. - General Estimating | 100% | 0 | -100487.45 | -20759.22 | 0 | 100487.45 | -100487.45 | 0 | 0 | 100487.45 | -100487.45 | -20759.22 | -79728.23
50.0543 | American Paving | 100% | 7051.01 | 0 | 0 | 7051.01 | 7051.01 | 0 | 0 | 7051.01 | 7051.01 | 0 | 0 | 0
50.0544 | Lyles Services Co. | 100% | 13555.8 | 0 | 0 | 13555.8 | 13555.8 | 0 | 0 | 13555.8 | 13555.8 | 0 | 0 | 0
50.0545 | New England Sheet Metal and Mechanical Co. | 100% | 2226.16 | 0 | 0 | 2226.16 | 2226.16 | 0 | 0 | 2226.16 | 2226.16 | 0 | 0 | 0
50.0546 | Lyles Utility Construction, LLC | 100% | 11256.72 | 788.66 | 0 | 11256.72 | 10468.06 | 788.66 | 0 | 11256.72 | 10468.06 | 788.66 | 0 | 788.66
50.0551 | Advanced Integration & Controls | 100% | 5457.42 | 0 | 0 | 5457.42 | 5457.42 | 0 | 0 | 5457.42 | 5457.42 | 0 | 0 | 0
50 Jobs Total |  |  | 39547.11 | -3741738.68 | -441384.73 | 39547.11 | 3781285.79 | -3741738.68 | 0 | 39547.11 | 3781285.79 | -3741738.68 | -441384.73 | -3300353.95
| Contract Balance | 0 |  |  | Construction Backlog |  | 0 |  |  | WIP | 0
Open Jobs Totals |  |  | 1871949205.41 | 126137111.39 | 499973.14 | 1107807669.4931 | 1041534998.27 | 66272671.2231 | 41070417.0828 | 328738312.8804 | 303536058.74 | 25202254.1404 | 2700015.6974 | 127067218
Closed Job Totals |  |  | 152608093.41 | 4767940.6 | -1349047.26 | 152608093.41 | 147840152.81 | 4767940.6 | 17833981.0821 | 22281669.6579 | 35347710.14 | -13066040.4821 | -1259578.5038 | 4686908.11
Company Totals |  |  | 2024557298.82 | 130905051.99 | -849074.12 | 1260415762.9031 | 1189375151.08 | 71040611.8231 | 58904398.1649 | 351019982.5383 | 338883768.88 | 12136213.6583 | 1440437.1936 | 131754126.11
| Contract Balance | 764525121.15 |  |  | Construction Backlog |  | 764141535.9169 |  |  | WIP | -3998374.5269
| Variance with Bonus P&L Schedule |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8476e-09 | 0